WORKFLOW BLUEPRINT

IBM Turbonomic
Post-Deployment Test & Validation Workflow
Version 1.0 | Plain-Language Guide

A simple, step-by-step explanation of the workflow diagram for all teams

# Document Control

| Document Attribute | Value |
| --- | --- |
| Document reference | Turbonomic Test & Validation Workflow - Plain-Language Blueprint (v1.0) |
| Purpose | Explain the post-deployment test and validation workflow in simple words, so it is easy to understand and to present |
| Companion picture | Turbonomic_Test_Validation_Workflow.jpg |
| Status | DRAFT |
| Prepared by | Amitendra / Saikat |
| Date | 2026-10-22 |

# 1. What This Workflow Is For

Once the new Turbonomic is installed on AKS, we prove it works before anyone relies on it. This workflow is the route from "installed" to "handed over to operations": check it, test it, get approval, switch users over, then watch it closely for a while.

It has 11 stages. Five teams each have a job in every stage. A checkpoint at the end of each stage decides whether we can move on.

# 2. How to Read the Picture

| Part of the picture | What it means |
| --- | --- |
| Entry criteria (box on the left) | The 10 things that must be ready before testing starts. Think of it as the pre-flight checklist. |
| Columns (stages 1 to 11) | Read them left to right, in time order. Each column is one stage of the journey. |
| Rows (the five teams) | Each row shows what one team does in every stage. Read across a row to see one team's whole journey. |
| Diamonds at the bottom (G1 to G11) | Checkpoints, or decision gates. The line joining them means you pass them one after another; you cannot jump ahead. |
| Coloured columns (9, 10, 11) | The go-live part of the journey: cutover, test completion and hypercare. |
| Line at the bottom | Evidence collection, defect tracking and communication happen all the way through, not at one stage. |

# 3. Who Is Involved

| Short name | Team | In one line |
| --- | --- | --- |
| PE | Platform Engineer | Looks after the AKS cluster, storage and the technical health of the platform |
| TA | Turbonomic Administrator | Sets up and runs the Turbonomic application itself: licence, users, targets |
| NW | Network / DNS Owner | Makes sure the network paths, DNS names, firewall rules and certificates work |
| TU | Test User | Uses Turbonomic as a real user would and confirms it does the job |
| SR | Security Reviewer | Checks that security, access and compliance are right at each stage |

# 4. Before Testing Starts: The 10 Entry Checks

Testing does not begin until all ten are true. If any one is missing, we wait.

| Check | Name | What it means |
| --- | --- | --- |
| E1 | Design approved | The architecture, AKS set-up, Turbonomic version, database and access model are signed off. |
| E2 | Platform ready | The nodes, storage, quotas and capacity are in place. |
| E3 | IBM pieces ready | The CRD, Operator and installation files are available. |
| E4 | Network and security ready | DNS, firewall, ingress and TLS certificates are done. |
| E5 | Dependencies ready | The database, Azure, vCenter, ServiceNow and SMTP can be reached. |
| E6 | Test accounts ready | We have an admin, an operator, a read-only user and an unauthorized user to test with. |
| E7 | Baselines ready | Test targets exist and we know what the inventory should look like. |
| E8 | Record-keeping ready | The evidence store, defect register and exception log are set up. |
| E9 | Way back ready | The rollback plan exists and the old appliance is healthy. |
| E10 | Change window ready | The change window is approved, and we have a snapshot of how the shared cluster behaves today. |

# 5. The 11 Stages, Step by Step

Each stage below says what it is about in plain words, what each team does, and the checkpoint that must be passed before the next stage starts.

## Stage 1: Environment Validation

In simple words: Is the ground ready to build on?

| Team | What they do |
| --- | --- |
| Platform Engineer | Checks the AKS cluster, nodes, storage, namespace and spare capacity. |
| Turbonomic Administrator | Checks the prerequisites and their own access. |
| Network / DNS Owner | Checks the network, DNS, firewall and the path users will take in. |
| Test User | Checks they have the access they need. |
| Security Reviewer | Checks the security prerequisites. |

Move on when: G1 Environment Ready.

## Stage 2: Deployment Validation

In simple words: Did the installation actually work?

| Team | What they do |
| --- | --- |
| Platform Engineer | Confirms the Operator and the Turbonomic resource are deployed, and the pods and services are running. |
| Turbonomic Administrator | Starts the application, applies the licence and checks the core components. |
| Network / DNS Owner | Helps with image downloads and outside connections. |
| Test User | Logs in and checks basic access. |
| Security Reviewer | Checks the installation against security standards. |

Move on when: G2 Deployment Successful.

## Stage 3: Configuration & Integration

In simple words: Set it up the way GEHA needs it, and connect it to the other systems.

| Team | What they do |
| --- | --- |
| Platform Engineer | Configures storage, database, ingress and TLS. |
| Turbonomic Administrator | Sets up users, roles, policies and the Azure and vCenter targets. |
| Network / DNS Owner | Checks TLS and the network rules for each integration. |
| Test User | Checks that role-based access and the UI set-up are right. |
| Security Reviewer | Reviews access controls, encryption and integration security. |

Move on when: G3 Configuration Complete.

## Stage 4: Functional Validation

In simple words: Does Turbonomic do its job?

| Team | What they do |
| --- | --- |
| Platform Engineer | Supports target connections and the collection of infrastructure data. |
| Turbonomic Administrator | Tests the application's features, actions and reports. |
| Network / DNS Owner | Confirms Azure and vCenter can be reached. |
| Test User | Runs the UI, action and report test cases. |
| Security Reviewer | Checks audit logs, roles and compliance needs. |

Move on when: G4 Functional Tests Passed.

## Stage 5: Non-Functional Validation

In simple words: Is it fast, stable, recoverable and secure enough?

| Team | What they do |
| --- | --- |
| Platform Engineer | Watches performance, and checks backup, recovery, logging and upgrade readiness. |
| Turbonomic Administrator | Tests resilience, failover and data retention. |
| Network / DNS Owner | Watches network stability and performance. |
| Test User | Uses the system under normal load. |
| Security Reviewer | Reviews vulnerability results and the overall security position. |

Move on when: G5 Non-Functional Tests Passed.

## Stage 6: Defect Management & Sign-off

In simple words: Fix what we found, and prove the fixes work.

| Team | What they do |
| --- | --- |
| Platform Engineer | Helps analyse and fix issues. |
| Turbonomic Administrator | Sorts defects by priority and retests the fixes. |
| Network / DNS Owner | Helps with network issues. |
| Test User | Retests the fixes and confirms the results. |
| Security Reviewer | Confirms security defects are closed. |

Move on when: G6 Critical Defects Closed.

## Stage 7: Acceptance & Readiness

In simple words: Does everyone agree it is ready?

| Team | What they do |
| --- | --- |
| Platform Engineer | Confirms the environment is stable and ready for cutover. |
| Turbonomic Administrator | Confirms all tests passed and gets stakeholder approval. |
| Network / DNS Owner | Confirms there are no open network or security issues. |
| Test User | Gives user acceptance sign-off. |
| Security Reviewer | Gives final security acceptance. |

Move on when: G7 Testing Ready for CAB.

## Stage 8: CAB Approval

In simple words: Ask the Change Advisory Board for permission to go live.

| Team | What they do |
| --- | --- |
| Platform Engineer | Presents the test summary and readiness evidence to CAB. |
| Turbonomic Administrator | Answers questions about application readiness. |
| Network / DNS Owner | Confirms the network and DNS changes are ready. |
| Test User | Confirms the user impact and the communications are ready. |
| Security Reviewer | Confirms security acceptance and any agreed exceptions. |

Move on when: G8 CAB Approved.

## Stage 9: Cutover Day

In simple words: Switch users over to the new Turbonomic.

| Team | What they do |
| --- | --- |
| Platform Engineer | Runs the cutover plan and watches AKS health. |
| Turbonomic Administrator | Checks the application, targets and integrations. |
| Network / DNS Owner | Applies the approved DNS and access changes. |
| Test User | Does a quick business check (smoke test). |
| Security Reviewer | Watches security events and controls. |

Move on when: G9 Cutover Completed.

## Stage 10: Test Complete

In simple words: Close testing formally.

| Team | What they do |
| --- | --- |
| Platform Engineer | Confirms every planned test was run and the evidence is complete. |
| Turbonomic Administrator | Confirms application acceptance and the defect status. |
| Network / DNS Owner | Confirms connectivity is still stable. |
| Test User | Confirms business acceptance. |
| Security Reviewer | Confirms security acceptance. |

Move on when: G10 Test Complete.

## Stage 11: Hypercare Exit

In simple words: A period of close watching after go-live, then handover to normal support.

| Team | What they do |
| --- | --- |
| Platform Engineer | Watches the system and integrations, then hands over to operations. |
| Turbonomic Administrator | Fixes any application issues found after cutover. |
| Network / DNS Owner | Supports any network issues after cutover. |
| Test User | Confirms business acceptance. |
| Security Reviewer | Closes any open security observations. |

Finish when: G11 Hypercare Exit.

# 6. The Checkpoints at a Glance

Each gate is one yes/no question. Only a "yes" opens the next stage.

| Gate | Name | The question to answer "yes" to |
| --- | --- | --- |
| G1 | Environment Ready | Is the cluster, network and access ready to start? |
| G2 | Deployment Successful | Is Turbonomic installed and running? |
| G3 | Configuration Complete | Is it set up and connected to Azure, vCenter and the other systems? |
| G4 | Functional Tests Passed | Does it do its job correctly? |
| G5 | Non-Functional Tests Passed | Is it stable, fast enough, recoverable and secure? |
| G6 | Critical Defects Closed | Are all serious problems fixed and retested? |
| G7 | Testing Ready for CAB | Have all teams signed off? |
| G8 | CAB Approved | Has the Change Advisory Board approved go-live? |
| G9 | Cutover Completed | Are users on the new system and working? |
| G10 | Test Complete | Is all testing formally closed, with evidence? |
| G11 | Hypercare Exit | Is it stable enough to hand to normal operations? |

# 7. What Runs the Whole Time

Three things happen in every stage, from the first to the last:

Evidence collection: screenshots, command outputs and sign-offs go into the evidence store as we go, not at the end.

Defect tracking: every problem goes into the defect register with an owner, even if it is fixed the same day.

Stakeholder communication: everyone affected knows where we are and what comes next.

# 8. How to Explain It in One Minute

"Before we test anything, we tick off 10 entry checks: design approved, platform, network, dependencies, test accounts, a rollback plan and an approved change window.

Then we move through 11 stages. First we check the environment and the installation. Then we configure Turbonomic and connect it to Azure and vCenter. Next we test that it works and that it is stable and secure, and we fix what we find.

When every team has signed off, we go to CAB for approval. On cutover day we switch users over. We then close testing formally and watch the system closely during hypercare, before handing it to operations.

Five teams take part in every stage: platform, Turbonomic admin, network, test users and security. Each stage ends with a checkpoint, and we only move on when the answer is yes."

# 9. Common Questions

| Question | Answer |
| --- | --- |
| What happens if a checkpoint is not passed? | We stay in that stage. The issue goes into the defect register, the right team fixes it, and the checkpoint is checked again. |
| Can two stages run at the same time? | No. The gates are joined in a line on purpose: each one has to be passed before the next stage starts. |
| Why do all five teams appear in every stage? | Every stage needs something from each team, even if only a confirmation. That way nobody is surprised later, and each team's sign-off is on record. |
| What if something goes badly wrong after cutover? | We use the rollback plan prepared in entry check E9. The old appliance is kept healthy until hypercare ends, so users can be moved back to it. |
| Who gives the final go-ahead to go live? | The Change Advisory Board, at Stage 8. Without CAB approval (G8), cutover does not happen. |
| When is the work finished? | At G11 Hypercare Exit, when the system has been stable after go-live and operations has taken it over. |