Execution Workflow

CyberArk PAS

Datacentre to Azure Migration v0.1

| Document Reference | Execution Workflow — CyberArk PAS (v0.1 DRAFT) |
| --- | --- |
| Stakeholders (GEHA) | Eric Ullmann (Application Owner), Phil Costanzo (Admin / Support Manager) |
| Authors | Saikat Majumdar, Amitendra Kushwaha (Citius Healthcare Consulting) |
| Design Authority | George Galindo (Cloud Architect) |
| Companion Document | CyberArk PAS Application Migration Playbook v0.1 |
| Date | 18-Sep-2026 |

Contents

1. Executive Summary	3

Future State Specifications	3

2. Prerequisites & Governance	3

2.1 Access Requirements	3

2.2 Platform Provisioning & Exemptions	4

2.3 Network & Firewall Policy	4

3. Implementation Roadmap	5

Execution Steps & Dependencies	5

4. Technical Playbook	6

Step 1: Access & Prerequisite Requests	6

Step 2: Subnet & Governance Provisioning	6

Step 3: Bicep Repository Configuration	6

Step 4: Infrastructure & Load Balancer Setup	6

Step 5: Network Routing & DNS	7

Step 6: CyberArk Connector Registration	7

Step 7: Component Installation	7

Step 8: Security Hardening & GPO	7

5. End-to-End Solution Validation	8

6. Cutover & Rollback Plan	9

Cutover Execution Matrix	9

Cutover Steps	9

Rollback Protocol	9

7. RACI Matrix	10

Abbreviations	11

1. Executive Summary

This execution workflow outlines the operational steps required to deploy, configure, and operationalize CyberArk Privileged Access Security (PAS) connectors within Microsoft Azure. It serves as a step-by-step implementation guide for technical engineering teams.

Future State Specifications

| Configuration Parameter | Specification Details |
| --- | --- |
| Virtual Machine Count | 4 instances total (2 Production, 2 Non-Production) |
| Operating System | Windows Server 2022 (GEHA Approved Custom Image) |
| Compute SKU | Standard_D8ls_v5 (8 vCPU, 16 GB RAM) |
| Storage Allocation | 1x 128 GB OS Managed Disk (Recordings stream directly to CyberArk Tenant) |
| Target Subscriptions | CIP-PRD (Production), CIP-DEV (Non-Production) |
| Azure Region & Zones | Central US (Zone 1 and Zone 2 per environment for High Availability) |
| Subnet Allocations | snet-cyberark-cus-prd-01 (/27), snet-cyberark-cus-dev-01 (/27) |
| Load Balancing | 1x Internal Load Balancer (ILB) per environment with dedicated Private DNS entry |
| Administrative Access | Azure Bastion exclusive access (No Public IP addresses assigned) |

2. Prerequisites & Governance

All prerequisite activities must be initiated in parallel during Week 1 to prevent downstream project bottlenecks.

2.1 Access Requirements

| Access Scope | Justification / Purpose | Granting Authority |
| --- | --- | --- |
| Contributor on rg-sec-cyberark-npd | Provisioning non-production infrastructure | Azure Platform Team |
| Contributor on rg-sec-cyberark-prd | Provisioning production infrastructure (Requires CAB approval) | Azure Platform Team |
| Sandbox Subscription Access | Pre-validation and testing of Bicep templates prior to target deployment | Azure Platform Team |
| Azure DevOps Project (TIO) | Hosting source repository and pipeline pipelines | Azure Platform Team |
| Shared Bicep Module Registry Read | Referencing centralized, enterprise-approved Bicep modules | Azure Platform Team |
| CyberArk Portal Access | Connector registration, component setup, and platform configuration | GEHA CyberArk Administration |
| Azure Bastion Access | Administrative RDP access to target connector VMs | Azure Platform Team |

2.2 Platform Provisioning & Exemptions

| Requirement Item | Detailed Specification | Operational Impact / Reason |
| --- | --- | --- |
| Production Subnet | /27 in vnet-cip-cus-prd-01 (snet-cyberark-cus-prd-01) | Host allocation & HA load balancing |
| Non-Production Subnet | /27 in vnet-cip-cus-dev-01 (snet-cyberark-cus-dev-01) | Host allocation & HA load balancing |
| Policy Exemption: RDS Role | Approval to enable Remote Desktop Services role | Required by CyberArk Session Manager |
| Policy Exemption: NLA | Approval to disable Network Level Authentication | Required by CyberArk PSM listener |
| Shared Image Gallery Path | Full Resource ID of GEHA-approved Windows 2022 image | Core parameter for Bicep template deployment |
| Core Quota Check | Minimum 32 vCPUs (Dls_v5 family) in Central US | Compute provisioning for 4 virtual machines |

2.3 Network & Firewall Policy

| Rule Scope | Source / Destination Ports | Protocol / Purpose | Special Handling |
| --- | --- | --- | --- |
| Admin Session Inbound | TCP 3389, 443 | Admin connections to Internal Load Balancer | Standard Inspection |
| Connector to Target | TCP 3389, 22, 443 | Brokered sessions to migrated workload VMs | Standard Inspection |
| Connector to CyberArk | TCP 1858, 443 Outbound | Outbound communication to CyberArk Cloud Tenant | Bypass IDS/IPS Inspection on Port 1858 |
| Connector to Directory | TCP 389, 3268 | Active Directory lookup via ExpressRoute | Standard Inspection |
| Connector to SIEM/Logs | TCP 9998, 8089 | Event log forwarding to Enterprise Log Platform | Standard Inspection |
| Endpoint Security | TCP 443 Outbound | Security agent update feeds | Standard Inspection |
| Deny On-Premises Target | All Traffic | Explicit block to prevent Azure connectors from picking up legacy on-prem workloads | Enforced via Azure Firewall |

3. Implementation Roadmap

The implementation follows an 11-step sequence structured across four primary phases.

| PREPARATION & FOUNDATION | Steps 1 – 3 | Access Requests → Subnets & Policy Exemptions → Bicep Repository Setup |
| --- | --- | --- |
| INFRASTRUCTURE & NETWORK DEPLOYMENT | Steps 4 – 5 | Bicep VM/ILB Provisioning → Firewall Policy Rules & DNS Record Creation |
| CYBERARK CONFIGURATION & HARDENING | Steps 6 – 8 | Connector Registration → Component Installation → Domain GPO Hardening |
| VALIDATION, CUTOVER & HANDOVER | Steps 9 – 11 | End-to-End Testing → Phased App Cutover → Operational Handover & Decommission |

Execution Steps & Dependencies

| Step Reference | Task Description | Technical Dependencies |
| --- | --- | --- |
| Step 1 | Initiate Access and Prerequisite Requests | None (Day 1 Activity) |
| Step 2 | Subnet Allocation & Policy Exemption Approvals | Step 1 |
| Step 3 | Bicep Infrastructure Repository Setup | Step 1 |
| Step 4 | Server Infrastructure & Load Balancer Provisioning | Steps 2, 3 |
| Step 5 | Firewall Rules Activation & DNS Configuration | Step 2 |
| Step 6 | CyberArk Connector Registration | Steps 4, 5 |
| Step 7 | Install CyberArk Components (PSM / CPM) | Step 6 |
| Step 8 | Apply Group Policy Hardening & Final Configuration | Step 7 |
| Step 9 | Validate End-to-End Solution Functionality | Step 8 |
| Step 10 | Execute Phased Workload Cutover | Step 9 |
| Step 11 | Operational Handover & On-Premises Decommissioning | Step 10 |

4. Technical Playbook

Step 1: Access & Prerequisite Requests

- Request Reader access on resource groups rg-sec-cyberark-npd and rg-sec-cyberark-prd.

- Request Sandbox subscription access for initial Bicep template validation.

- Obtain access to the Azure DevOps TIO project repository.

- Obtain CyberArk Portal credentials and configure the Installer Service Account password with GEHA Administration.

- Confirm if the CyberArk tenant enforces IP Allowlisting; register outbound NAT addresses if enabled.

Step 2: Subnet & Governance Provisioning

- Request /27 dedicated subnets for Production (snet-cyberark-cus-prd-01) and Non-Production (snet-cyberark-cus-dev-01).

- Submit formal policy exemptions for Remote Desktop Services (RDS) role enablement and Network Level Authentication (NLA) relaxation.

- Verify platform inherited policy constraints prior to template development:

  - Public IP addresses on NICs are Denied.

  - Local Private DNS Zone creation is Denied (records must be hosted in on-premises DNS).

  - Direct internet management ports are Denied (Bastion access mandatory).

Step 3: Bicep Repository Configuration

- Configure dot-notation repository structure (cyberark.bicep) referencing the shared GEHA Bicep module registry (br:gehabicep.azurecr.io/bicep/modules/...).

- Ensure templates consume centralized networking, subnets, and compute definitions without duplicating local module code.

Step 4: Infrastructure & Load Balancer Setup

- Execute Bicep deployment to provision Standard_D8ls_v5 instances across Availability Zones 1 and 2.

- Assign static internal IP addresses (e.g., Load Balancer: .4, VM1: .5, VM2: .6).

- Configure Internal Load Balancer settings:

| ILB Setting | Value | Technical Justification |
| --- | --- | --- |
| Session Persistence | Client IP (Direct Server Return disabled) | Prevents broken mid-handshake user sessions |
| Health Probe | TCP 3389 (Interval: 5s, Threshold: 2) | Probes service responsiveness, not just VM power state |
| Idle Timeout | 30 Minutes | Accommodates administrative session idle time |
| TCP Reset on Idle | Enabled | Explicitly notifies client upon session expiration |

- Apply mandatory enterprise tags (Environment, Owner, ApplicationName, CostCenter, DataClassification, DRTier).

- Configure baseline Azure Monitor metric alerts (Unreachable Connector, PSM/CPM Service Stopped, Disk Space > 85%).

Step 5: Network Routing & DNS

- Implement Central US Hub Firewall rules including Port 1858 inspection bypass.

- Provision internal CNAME/A-records in on-premises DNS pointing to the respective ILB static IP addresses (cyberark-prd.geha.com and cyberark-npd.geha.com).

- Perform manual network connectivity verification (TCP ping/telnet) from target VMs to domain controllers, SIEM indexers, and CyberArk tenant endpoints.

Step 6: CyberArk Connector Registration

- Sign in to the target VM via Azure Bastion using local administrative credentials.

- Download Privilege Cloud software packages and standalone deployment tools from CyberArk Marketplace.

- Temporarily disable endpoint protection agents during software installation.

- Execute prerequisite check script via PowerShell:

.\ConnectorCheckPrerequisites_PrivilegeCloud.ps1

- Address all reported failures (the script automatically installs required RDS roles).

- Initiate "Add Connector" in CyberArk Portal, generate a registration token/script, and execute the command within the active 5-minute validity window.

Step 7: Component Installation

- Select target connector in CyberArk Portal (⋮ → Add Component).

- Select deployment mode: Production (do not use Proof-of-Concept mode).

- Provide Installer Service Account credentials and local domain admin accounts.

- Complete installation of Session Manager (PSM) and Rotation Engine (CPM) components; reboot host upon completion.

- Note: Deploy connectors sequentially. Parallel component installation on multiple hosts is unsupported.

Step 8: Security Hardening & GPO

- Import the official CyberArk GPO hardening package into Domain Group Policy Management.

- Link the hardened GPO exclusively to the dedicated Organizational Unit (OU) housing CyberArk Connector computer accounts.

- Execute gpupdate /force on target connector hosts.

- Re-enable endpoint protection tools with mandatory CyberArk file/folder exclusion paths applied.

5. End-to-End Solution Validation

Execute the following test cases in non-production prior to authorizing production cutover activities.

| Test ID | Test Category | Execution Procedure | Acceptance Criteria |
| --- | --- | --- | --- |
| 01 | Connector Health | Verify portal status across all deployed nodes. | Status indicates Green/Active across all components. |
| 02 | Health Probe | Audit ILB backend pool status. | Both backend servers report Healthy. |
| 03 | DNS Resolution | Resolve cyberark-npd.geha.com from an administrative endpoint. | Returns ILB virtual IP address. |
| 04 | Credential Rotation | Initiate manual password rotation on an Azure-hosted account. | Password changes successfully in target and vault. |
| 05 | Log Ingestion | Validate event log pipeline generation. | Audit events reflect in log platform (Splunk etc) |
| 06 | HA Failover | Shut down primary connector node during active administration. | ILB routes active traffic to secondary node; rotation shifts. |
| 07 | Network Isolation | Attempt outbound connection from Azure connector to legacy on-prem host. | Traffic is blocked by Azure Firewall rule. |
| 08 | Zero Trust Access | Attempt direct external connection to connector OS. | Access denied; connection restricted to Azure Bastion. |
| 09 | Disaster Rebuild | Teardown a dev connector and rebuild via Bicep pipeline. | Node successfully restored using automated runbook. |

6. Cutover & Rollback Plan

Workload migration occurs on an application-by-application basis.

Cutover Execution Matrix

| Change Items | Action Required | Owner | Change When |
| --- | --- | --- | --- |
| PSM Platform Settings | Copy platform settings pointing to Azure ILB | GEHA CyberArk Admin | Before window |
| CPM Safe Assignment | Re-assign safe rotation engine to Azure CPM | GEHA CyberArk Admin | During Window |
| Administrative DNS | Provision cyberark-prd.geha.com pointing to Azure ILB | Azure Platform Team | Before window |
| Firewall Rules | Staged rules in Central US Azure Firewall | Network Team | Before window |

Cutover Steps

- Pre-configure CyberArk platform settings for the Azure connector pools

- Verify target application workloads are operational within Azure subnets.

- Activate the updated platform settings and move the CPM Safe to the Azure pool

- Perform validation logon and execute a test credential rotation.

Rollback Protocol

If validation fails post-cutover:

- Re-point the CyberArk Safe and Platform settings back to the active on-premises connector pool.

- Note: Rollback is purely a configuration update within the CyberArk portal. No server state migration or restoration is required.

7. RACI Matrix

| Migration Activity | Saikat M. | Bhagyashri S. | Amitendra K. | Syed A. | Mulinti R. | George G. | GEHA Admin | Platform Team |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Bicep Repository & Infrastructure | A/R | C | C | I | I | C | I | C |
| OS Preparation & Hardening | I | A/R | C | I | I | C | I | I |
| CyberArk Registration & Setup | C | C | A/R | I | I | C | C | I |
| Firewall & Routing Policy | I | I | I | A/R | I | C | I | C |
| Database Account Rotation | I | I | I | I | A/R | I | C | I |
| Architecture Sign-Off & Reviews | C | I | I | I | I | A/R | C | C |
| CyberArk Portal Configuration | I | I | C | I | I | I | A/R | I |
| Subnet & Policy Provisioning | I | I | I | I | I | I | I | A/R |

Legend: R = Responsible | A = Accountable | C = Consulted | I = Informed

Abbreviations

| Abbreviation | Expansion |
| --- | --- |
| CAB | Change Advisory Board |
| CNAME | Canonical Name (DNS alias record) |
| CPM | Central Policy Manager - CyberArk credential rotation engine |
| DNS | Domain Name System |
| DR | Disaster Recovery |
| GEHA | Government Employees Health Association |
| GPO | Group Policy Object |
| HA | High Availability |
| IDS / IPS | Intrusion Detection System / Intrusion Prevention System |
| ILB | Internal Load Balancer |
| IP | Internet Protocol |
| NAT | Network Address Translation |
| NIC | Network Interface Card |
| NLA | Network Level Authentication |
| OS | Operating System |
| OU | Organizational Unit |
| PAS | Privileged Access Security |
| PSM | Privileged Session Manager - CyberArk session brokering component |
| RACI | Responsible, Accountable, Consulted, Informed |
| RAM | Random Access Memory |
| RDP | Remote Desktop Protocol |
| RDS | Remote Desktop Services |
| SIEM | Security Information and Event Management |
| SKU | Stock Keeping Unit - Azure virtual machine size designation |
| TCP | Transmission Control Protocol |
| TIO | GEHA Azure DevOps project hosting the source repository and pipelines |
| vCPU | Virtual Central Processing Unit |
| VM | Virtual Machine |