Application Migration Playbook CyberArk PAS Datacenter to Azure Migration v0.2 — DRAFT, FOR GEHA REVIEW

CyberArk PAS is GEHA's Privileged Access Management platform and is a foundational dependency for the entire migration program

Prepared for: G.E.H.A.

Eric Ullmann (Application Owner); Eric Ullmann (Director); Phil Costanzo (Admin / Support Manager)

Prepared by: Citius Healthcare Consulting

George Galindo, Cloud Architect

Peer Reviewer:Not yet assigned

Document Status:☒ DRAFT ☐ RELEASE CANDIDATE ☐ PUBLISHED

Date:14-Aug-2026

Everything a reader needs to orient themselves on this application is gathered here in a single view, so that no one has to hunt through later sections for a date, an owner or a target platform. Each field is owned by the section named beside it, and that owning section remains the authoritative source; this table is corrected to match it rather than the other way round. The scheduling fields — wave placement, migration strategy, cliff date, cliff driver and target cutover date — are recorded here in structured form and narrated in the executive summary that follows. Reading this table alone should be enough to understand what is moving, when it must move, and what forces the timing.

| Field | Value |
| --- | --- |
| Playbook Index ID | GEHA-DCM-CYBERARK-PAS-v0.1 |
| Application Version |  |
| Wave Placement | W1 |
| Migration Strategy | Parallel deployment. No migration. |
| Target Cutover Date | 10/01/2026 |
| User Access Method |  |
| Key Dependencies |  |
| Target Subscription & Landing Zone |  |
| Target Region & Paired Region | Central US, primary. East US, paired |
| Application Tier | 24h |
| RTO and RPO | 24h |
| Load Balancer | Internal load balancer. Cyberark.geha.com 10.110.12.39/10/100/12.39 |
| Deployment Pattern | 4 host(s) across 2 environment(s) |

Table 1.0 — Key Information

# 1. Document Control

Document control establishes who has changed this playbook, who has approved it, and the standard of evidence every statement within it must meet

## 1.1 Version History

| Version | Date | Author | Summary of Changes |
| --- | --- | --- | --- |
| 0.2 | 14-Aug-2026 | George Galindo, CitiusTech | Prepared for GEHA technical review. Evidenced fields cite their source and as-of date; fields GEHA has not yet supplied are shown as dated requests in Appendix B. Program decisions are not restated in the body — they are cited to Appendix A. |
| 0.3 | 08/15 – 09/15 2026 | Syed Ahmed | Various changes throughout the document. |

Table 1.1 — Version History

## 1.2 Approvers

| Name | Role | Approval Date |
| --- | --- | --- |
| Eric Ullmann | Application Owner |  |
| Phil Costanzo | Application Administrator |  |
| Phil Costanzo | Security Lead |  |
| George Galindo | Cloud Architect — Citius Healthcare Consulting |  |
| Saikat Majumdar | Migration & Platform Lead — Citius Healthcare Consulting |  |
| Scott Schultz | Enterprise Architect G.E.H.A. |  |

Table 1.2 — Approvers

# 2. Executive Summary

G.E.H.A will extend the existing CyberArk on premises configuration boundary  to Microsoft Azure by deploying two CyberArk  Privileged Cloud Connector servers to the Central US Azure region. The deployment will include both production and non-production environments . Each environment will consist of two Windows Server 2022 virtual machines deployed in Azure and placed behind an Azure standard internal load balancer. The solution will use G.E.H.A’s existing Azure landing zone/  landing zone management group pattern .

# 3. Application Overview

## 3.1 Business Purpose

CyberArk PAS is GEHA's enterprise Privileged Access Management (PAM) platform and a foundational dependency for the migration program. All migrated servers must have privileged credentials, service accounts, and application credentials managed through CyberArk. Because of this dependency, CyberArk support for Azure-hosted workloads must be established before the majority of application migrations can occur.

CyberArk is currently delivered as a SaaS-based solution, with cloud-hosted Vault and Central Policy Manager (CPM) services providing privileged access management, secure credential management, credential rotation, and RDP session monitoring and recording. These capabilities are required to satisfy GEHA's operational, security, and audit requirements for both existing and migrated workloads.

To extend CyberArk services to Azure, new CyberArk connector servers will be deployed within Azure to support migrated workloads while existing connectivity continues to support servers that remain in the datacenter. This dual-site operating model allows CyberArk services to be maintained across both environments throughout the migration program.

The Azure connector servers are a prerequisite for workload migration because they provide the communication path between Azure-hosted systems and the CyberArk SaaS platform. Without these connectors, migrated servers would not be able to leverage CyberArk for privileged access management, credential management, or session recording. As a result, the Azure connector deployment must be completed and operational before the associated application and server migrations can proceed.

Although Microsoft Entra Privileged Identity Management (PIM) has been identified as a potential alternative for certain privilege elevation functions, it does not provide equivalent session recording capabilities. Therefore, CyberArk will remain a required component of the target-state architecture to support GEHA's privileged access management, auditing, and compliance requirements.

## 3.2 Ownership & Stakeholders

| Role | Name |
| --- | --- |
| Business / Application Owner | Eric Ullmann |
| On-call / Support (Admin / Support Manager) | Phil Costanzo |

Table 3.2 — Ownership & Stakeholders

## 3.3 Criticality & Service Levels

This section captures the application's service-level and operational requirements, including availability targets, Recovery Time Objectives (RTOs), Recovery Point Objectives (RPOs), peak business operating periods, and migration scheduling constraints. These requirements establish the baseline for evaluating the target-state architecture and developing the migration approach.

| Business Criticality | Tier 2 |
| --- | --- |
| RTO (Recovery Time Objective) | 24 Hours |
| RPO (Recovery Point Objective) | undefined |
| Business Calendar Constraints | Open enrolment / open season — GEHA-wide constraint; Program blackouts: 2026-11, 2027-11 |
| Regulatory / Compliance Scope | Business impact: If the application was unavailable the impact could result in the loss of application certain privileged access management services. |

Table 3.3 — Criticality & Service Levels

# 4.0 Current State

The current state includes two Windows Server 2022 virtual machines running in an active active load balanced configuration with each server running  CyberArk Privilege  Cloud  Connector . The discovered CyberArk estate differs from the current state due to legacy tech debt as an outcome of Cyberark’s evolution to SaaS.

This section provides a detailed view of the application's current-state including its infrastructure, dependencies, integrations, data stores, service accounts, certificates, scheduled jobs, and supporting services. The information documented here establishes the baseline for target-state design, migration planning, testing, and validation activities.

## 4.1.1 Connector Host Inventory

| Host | Role | vCPU | Memory | Disk | Notes |
| --- | --- | --- | --- | --- | --- |
| PASPCCPRD101 | PSM (session broker) | 8 | 8 GB | 80 GB | Load-balanced pair |
| PASPCCPRD102 | PSM (session broker) | 8 | 8 GB | 80 GB | Load-balanced pair |
| PASCCPPRD101 | CCP / AIM | 2 | 4 GB | 80 GB |  |
| PASCCPPRD102 | CCP / AIM | 2 | 4 GB | 80 GB |  |
| PASCCPPRD103 | CCP / AIM | — | — | — | Sizing not supplied (D2) |
| PASCCPPRD104 | CCP / AIM | — | — | — | Sizing not supplied (D2) |

## 4.1.2 Primary Connectivity and Data Flows

CyberArk supports two primary access patterns within the GEHA environment: privileged user access and application credential retrieval.

For privileged user access, administrators connect through a load balancer that distributes traffic across the CyberArk Privileged Session Manager (PSM) servers (PASPCCPRD101 and PASPCCPRD102). The PSM servers broker the connection to the target production server, eliminating the need for direct administrative access. All privileged sessions are monitored and recorded, with session recordings stored within the CyberArk cloud recording vault and retained for 180 days in accordance with operational and compliance requirements.

For machine-to-machine authentication, applications retrieve credentials dynamically from CyberArk rather than storing privileged credentials locally. Current consumers include Venafi, Nexpose, UiPath Orchestrator, and ServiceNow, which obtain credentials through the CyberArk Central Credential Provider (CCP) servers (PASCCPPRD101-104). This approach reduces credential exposure and centralizes password management within the CyberArk platform.

CyberArk connector servers and the systems they support reside within the same on-premises production network, eliminating the need for firewall traversal between the connectors and their target systems. The primary controlled network path is the outbound connection from the CyberArk connector servers to the CyberArk Privileged Cloud tenant through the Palo Alto perimeter firewalls. This communication is established over TCP 1858 and TCP 443 and enables connectivity between the on-premises components and the CyberArk SaaS platform.

In addition, CyberArk components communicate with Active Directory to perform directory and identity-related functions using LDAP (TCP 389) and Global Catalog (TCP 3268) services. These directory integrations support authentication, user lookup, and authorization workflows across the CyberArk environment.

| Source | Destination | Data Flow / Purpose | Protocol / Port | Comments |
| --- | --- | --- | --- | --- |
| Administrators | Load Balancer | Initiate privileged administrative access sessions | HTTPS / RDP-related traffic | Entry point for privileged user access. |
| Load Balancer | PSM Servers (PASPCCPRD101, PASPCCPRD102) | Distribute privileged session traffic | Internal Application Traffic | Provides load balancing and high availability for PSM services. |
| PSM Servers | Production Target Servers | Broker privileged access sessions and record administrator activity | RDP | All privileged sessions are recorded and audited. |
| PSM Servers | CyberArk Recording Vault (SaaS) | Transfer and store session recordings | TCP 443 | Session recordings are retained for 180 days. |
| Venafi | CCP Servers (PASCCPPRD101-104) | Runtime credential retrieval | HTTPS | Credentials are retrieved dynamically rather than stored locally. |
| Nexpose | CCP Servers (PASCCPPRD101-104) | Runtime credential retrieval | HTTPS | Credentials are retrieved dynamically rather than stored locally. |
| UiPath Orchestrator | CCP Servers (PASCCPPRD101-104) | Runtime credential retrieval | HTTPS | Credentials are retrieved dynamically rather than stored locally. |
| ServiceNow | CCP Servers (PASCCPPRD101-104) | Runtime credential retrieval | HTTPS | Credentials are retrieved dynamically rather than stored locally. |
| CyberArk Connector Servers | CyberArk Privileged Cloud (SaaS) | Connector-to-cloud communication | TCP 1858, TCP 443 (Outbound) | Required for CyberArk SaaS connectivity and service operations. |
| CyberArk Connector Servers | Active Directory | Authentication, directory lookups, and authorization services | LDAP (TCP 389), Global Catalog (TCP 3268) | Supports Active Directory integration. |
| CyberArk Connector Servers | Managed Target Servers | Privileged access and credential management communications | Internal Network Traffic | Connectors and targets reside in the same production network. No firewall traversal is required. |

# 4.2 Session recording configuration

| PSM servers defined | PASPCCPRD101, PASPCCPRD102 |
| --- | --- |
| Load balancing | Load-balanced pair |
| Recording retention | 180 days |
| Recording storage | Recordings vault, cloud-hosted |

# 4.3 CCP application registrations (AIM)

| Consuming applications | Venafi, Nexpose, UiPath_Orchestrator, ServiceNow |
| --- | --- |
| CCP hosts | PASCCPPRD101, 102, 103, 104 |

# 4.4 Service Accounts

: Svcnexpose, SvcCMDBdc, SvcAutoQA, SVCVenafi.

# 4.5 Component versions

| Component | Version |
| --- | --- |
| CyberArk Privileged Cloud | 14.9 |
| Management Agent | 3.0 |
| Password Manager | 15 |
| Central Policy Manager (CPM) | 15 |
| Privileged Session Manager (PSM) | 15 |

## 4.5.1 Host Resource Specifications

| Server / Component | Role | OS / Version | Environment | Assessment Readiness | Holds Data? | CMDB / Asset ID |
| --- | --- | --- | --- | --- | --- | --- |
| PASCCPPRD101 | application/server host | Not yet provided —. | — | Not assessed — no Azure Migrate export on file (Appendix B item 01) | No | CMDB ID not recorded |
| PASCCPPRD102 | application/server host | Not yet provided — ). | — | Not assessed — no Azure Migrate export on file (Appendix B item 01) | No | CMDB ID not recorded |
| PASPCCPRD101 | application/server host | Not yet provided —. | — | Not assessed — no Azure Migrate export on file (Appendix B item 01) | No | CMDB ID not recorded |
| PASPCCPRD102 | application/server host | Not yet provided — | — | Not assessed — no Azure Migrate export on file (Appendix B item 01) | No | CMDB ID not recorded |

### 4.5.2 Operating System & Platform Readiness

The attributes recorded here determine whether a supported migration path exists at all and whether the machine will boot once it arrives in Azure. Operating system support status, boot type and partition style, architecture, clustering, static addressing, installed agents, licensing entitlement and any special storage are each confirmed against the running system rather than the inventory record. An out-of-support operating system is a decision for the business before it is a task for the migration team, and hardware-bound licensing can stop an application working the moment it moves. Several of these attributes also constrain the migration method chosen later, so they are settled before the method is fixed.

## 4.5.3 Application Software & Dependencies

The software layer is documented here in the terms that matter to a migration: exact installed version, whether the vendor supports that version on the target platform, and what else must travel with it. Scheduled jobs, file storage dependencies, license binding and client-side components are each recorded, because every one of them is a thing that silently stops working when the server underneath changes. License binding deserves particular attention: a license tied to a MAC address, host fingerprint or dongle will fail at the moment of cutover, and re-hosting it carries a vendor lead time. An unsupported configuration is a go/no-go item, not a hypercare issue.

## 4.4 Data & Database Tier

Not Applicable

### 4.5.1 Single Sign-On

Not Applicable4.5.4 Active Directory Security Group Register

Not Applicable

### 4.5.5 Service & Application Account Register

Service and application accounts are registered here separately from user accounts, because they fail differently: nothing breaks at cutover, and then a scheduled job runs and fails silently hours later. Each account records what it authenticates to, where its credential is held, its expiry or rotation position, the rights it carries, and the job or integration that depends on it. Every account must trace to a scheduled job, an integration or an explicit retirement decision; an account tracing to none of these is recorded as an open item. Where a managed identity can replace an account in the target, that substitution is recorded, and where it cannot, the reason is stated.- to be determined down

| Account Name | Type | What It Authenticates To | Credential Holder / Vault | Password Policy & Expiry | Rights Held | Depends On / Used By | Disposition at Cutover |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Cyberarkpc rec@geha.com | Not yet provided — | Not yet provided — T | To be provided by GEHA | ☐ Expiry date: ☐ Non-expiring | Not yet provided — I | Not yet provided | ☐ Replaced by a target credential or managed identity in §5.7 ☐ Retained for another purpose ☐ Disabled and deleted |

Table 4.5.5 — Service & Application Account Register

## 4.6 Network

## Cyberark currently uses an on premises F5 load balancer to provide access through DNS name cyberark.Geha.com The DNS currently resolved to 10.110.12.39 and 10.100.12.39. Because the on-premises F5 environment will be retired, an Azure load balancing solution will be required for the future-state CyberArk environment.The connector servers use outbound TCP 1858 and TCP 443 to the SaaS tenant. The connector servers are in the network as its targets so theres no firewall in-between    timetable.

PASCCPPRD101

PASCCPPRD102

PASCCPPRD103

PASCCPPRD104

## 4.7 Environment Inventory

Not applicable

## 4.8 Availability & Backup Position

Not applicable

## 5.0 Design Overview

CyberArk Privileged Access Security is a software-as-a-service platform. CyberArk hosts and operates the vault, the web portal, the policy engine and the session recording store. None of that moves. What GEHA operates is the connector tier: the servers that broker privileged sessions, rotate the credentials held in the vault, and hold the outbound tunnel to the tenant. The connector tier is what moves to Azure.

CyberArk will be deployed to Azure using a parallel deployment pattern. Two new Microsoft Windows Server 2022 servers are built for production and two for non-production, four in total. All four are deployed from the approved GEHA server image through the Bicep module library. The existing on-premises connectors are not migrated. They stay in service for the whole program, so privileged access never depends on one estate. As each application migrates, its credentials are re-pointed from the on-premises connectors to the Azure connectors. GEHA decommissions the on-premises connectors after the final wave, once no on-premises target remains.

Each environment is a pair of Standard_D8ls_v5 servers, eight virtual processors and sixteen gigabytes of memory, one in availability zone 1 and one in availability zone 2 in the Central US region. They sit behind a standard internal load balancer. The load balancer holds a client to the same server for the life of a session, which the CyberArk brokering handshake requires. Both servers run the Privileged Session Manager and the Secure Tunnel. Credential rotation runs active on the first server and passive on the second, so rotation survives the loss of either. The connector management agent, the identity connector and the dynamic access connector run on both.

The estate lands in the two security landing zone subscriptions, CIP-PRD and CIP-DEV, beneath Landing Zones and Corp. Each takes a /27 subnet inside the landing zone virtual network that already serves its subscription. No dedicated network is built. No connector holds a public address. All traffic transits the Azure Firewall Premium in the Central US secured hub, where it is inspected and, where outbound, translated. That covers administrator sessions inbound, brokered sessions to migrated servers, directory authentication and log forwarding to the data centers over ExpressRoute, and outbound traffic to the CyberArk tenant. Administrative access to the operating systems is through Azure Bastion only.

One firewall rule holds the boundary that makes the parallel pattern safe. The Azure connectors are denied brokered access to on-premises targets that have not yet migrated. Directory authentication and log forwarding to those same networks stay permitted, so the rule works by service, not by address. An application is served by one connector estate at any moment. The change that moves it is a configuration change in the CyberArk platform, not a cutover of a running server.

The design is stateless. The connectors hold no database, no application data and no persistent copy of any credential. Session recordings upload to the tenant and are not kept locally. Recovery from the loss of a server, a zone or the region is a redeployment from the approved image and a re-registration with the tenant, not a restore. This is also what keeps the migration low risk. Nothing is copied. Nothing is transformed. Reversing an application is the same configuration change applied in the opposite direction.

## Target State Architecture Diagram

## Design Overview

CyberArk Privileged Access Security is a software-as-a-service platform. CyberArk hosts and operates the vault, the web portal, the policy engine and the session recording store. None of that moves. What GEHA operates is the connector tier: the servers that broker privileged sessions, rotate the credentials held in the vault, and hold the outbound connection to the tenant. The connector tier is what moves to Azure.

CyberArk will be deployed to Azure using a parallel deployment pattern. Two new Microsoft Windows Server 2022 servers are built for production and two for non-production, four in total. All four are deployed from the approved GEHA server image through the Bicep module library. The existing on-premises connectors are not migrated. They stay in service for the whole program, so privileged access never depends on one estate. As each application migrates, its credentials are re-pointed from the on-premises connectors to the Azure connectors. GEHA decommissions the on-premises connectors after the final wave, once no on-premises target remains.

Each environment is a pair of Standard_D8ls_v5 servers, eight virtual processors and sixteen gigabytes of memory, one in availability zone 1 and one in availability zone 2 in the Central US region. They sit behind a standard internal load balancer with no session persistence, which the vendor requires only where automatic reconnection is enabled. Both servers run the Privileged Session Manager. Credential rotation runs active on the first server and passive on the second, so rotation survives the loss of either. The connector management agent, the identity connector and the dynamic access connector run on both. The Secure Tunnel, which runs on the existing on-premises connectors, is not installed here. It carries the tenant audit feed to the GEHA syslog collector today; that feed is re-pointed before the on-premises connectors are decommissioned and is tracked as a decommission dependency. The vendor also requires the component for the browser based remote session method used by employees working outside the GEHA network, so servers built without it serve remote desktop sessions from inside the network only; whether GEHA uses that method is not recorded in any source.

The estate lands in the two security landing zone subscriptions, CIP-PRD and CIP-DEV, beneath Landing Zones and Corp. Each takes a /27 subnet inside the landing zone virtual network that already serves its subscription. No dedicated network is built. No connector holds a public address. All traffic transits the Azure Firewall in the Central US secured hub, where it is inspected and, where outbound, translated. That covers administrator sessions inbound, brokered sessions to migrated servers, directory authentication and log forwarding to the data centers over ExpressRoute, and outbound traffic to the CyberArk tenant. Administrative access to the operating systems is by remote desktop from the GEHA administrative network to the connector private address.

One firewall rule holds the boundary that makes the parallel pattern safe. The Azure connectors are denied brokered access to on-premises targets that have not yet migrated. Directory authentication and log forwarding to those same networks stay permitted, so the rule works by service, not by address. An application is served by one connector estate at any moment. The change that moves it is a configuration change in the CyberArk platform, not a cutover of a running server.

The design is stateless. The connectors hold no database, no application data and no persistent copy of any credential. Session recordings upload to the tenant and are not kept locally. Recovery from the loss of a server, a zone or the region is a redeployment from the approved image and a re-registration with the tenant, not a restore. This is also what keeps the migration low risk. Nothing is copied. Nothing is transformed. Reversing an application is the same configuration change applied in the opposite direction.

## 5.0  Target State Architecture Diagram

| Field | Value |
| --- | --- |
| Diagram Name | CyberArk PAS Azure Future State, production and non-production CyberArk PAS Azure Build Detail, production and non-production CyberArk PAS Azure Subnet Address Allocation |
| Description | The future state figures show each environment, the traffic paths and the boundary maintained during the parallel run. The build detail figures show every resource the build creates, its containment within subscription, resource group, virtual network and subnet, the governance applied at deployment and the rule sets behind the paths. The subnet figure shows the address allocation within each subnet. |
| Use Case | Design review and sign-off; the Well-Architected review at 5.14; briefing the platform, network and security teams ahead of the build. |
| Source of Truth | CyberArk PAS Azure Future State Design and CyberArk PAS Azure Build Parameters. Every element on the figures corresponds to a row in the build parameters tables. |
| Author & Date | CitiusTech, 10 September 2026 |
| Sign-Off | Client approver Vendor approver |

Table 5.0: Target state architecture diagram

## 5.1  Migration Strategy

| Component | Approach | Target Service | Description |
| --- | --- | --- | --- |
| Connector tier | Build | CyberArk Privilege Cloud connectors on Azure infrastructure | New servers are deployed in Azure and registered as new connectors, extending the connector boundary of the existing platform. The on-premises connectors are not migrated. |
| Vault, web portal and platform services | Retain | CyberArk Privilege Cloud | Hosted and operated by CyberArk. No migration action. |
| On-premises connectors | Decommission in place | Not applicable | Retained in parallel until the final wave, then decommissioned by GEHA under its standard internal process. |
| Credential provider tier | Later phase | Not applicable | Addressed as a separate phase, sequenced with CyberArk. |
| Secure shell proxy tier | Later phase | Not applicable | Addressed as a separate phase. |
| DMZ environment | Later phase | Not applicable | Sequenced with the wider DMZ migration. |
| Privileged Threat Analytics | Retired | Not applicable | Decommissioned. |

Table 5.1: Migration strategy per component

This is a build rather than a move. There is no cutover of a running server and no data transfer. A target server joins the Azure estate when its platform is assigned to the Azure session manager group; the rotation engine assignment follows once its placement is confirmed by GEHA Security. The production connectors are replicated to East US 2 by Azure Site Recovery for disaster recovery.

## 5.2  Landing Zone Placement

| Field | Production | Non-production |
| --- | --- | --- |
| Management Group | GEHA › Landing Zones › Corp | GEHA › Landing Zones › Corp |
| Subscription Name and ID | CIP-PRD 87c9e9d1-06a7-4b33-87e0-5f04bcbfbfae | CIP-DEV e657afbe-61e4-4a5f-b6cb-cfbba50fd3a6 |
| Resource Groups | rg-sec-cyberark-prd. Workload lifecycle, created for this deployment. rg-alz-centralus-vnet-cip-cus-prd-01. Platform lifecycle, holds the network. | rg-sec-cyberark-dev. Workload lifecycle, created for this deployment. rg-alz-centralus-vnet-cip-cus-dev-01. Platform lifecycle, holds the network. |
| Primary Region | Central US | Central US |
| Paired Region | None. The connectors hold no state and are rebuilt rather than recovered. | As production. |
| Naming Standard | Security workload resource groups follow rg-sec-workload-environment. Virtual networks and subnets follow the platform convention for the region and environment. | As production. |
| Tagging | Environment, Owner, ApplicationName, Migrate Project, DataClassification, BusinessUnit, CostCenter, Criticality, DR and the backup exclusion tag, applied at deployment by the Bicep module per the CyberArk PAS Azure Tag Plan v1.0. | As production. |
| Inherited Policy Assignments | Corp scope: public IP on a network interface denied; workload gateway resources denied; private DNS zone creation denied; public network access disabled for platform services. Landing Zones scope: management port access from the internet blocked. GEHA management group: Allowed locations; Azure Compute Security Baseline compliance auditing. | As production. |
| Policy Exemptions | Proposed: two exemptions against the compute security baseline, scoped to the connector servers, covering the two operating system settings the product requires at 5.3. Raising them is a build step; no exemption exists today. | As production. |
| Role-Based Access Control | The workload team operates within rg-sec-cyberark-prd. Network, subnet and private endpoint provisioning remain with Cloud and Platform Services. Role assignment and privileged identity management remain with Security. | As production. |

Table 5.2: Landing zone placement

## 5.3  Compute

The connector servers are deployed from the approved GEHA Windows Server image through the Bicep module library. Operating system version and edition, hardening, security type, boot configuration, the installed agent set, endpoint protection and the patching mechanism are carried by that image. The table below records the values specific to this workload.

| Field | Production | Non-production |
| --- | --- | --- |
| Source Image | The approved GEHA Windows Server image, deployed by Bicep module. | As production. |
| Virtual Machine Size | Standard_D8ls_v5, 8 virtual processors and 16 GB memory. Two servers. | Standard_D8ls_v5, 8 virtual processors and 16 GB memory. Two servers. |
| Sizing Basis | Eight processors is the CyberArk small tier for the session manager and matches the current connector allocation. Observed utilization on the current connectors is 3.75 to 6 per cent processor and 66 to 68 per cent memory at the ninety-fifth percentile against 8 GB; memory is doubled accordingly. | As production. |
| Availability Design | Availability zones. One server in zone 1, one in zone 2. The physical zone behind each logical number is recorded in the build record. | As production. |
| Disk Configuration | Operating system disk only, 128 GB premium solid state. No data disk. Session recordings are uploaded to the tenant and are not retained on the connector. | As production. |
| Operating System Configuration | The Remote Desktop Services role is enabled; the session manager runs on it. Network level authentication is disabled on the session manager listener, as the product requires. The listener is reachable only through the internal load balancer from the on-premises client ranges. Both settings are covered by the proposed exemptions at 5.2. | As production. |
| Client Access Licensing | Remote Desktop Services client access licenses are required for the session host role; the scheme and source are with GEHA licensing. The session manager service accounts are created as domain accounts, which the vendor requirements call for on Server 2022. The license server route is recorded in the flow document. | As production. |
| Agents and Extensions | Monitoring, endpoint security, log forwarding and domain join are carried by the approved image. The CyberArk components are installed by the vendor connector installer following deployment. | As production. |
| Proximity and Latency | No co-location requirement. The two servers are deliberately separated across zones; session brokering tolerates inter-zone latency; a connection stays on one node for its life under the five tuple hash. | As production. |
| Scheduling | No scheduled shutdown. The connectors must be reachable whenever a privileged session is requested. | No scheduled shutdown, on the same basis. |
| Scaling | Fixed size, two servers per environment. A further connector is added by deploying an additional server from the same image into the same subnet and joining it to the farm; the subnet is sized to accommodate this. | As production. |

Table 5.3: Compute

## 5.4  Data Platform

Not applicable. The connectors hold no database and no persistent application data. Credentials, safes, policies, audit records and session recordings are held in the CyberArk Privilege Cloud tenant. A connector that fails is redeployed and re-registered; there is nothing to restore.

## 5.5  Storage and File Services

Not applicable. No file share, object storage or attached data volume is required. The only storage is the operating system disk recorded at 5.3 and the managed storage account used for boot diagnostics. Session recordings transit the connector and are written to the tenant.

## 5.6  Network

| Field | Production | Non-production |
| --- | --- | --- |
| Virtual Network | vnet-cip-cus-prd-01, in rg-alz-centralus-vnet-cip-cus-prd-01. | vnet-cip-cus-dev-01, in rg-alz-centralus-vnet-cip-cus-dev-01. |
| Subnet | snet-sec-cyberark-cus-prd-01, a /27 within the landing zone address space, allocated by Cloud and Platform Services. | snet-sec-cyberark-cus-dev-01, a /27 within the landing zone address space, allocated by Cloud and Platform Services. |
| IP Addressing | Static on all three addresses. The load balancer front end takes the fourth usable address in the subnet, connector 01 the fifth and connector 02 the sixth. Three of twenty-seven usable addresses are consumed. | As production. |
| Connectivity to On-Premises | ExpressRoute. Two redundant circuits at 1 Gbps each, per the landing zone record of 01-Jul-2026, attached to the virtual wide area network; the hub each lands on is not an exported object. | As production. |
| Hub Attachment | Both landing zone networks attach to the virtual wide-area network hub. No workload peering is created. | As production. |
| Network Security Group | nsg-sec-cyberark-cus-prd-01, associated to the subnet. Inbound: TCP 3389 from the on-premises client and administrative ranges, since the load balancer preserves the client address; the platform probe tag on both probe ports; TCP 135, 445 and the dynamic range from the SCCM site server and the ServiceNow MID server. Outbound: as permitted by the hub firewall rule set. | nsg-sec-cyberark-cus-dev-01, on the same terms. |
| Routing | No user-defined route. Egress is directed through the hub firewall by the platform route. | As production. |
| Firewall and Egress Control | Azure Firewall in the Central US secured hub performs east-west inspection and outbound translation. Eight rules govern this workload: administrator session inbound; connector to Azure target; connector to the CyberArk tenant; connector to directory services; connector to the log platform; connector to endpoint security; site server and discovery inbound; and a deny on brokered sessions from the Azure connectors to on-premises targets that have not yet migrated. | As production. |
| Private Endpoints and Private DNS | None required. No platform service is consumed privately by this workload. | As production. |
| Load Balancing | lbi-sec-cyberark-cus-prd-01, standard internal, no public address. Distribution is by the platform default five tuple hash and no session persistence is configured. The vendor requires persistence only where automatic session reconnection is enabled, and that feature is off unless turned on; this build leaves it off. Two health probes are configured, both taken from the vendor worked example: a transport check on TCP 3389 and a service check against the session manager health endpoint, each at a thirty second interval with an unhealthy threshold of three, the Azure form of the vendor values. Idle timeout twelve hundred seconds. TCP reset on idle enabled. The backend pool contains both connector interfaces. | lbi-sec-cyberark-cus-dev-01, on the same terms. |
| Web Application Firewall | Not applicable. No web application is published by this workload. | As production. |
| DNS Records | cyberark-prd.geha.com, an A record resolving to the load balancer front end, placed in the geha.com zone by the platform team. Azure networks resolve through the on-premises domain controllers. | cyberark-dev.geha.com, on the same terms. |
| Certificates | The session manager health endpoint requires a web server binding with a certificate on each connector; its issuer follows the GEHA certificate standard and is set at build. The connectors validate the tenant certificate outbound. | As production. |

Table 5.6: Network

## 5.7  Identity and Access

| Field | Production | Non-production |
| --- | --- | --- |
| Directory Model | On-premises Active Directory Domain Services, reached over ExpressRoute. Six domain controllers across the two data centers. The connectors bind domain services directly. | As production. |
| Application Authentication | Unchanged. Administrators authenticate to the CyberArk platform, which brokers the session. No new authentication method is introduced. | As production. |
| Group-to-Role Mapping | Unchanged. The Active Directory groups governing platform access are not affected by the connector build; access is granted at the platform, not at the connector. | As production. |
| Azure Role Assignments | Proposed. Workload team: Contributor within rg-sec-cyberark-prd. Platform team: Network Contributor at the network resource group. Security team: role assignment and privileged identity management at subscription scope. No standing Owner assignment. | As production. |
| Managed Identities | As required by the approved image and the platform agents. The CyberArk service accounts are not replaced by managed identities; the product authenticates to its own tenant. | As production. |
| Service Accounts | The existing connector service accounts are reused rather than replaced, so safe permissions and audit history remain continuous. Credential custody, rotation owner and rotation interval are unchanged. | As production. |
| Secrets and Certificate Storage | No workload secret is stored in Azure. The connector holds its registration credential locally as the product requires; all other credentials are held in the CyberArk vault. | As production. |
| Privileged Access | Administrative access to the connector operating system is by remote desktop from the GEHA administrative address ranges to the connector private address, over ExpressRoute. The network security group on the connector subnet permits those ranges and denies all other inbound management traffic. No connector holds a public address, and management port access from the internet is blocked by policy. Elevation follows the existing privileged identity management model. | As production. |
| Break-Glass Access | Per the landing zone standard; break glass exclusions sit in the conditional access policy list per the landing zone record of 01-Jul-2026. No workload-specific break-glass account is created. | As production. |
| Programmatic Access Paths | The identity connector binds the directory for the platform. The dynamic access connector is carried forward with its existing target inventory and policies. | As production. |

Table 5.7: Identity and access

## 5.8  Security and Compliance

| Field | Production | Non-production |
| --- | --- | --- |
| Cloud Security Posture | Microsoft Defender for Cloud, applied at the tenant root. | As production. |
| Endpoint Protection | Carried by the approved image. Reports outbound on TCP 443 through the hub firewall. | As production. |
| Encryption at Rest | Platform-managed keys. The connectors hold no persistent sensitive data. | As production. |
| Encryption in Transit | All traffic is encrypted in transit: session brokering on TCP 3389, tenant traffic on TCP 443, vault protocol on TCP 1858 and directory traffic over the standard signed channels. | As production. |
| Security Log Collection | Operating system and application logs are forwarded to the four log platform indexers on TCP 9998, with forwarder management on TCP 8089 to the Splunk deployment server. The program log platform target is Datadog forwarded to Exabeam, per the SIEM and IAM discovery record of 10-Jul-2026; the connector forwarding destination follows that program decision and is open item O-07 in the design. The tenant audit feed that reaches the GEHA syslog collector through the on-premises Secure Tunnel today is re-pointed before decommission, open item O-18. Platform diagnostics are collected to the platform workspace by policy. Session recordings are held in the CyberArk tenant. | As production. |
| Vulnerability Management | Carried by the approved image, under the existing scanning cadence, remediation ownership and remediation window by severity. | As production. |
| Patching | Carried by the approved image and the platform update mechanism. Maintenance is staggered so that a patch never takes both servers in an environment at once. | As production. |
| Compliance | Data residency within the continental United States. The regional policy assignment restricts deployment to approved United States regions and the design lands in Central US. Compute, disks, diagnostics and the log platform are all within the United States. | As production. |

Table 5.8: Security and compliance

## 5.9  Resilience and Recovery

| Field | Production | Non-production |
| --- | --- | --- |
| Backup | Backup is provided by Cohesity, the GEHA enterprise backup service, by agentless snapshots of the managed disks; no agent is installed. The connector servers carry the backup exclusion tag from deployment so that the native Azure enrollment policy does not bind them. The only Recovery Services vault is the Site Recovery vault in East US 2, which holds replication and no backup items. | As production. |
| Recovery Method | Redeployment from the approved image and re-registration with the tenant. The connectors hold no state, so recovery is a rebuild rather than a restore. | As production. |
| Recovery Objectives | Recovery time is bounded by redeployment and re-registration. A single server failure carries no recovery objective, as the surviving server continues to serve. No recovery point objective applies; no state is held on the connector. | As production. |
| Availability Commitment | Two servers across two availability zones behind a zone-redundant internal load balancer. Loss of a single zone removes one server and sessions continue on the survivor. | As production. |
| Disaster Recovery Design | Azure Site Recovery replication of both production connectors from Central US to East US 2 (Recovery Services vault rsv-sec-cyberark-eus2-dr-01 *, recovery plan rp-sec-cyberark-prd-01 *, replica disks only until failover). At failover the replicas start in East US 2 zones 1 and 2 with the same host names, join the DR load balancer lbi-sec-cyberark-eus2-dr-01 *, and GEHA DNS re-points cyberark-prd.geha.com. The DR virtual network reaches the East US hub by cross-region connection, pending confirmation by GEHA Network. Failback and the full procedure are in the Rollback Plan v1.0. | Not replicated. Non-production is rebuilt from the pipeline. |
| Disaster Recovery Test | Connector loss and zone loss at build validation (test plan cases D-04 and D-05); replication status, a test failover into an isolated East US 2 network, replica start and registration, DR load balancer, DNS re-point rehearsal, tenant allowlist and cleanup on test day 4 (cases G-01 to G-09); failback rehearsed at the first annual GEHA DR exercise. | As production. |

Table 5.9: Resilience and recovery

## 5.10  Monitoring and Operations

| Field | Production | Non-production |
| --- | --- | --- |
| Log Analytics Workspace | The platform workspace. No workload workspace is created. | As production. |
| Diagnostic Settings | Applied automatically to every resource by policy assignment. | As production. |
| Platform and Guest Metrics | Platform metrics by default. Guest metrics through the monitoring agent carried by the approved image. | As production. |
| Alert Rules | Proposed. Six workload alerts in addition to the platform standard: connector unreachable; session manager service stopped; credential rotation engine stopped; connector management agent unregistered; load balancer probe failure on both servers; operating system disk above eighty-five per cent. | As production, at a lower severity on each. |
| Action Groups and Routing | Proposed: the existing platform action group and its escalation path. | As production. |
| Application Monitoring | Connector health and component status are reported in the CyberArk tenant, which is the authoritative view of whether a connector is serving. | As production. |
| Dashboards and Reporting | Connector status is read from the CyberArk tenant; platform health from the standard Azure workbooks. No workload dashboard is required. | As production. |
| Update Management | Carried by the approved image and the platform update mechanism, against the staggered maintenance at 5.8. | As production. |

Table 5.10: Monitoring and operations

## 5.11  Cost and Licensing

| Field | Production | Non-production |
| --- | --- | --- |
| Cost Model | Run cost for the connector estate is carried in the program cost model against the sizes at 5.3 and Central US pricing. It is not restated here. | As production. |
| Cost Profile During Migration | Both estates run in parallel until the final wave, so the program carries the on-premises connectors and the Azure connectors concurrently. The reduction is realized at decommission. | As production. |
| Reservations and Commitments | None. The workload runs at on-demand pricing until it reaches steady state and the estate has stopped growing. | As production. |
| Windows Licensing | Azure Hybrid Benefit applicability is open item O-08 in the design, with GEHA licensing. | As production. |
| Remote Desktop Services Licensing | Client access licenses for the session host role; scheme and source with GEHA licensing. | As production. |
| Cost Controls | No scheduled shutdown applies. The connectors must be reachable whenever a privileged session is requested. | As production. |
| Attribution | Cost is attributed by the tags applied at 5.2, with a budget and threshold alerts set at deployment. | As production. |

Table 5.11: Cost and licensing

## 5.12  Deployment Method

| Field | Production | Non-production |
| --- | --- | --- |
| Deployment Approach | Infrastructure as code. The servers are deployed from the approved GEHA Windows Server image through the Bicep module library and the existing release pipeline. | As production. |
| Tooling and Repository | Bicep modules from the vetted GEHA module library, deployed through Azure DevOps pipelines. | As production. |
| Pipeline and Approvals | The existing release pipeline and its approval gates. Production change control follows the GEHA standard. | The existing release pipeline and its approval gates. |
| Environment Parity | Both environments are deployed from the same image and one parameterized module. They differ only in subscription, network, name tokens and alert severity. | As production. |
| Configuration Drift | Pipeline redeployment corrects infrastructure drift. Operating system drift is answered by redeployment from the approved image rather than in-place remediation. Connector component versions are managed from the CyberArk tenant by the connector management agent. | As production. |
| State and Secret Handling | Deployment state and pipeline secrets are held in Azure Key Vault, the GEHA standard for secrets per the landing zone record of 01-Jul-2026, under the existing access model. Service principals are used for pipeline authentication. | As production. |

Table 5.12: Deployment method

CyberArk Privileged Access Security

Azure Connector Estate · Post-Migration Test and Validation Plan

Version 1.1  ·  23 September 2026  ·  Draft for GEHA review

| Program | Data Center Migration | Author | George Galindo, Cloud Architect |
| --- | --- | --- | --- |
| Application | CyberArk PAS, Privilege Cloud connectors | Application owner | Eric Ullmann, GEHA Security |
| Scope | Production connector pair, parallel run, disaster recovery | Peer reviewer | To be assigned |
| Basis | Azure Future State Design v2.9; Network Data Flows v3.1; Azure Build Parameters v3.2 | Status | Draft |

Summary

Here is the short version of what this plan does and why it matters.

What we are testing. Two new CyberArk Privilege Cloud connectors in Azure, sitting behind an internal load balancer at cyberark-prd.geha.com. Nothing is being moved or switched off. The on-premises connectors keep doing their job for every server that hasn't migrated, and the vault, portal and discovery stay in the CyberArk tenant exactly as they are today. That makes this a parallel run, and the test plan is built around proving the two estates can coexist safely.

How the test is organized. Seven groups, run over four days. Day 1 confirms the Azure build matches the build parameters (group A), every network path opens and every deny path refuses (group B), and both connectors register cleanly in the tenant next to the on-premises pair (group C). Days 2 and 3 put real sessions through the Azure connectors, spread them across both servers, and knock one server out to prove failover works (group D). Day 3 also runs the controls that keep the two estates apart (group E) and checks that backup, alerting and patching see the new servers (group F). Day 4 proves the connectors replicate to East US 2 and can be started there on a test failover (group G).

The two tests that matter most. Group E is the one to watch. It moves an account so that an Azure connector is asked to reach a server that hasn't migrated, and the expected result is a refusal logged at the hub firewall. If that session ever reaches the target, testing stops and no cutover request goes forward until the rule is fixed and the case reruns clean. The second is the failover pair in group D: stop the session manager on one connector, then take a whole availability zone away, and confirm users on the other connector never notice.

How a case passes. Every case names the steps, the role that runs it, the evidence file to save and the expected result. A case passes only when that evidence is in the evidence store and matches. Anything without evidence is recorded as not run, never as passed. The pack goes to GEHA Security and Enterprise Architecture for acceptance before the CAB agenda request.

Who is involved. A CitiusTech build engineer runs the build and network cases and assembles the evidence. GEHA's CyberArk administrator owns everything in the tenant. The GEHA Cloud Platform Team owns the firewall policy and supplies addresses. A GEHA test user opens the sessions. Service owners for Splunk, SCCM, ServiceNow, RDS licensing, Cohesity, Rapid7 and DNS confirm their services see the new servers. Plan on about 12.6 hours of hands-on execution over days 1 to 3, roughly 3.8 hours on day 4, plus the built-in waits for configuration refresh, CPM cycles and initial replication.

Cutover and rollback. Cutover is a tenant configuration change, not an infrastructure change: the first production platform is pointed at the Azure group, one session is run each way, and both groups are confirmed active. If anything fails, the platform is pointed back at the on-premises group and the same checks rerun. Rollback takes under 30 minutes and no system is ever taken out of service. The rollback call belongs to Phil Costanzo, GEHA’s admin and support manager for CyberArk; cutover itself is approved by Security, Enterprise Architecture and CAB together. The companion Rollback Plan has the full procedure.

What's still open. Four items sit outside this test cycle and carry an owner and a date in the program decision register: where the rotation engine will run, the Secure Tunnel audit feed re-point, the credential provider decommission, and a direct monitoring route if live session monitoring can't pass through the load balancer. Disaster recovery adds one more: how the tenant treats a replica that starts with the same name as its production connector, which day 4 is designed to find out.

Workflow at a glance

Figure 1. Validation workflow: roles as lanes, phases as columns, gates G0 to G9 on the phase boundaries, decision points along the bottom, and the evidence store every case feeds. Appendix A describes the same workflow in table form.

1  Purpose and scope

This plan validates the two new Privilege Cloud connector servers built in the CIP-PRD subscription, vm-sec-cyberark-cus-prd-01 and 02 (computer names AZPASPCCPRD101 and AZPASPCCPRD102), behind the internal load balancer cyberark-prd.geha.com, and their recovery in East US 2. The deployment is parallel: the on-premises connectors PASPCCPRD101 and PASPCCPRD102 keep serving on-premises servers, and the vault, portal and account discovery remain in the Privilege Cloud tenant unchanged.

Sessions are routed to a connector group by platform. The Azure pair is registered in the tenant as one Configured PSM Server whose address is the load balancer name, and a platform sends its accounts to that group by carrying the group ID. A migrated server is served by the Azure group when its account sits on a platform that carries the Azure ID; unmigrated servers stay on platforms that carry the on-premises ID.

The plan proves five things in order: the Azure estate is built as specified (group A), its network paths work (B), both connectors are registered in the tenant beside the on-premises pair (C), a migrated server can be brokered through the Azure group with failover across both zones (D), and the two estates cannot cross (E). Group F confirms the platform services that operate the servers see them. Group G proves the connectors replicate to East US 2 and start there on a test failover.

Non-production is validated with the same cases using the dev names, after production. Performance under production load and the ServiceNow change record are outside this plan. Open items are named in words; their owners and dates are kept in the program decision register.

2  Roles

| Code | Role | Responsibility |
| --- | --- | --- |
| BE | Build engineer | CitiusTech. Deploys and configures the Azure resources, the connector software and the Site Recovery objects; captures build evidence. |
| CA | CyberArk administrator | GEHA Security. Owns the Privilege Cloud tenant configuration: Configured PSM Servers, platforms, safes, accounts, tenant allowlist. |
| CP | Cloud Platform Team | GEHA. Supplies subnet and address values; owns the hub firewall policy, the landing zone networks and the East US 2 landing zone. |
| TU | Test user | A GEHA privileged user working from the administrative ranges, with membership of the test safes. |
| SO | Service owner | GEHA owner of the platform service under test (Splunk, SCCM, ServiceNow, RDS licensing, Cohesity, Rapid7, DNS). |
| SR | Security and EA reviewers | GEHA Security and Enterprise Architecture. Accept the evidence pack at the presentation. |

Table 1. Roles used in the case tables

3  Entry criteria

Testing starts when every row below is true. Each row names who confirms it. E-11 applies to day 4 only.

| Ref | Criterion | Detail | Confirmed by |
| --- | --- | --- | --- |
| E-01 | Build complete | Every Built row of Azure Build Parameters Table 2 exists; the values in Table 8 have been supplied by the Cloud Platform Team and applied. | BE, CP |
| E-02 | Domain and service accounts | Both connectors joined to GEHA.com; PSMConnect and PSMAdminConnect exist as domain accounts and are used by the PSM services. | BE |
| E-03 | Network rules | Rule collection group rcg-sec-cyberark applied to DefaultFirewallPolicy; the NSG rule set applied to nsg-sec-cyberark-cus-prd-01; IP groups created. | CP |
| E-04 | Connector software | Connector Management, Identity Connector, Privileged Session Manager and the dynamic access connector installed on both servers in that order, both at the same PSM version; each server restarted after the PSM install; PSM hardening run in the In Domain mode. The rotation engine is installed only once GEHA Security has confirmed its placement. | BE, CA |
| E-05 | Installer ownership | The account used for the second PSM install is not a direct owner of the PSMUnmanagedSessionAccounts safe. | CA |
| E-06 | Certificates | Each connector holds a certificate from GEHA internal PKI whose subject alternative names include the server name and cyberark-prd.geha.com, bound to the PSM listener. | BE |
| E-07 | Tenant configuration | Configured PSM Servers holds an entry for the Azure group, created by copying an existing entry so that PSMProtocolVersion is retained, with ID equal to the Azure group name and Address cyberark-prd.geha.com. A test platform cloned from the production Windows platform, and one from the Linux platform, carry the Azure group ID under UI and Workflows, Privileged Session Management. | CA |
| E-08 | Test targets | One migrated Windows server and one migrated Linux server in the Corp landing zone, each with an account onboarded to a test safe on the matching test platform. One unmigrated on-premises server with an account on a production platform that carries the on-premises group ID. | CA, SO |
| E-09 | Test users | One test user with the Use Accounts and List Accounts permissions on the test safes and Initiate CPM account management operations; one reviewer with Monitor and View Audit permissions. | CA |
| E-10 | Evidence store | A folder under the program workspace for this test cycle, one subfolder per case, receiving screenshots, exports and logs as each case closes. | BE |
| E-11 | Disaster recovery ready | Replication enabled on both connectors at least one day before day 4 and both replicated items Protected; the East US 2 landing zone, DR subnet, NSG and load balancer built per Azure Build Parameters Table 2; the recovery plan created; an isolated test-failover virtual network in East US 2 provided by the Cloud Platform Team. | BE, CP |

Table 2. Entry criteria

4  Test cases

Each case lists the steps in order, the evidence to capture, the expected result, the role that runs it and an estimated duration. A case passes only when the evidence is in the evidence store and matches the expected result. Durations are for one environment and exclude waiting on external teams.

4.1  Group A: Platform build verification

Day 1, morning. Proves the Azure estate exists as specified before any connector test runs. All cases are read only.

| Ref | Case | Steps | Evidence | Expected result | Role | Min |
| --- | --- | --- | --- | --- | --- | --- |
| A-01 | Resource inventory | 1. Run az resource list for rg-sec-cyberark-prd and export to CSV. 2. Compare each row with Azure Build Parameters Table 2, Built rows. 3. Record any resource present but not in Table 2. | CSV export; marked-up copy of Table 2 | Every Built row present with the name, type, SKU, zone and location in Table 2; no extra resources | BE | 20 |
| A-02 | Network placement | 1. Run az network nic show for nic-sec-cyberark-cus-prd-01 and 02. 2. Confirm the subnet reference and the private address of each. 3. Run az network vnet subnet show for snet-sec-cyberark-cus-prd-01 and confirm the NSG association. | Command output for both NICs and the subnet | Both NICs in snet-sec-cyberark-cus-prd-01 with the addresses from Table 8; nsg-sec-cyberark-cus-prd-01 associated with the subnet | BE | 15 |
| A-03 | Load balancer configuration | 1. Open lbi-sec-cyberark-cus-prd-01 in the portal. 2. Record the front end address, backend pool members, load balancing rule and both health probes. | Portal screenshots of each blade | Front end at the Table 8 address; both NICs in the pool; TCP 3389 rule with five tuple hash and no session persistence; probes on TCP 3389 and HTTPS 443, interval 30 seconds, unhealthy threshold 3 | BE | 15 |
| A-04 | Policy compliance | 1. Open Azure Policy, Compliance, filter to rg-sec-cyberark-prd. 2. Export the compliance state. | Compliance export | No non-compliant resource against the Corp landing zone assignments | BE | 10 |
| A-05 | Diagnostic settings | 1. Open Diagnostic settings on the load balancer, the NSG and both virtual machines. 2. Record the destination workspace. | Screenshots | Diagnostic settings present on all four resources and sent to the platform workspace named in the design | BE | 10 |
| A-06 | Domain membership and time | 1. On each connector run nltest /dsgetdc:geha.com and w32tm /query /status. 2. Run whoami /upn as the build engineer. | Command output | Secure channel to a GEHA.com domain controller; time source is a domain controller; offset under five minutes | BE | 10 |
| A-07 | PSM service accounts and NLA | 1. Open Services on each connector and record the logon account of the CyberArk Privileged Session Manager service. 2. Open System Properties, Remote, and record the Network Level Authentication setting. | Screenshots | Service runs as the GEHA.com PSMConnect account; Network Level Authentication disabled on both servers | BE | 10 |
| A-08 | Hardening applied | 1. Open Local Security Policy, AppLocker, and confirm rules exist for executables and DLLs. 2. Read the RDS SecurityLayer and MinEncryptionLevel registry values. 3. Confirm SMB1 is disabled (Get-WindowsOptionalFeature). | Screenshots and command output | AppLocker rules present; SecurityLayer and MinEncryptionLevel set by the hardening; SMB1 disabled | BE | 15 |
| A-09 | Probe health after hardening | 1. After A-08, open the load balancer backend pool health. 2. If a probe reads unhealthy, inspect the Windows firewall rule added by hardening for 168.63.129.16. | Screenshot of backend health | Both servers Healthy on both probes. If the hardening rule blocks inbound probes from 168.63.129.16, add an inbound exception and record the change against the build | BE | 10 |
| A-10 | Health endpoint | 1. From a client in the subnet, request https://CONNECTOR/psm/api/health on each server, substituting the connector name. 2. Request the same path through cyberark-prd.geha.com. | Response captures | HTTP 200 from each server and through the load balancer name | BE | 10 |
| A-11 | Certificate binding | 1. In IIS on each connector open the site binding for 443 and export the certificate details. 2. From a client in the administrative ranges, browse to https://cyberark-prd.geha.com/psm/api/health and inspect the certificate. | Certificate details and browser capture | Subject alternative names include the server name and cyberark-prd.geha.com; issuer is GEHA internal PKI; chain trusted; not expired | BE | 10 |
| A-12 | Tags | 1. Run az resource list with tag output for rg-sec-cyberark-prd. | Export | Every resource carries the keys and values in Azure Build Parameters Table 7 | BE | 5 |

Table 3. Group A, 12 cases, about 2.3 hours of execution.

4.2  Group B: Network path verification

Day 1, afternoon. One case per path in Network Data Flows Table 2.1. Run from each connector unless the step says otherwise.

| Ref | Case | Steps | Evidence | Expected result | Role | Min |
| --- | --- | --- | --- | --- | --- | --- |
| B-01 | Vault protocol | 1. On each connector run Test-NetConnection VAULTHOST -Port 1858, substituting the vault host from the tenant export. 2. Pull the hub firewall log entry for the connection. | Command output; firewall log line | TcpTestSucceeded True on both; the log shows the exact FQDN network rule matched | BE, CP | 10 |
| B-02 | Tenant services | 1. On each connector run Test-NetConnection on port 443 to one host in each FQDN set in Azure Build Parameters Table 3. 2. Run the same test to a host not in any set (for example a public news site). 3. Run the revocation host tests on port 80. | Command output for every host | Every listed host succeeds; the unlisted host is refused; the firewall log shows the application rule matched for each success | BE, CP | 20 |
| B-03 | Rapid7 agent | 1. On each connector confirm the Insight agent service is running. 2. In the Insight console locate both servers and record the last check in. | Service screenshot; console screenshot | Both servers registered; last check in within 15 minutes | BE, SO | 10 |
| B-04 | Domain controllers | 1. On each connector run klist purge, then klist get krbtgt. 2. Run nslookup geha.com and nslookup of the vault host. 3. Run w32tm /resync. | Command output | Ticket granting ticket issued; DNS answers from a GEHA.com domain controller; time resync succeeds | BE | 10 |
| B-05 | Splunk forwarding | 1. On each connector run splunk list forward-server. 2. In Splunk search index=* host=CONNECTOR earliest=-15m. 3. In the deployment server console confirm both servers appear. | Command output; search results; console screenshot | Forwarder connected to an indexer on 9998; events from both servers present; both listed under the deployment server on 8089 | BE, SO | 15 |
| B-06 | SCCM client | 1. Push the client from MECMSITEPRD101 to both connectors. 2. In the SCCM console open the device record for each. 3. On each connector open Configuration Manager in Control Panel and run Machine Policy Retrieval. | Console screenshots; client log extract | Client installed; device record active with a management point assignment; policy retrieval succeeds | SO | 30 |
| B-07 | ServiceNow discovery | 1. Run a discovery schedule from SNMIDPRD301 that includes the connector subnet. 2. Open the resulting CI records. | Discovery status; CI screenshots | A CI exists for each connector with the correct name, addresses and operating system | SO | 20 |
| B-08 | Remote desktop licensing | 1. On each connector run Get-RDLicenseConfiguration. 2. Open Event Viewer, TerminalServices-Licensing, after the first brokered session in D-01. | Command output; event log extract | RDSLICPRD301 listed as the license server; a client access license issued on first session | BE, SO | 10 |
| B-09 | Administrator entry | 1. From a workstation in the GEHA administrative ranges, RDP to cyberark-prd.geha.com and to each connector name. 2. From a workstation outside those ranges, repeat. | Connection results | Succeeds from the administrative ranges; refused from outside them (NSG rules 100 and 120) | TU | 15 |
| B-10 | Inbound deny from the network | 1. From a server in another Corp subnet, run Test-NetConnection CONNECTOR -Port 3389. | Command output | Refused (NSG rule 4000) | BE | 5 |

Table 4. Group B, 10 cases, about 2.4 hours of execution.

4.3  Group C: Tenant registration

Day 1, end of day. The vendor verification steps for a new connector, applied to both servers.

| Ref | Case | Steps | Evidence | Expected result | Role | Min |
| --- | --- | --- | --- | --- | --- | --- |
| C-01 | Connector Management status | 1. In the Privilege Cloud portal open Connector Management, Connectors. 2. Select the row for each Azure connector and open the component list. 3. Record the status of every component and its version. 4. Repeat for PASPCCPRD101 and PASPCCPRD102. | Screenshots of each component list | Every component on both Azure connectors shows an active status with no failed component; both on-premises connectors unchanged | CA | 15 |
| C-02 | System health | 1. Open the system health dashboard in the portal. 2. Record the entries for both Azure connectors. | Screenshot | Both Azure connectors present and healthy | CA | 5 |
| C-03 | Identity Connector | 1. On each connector open the Identity Connector Configuration program, Status tab. 2. Record the last connection time and result. | Screenshots | Last connection recent and successful on both; both registered under the same customer ID | CA | 10 |
| C-04 | PSM service and server entry | 1. On each connector confirm the CyberArk Privileged Session Manager service is running. 2. In the portal open Configured PSM Servers and record the Azure group entry and the on-premises entry. | Screenshots | Service running on both; the Azure entry shows ID equal to the group name, Address cyberark-prd.geha.com and the PSM credential object; the on-premises entry unchanged | CA | 10 |
| C-05 | Dynamic access connector | 1. In the portal open the dynamic access connector pool and record both connectors. | Screenshot | Both connectors registered and online in the designed pool | CA | 5 |
| C-06 | Rotation engine | 1. In Connector Management record whether the rotation engine component is present on either Azure connector. | Screenshot | Present only once GEHA Security has confirmed its placement; otherwise absent on both and recorded as deferred | CA | 5 |

Table 5. Group C, 6 cases, about 0.8 hours of execution.

4.4  Group D: Brokered sessions to migrated targets

Days 2 and 3. Proves the Azure group serves a migrated server end to end, distributes across both connectors and survives the loss of one.

| Ref | Case | Steps | Evidence | Expected result | Role | Min |
| --- | --- | --- | --- | --- | --- | --- |
| D-01 | RDP session through the Azure group | 1. Test user signs in to the portal from the administrative ranges. 2. Opens the Windows test account (test platform carrying the Azure group ID) and clicks Connect. 3. Runs one command on the target that leaves a trace (for example creates a file). 4. Ends the session. 5. Reviewer opens the session in Monitoring and records the PSM server name. | Session record with PSM server name; recording; target evidence | Session brokered by AZPASPCCPRD101 or 102; recording complete and playable; the trace exists on the target | TU, CA | 20 |
| D-02 | SSH session through the Azure group | 1. As D-01 with the Linux test account. | As D-01 | As D-01 on TCP 22 | TU, CA | 15 |
| D-03 | Distribution across connectors | 1. Open ten sessions in succession to the Windows test target, closing each before the next. 2. Record the PSM server for each session. | Session list export | Sessions land on both connectors; no run of sessions pinned to one server | TU, CA | 30 |
| D-04 | Connector failure | 1. Stop the CyberArk Privileged Session Manager service on connector 01. 2. Note the time; watch the load balancer backend health. 3. Open three sessions. 4. Start the service; watch backend health return. | Timestamps; backend health screenshots; session records | Connector 01 marked unhealthy within 90 seconds; all three sessions brokered by 02 with no user error; 01 returns to Healthy after restart | BE, TU | 30 |
| D-05 | Zone loss | 1. Deallocate vm-sec-cyberark-cus-prd-01 (zone 1). 2. Repeat D-01 and D-06. 3. Start the virtual machine and confirm C-01 status returns. | Portal screenshots; session record | Sessions continue on connector 02; recordings retrievable; 01 rejoins with all components active | BE, TU, CA | 40 |
| D-06 | Recording retrieval | 1. Reviewer retrieves the D-01 and D-02 recordings from the portal and plays each to the end. | Playback screenshots | Both recordings complete, with the session end visible | CA | 10 |
| D-07 | Live session monitoring | 1. Test user opens a session as in D-01 and keeps it open. 2. Reviewer opens live monitoring of that session from the portal. 3. Record whether monitoring connects and to which server. | Screenshots | Monitoring connects to the connector running the session. If it fails, record it as the live monitoring route item: live monitoring needs a direct route to each connector name | TU, CA | 20 |
| D-08 | Concurrent sessions | 1. Five test users, or one user with five accounts, open sessions in parallel to the test targets and hold them for ten minutes. 2. Record CPU and memory on both connectors from Azure Monitor. | Session list; metrics charts | All sessions brokered; CPU and memory within the headroom stated in the design for Standard_D8ls_v5 | TU, BE | 30 |
| D-09 | CPM verification | 1. In the portal open the Windows test account, Overview, Last Verified, and click Verify. 2. Wait one CPM cycle. 3. Record the compliance status and which CPM performed the verification. | Screenshots | Account marked for verification then verified. If the rotation engine is not on the Azure connectors, the verification is performed by the existing CPM and this is recorded against the rotation engine placement item | CA | 20 |
| D-10 | Account discovery | 1. Run a discovery that includes the migrated test target. 2. Confirm the target is found. | Discovery results | Target discovered through the tenant scanner; no dependency on the Azure connectors | CA | 15 |

Table 6. Group D, 10 cases, about 3.8 hours of execution.

4.5  Group E: Parallel run and separation

Day 3. The controls that make the parallel run safe: the on-premises estate is unchanged, and no session can cross from the Azure group to an unmigrated server.

| Ref | Case | Steps | Evidence | Expected result | Role | Min |
| --- | --- | --- | --- | --- | --- | --- |
| E-01 | On-premises estate unchanged | 1. Test user opens a session to the unmigrated test target (account on a production platform carrying the on-premises group ID). 2. Reviewer records the PSM server. | Session record | Brokered by PASPCCPRD101 or 102; recording playable | TU, CA | 15 |
| E-02 | No session from Azure to an unmigrated server | 1. CyberArk administrator moves the unmigrated target account to the test platform carrying the Azure group ID. 2. Wait one configuration refresh (ConfigurationRefreshInterval, default 600 seconds). 3. Test user attempts a session. 4. Administrator moves the account back and waits one refresh. 5. Repeat E-01. | Session attempt result; firewall log; E-01 repeat record | The attempt fails to reach the target; the hub firewall log shows the deny (no rule from the connector subnet to on-premises server ranges); E-01 succeeds again after the move back | CA, TU, CP | 40 |
| E-03 | Platform re-point rehearsal | 1. Move the migrated Windows test account from the test platform (Azure ID) to a platform carrying the on-premises ID. 2. Wait one refresh; open a session; record the PSM server. 3. Move it back; wait one refresh; open a session; record the PSM server. | Two session records; account property export before and after | Sessions follow the platform on the next connection; no account property lost | CA, TU | 40 |
| E-04 | Secure Tunnel and audit feed unaffected | 1. On PASPCCPRD101 confirm the Secure Tunnel service is running. 2. In the SIEM confirm audit events from the tenant are still arriving. | Service screenshot; SIEM search | Running; events arriving. The re-point of this feed is a separate item and is not part of this test | CA, SO | 10 |
| E-05 | Credential provider consumers | 1. Pull the IIS logs from the four PASCCP hosts for the test window. 2. Filter for source addresses in the migrated test target set. | Log extract | No requests from any migrated test target | CA | 15 |

Table 7. Group E, 5 cases, about 2 hours of execution.

4.6  Group F: Operations evidence

Day 3. Confirms the platform services that run the servers after cutover see them.

| Ref | Case | Steps | Evidence | Expected result | Role | Min |
| --- | --- | --- | --- | --- | --- | --- |
| F-01 | Backup protection | 1. In the Cohesity console open the protection status of both virtual machines. 2. Confirm a snapshot completed after build. 3. Restore one disk to an isolated resource group, or schedule the restore and record the date. | Console screenshots; restore job record | Both protected by the agentless Azure policy; snapshot present; restore succeeds or is scheduled | SO | 30 |
| F-02 | Alerting | 1. Stop the PSM service on one connector for two minutes. 2. Record the alert received and its route. | Alert record | The alert rule named in the design fires and reaches the named route | BE | 15 |
| F-03 | Patching | 1. Deploy one approved update to both connectors through SCCM outside session hours. 2. Confirm installation and reboot. | SCCM deployment status | Installed on both; reboot completed; C-01 status active afterwards | SO | 30 |

Table 8. Group F, 3 cases, about 1.3 hours of execution.

4.7  Group G: Disaster recovery

Day 4, after day 3 closes and before hypercare exit. Proves the connectors replicate to East US 2 and start there. The test failover uses an isolated virtual network so that production, the DR subnet and the tenant registration of the production pair are untouched; G-09 proves production is unaffected while it runs.

| Ref | Case | Steps | Evidence | Expected result | Role | Min |
| --- | --- | --- | --- | --- | --- | --- |
| G-01 | Replication status | 1. In the portal open the Recovery Services vault, Replicated items, and record both connectors with status, RPO and last recovery point. 2. Record the time from enable replication to Protected. | Screenshots; timing note | Both items Protected; RPO within the replication policy; recovery points present for both | BE, CP | 15 |
| G-02 | Replication paths | 1. On each connector run Test-NetConnection on port 443 to the cache storage account blob endpoint, to login.microsoftonline.com and to the Site Recovery service host for the vault region. | Command output | All succeed on both connectors (NSG rules 210 to 240 and the allow-site-recovery firewall rule in Azure Build Parameters Tables 3 and 4) | BE | 15 |
| G-03 | Test failover | 1. Open the recovery plan and run Test failover with the latest processed recovery point into the isolated test-failover virtual network. 2. Record start and completion times. 3. Record both test virtual machines with zone, size and tags. | Job record; screenshots; timing note | Both replicas running in East US 2, zone 1 and zone 2, Standard_D8ls_v5; the plan completes without error; tags recorded against the Azure Tag Plan, including the backup exclusion tag | BE, CA | 60 |
| G-04 | Replica start and registration | 1. From a jump host in the isolated network, on each test virtual machine record the computer name, domain membership and the state of the CyberArk Privileged Session Manager service. 2. In Connector Management record what the tenant shows for the replica while it runs. | Screenshots | Computer names AZPASPCCPRD101 and 102; PSM service running. The tenant behaviour for a second instance of a registered connector is recorded, whatever it is; a conflict or duplicate entry becomes a recovery-plan action owned by GEHA Security | CA, BE | 30 |
| G-05 | DR load balancer | 1. Open lbi-sec-cyberark-eus2-dr-01 and record the front end, probes and rule. 2. Add the two test virtual machine NICs to the backend pool and record health. 3. Remove them after G-08. | Screenshots | Parameters match Azure Build Parameters Table 5; both test virtual machines Healthy on both probes | BE | 20 |
| G-06 | DNS re-point rehearsal | 1. GEHA DNS creates cyberark-drtest.geha.com pointing at the DR front end address. 2. From the isolated network run nslookup and request https://cyberark-drtest.geha.com/psm/api/health. 3. Record the time to change and propagate; remove the record after G-08. | Command output; timing note | The record resolves; HTTP 200 through the DR load balancer; change time recorded | CP, SO | 30 |
| G-07 | Tenant allowlist | 1. Cloud Platform Team provides the East US egress public address. 2. CyberArk administrator confirms it is on the tenant allowlist. | Screenshot | Address present on the allowlist before any real failover | CA, CP | 15 |
| G-08 | Cleanup | 1. Run Cleanup test failover on the recovery plan with notes. 2. Confirm the test virtual machines are removed and replication remains Protected. | Job record; screenshot | Test virtual machines removed; both items Protected | BE | 20 |
| G-09 | Production unaffected | 1. During G-03 and after G-08 repeat D-01 against production. 2. Reviewer records the PSM server and the Connector Management status of the production pair. | Session records; screenshots | Brokered by AZPASPCCPRD101 or 102 both times; the production pair active throughout | TU, CA | 20 |

Table 9. Group G, 9 cases, about 3.8 hours of execution, plus the initial replication before day 4.

5  Schedule

The cases total about 12.6 hours of execution across the three test days and about 3.8 hours on day 4: groups A, B and C on day 1, group D on days 2 and 3, groups E and F on day 3, group G on day 4. Waiting time for configuration refresh (600 seconds per platform change), CPM cycles, initial replication and service owner actions is additional. Day 3 closes with the evidence pack and the summary sheet for the Security and Enterprise Architecture presentation; day 4 evidence is added to the pack before hypercare exit.

6  Exit criteria

| Ref | Criterion |
| --- | --- |
| X-01 | Groups A, B and C pass, or each failure has a named owner and a fix date before the CAB agenda request. |
| X-02 | D-01 to D-07 pass. D-08 passes or the sizing is re-examined before cutover. |
| X-03 | E-01, E-02 and E-04 pass with no exception. |
| X-04 | F-01 shows both connectors protected. |
| X-05 | Deferred items are recorded with an owner and a date: rotation engine placement, Secure Tunnel audit feed re-point, credential provider decommission, live monitoring route. |
| X-06 | The evidence pack is complete: one subfolder per case, each holding the evidence named in the case, and a signed summary sheet. |
| X-07 | Before hypercare exit: G-01, G-03, G-07, G-08 and G-09 pass; the G-04 result is recorded with any recovery-plan action and its owner; the G-06 change time is recorded. |

Table 10. Exit criteria

7  Cutover day validation and rollback

Cutover for this application is the first production platform, or set of production accounts, pointed at the Azure group. The steps below run on the cutover day in order; CV-06 runs only if rollback is invoked. Cutover is approved by GEHA Security, Enterprise Architecture and CAB together; the rollback decision belongs to Phil Costanzo, application admin and support manager, on the recommendation of the CyberArk administrator. The CyberArk PAS Rollback Plan v1.0 holds the full procedure.

| Ref | Step | Detail | Role | Min |
| --- | --- | --- | --- | --- |
| CV-01 | Pre-cutover check | Morning of cutover: repeat A-09, A-10, C-01 and C-02, and confirm G-01 shows both replicated items Protected. | BE, CA | 30 |
| CV-02 | Production re-point | Apply the Azure group ID to the first production platform, or move the first production accounts to the Azure platform, per the platform assignment model. Wait one configuration refresh. | CA | 20 |
| CV-03 | Production session check | Repeat D-01 and D-02 against one production target per platform re-pointed. | TU, CA | 30 |
| CV-04 | On-premises check | Repeat E-01 for one unmigrated production target. | TU, CA | 15 |
| CV-05 | Both groups active | Confirm the tenant session list shows sessions on both the Azure and the on-premises groups. | CA | 10 |
| CV-06 | Rollback, if invoked | Restore the on-premises group ID on the platform, or move the accounts back. Wait one refresh. Repeat CV-03 against the on-premises group. No infrastructure change is needed. | CA | 30 |

Table 11. Cutover day steps

8  Deferred items

The following are outside this test cycle and carry an owner and a date in the program decision register: the rotation engine on the Azure connectors; the credential provider tier, which decommissions with the on-premises connectors; the Secure Tunnel audit feed re-point; a direct monitoring route to each connector if D-07 shows the load balancer cannot carry live monitoring; and any recovery-plan action recorded at G-04.

Appendix A  Workflow description

This appendix describes the validation workflow drawn in Figure 1 as swimlanes, phases, tasks, gates and decisions. Task identifiers are the case references in section 4; gate identifiers are new.

A.1  Swimlanes

Six lanes, top to bottom: Cloud Platform Team (CP), Build engineer (BE), CyberArk administrator (CA), Test user (TU), Service owners (SO), Security and EA reviewers (SR). The evidence store is drawn as a data store at the right edge, receiving an artifact from every task.

A.2  Phases and gates

| Phase | Lane | Tasks in order | Gate at the end | Gate rule |
| --- | --- | --- | --- | --- |
| 0 Entry | CP, BE, CA | E-01 to E-10 in Table 2 | G0 Ready to test | All ten entry criteria confirmed; otherwise return to the owner of the failed criterion |
| 1 Platform build (day 1 am) | BE | A-01 to A-12, sequential; A-09 follows A-08 directly | G1 Built as specified | No failed case, or every failure has an owner and a fix date; A-09 unhealthy sends a firewall exception task to BE before G1 |
| 2 Network paths (day 1 pm) | BE, CP, SO, TU | B-01 to B-10; B-03, B-05, B-06, B-07 may run in parallel with the service owners | G2 Paths open | All paths pass; a refused path returns to CP for the rule collection |
| 3 Tenant registration (day 1 close) | CA | C-01 to C-06 in order | G3 Registered | C-01 to C-05 active on both connectors; C-06 recorded as present or deferred |
| 4 Brokered sessions (days 2 and 3) | TU, CA, BE | D-01, D-02, D-06, D-03, D-04, D-05, D-07, D-08, D-09, D-10 | G4 Serves migrated targets | D-01 to D-07 pass; D-08 pass or sizing review; a D-07 failure opens the live monitoring route item and a decision |
| 5 Parallel run (day 3) | CA, TU, CP, SO | E-01, E-02, E-03, E-04, E-05 | G5 Estates separated | E-01, E-02 and E-04 pass with no exception; an E-02 session that reaches the target is a stop: cutover cannot be requested |
| 6 Operations (day 3) | SO, BE | F-01, F-02, F-03 | G6 Operable | F-01 protected; F-02 and F-03 pass or deferred with owner |
| 7 Acceptance | BE, SR | Assemble evidence pack and summary sheet; one hour presentation to Security and EA | G7 Accepted | Both teams accept; playbook status set to Finalized; CAB agenda request submitted the Friday before CAB |
| 8 Cutover day | BE, CA, TU | CV-01 to CV-05; CV-06 on rollback | G8 Cut over | CV-03, CV-04 and CV-05 pass; otherwise CV-06 and a return to G7 for the next CAB |
| 9 Disaster recovery (day 4, before hypercare exit) | BE, CP, CA, TU, SO | E-11, then G-01, G-02, G-03, G-04, G-09 during G-03, G-05, G-06, G-07, G-08, G-09 after G-08 | G9 Recoverable | G-01, G-03, G-07, G-08 and G-09 pass; G-04 recorded with any recovery-plan action and owner; G-06 change time recorded |

Table 12. Phases, tasks and gates

A.3  Decision points

| Decision | Where | Yes path | No path |
| --- | --- | --- | --- |
| Probes healthy after hardening? | After A-09 | A-10 | Add inbound exception for 168.63.129.16, rerun A-09 |
| All tenant paths open? | After B-02 | B-03 | Return to CP: rule collection fix, rerun B-01 and B-02 |
| Rotation engine present? | C-06 | D-09 verifies through the Azure engine | D-09 verifies through the existing CPM; record against the rotation engine placement item |
| Live monitoring reaches the host? | D-07 | Continue | Open the live monitoring route item; decide a direct monitoring route before G4 |
| Session from Azure reaches an unmigrated server? | E-02 | Stop: firewall finding to CP; no cutover request until rerun passes | Continue to E-03 |
| Evidence accepted by Security and EA? | G7 | Finalize playbook, submit CAB agenda request | Address findings, re-present |
| Production sessions pass on cutover day? | CV-03 to CV-05 | Hypercare begins | CV-06 rollback; return to G7 for the next CAB |
| Replica registers with the tenant? | G-04 | Continue to G-05 | Record a re-registration step as a recovery-plan action owned by GEHA Security; continue to G-05 |
| Test failover cleaned up and replication Protected? | G-08 | G-09, then G9 | Remove the test resources by hand, record, rerun G-01 |

Table 13. Decision points

A.4  Drawing notes

Draw phases as columns left to right and lanes as rows. Each task is a box labeled with its reference and title, placed in the lane of the role that runs it; tasks with two roles sit in the first role's lane with a dashed link to the second. Gates are diamonds on the phase boundary spanning all lanes, labeled G0 to G9. Decision points are diamonds inside a phase with Yes and No exits labeled per Table 13. Every task has a thin arrow to the evidence store. Waiting time (configuration refresh, CPM cycle, initial replication) is drawn as a clock marker on E-02, E-03, D-09, CV-02 and G-01. The cutover day phase is separated from the test phases by a heavier vertical rule labeled CAB approval; the disaster recovery phase follows it and ends at a vertical rule labeled Hypercare exit.

Revision history

| Version | Date | Change |
| --- | --- | --- |
| v1.1 | 23-Sep-2026 | Basis moved to Azure Build Parameters v3.2 and its table numbers. Register codes removed; open items named in words. Group G, disaster recovery, added with entry criterion E-11, exit criterion X-07, cutover check CV-01 extended, phase 9 and gate G9, two decision points and drawing notes. Roles extended for Site Recovery, the East US 2 landing zone and DNS. Rollback authority named. Workflow diagram added as Figure 1. |
| v1.0 | 15-Sep-2026 | Initial plan: groups A to F, entry and exit criteria, cutover day steps, workflow description. |

Table 14. Revision history

# 9. Roles & Responsibilities

Responsibility across the migration lifecycle is assigned here using the RACI model, with exactly one accountable owner for each task. The distinction between responsible and accountable matters most at the two points where migrations stall: the go/no-go decision and the rollback decision. Consulted and informed parties are recorded so that teams learn of changes affecting them before rather than after the event. Where this matrix and the ownership register disagree, the ownership register governs and the discrepancy is corrected here. TBD

| Task | App Owner | Migration Team | Platform / Cloud | Security | End Users | Admin / Support Manager Phil Costanzo |
| --- | --- | --- | --- | --- | --- | --- |
| Landing zone placement | I | C | A/R | C | I | I |
| Target design | C | A/R | C | C | I | C |
| Sizing & cost model | C | R | A | I | I | C |
| Replication build | I | A/R | C | I | I | I |
| Identity & RBAC | C | R | C | A | I | C |
| Migration rehearsal | C | A/R | C | I | I | C |
| Integration re-point | I | R | C | C | I | A |
| Go / no-go decision | A | R | C | C | I | C |
| Cutover execution | A | R | C | I | I | C |
| Reconciliation & acceptance | A | R | I | I | C | C |
| Rollback decision | A | R | C | I | I | C |
| Operational readiness | C | R | A | C | I | C |
| Decommission | A | R | C | C | I | C |

Table 9 — Roles & Responsibilities

.

## 10.3 Dependencies

Dependencies are requirements controlled outside this migration and therefore outside the migration team's ability to accelerate. Subscription provisioning, quota increases, circuit changes, policy exemptions, desktop image cadence and the readiness of other waves are typical, and each runs to a schedule owned by someone else. Every entry names an owner, the date by which it is needed and its current status, so that a slipping dependency is visible while there is still time to act. Dependencies at risk are escalated to the program rather than absorbed silently into the application's own float.

Table 10.3 — Dependencies

# 12. Sign-Off

Approval to execute is recorded here, and each signatory is a named individual accountable for the sections relevant to their role rather than a representative of a team. Signing confirms that the target design, the cutover plan and the rollback position documented in this playbook are approved for execution as written. Signatures are obtained before the go/no-go gate rather than retrospectively. A playbook signed on this basis is the authority under which the cutover proceeds.

By signing below, stakeholders confirm that the target design, cutover plan and rollback position documented in this playbook are approved for execution.

| Name | Role | Date |
| --- | --- | --- |
| To be prov TBD | Application Owner |  |
| To be provided by GEHA TBD | Migration / Technical Lead |  |
| To be provided by GEHATBD | Platform / Cloud Lead |  |
| To be provided by GEHA TBD | Security | T |
| To be provided by GEHATBD | DBA / Production Control |  |
| To be provided by GEHATBD | Network |  |

Table 12 — Sign-Off

CONFIDENTIAL — Prepared by Citius Healthcare Consulting. This document contains confidential and proprietary information and is intended solely for the named recipient. It may not be copied, disclosed or distributed, in whole or in part, without the prior written consent of Citius Healthcare Consulting.