## Cover Page
CyberArk PAS Test Cases
Project Name: | GEHA Data Center Migration: CyberArk PAS |  |  | Client Name: | GEHA
Application: | CyberArk PAS, Privilege Cloud connectors |  |  | Application Owner: | Eric Ullmann, GEHA Security
Scope: | Dev first, then production |  |  | Test Cases: | 14 cases
Prepared By: | CT Team |  |  | Peer Reviewer: | George Gallindo
Version / Date: | 1.0 / 05-10-2026 |  |  | Status: | Draft for GEHA review
Document Revision History:
Document Version # | Revision Date | Prepared By | Approved By | Approval Date | Summary of Changes
1 | 2026-10-05 | Saikat/Amitendra | TBD
This document is CitiusTech Internal and contains proprietary information, including trade secrets of CitiusTech or the Client. Neither the document nor any of the information contained in it may be reproduced or disclosed to any unauthorized person under any circumstances without the express written permission of CitiusTech.

## TC-INF-01
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm the internal load balancer health probes show both connectors as healthy | Module/Program Name/Menu Path: | Phase 1: Azure infrastructure and network connectivity Azure portal > Internal load balancer > Backend pools, Monitoring > Metrics, Load balancing rules
Test Case ID: | TC-INF-01 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm both connector servers are members of the internal load balancer backend pool, both are healthy on the RDP and session manager probes, and the RDP rule forwards TCP 3389 to 3389. | Pre-requisites/Test Set-up: | 1. Both connector servers, their network interfaces and the internal load balancer have been deployed through the Bicep pipeline, and the pipeline run finished without errors. 2. The connector software is installed on both servers through Connector Management, both are on the same version, and both have been restarted after installation. 3. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off.
Dependencies (H/W and S/W): | 1. Azure portal access to the CIP-DEV subscription (non-production) or the CIP-PRD subscription (production). 2. Internal load balancer: recorded before testing in non-production; lbi-sec-cyberark-cus-prd-01 in rg-sec-cyberark-prd in production. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (Build engineer) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | In the Azure portal, open the internal load balancer for the environment. | Non-production: load balancer name recorded before testing Production: lbi-sec-cyberark-cus-prd-01 | The internal load balancer for the environment opens in the portal.
2 | Open Backend pools and confirm both connector network interfaces are members. | Non-production: connector 01 (zone 1) and connector 02 (zone 2) Production: vm-sec-cyberark-cus-prd-01 and 02 (AZPASPCCPRD101 and AZPASPCCPRD102) | Both connectors are in the backend pool.
3 | Open Monitoring, Metrics, choose Health Probe Status and split by backend IP address. Record the result for each server on both probes. | RDP probe: TCP 3389 Session manager health check: HTTPS 443 (/psm/api/health) | Both connectors show 100% healthy on both probes.
4 | Open Load balancing rules and record the RDP rule and its idle timeout. | RDP rule: TCP 3389 | The RDP rule forwards TCP 3389 to 3389. The idle timeout is recorded.

## TC-INF-02
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm the connection name resolves to the load balancer private front-end address | Module/Program Name/Menu Path: | Phase 1: Azure infrastructure and network connectivity GEHA DNS: nslookup from an administrative workstation and from connector 01; session manager health page in a browser
Test Case ID: | TC-INF-02 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the name users connect to resolves to the load balancer private front-end address from both the GEHA network and the connector, no public address is returned, and the health page answers with a trusted certificate. | Pre-requisites/Test Set-up: | 1. The connection name for the environment exists in GEHA DNS and points at the load balancer front-end address. 2. An administrative workstation on the GEHA network is available, and connector 01 can be reached through the approved administrative path. 3. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off.
Dependencies (H/W and S/W): | 1. Administrative workstation on the GEHA network with a web browser. 2. Connector 01. 3. Azure portal access to view the load balancer front-end address. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (Build engineer) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | From an administrative workstation on the GEHA network, run nslookup for the connection name. | Non-production: nslookup cyberark-connector-dev.geha.com Production: nslookup cyberark-prd.geha.com | The name resolves to the load balancer private front-end address . No public address is returned.
2 | Run the same lookup from connector 01. | Non-production: nslookup cyberark-connector-dev.geha.com Production: nslookup cyberark-prd.geha.com | The name resolves to the load balancer private front-end address. No public address is returned.
3 | Compare the address returned with the load balancer front-end address shown in the Azure portal. | Non-production: front-end address recorded before testing Production: 10.9.250.7 | The address returned from both machines matches the load balancer front-end address.
4 | From the workstation, browse to the session manager health page using the connection name. | https://<connection name>/psm/api/health | The health page returns HTTP 200 with a trusted certificate.

## TC-INF-03
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm approved firewall paths are allowed and traffic to unmigrated on-premises servers is blocked | Module/Program Name/Menu Path: | Phase 1: Azure infrastructure and network connectivity Hub firewall; PowerShell Test-NetConnection on connector 01 and connector 02
Test Case ID: | TC-INF-03 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the hub firewall lets the connectors reach the approved destinations and blocks an Azure connector from reaching an on-premises server that has not migrated yet. | Pre-requisites/Test Set-up: | 1. The CyberArk rule set is applied to the hub firewall: the approved ports are open, and the rule that blocks connector traffic to unmigrated on-premises servers is in place. 2. One migrated Windows server and one migrated Linux server are in Azure, and one on-premises server that has not migrated is available for the blocked-connection test. 3. GEHA Network is available to pull the hub firewall log lines. 4. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off.
Dependencies (H/W and S/W): | 1. Connector 01 and connector 02, reached through the approved administrative path. 2. Windows PowerShell (Test-NetConnection). 3. Hub firewall logs (GEHA Network). | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (Build engineer, GEHA Network) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Medium
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Sign in to connector 01 through the approved administrative path and open PowerShell. | NA | PowerShell is open on connector 01.
2 | Run Test-NetConnection to a GEHA.com domain controller on ports 389 and 3268. | GEHA.com domain controller Ports 389 and 3268 | TcpTestSucceeded returns True on both ports.
3 | Run Test-NetConnection to the Splunk indexer on port 9998. | Splunk indexer Port 9998 | TcpTestSucceeded returns True.
4 | Run Test-NetConnection to the migrated Windows test server on port 3389 and to the migrated Linux test server on port 22. | Migrated Windows test server, port 3389 Migrated Linux test server, port 22 | TcpTestSucceeded returns True for both servers.
5 | Run Test-NetConnection to the CyberArk portal address on port 443. | CyberArk portal address Port 443 | TcpTestSucceeded returns True.
6 | Run Test-NetConnection on port 3389 to the on-premises test server that has not migrated. | Unmigrated on-premises test server Port 3389 | The connection fails. If this connection succeeds, stop testing and raise it with GEHA Network before going further.
7 | Repeat steps 2 to 6 from connector 02. | Same destinations and ports as steps 2 to 6 | Steps 2 to 5 return TcpTestSucceeded True and step 6 fails, the same as on connector 01.
8 | GEHA Network pulls the hub firewall log lines for every connection attempt. | Firewall log for all attempts from both connectors | The firewall log shows an allow rule for each connection in steps 2 to 5, and shows the step 6 connection denied, on both connectors.

## TC-INF-04
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm both connectors can reach the CyberArk tenant on ports 443 and 1858 | Module/Program Name/Menu Path: | Phase 1: Azure infrastructure and network connectivity PowerShell Test-NetConnection on both connectors; hub firewall log; CyberArk portal > Connector Management
Test Case ID: | TC-INF-04 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm both connectors reach the tenant vault on port 1858 and the portal on port 443, port 1858 passes the vault rule without inspection, and both connectors show current communication with the vault. | Pre-requisites/Test Set-up: | 1. The hub firewall public address is on the tenant IP allowlist. 2. The CyberArk rule set is applied to the hub firewall. 3. The connector software is installed on both servers through Connector Management. 4. The CyberArk administrator is available to give the vault and portal addresses, and GEHA Network is available to check the firewall log. 5. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off.
Dependencies (H/W and S/W): | 1. Connector 01 and connector 02. 2. Windows PowerShell (Test-NetConnection). 3. Hub firewall logs (GEHA Network). 4. CyberArk Privilege Cloud portal (Connector Management). | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (Build engineer, GEHA Network) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Medium
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Ask the CyberArk administrator for the vault address and portal address of the tenant. | NA | The vault and portal addresses are received and recorded.
2 | On connector 01, run Test-NetConnection to the vault address on port 1858. | Test-NetConnection <vault address> -Port 1858 | The connection succeeds.
3 | Run Test-NetConnection to the portal address on port 443. | Test-NetConnection <portal address> -Port 443 | The connection succeeds.
4 | Repeat steps 2 and 3 on connector 02. | Same commands as steps 2 and 3 | Both ports succeed from connector 02.
5 | GEHA Network confirms from the firewall log which rule allowed port 1858, and that the traffic was not sent through TLS or IDS/IPS inspection. | Firewall log for port 1858 from both connectors | Port 1858 matches the vault rule and passes without inspection. No resets or drops are logged against it.
6 | In Connector Management, check the last communication time for both connectors. | NA | Both connectors show current communication with the vault.
7 | Save the evidence in the TC-INF-04 subfolder of the evidence folder for the environment. | Command output; firewall log line; Connector Management screenshot | Evidence is saved in the case subfolder and matches the expected results. A case without evidence is recorded as not run, never as passed.

## TC-INF-05
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm administrative access to the connectors is restricted to the approved path | Module/Program Name/Menu Path: | Phase 1: Azure infrastructure and network connectivity Azure portal > connector network interfaces; RDP attempts from outside GEHA, from on-premises and from the administrative ranges
Test Case ID: | TC-INF-05 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm neither connector has a public IP address, and that RDP to the connectors works only from the GEHA administrative ranges and is refused from anywhere else. | Pre-requisites/Test Set-up: | 1. The CyberArk rule set is applied to the hub firewall. 2. The test user is a GEHA privileged user working from the administrative ranges. 3. A connection outside the GEHA network (for example, a home internet connection without VPN) and an on-premises workstation outside the GEHA administrative ranges are available. 4. GEHA Network is available to pull the firewall log lines. 5. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off.
Dependencies (H/W and S/W): | 1. Azure portal access. 2. RDP client on each test machine. 3. Azure Bastion, only if GEHA provides it for this subscription. 4. Hub firewall logs (GEHA Network). | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (Build engineer, Test user, GEHA Network) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Medium
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | In the Azure portal, confirm neither connector network interface has a public IP address. | Connector 01 and connector 02 network interfaces | No public address exists on either connector.
2 | From outside the GEHA network, try to open RDP to each connector. | Home internet connection without VPN | The connection is refused on both connectors.
3 | From an on-premises workstation outside the GEHA administrative ranges, try to open RDP to each connector. | On-premises workstation outside the administrative ranges | The connection is refused on both connectors.
4 | From a workstation in the administrative ranges (or through Azure Bastion, if GEHA provides it for this subscription), open RDP to each connector. | Workstation in the GEHA administrative ranges | RDP succeeds on both connectors.
5 | GEHA Network pulls the firewall log lines for steps 3 and 4. | Firewall log for steps 3 and 4 | The firewall log shows the step 3 attempts blocked.

## TC-CON-01
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm both Azure connectors and all their components are active in the CyberArk portal | Module/Program Name/Menu Path: | Phase 2: Connector health and service hardening CyberArk Privilege Cloud portal > Connector Management > Connectors; Configured PSM Servers settings
Test Case ID: | TC-CON-01 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm both Azure connectors are registered and healthy, every component is active and on the same version, the Azure session manager entry uses the load balancer name, and the on-premises connectors are unchanged. | Pre-requisites/Test Set-up: | 1. The connector software is installed on both servers through Connector Management, both are on the same version, and both have been restarted after installation. 2. The Azure session manager entry exists in the tenant with the load balancer name as its address. 3. The CyberArk administrator can sign in to the Privilege Cloud portal. 4. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off.
Dependencies (H/W and S/W): | 1. CyberArk Privilege Cloud portal. 2. CyberArk administrator account. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (CyberArk administrator) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Sign in to the CyberArk Privilege Cloud portal as the CyberArk administrator. | CyberArk administrator account | The portal opens with administrator access.
2 | Go to Connector Management, Connectors. | NA | Both Azure connectors are listed.
3 | Open each Azure connector and record the status and version of every component on it. | Connector 01 and connector 02 Production password manager: AZ-CPM-PRD-01 | Every component on both Azure connectors shows Active with no failed component, and both are on the same version. The session manager runs on both connectors. The password manager runs on connector 01 and is installed but stopped on connector 02.
4 | Open the Configured PSM Servers settings and record the Azure session manager entry and its address. | Load balancer name for the environment | The Azure session manager address is the load balancer name.
5 | Confirm the on-premises connectors are still listed and active. | NA | The on-premises connectors are unchanged.

## TC-CON-02
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Verify the CyberArk hardening Group Policy is applied on both connectors | Module/Program Name/Menu Path: | Phase 2: Connector health and service hardening Connector servers: PowerShell (gpupdate, gpresult), Event Viewer, Local Security Policy; Azure portal > load balancer health probes
Test Case ID: | TC-CON-02 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the CyberArk hardening GPO is applied on both connectors with no other hardening policy, the user rights and AppLocker rules match the CyberArk baseline, and the load balancer health probes stay healthy after the refresh. | Pre-requisites/Test Set-up: | 1. Both servers are joined to GEHA.com in the connector organizational unit. The CyberArk hardening GPO is linked to that unit, and no other hardening policy applies to it. 2. Administrator access to each connector through the approved administrative path. 3. GEHA Identity is available to confirm the organizational unit and GPO. 4. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off.
Dependencies (H/W and S/W): | 1. Connector 01 and connector 02 (Windows PowerShell, Event Viewer, Local Security Policy). 2. Active Directory connector organizational unit and the CyberArk hardening GPO. 3. Azure portal access to the load balancer. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (Build engineer, GEHA Identity) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Medium (about 20 minutes)
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | On each connector, open PowerShell as Administrator and run gpupdate /force. | gpupdate /force | The policy refresh completes without errors.
2 | Run gpresult /r /scope computer and record the organizational unit and the applied policies. | gpresult /r /scope computer | The server is in the connector organizational unit. The CyberArk hardening GPO is applied and no other hardening policy is.
3 | Open Event Viewer, System log, and check for Group Policy errors since the update. | Event Viewer > System log | No Group Policy errors are logged since the update.
4 | Open Local Security Policy and record the user rights assignments and the AppLocker rules set by the policy. | Local Security Policy > User Rights Assignment, AppLocker | User rights and AppLocker rules match the CyberArk baseline.
5 | In the Azure portal, check the load balancer health probes are still healthy after the refresh. | Azure probe address: 168.63.129.16 | Both probes stay healthy. If a probe fails, add a Windows firewall exception for the Azure probe address 168.63.129.16 and record it as a policy customization.

## TC-CON-03
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm endpoint protection is running on both connectors with the CyberArk exclusions in place | Module/Program Name/Menu Path: | Phase 2: Connector health and service hardening Endpoint protection agent on each connector and the agent console
Test Case ID: | TC-CON-03 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm endpoint protection is installed, enabled and reporting on both connectors, the CyberArk folder and process exclusions are in place, and no CyberArk file has been blocked or quarantined. | Pre-requisites/Test Set-up: | 1. The endpoint protection agent is installed on both servers with the CyberArk exclusions applied. 2. The endpoint protection service owner is available with access to the agent console. 3. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off.
Dependencies (H/W and S/W): | 1. Endpoint protection agent and console. 2. Connector 01 and connector 02. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (Build engineer, Endpoint protection service owner) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | On each connector, confirm the endpoint protection agent is running and up to date. | NA | The agent is installed, enabled and up to date on both connectors.
2 | In the agent console, confirm both connectors are checking in. | NA | Both connectors are reporting to the console.
3 | Review the exclusion list and confirm it covers the CyberArk folders and the CyberArk processes. | C:\Program Files (x86)\CyberArk\PSM C:\Program Files (x86)\CyberArk\Password Manager CyberArk processes | The CyberArk folder and process exclusions are in place.
4 | Check the agent event history on each connector for any CyberArk file that was blocked or quarantined. | NA | No CyberArk file has been blocked or quarantined.

## TC-FUN-01
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Open a privileged RDP session to a migrated Windows server through the Azure connectors | Module/Program Name/Menu Path: | Phase 3: Privileged sessions and credential management CyberArk Privilege Cloud portal > Windows test account > Connect; Monitoring
Test Case ID: | TC-FUN-01 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm a privileged RDP session opens through one of the Azure connectors without the user being asked for or shown the password, and that work done in the session reaches the target server. | Pre-requisites/Test Set-up: | 1. A Windows test platform sends sessions to the Azure connectors. 2. One migrated Windows server in Azure with a test account in a test safe. 3. A test user with Use Accounts, List Accounts and Initiate CPM account management rights on the test safes, working from an administrative workstation. 4. A reviewer with Monitor and View Audit rights. 5. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off.
Dependencies (H/W and S/W): | 1. Administrative workstation with a web browser. 2. CyberArk Privilege Cloud portal. 3. Migrated Windows test server in Azure. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (Test user, CyberArk administrator) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Medium (about 20 minutes)
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | The test user signs in to the CyberArk portal from an administrative workstation. | Test user account | The test user is signed in to the portal.
2 | Open the Windows test account and click Connect. | Windows test account in the test safe | The session opens without asking the user for a password.
3 | On the target server, create a text file named with the date and the case reference. | File name: <date>-TC-FUN-01.txt | The file exists on the target server.
4 | Confirm the password was never shown on screen at any point. | NA | The password is never shown.
5 | Sign out of the target to end the session. | NA | The session ends.
6 | The reviewer opens the session in Monitoring and records which connector handled it. | Reviewer account with Monitor and View Audit rights | The session is handled by one of the two Azure connectors.

## TC-FUN-02
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Play back the recordings of the RDP and SSH test sessions | Module/Program Name/Menu Path: | Phase 3: Privileged sessions and credential management CyberArk Privilege Cloud portal > Monitoring > Recordings
Test Case ID: | TC-FUN-02 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the RDP sessions are recorded against the right account and time, play to the end without error, and show the action taken on the target and the end of the session. | Pre-requisites/Test Set-up: | 1. TC-FUN-01 have been run in this environment. 2. A reviewer with Monitor and View Audit rights. 3. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off.
Dependencies (H/W and S/W): | 1. CyberArk Privilege Cloud portal. 2. Session recordings from TC-FUN-01 and TC-FUN-02. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (CyberArk administrator) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | The reviewer opens Monitoring, Recordings in the portal. | Reviewer account with Monitor and View Audit rights | The recordings list opens.
2 | Find the sessions from TC-FUN-01 by account name and time. | Windows test account names Session times from TC-FUN-01 | Both recordings are listed against the right account and time.
3 | Play each recording from start to finish. | NA | Both recordings play to the end without error.
4 | Check that each recording shows the action taken on the target and the end of the session. | TC-FUN-01: text file created on the Windows server | The action on the target and the session end are both visible.

## TC-FUN-03
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Change the test account passwords immediately through the Azure password manager | Module/Program Name/Menu Path: | Phase 3: Privileged sessions and credential management CyberArk Privilege Cloud portal > Windows test accounts > Change, Verify
Test Case ID: | TC-FUN-03 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the Azure password manager changes and verifies the password on the Windows test accounts with no error, and that sessions open normally with the new password. | Pre-requisites/Test Set-up: | 1. The test safe is managed by the Azure password manager (AZ-CPM-PRD-01 in production). 2. The password manager is running on connector 01 and is installed and stopped on connector 02. 3. Windows test accounts are in a test safe on migrated servers. 4. A test user with Use Accounts, List Accounts and Initiate CPM account management rights on the test safes. 5. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off.
Dependencies (H/W and S/W): | 1. CyberArk Privilege Cloud portal. 2. Azure password manager on connector 01. 3. Migrated Windows and Linux test servers. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (CyberArk administrator, Test user) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Medium (about 30 minutes, plus the password manager cycle)
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | The CyberArk administrator confirms the test safe is managed by the Azure password manager. | Non-production: password manager on connector 01 Production: AZ-CPM-PRD-01 | The test safe is managed by the Azure password manager.
2 | Open the Windows test account and note the Last modified date. | Windows test account | The current Last modified date is recorded.
3 | Click Change and choose to have the password manager change the password immediately. | NA | The change request is submitted.
4 | Wait for the password manager to pick up the request, refresh the account and record the new Last modified date and status. | NA | The password is changed by the Azure password manager with no error, and Last modified is updated.
5 | Click Verify and wait for the result. | NA | Verify succeeds.
6 | Open a session to the account as in TC-FUN-01 to prove the new password works. | Windows test account | The session opens normally with the new password.
7 | Repeat steps 2 to 6 for the Linux test account. | Linux test account | The password is changed with no error, Last modified is updated, Verify succeeds and the session opens normally with the new password.

## TC-FUN-04
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm CyberArk audit events from both connectors arrive in Splunk | Module/Program Name/Menu Path: | Phase 3: Privileged sessions and credential management Splunk forwarder on each connector; Splunk search; Splunk deployment server console
Test Case ID: | TC-FUN-04 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the Splunk forwarder on each connector is connected to an indexer, and that the sign-in, session and password change events from the earlier tests arrive in Splunk within a few minutes of the activity. | Pre-requisites/Test Set-up: | 1. TC-FUN-01 to TC-FUN-04 have been run in this environment. 2. The Splunk forwarder is in place on both connectors. 3. The Splunk service owner is available with search access and access to the deployment server console. 4. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off. 5. Evidence folder for this test cycle is in place, with a subfolder for this case.
Dependencies (H/W and S/W): | 1. Splunk forwarder on connector 01 and connector 02. 2. Splunk indexer (port 9998). 3. Splunk deployment server (port 8089). | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (Build engineer, Splunk service owner) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Medium (about 20 minutes)
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | On each connector, run splunk list forward-server from the Splunk forwarder bin folder. | splunk list forward-server | The forwarder on each connector is connected to an indexer on port 9998.
2 | Note the times of the activity in TC-FUN-01 to TC-FUN-04. | Activity times from TC-FUN-01 to TC-FUN-04 | The activity times are recorded.
3 | In Splunk, run the search for each connector and confirm events from both connectors. | index=* host=<connector name> earliest=-60m | Events from both connectors are present.
4 | Search for the CyberArk audit events for that activity. | Portal sign-in, session start and end, and the password change | The sign-in, session and password change events arrive within a few minutes of the activity.
5 | In the Splunk deployment server console, confirm both connectors are listed. | Deployment server, port 8089 | Both connectors are listed on the deployment server.
6 | Save the evidence in the TC-FUN-05 subfolder of the evidence folder for the environment. | Command output; Splunk search results; deployment server screenshot | Evidence is saved in the case subfolder and matches the expected results. A case without evidence is recorded as not run, never as passed.

## TC-HA-01
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Stop the session manager on connector 01 and confirm sessions continue on connector 02 | Module/Program Name/Menu Path: | Phase 4: High availability, failover and recovery Connector 01 Windows services; Azure portal > load balancer health; CyberArk Privilege Cloud portal > Monitoring
Test Case ID: | TC-HA-01 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm that when the session manager on connector 01 goes down, the load balancer marks it unhealthy, new sessions go to connector 02 without any error for the user, sessions on connector 02 carry on, and connector 01 takes sessions again once it is back. | Pre-requisites/Test Set-up: | 1. Phases 1 to 3 have been run in this environment. 2. Both connectors are healthy on the load balancer probes. 3. In production, this case runs in an agreed test window with the CyberArk administrator present. 4. A test user with access to the test accounts, and a reviewer with Monitor rights. 5. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off.
Dependencies (H/W and S/W): | 1. Connector 01 and connector 02. 2. Azure portal access to the load balancer health. 3. CyberArk Privilege Cloud portal (Monitoring). 4. Test accounts and migrated test servers. | Tear-down: | Start the CyberArk Privileged Session Manager service on connector 01 and confirm it returns to healthy and takes sessions again (steps 6 and 7).
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (Build engineer, Test user, CyberArk administrator) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Medium
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | The test user opens a session and the reviewer records which connector is handling it. Repeat until a session is running on connector 02, and keep that session open. | Test account | A session is running on connector 02 and is kept open.
2 | On connector 01, stop the CyberArk Privileged Session Manager service and note the time. | Service: CyberArk Privileged Session Manager | The service stops and the time is recorded. Sessions running on connector 01 when it stops will disconnect; this is expected.
3 | Watch the load balancer health until connector 01 shows unhealthy on the session manager probe, and note the time. | Session manager probe: HTTPS 443 (/psm/api/health) | Connector 01 is marked unhealthy within about 90 seconds.
4 | While connector 01 is down, open three new sessions. | Test account | All three new sessions go to connector 02 without any error for the user.
5 | Check the session opened in step 1 is still working. | NA | The session on connector 02 carries on without interruption.
6 | Start the service on connector 01 and watch its health return to healthy. | Service: CyberArk Privileged Session Manager | Connector 01 returns to healthy.
7 | Open one more session and confirm connector 01 can take sessions again. | Test account | Connector 01 takes sessions again.

## TC-HA-02
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Move the password manager to connector 02 and confirm password changes continue | Module/Program Name/Menu Path: | Phase 4: High availability, failover and recovery Password manager services on connector 01 and connector 02; CyberArk Privilege Cloud portal > Connector Management, Windows test account
Test Case ID: | TC-HA-02 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm that if connector 01 is lost, the password manager on connector 02 can be started manually, takes over under the same name, and completes a password change and verification. | Pre-requisites/Test Set-up: | 1. Phases 1 to 3 have been run in this environment. 2. The password manager is running on connector 01 and installed and stopped on connector 02 (AZ-CPM-PRD-01 in production). 3. In production, this case runs in an agreed test window with the CyberArk administrator present. 4. The Windows test account is in a test safe managed by the Azure password manager. 5. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off.
Dependencies (H/W and S/W): | 1. Connector 01 and connector 02 (Windows services). 2. CyberArk Privilege Cloud portal (Connector Management, Accounts). 3. Windows test account and migrated Windows test server. | Tear-down: | Stop the password manager services on connector 02, start them again on connector 01, and confirm connector 01 is active again (step 7).
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (CyberArk administrator) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | High
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Confirm the password manager service is running on connector 01 and stopped on connector 02. | NA | The password manager is running on connector 01 and stopped on connector 02.
2 | Stop the password manager services on connector 01 to simulate the loss of that connector, and note the time. | Password manager services on connector 01 | The password manager services are stopped on connector 01.
3 | On connector 02, start the password manager services. Only one password manager may run at any time. | Password manager services on connector 02 | The password manager services start on connector 02. The switch is manual.
4 | In Connector Management, confirm the password manager is now active from connector 02. | NA | The password manager on connector 02 takes over under the same name. Record the time it took from step 2 to step 4.
5 | Trigger an immediate password change on the Windows test account, then Verify it. | Windows test account | The password manager on connector 02 completes the change and verification.
6 | Open a session with the account to prove the new password works. | Windows test account | The session opens with the new password.
7 | Stop the services on connector 02, start them again on connector 01, and confirm connector 01 is active again. | Password manager services on both connectors | Connector 01 is active and connector 02 is stopped.