Execution Workflow

CyberArk PAS

Datacentre to Azure Migration v0.1

| Document Reference | Execution Workflow — CyberArk PAS (v0.1 DRAFT) |
| --- | --- |
| Stakeholders (GEHA) | Eric Ullmann (Application Owner), Phil Costanzo (Admin / Support Manager) |
| Authors | Saikat Majumdar, Amitendra Kushwaha (Citius Healthcare Consulting) |
| Design Authority | George Galindo (Cloud Architect) |
| Companion Document | CyberArk PAS Application Migration Playbook v0.1 |
| Date | 18-Sep-2026 |

Contents

1. Executive Summary	3

Future State Specifications	3

2. Prerequisites & Governance	3

2.1 Access Requirements	4

2.2 Platform Provisioning & Exemptions	4

2.3 Network & Firewall Policy	5

3. Implementation Roadmap	6

Execution Steps & Dependencies	6

4. Technical Playbook	7

Step 1: Access & Prerequisite Requests	7

Step 2: Subnet & Governance Provisioning	7

Step 3: Bicep Repository Configuration	7

Step 4: Infrastructure & Load Balancer Setup	7

Step 5: Network Routing & DNS	8

Step 6: CyberArk Connector Registration	8

Step 7: Component Installation	9

Step 8: Security Hardening & GPO	9

5. End-to-End Solution Validation	10

Entry Criteria	10

Test Groups and Sequence	11

Exit Criteria	11

6. Cutover & Rollback Plan	12

Cutover Execution Matrix	12

Cutover Steps	12

Cutover Day Steps	13

Rollback Protocol	13

7. RACI Matrix	14

8. Disaster Recovery Validation	15

Prerequisites	15

Validation Steps	15

Abbreviations	16

1. Executive Summary

This execution workflow outlines the operational steps required to deploy, configure, and operationalize CyberArk Privileged Access Security (PAS) connectors within Microsoft Azure. It serves as a step-by-step implementation guide for technical engineering teams.

Future State Specifications

| Configuration Parameter | Specification Details |
| --- | --- |
| Virtual Machine Count | 4 instances total (2 Production, 2 Non-Production) |
| Operating System | Windows Server 2022 (GEHA Approved Custom Image) |
| Compute SKU | Standard_D8ls_v5 (8 vCPU, 16 GB RAM) |
| Storage Allocation | 1x 128 GB OS Managed Disk (Recordings stream directly to CyberArk Tenant) |
| Target Subscriptions | CIP-PRD (Production), CIP-DEV (Non-Production) |
| Azure Region & Zones | Central US (Zone 1 and Zone 2 per environment for High Availability) |
| Subnet Allocations | snet-sec-cyberark-cus-prd-01 (/27), snet-sec-cyberark-cus-dev-01 (/27) |
| Load Balancing | 1x Internal Load Balancer (ILB) per environment with dedicated Private DNS entry |
| Administrative Access | Remote desktop from the GEHA administrative address ranges to the connector private address over ExpressRoute. No public IP addresses assigned. |
| Connector Host Names | AZPASPCCPRD101 and AZPASPCCPRD102 (virtual machines vm-sec-cyberark-cus-prd-01 and 02) |
| Network Security Group | nsg-sec-cyberark-cus-prd-01, associated to the connector subnet |
| Backup | Cohesity agentless snapshots of the managed disks; backup exclusion tag applied at deployment |
| Disaster Recovery | Azure Site Recovery replication to East US 2 (vault rsv-sec-cyberark-eus2-dr-01, recovery plan rp-sec-cyberark-prd-01, DR load balancer lbi-sec-cyberark-eus2-dr-01) |

2. Prerequisites & Governance

All prerequisite activities must be initiated in parallel during Week 1 to prevent downstream project bottlenecks.

2.1 Access Requirements

| Access Scope | Justification / Purpose | Granting Authority |
| --- | --- | --- |
| Contributor on rg-sec-cyberark-npd | Provisioning non-production infrastructure | Azure Platform Team |
| Contributor on rg-sec-cyberark-prd | Provisioning production infrastructure (Requires CAB approval) | Azure Platform Team |
| Sandbox Subscription Access | Pre-validation and testing of Bicep templates prior to target deployment | Azure Platform Team |
| Azure DevOps Project (TIO) | Hosting source repository and pipeline pipelines | Azure Platform Team |
| Shared Bicep Module Registry Read | Referencing centralized, enterprise-approved Bicep modules | Azure Platform Team |
| CyberArk Portal Access | Connector registration, component setup, and platform configuration | GEHA CyberArk Administration |
| Azure Bastion Access | Administrative RDP access to target connector VMs | Azure Platform Team |

2.2 Platform Provisioning & Exemptions

| Requirement Item | Detailed Specification | Operational Impact / Reason |
| --- | --- | --- |
| Production Subnet | /27 in vnet-cip-cus-prd-01 (snet-cyberark-cus-prd-01) | Host allocation & HA load balancing |
| Non-Production Subnet | /27 in vnet-cip-cus-dev-01 (snet-cyberark-cus-dev-01) | Host allocation & HA load balancing |
| Policy Exemption: RDS Role | Approval to enable Remote Desktop Services role | Required by CyberArk Session Manager |
| Policy Exemption: NLA | Approval to disable Network Level Authentication | Required by CyberArk PSM listener |
| Shared Image Gallery Path | Full Resource ID of GEHA-approved Windows 2022 image | Core parameter for Bicep template deployment |
| Core Quota Check | Minimum 32 vCPUs (Dls_v5 family) in Central US | Compute provisioning for 4 virtual machines |
| Firewall Rule Collection Group | rcg-sec-cyberark applied to DefaultFirewallPolicy, with the IP groups created | Required before network path testing begins |
| NSG Rule Set | Applied to nsg-sec-cyberark-cus-prd-01 | Controls administrator entry and site server access |
| Connector Certificates | One certificate per connector from GEHA internal PKI, with subject alternative names for the server name and cyberark-prd.geha.com | Required by the session manager health endpoint |
| PSM Service Accounts | PSMConnect and PSMAdminConnect created as GEHA.com domain accounts | Required by the PSM services at installation |
| East US 2 DR Landing Zone | DR virtual network, subnet, NSG and load balancer, plus an isolated test-failover virtual network | Required for disaster recovery validation |

2.3 Network & Firewall Policy

| Rule Scope | Source / Destination Ports | Protocol / Purpose | Special Handling |
| --- | --- | --- | --- |
| Admin Session Inbound | TCP 3389, 443 | Admin connections to Internal Load Balancer | Standard Inspection |
| Connector to Target | TCP 3389, 22, 443 | Brokered sessions to migrated workload VMs | Standard Inspection |
| Connector to CyberArk | TCP 1858, 443 Outbound | Outbound communication to CyberArk Cloud Tenant | Bypass IDS/IPS Inspection on Port 1858 |
| Connector to Directory | TCP 389, 3268 | Active Directory lookup via ExpressRoute | Standard Inspection |
| Connector to SIEM/Logs | TCP 9998, 8089 | Event log forwarding to Enterprise Log Platform | Standard Inspection |
| Endpoint Security | TCP 443 Outbound | Security agent update feeds | Standard Inspection |
| Deny On-Premises Target | All Traffic | Explicit block to prevent Azure connectors from picking up legacy on-prem workloads | Enforced via Azure Firewall |
| Site Server & Discovery Inbound | TCP 135, 445, dynamic range | SCCM site server and ServiceNow MID server reaching the connectors | Standard Inspection |

3. Implementation Roadmap

The implementation follows an 11-step sequence structured across four primary phases.

| PREPARATION & FOUNDATION | Steps 1 – 3 | Access Requests → Subnets & Policy Exemptions → Bicep Repository Setup |
| --- | --- | --- |
| INFRASTRUCTURE & NETWORK DEPLOYMENT | Steps 4 – 5 | Bicep VM/ILB Provisioning → Firewall Policy Rules & DNS Record Creation |
| CYBERARK CONFIGURATION & HARDENING | Steps 6 – 8 | Connector Registration → Component Installation → Domain GPO Hardening |
| VALIDATION, CUTOVER & HANDOVER | Steps 9 – 11 | End-to-End Testing → Phased App Cutover → Operational Handover & Decommission |

Execution Steps & Dependencies

| Step Reference | Task Description | Technical Dependencies |
| --- | --- | --- |
| Step 1 | Initiate Access and Prerequisite Requests | None (Day 1 Activity) |
| Step 2 | Subnet Allocation & Policy Exemption Approvals | Step 1 |
| Step 3 | Bicep Infrastructure Repository Setup | Step 1 |
| Step 4 | Server Infrastructure & Load Balancer Provisioning | Steps 2, 3 |
| Step 5 | Firewall Rules Activation & DNS Configuration | Step 2 |
| Step 6 | CyberArk Connector Registration | Steps 4, 5 |
| Step 7 | Install CyberArk Components (PSM / CPM) | Step 6 |
| Step 8 | Apply Group Policy Hardening & Final Configuration | Step 7 |
| Step 9 | Validate End-to-End Solution Functionality | Step 8 |
| Step 10 | Execute Phased Workload Cutover | Step 9 |
| Step 11 | Operational Handover & On-Premises Decommissioning | Step 10 |

4. Technical Playbook

Step 1: Access & Prerequisite Requests

- Request Reader access on resource groups rg-sec-cyberark-npd and rg-sec-cyberark-prd.

- Request Sandbox subscription access for initial Bicep template validation.

- Obtain access to the Azure DevOps TIO project repository.

- Obtain CyberArk Portal credentials and configure the Installer Service Account password with GEHA Administration.

- Confirm if the CyberArk tenant enforces IP Allowlisting; register outbound NAT addresses if enabled.

Step 2: Subnet & Governance Provisioning

- Request /27 dedicated subnets for Production (snet-cyberark-cus-prd-01) and Non-Production (snet-cyberark-cus-dev-01).

- Submit formal policy exemptions for Remote Desktop Services (RDS) role enablement and Network Level Authentication (NLA) relaxation.

- Verify platform inherited policy constraints prior to template development:

  - Public IP addresses on NICs are Denied.

  - Local Private DNS Zone creation is Denied (records must be hosted in on-premises DNS).

  - Direct internet management ports are Denied (Bastion access mandatory).

Step 3: Bicep Repository Configuration

- Configure dot-notation repository structure (cyberark.bicep) referencing the shared GEHA Bicep module registry (br:gehabicep.azurecr.io/bicep/modules/...).

- Ensure templates consume centralized networking, subnets, and compute definitions without duplicating local module code.

Step 4: Infrastructure & Load Balancer Setup

- Execute Bicep deployment to provision Standard_D8ls_v5 instances across Availability Zones 1 and 2.

- Assign static internal IP addresses (e.g., Load Balancer: .4, VM1: .5, VM2: .6).

- Configure Internal Load Balancer settings:

| ILB Setting | Value | Technical Justification |
| --- | --- | --- |
| Session Persistence | None. Distribution by the platform default five tuple hash. | Persistence is required only where automatic session reconnection is enabled; that feature is left off in this build. |
| Health Probe | Two probes: TCP 3389 and the session manager health endpoint on HTTPS 443. Interval 30 seconds, unhealthy threshold 3. | Transport check and service check, taken from the vendor worked example. |
| Idle Timeout | 1200 seconds | Accommodates administrative session idle time |
| TCP Reset on Idle | Enabled | Explicitly notifies client upon session expiration |

- Apply mandatory enterprise tags (Environment, Owner, ApplicationName, CostCenter, DataClassification, DRTier).

- Configure baseline Azure Monitor metric alerts (Unreachable Connector, PSM/CPM Service Stopped, Disk Space > 85%).

- Extend the alert set to the six workload rules: connector unreachable; session manager service stopped; credential rotation engine stopped; connector management agent unregistered; load balancer probe failure on both servers; operating system disk above 85 per cent.

- Apply the backup exclusion tag at deployment so the native Azure backup enrolment policy does not bind the connectors, and confirm Cohesity protects both servers.

- Hold deployment state and pipeline secrets in Azure Key Vault under the existing access model, and authenticate the pipeline with service principals.

Step 5: Network Routing & DNS

- Implement Central US Hub Firewall rules including Port 1858 inspection bypass.

- Provision internal CNAME/A-records in on-premises DNS pointing to the respective ILB static IP addresses (cyberark-prd.geha.com and cyberark-npd.geha.com).

- Perform manual network connectivity verification (TCP ping/telnet) from target VMs to domain controllers, SIEM indexers, and CyberArk tenant endpoints.

- Apply rule collection group rcg-sec-cyberark to DefaultFirewallPolicy and create the IP groups before path testing begins.

- Apply the NSG rule set to nsg-sec-cyberark-cus-prd-01: inbound TCP 3389 from the on-premises client and administrative ranges (rules 100 and 120); the platform probe tag on both probe ports; TCP 135, 445 and the dynamic range from the SCCM site server and the ServiceNow MID server; deny all other inbound management traffic (rule 4000).

Step 6: CyberArk Connector Registration

- Sign in to the target VM via Azure Bastion using local administrative credentials.

- Download Privilege Cloud software packages and standalone deployment tools from CyberArk Marketplace.

- Temporarily disable endpoint protection agents during software installation.

- Execute prerequisite check script via PowerShell:

.\ConnectorCheckPrerequisites_PrivilegeCloud.ps1

- Address all reported failures (the script automatically installs required RDS roles).

- Initiate "Add Connector" in CyberArk Portal, generate a registration token/script, and execute the command within the active 5-minute validity window.

- Confirm both connectors are joined to GEHA.com and that PSMConnect and PSMAdminConnect exist as domain accounts before starting the installation.

- Confirm the account used for the second PSM installation is not a direct owner of the PSMUnmanagedSessionAccounts safe.

Step 7: Component Installation

- Select target connector in CyberArk Portal (⋮ → Add Component).

- Select deployment mode: Production (do not use Proof-of-Concept mode).

- Provide Installer Service Account credentials and local domain admin accounts.

- Complete installation of Session Manager (PSM) and Rotation Engine (CPM) components; reboot host upon completion.

- Note: Deploy connectors sequentially. Parallel component installation on multiple hosts is unsupported.

- Install the components on each connector in this order: Connector Management, Identity Connector, Privileged Session Manager, then the dynamic access connector. Keep both servers on the same PSM version and restart each server after the PSM installation.

- Install the rotation engine only once GEHA Security has confirmed its placement; otherwise record it as deferred.

- Create the Configured PSM Servers entry for the Azure group by copying an existing entry so that PSMProtocolVersion is retained. Set ID to the Azure group name and Address to cyberark-prd.geha.com.

- Clone the production Windows and Linux platforms for testing and set the Azure group ID under UI and Workflows, Privileged Session Management.

Step 8: Security Hardening & GPO

- Import the official CyberArk GPO hardening package into Domain Group Policy Management.

- Link the hardened GPO exclusively to the dedicated Organizational Unit (OU) housing CyberArk Connector computer accounts.

- Execute gpupdate /force on target connector hosts.

- Re-enable endpoint protection tools with mandatory CyberArk file/folder exclusion paths applied.

- Run the PSM hardening in the In Domain mode.

- Confirm the hardening result: AppLocker rules present for executables and DLLs; RDS SecurityLayer and MinEncryptionLevel set; SMB1 disabled.

- Re-check both load balancer probes after hardening. If a probe reads unhealthy, add an inbound Windows firewall exception for 168.63.129.16 and record the change against the build.

- Bind the connector certificate to the session manager listener on port 443, then confirm https://<connector>/psm/api/health returns HTTP 200 from each server and through cyberark-prd.geha.com.

5. End-to-End Solution Validation

Execute the following test cases in non-production prior to authorizing production cutover activities.

Entry Criteria

Testing starts only when every point below is confirmed.

- Every Built row of the build parameters exists and the platform-supplied address values are applied.

- Both connectors are joined to GEHA.com, with PSMConnect and PSMAdminConnect in use by the PSM services.

- Rule collection group rcg-sec-cyberark is applied, the NSG rule set is applied and the IP groups exist.

- Connector Management, Identity Connector, PSM and the dynamic access connector are installed on both servers in that order, at the same PSM version, each server restarted after the PSM install, with hardening run in the In Domain mode.

- The account used for the second PSM install is not a direct owner of PSMUnmanagedSessionAccounts.

- Each connector holds its GEHA internal PKI certificate, bound to the PSM listener.

- Configured PSM Servers holds the Azure group entry, and the cloned Windows and Linux test platforms carry the Azure group ID.

- Test targets exist: one migrated Windows server, one migrated Linux server, and one unmigrated on-premises server on a platform carrying the on-premises group ID.

- Test users exist: one with Use Accounts and List Accounts on the test safes, one reviewer with Monitor and View Audit.

- The evidence store is created, one subfolder per case.

- For the disaster recovery day only: replication enabled at least one day beforehand with both items Protected, and the East US 2 DR objects and isolated test-failover network built.

| Test ID | Test Category | Execution Procedure | Acceptance Criteria |
| --- | --- | --- | --- |
| 01 | Connector Health | Verify portal status across all deployed nodes. | Status indicates Green/Active across all components. |
| 02 | Health Probe | Audit ILB backend pool status. | Both backend servers report Healthy. |
| 03 | DNS Resolution | Resolve cyberark-npd.geha.com from an administrative endpoint. | Returns ILB virtual IP address. |
| 04 | Credential Rotation | Initiate manual password rotation on an Azure-hosted account. | Password changes successfully in target and vault. |
| 05 | Log Ingestion | Validate event log pipeline generation. | Audit events reflect in log platform (Splunk etc) |
| 06 | HA Failover | Shut down primary connector node during active administration. | ILB routes active traffic to secondary node; rotation shifts. |
| 07 | Network Isolation | Attempt outbound connection from Azure connector to legacy on-prem host. | Traffic is blocked by Azure Firewall rule. |
| 08 | Zero Trust Access | Attempt direct external connection to connector OS. | Access denied; connection restricted to Azure Bastion. |
| 09 | Disaster Rebuild | Teardown a dev connector and rebuild via Bicep pipeline. | Node successfully restored using automated runbook. |

Test Groups and Sequence

| Group | Scope | Day | Cases |
| --- | --- | --- | --- |
| A | Platform build verification against the build parameters. Read only. | 1 am | A-01 to A-12 |
| B | Network path verification, including every deny path. | 1 pm | B-01 to B-10 |
| C | Tenant registration of both connectors beside the on-premises pair. | 1 close | C-01 to C-06 |
| D | Brokered sessions to migrated targets, distribution, failover and recording. | 2 and 3 | D-01 to D-10 |
| E | Parallel run and separation of the two estates. | 3 | E-01 to E-05 |
| F | Operations evidence: backup, alerting and patching. | 3 | F-01 to F-03 |
| G | Disaster recovery to East US 2. | 4 | G-01 to G-09 |

Execution is about 12.6 hours across days 1 to 3 and about 3.8 hours on day 4, excluding waits for configuration refresh, CPM cycles, initial replication and service owner actions.

Exit Criteria

- Groups A, B and C pass, or each failure carries a named owner and a fix date before the CAB agenda request.

- D-01 to D-07 pass. D-08 passes or the sizing is re-examined before cutover.

- E-01, E-02 and E-04 pass with no exception. A session from an Azure connector that reaches an unmigrated on-premises target is a stop: no cutover is requested until the rule is fixed and the case reruns clean.

- F-01 shows both connectors protected.

- Deferred items are recorded with an owner and a date: rotation engine placement, Secure Tunnel audit feed re-point, credential provider decommission and the live monitoring route.

- The evidence pack is complete, one subfolder per case, with a signed summary sheet. A case without evidence is recorded as not run, never as passed.

- Before hypercare exit: G-01, G-03, G-07, G-08 and G-09 pass; the G-04 result is recorded with any recovery-plan action and its owner; the G-06 change time is recorded.

6. Cutover & Rollback Plan

Workload migration occurs on an application-by-application basis.

Cutover Execution Matrix

| Change Items | Action Required | Owner | Change When |
| --- | --- | --- | --- |
| PSM Platform Settings | Copy platform settings pointing to Azure ILB | GEHA CyberArk Admin | Before window |
| CPM Safe Assignment | Re-assign safe rotation engine to Azure CPM | GEHA CyberArk Admin | During Window |
| Administrative DNS | Provision cyberark-prd.geha.com pointing to Azure ILB | Azure Platform Team | Before window |
| Firewall Rules | Staged rules in Central US Azure Firewall | Network Team | Before window |

Cutover Steps

- Pre-configure CyberArk platform settings for the Azure connector pools

- Verify target application workloads are operational within Azure subnets.

- Activate the updated platform settings and move the CPM Safe to the Azure pool

- Perform validation logon and execute a test credential rotation.

Cutover Day Steps

| Ref | Step | Detail | Minutes |
| --- | --- | --- | --- |
| CV-01 | Pre-cutover check | Repeat A-09, A-10, C-01 and C-02, and confirm both replicated items are Protected. | 30 |
| CV-02 | Production re-point | Apply the Azure group ID to the first production platform, or move the first production accounts to the Azure platform. Wait one configuration refresh. | 20 |
| CV-03 | Production session check | Repeat D-01 and D-02 against one production target per platform re-pointed. | 30 |
| CV-04 | On-premises check | Repeat E-01 for one unmigrated production target. | 15 |
| CV-05 | Both groups active | Confirm the tenant session list shows sessions on both the Azure and the on-premises groups. | 10 |
| CV-06 | Rollback, if invoked | Restore the on-premises group ID on the platform, or move the accounts back. Wait one refresh. Repeat CV-03 against the on-premises group. | 30 |

Allow one configuration refresh of 600 seconds after every platform change before testing.

Rollback Protocol

If validation fails post-cutover:

- Re-point the CyberArk Safe and Platform settings back to the active on-premises connector pool.

- Note: Rollback is purely a configuration update within the CyberArk portal. No server state migration or restoration is required.

- Rollback completes in under 30 minutes and no system is taken out of service; no infrastructure change is required.

- Cutover is approved by GEHA Security, Enterprise Architecture and CAB together. The rollback decision belongs to Phil Costanzo, admin and support manager.

7. RACI Matrix

| Migration Activity | Saikat M. | Bhagyashri S. | Amitendra K. | Syed A. | Mulinti R. | George G. | GEHA Admin | Platform Team |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Bicep Repository & Infrastructure | A/R | C | C | I | I | C | I | C |
| OS Preparation & Hardening | I | A/R | C | I | I | C | I | I |
| CyberArk Registration & Setup | C | C | A/R | I | I | C | C | I |
| Firewall & Routing Policy | I | I | I | A/R | I | C | I | C |
| Database Account Rotation | I | I | I | I | A/R | I | C | I |
| Architecture Sign-Off & Reviews | C | I | I | I | I | A/R | C | C |
| CyberArk Portal Configuration | I | I | C | I | I | I | A/R | I |
| Subnet & Policy Provisioning | I | I | I | I | I | I | I | A/R |

Legend: R = Responsible | A = Accountable | C = Consulted | I = Informed

8. Disaster Recovery Validation

Executed on test day 4, before hypercare exit. Replication must be enabled at least one day beforehand.

Prerequisites

- Replication enabled on both connectors with both replicated items showing Protected.

- East US 2 landing zone, DR subnet, NSG and DR load balancer built, and the recovery plan created.

- An isolated test-failover virtual network provided in East US 2 by the Cloud Platform Team.

- Outbound TCP 443 open from each connector to the cache storage account blob endpoint, login.microsoftonline.com and the Site Recovery service host for the vault region.

Validation Steps

| Ref | Step | Expected Result |
| --- | --- | --- |
| G-01 | Record both connectors in the Recovery Services vault with status, RPO and last recovery point. | Both items Protected and the RPO within the replication target. |
| G-02 | Test port 443 from each connector to the cache storage endpoint, login.microsoftonline.com and the Site Recovery host. | All paths succeed on both connectors. |
| G-03 | Run a test failover with the latest recovery point into the isolated network. | Both replicas running in East US 2 zones 1 and 2. |
| G-04 | Record computer name, domain membership and PSM service state on each replica, and what the tenant shows while it runs. | Computer names AZPASPCCPRD101 and AZPASPCCPRD102; the tenant result is recorded with any recovery-plan action. |
| G-05 | Record the DR load balancer front end, probes and rule, add the replica NICs to the pool, then remove them after G-08. | Parameters match the build parameters and the pool reports healthy. |
| G-06 | Have GEHA DNS create cyberark-drtest.geha.com against the DR front end, resolve it and request the health endpoint; remove the record after G-08. | Record resolves and the health endpoint returns HTTP 200; the change time is recorded. |
| G-07 | Obtain the East US egress public address and confirm it is on the tenant allowlist. | Address present on the allowlist before any replica registers. |
| G-08 | Run cleanup on the recovery plan. | Test virtual machines removed and both items still Protected. |
| G-09 | Repeat D-01 against production during G-03 and again after G-08. | Brokered by AZPASPCCPRD101 or 102 both times, with the production pair unchanged. |

Abbreviations

| Abbreviation | Expansion |
| --- | --- |
| CAB | Change Advisory Board |
| CNAME | Canonical Name (DNS alias record) |
| CPM | Central Policy Manager - CyberArk credential rotation engine |
| DNS | Domain Name System |
| DR | Disaster Recovery |
| GEHA | Government Employees Health Association |
| GPO | Group Policy Object |
| HA | High Availability |
| IDS / IPS | Intrusion Detection System / Intrusion Prevention System |
| ILB | Internal Load Balancer |
| IP | Internet Protocol |
| NAT | Network Address Translation |
| NIC | Network Interface Card |
| NLA | Network Level Authentication |
| OS | Operating System |
| OU | Organizational Unit |
| PAS | Privileged Access Security |
| PSM | Privileged Session Manager - CyberArk session brokering component |
| RACI | Responsible, Accountable, Consulted, Informed |
| RAM | Random Access Memory |
| RDP | Remote Desktop Protocol |
| RDS | Remote Desktop Services |
| SIEM | Security Information and Event Management |
| SKU | Stock Keeping Unit - Azure virtual machine size designation |
| TCP | Transmission Control Protocol |
| TIO | GEHA Azure DevOps project hosting the source repository and pipelines |
| vCPU | Virtual Central Processing Unit |
| VM | Virtual Machine |
| ASR | Azure Site Recovery |
| MID | Management, Instrumentation and Discovery - ServiceNow integration server |
| PKI | Public Key Infrastructure |
| RPO | Recovery Point Objective |
| SAN | Subject Alternative Name |
| SCCM | System Center Configuration Manager |