Application Migration Playbook Utility Datacenter to Azure Migration v0.4 — DRAFT, FOR GEHA REVIEW

Utility — descriptor not recorded in the corpus; complete from vendor documentation

Prepared for: G.E.H.A.

John Dean (Director); Dale Gibson (Admin / Support Manager)

Prepared by: Citius Healthcare Consulting

George Galindo, Cloud Architect

Peer Reviewer: Not yet assigned

Document Status: ☒ DRAFT ☐ RELEASE CANDIDATE ☐ PUBLISHED

Date: 26-Aug-2026

Everything a reader needs to orient themselves on this application is gathered here in a single view, so that no one has to hunt through later sections for a date, an owner or a target platform. Each field is owned by the section named beside it, and that owning section remains the authoritative source; this table is corrected to match it rather than the other way round. The scheduling fields — wave placement, migration strategy, cliff date, cliff driver and target cutover date — are recorded here in structured form and narrated in the executive summary that follows. Reading this table alone should be enough to understand what is moving, when it must move, and what forces the timing.

| Field | Value |
| --- | --- |
| Playbook Index ID | GEHA-DCM-UTILITY-v0.1 |
| Application Version | Installed software observed on the hosts: /proc/916/exe; svchost.exe; ir_agent.exe; splunkd.exe; svchost.exe; rapid7_endpoint_broker.exe (Source: Application Interface Details, full 451,897-row pass, as-of 12/24/25) |
| Wave Placement | Wave 3 — plan of record BASELINE v2.1, 26 Aug 2026. Prior tracker-derived placements superseded. W4 — engine placement (manual (dragged)); not listed in SOW Exhibit C — change order required |
| Migration Strategy | Rehost (tracker ruling, BASELINE v2.1) — Matilda recommends Replatform for the PROD environment; conflict logged in §5.1, register DECISION W3-UTIL-D1 |
| Target Cutover Date | 03/18/27, Thursday (BASELINE v2.1). CR Friday 03/12/27; CAB Wednesday 03/17/27. |
| Cliff Date | None on file |
| Cliff Date Driver | Datacenter exit (Source: Wave Plan Tracker (rev-3), as-of 07-Aug-2026) |
| User Access Method | Not yet provided — requested from GEHA, required by 2026-09-15 (Appendix B, item 05). |
| Key Dependencies | ORION (Inferred from Application Interface Details full pass, as-of 12/24/25; test: confirm with the far-side owning team) |
| Target Subscription & Landing Zone | Not yet provided — Subscription name and ID, management group, resource group — owned by §5.2. To be supplied by GEHA (Appendix B). |
| Target Region & Paired Region | Not yet provided — Primary Azure region and its pair — owned by §5.2. To be supplied by GEHA (Appendix B). |
| Application Tier | Not on file — no Utility application row in BIA_Applications_20251113 or BIA_Capability_and_Application (Application BIA tabs, read in full 26-Aug-2026); requested from GEHA (Appendix B item 12; register W3-UTIL-4). |
| RTO and RPO | Not on file — no Utility application row in BIA_Applications_20251113 or BIA_Capability_and_Application (Application BIA tabs, read in full 26-Aug-2026); requested from GEHA (Appendix B item 12; register W3-UTIL-4). |
| Load Balancer | Not yet provided — requested from GEHA, required by 2026-09-01 (Appendix B, item 06). |
| Deployment Pattern | 8 host(s) across 3 environment(s) (Source: Matilda Discovery Assessment, as-of 08-Aug-2026 + Application Interface Details full pass, as-of 12/24/25)— current owned by §4.1, target by §5.3 |

Table 1.0 — Key Information

# 1. Document Control

Document control establishes who has changed this playbook, who has approved it, and the standard of evidence every statement within it must meet. It exists so that a reader arriving months after authorship can tell how current the content is, whose judgment stands behind it, and how confident to be in any given figure. The revision history is maintained continuously rather than reconstructed at the end, and approvals are recorded against named individuals rather than teams. Taken together these records make the document auditable without recourse to the people who wrote it.

## 1.1 Version History

| Version | Date | Author | Summary of Changes |
| --- | --- | --- | --- |
| 0.2 | 13-Aug-2026 | George Galindo, CitiusTech | Prepared for GEHA technical review. Evidenced fields cite their source and as-of date; fields GEHA has not yet supplied are shown as dated requests in Appendix B. Program decisions are not restated in the body — they are cited to Appendix A. |
| 0.3 | 26-Aug-2026 | George Galindo, CitiusTech | Re-issued on the approved template (Azure Migration Playbook Template v3.0 as shared): sections 1.4 and 1.5 restored verbatim from the template; key dates rebaselined to the plan of record (BASELINE v2.1). Approved styling untouched. Full evidence remediation follows in wave order. |
| 0.4 | 26-Aug-2026 | George Galindo, CitiusTech | Evidence fill from source exhaustion (ruling 26 Aug): audit findings applied, evidenced values written in with citations, remaining gaps re-scoped to the information request register; conflicts recorded for ruling, not resolved. |

Table 1.1 — Version History

## 1.2 Approvers

| Name | Role | Approval Date |
| --- | --- | --- |
| To be provided by GEHA | Application Owner |  |
| Dale Gibson (Owners tab row 38, BASELINE v2.1) | Application Administrator |  |
| To be provided by GEHA | Security Lead |  |
| George Galindo | Cloud Architect — Citius Healthcare Consulting |  |
| To be provided by GEHA | Migration & Platform Lead (CHC) |  |

Table 1.2 — Approvers

## 1.3 Evidence Standard

Every factual entry in this playbook carries three things: a label declaring whether it is evidenced, inferred or assumed, a named source, and the date on which the value was true. This discipline exists because migration failures are rarely caused by missing information; they are caused by information that was true once and quietly stopped being true. An inference is recorded together with the test that would confirm it, and an assumption is recorded together with the person who must confirm it and the date by which they must do so. Where something was looked for and not found, that absence is written down as a finding in its own right, because an empty field and a confirmed absence carry very different weight at cutover .

| Convention | Applies to every factual field in this document |
| --- | --- |
| Label | Mark each value Evidenced, Inferred or Assumed. For Inferred, state the test that would confirm it. For Assumed, state who must confirm and by when — then it becomes an open item in §10.4. |
| Source and As-Of Date | Name the source system, file or person, and the date the value was true. A value with no as-of date cannot be relied on at cutover. |
| Absences | Record what was looked for and not found. An empty field and a confirmed absence are different findings. |

Table 1.3 — Evidence Standard

## 1.4 Reading Conventions

Description: The template distinguishes four categories of text — names, descriptions, instructions, and example data — each with a distinct appearance and purpose. Section headings and bold row labels serve as names; descriptions state what an element is; instructions state what to do; example data illustrates the expected form of an answer.

Instructions: Delete instruction text as each field is answered; a completed playbook contains names, descriptions, and content only. Every table carries a numbered caption in the form Table <section><letter> — <name> (for example, Table 3.2 — Ownership & Stakeholders); cite tables by this caption in narrative text.

| Text You See | What It Is | What To Do With It |
| --- | --- | --- |
| Plain black text | Content — headings, fixed labels, and the answers the author has entered | The finished document. Never delete labels; replace instruction text with answers in plain text |
| Dark slate text labeled Description | Description — what the section or table is and why it exists | Leave it in place; it survives into the finished playbook |
| Gray italic text in [brackets] or labeled Instructions | Instructions — what the field requires and the standard it must meet | Read it, answer it, delete it. Unreplaced instruction text means the field was never completed |
| Blue-gray italic text following “e.g.,” | Example data — an illustration of the expected form, never a suggested answer. Also appears as slash-separated value lists and format patterns such as [MM/DD/YY] or [HH:MM] | Do not copy examples as answers. If an example happens to be true, evidence it as if it were not |
| ☐ Checkbox options | Closed choices — the complete set of valid answers for that field | Tick exactly one unless the instructions say otherwise; a qualifier after the dash still requires text |

Table 1.4 — Reading Conventions

## 1.5 Completion Standard

Description: Completion of this playbook is a defined condition rather than a judgment call, and the criteria that must be satisfied before the document is considered complete and baselined are set out below. It applies uniformly across the playbook library so that completeness means the same thing in every application.

| Completion Tier Applied | ☐ Full ☐ Reduced — [Full is mandatory for Tier 1, high-complexity, and regulated applications. Reduced is available for low-complexity applications on the approval recorded below] |
| --- | --- |
| Reduced Tier Approved By | [Name and date. Reduced applies only where the application is single-tier or single-server, has no clustering, no partner-facing integration, and no functionality gap requiring a decision. If any of those conditions fails, Full applies] |

Table 1.5a — Completion Standard

| Section | Full | Reduced |
| --- | --- | --- |
| §1 Document Control; §2 Executive Summary; §3.1–§3.3 | Required | Required |
| §3.4 Performance Baseline | Required | Batch durations and peak concurrency only |
| §4 Current State, including all registers | Required | Required — this is the datacenter exit evidence and is not reducible |
| §4.0 / §5.0 Diagram Records | Required | Diagram attached; record rows optional |
| §5 Target State | Required | Decisions that differ from the landing zone standard only; conformance stated once for the remainder |
| §5.14 Well-Architected Review Record | Required | Omitted |
| §6.1 Move Groups & Sequencing | Required | Omitted where a single move group applies |
| §6.2–§6.8 Preparation | Required | Required |
| §7 Cutover Runbook | Required | Required — not reducible |
| §8 Post-Cutover; §10 Risks and Open Items; §11 Timeline and Effort; §12 Sign-Off | Required | Required |
| §9 Roles & Responsibilities | Required | Omitted; §3.2 ownership governs |

Table 1.5b — Completion Standard

| Condition | Met |
| --- | --- |
| Every instruction block answered and deleted; no bracketed placeholder text remains | ☐ Yes ☐ No |
| Every role in §3.2 resolved to a named individual | ☐ Yes ☐ No |
| Every factual field carries a label, source, and as-of date per §1.3 | ☐ Yes ☐ No |
| Every register entry carries a disposition; no entry left blank | ☐ Yes ☐ No |
| Confirmed absences recorded as such rather than left empty | ☐ Yes ☐ No |
| Every open question recorded in §10.4 with an owner and a due date | ☐ Yes ☐ No |
| Every attachment listed in §1.6 and stored at the location recorded there | ☐ Yes ☐ No |
| Approvers in §1.2 have signed | ☐ Yes ☐ No |

Table 1.5c — Completion Standard

| Baselined By | [Name and date. A baselined playbook is version-controlled in §1.1; subsequent changes increment the version] |
| --- | --- |

Table 1.5d — Completion Standard

## 1.6 Attachment Register

Some material this migration depends on is too large, too technical or too frequently updated to sit inside the playbook itself — configuration exports, discovery output, mappings and architecture diagrams among them. Each such artifact is registered here with its location, its owner and the date it was produced, so that anyone can retrieve the underlying evidence without asking the author. A document referenced in the body but missing from this register is effectively unfindable by anyone other than the person who created it. Registering an attachment also fixes its version, which matters when the same export is refreshed several times across the life of the program.

| Attachment | Referenced By | Location | Owner | As Of |
| --- | --- | --- | --- | --- |
| Wave Plan Tracker (rev-3) — App Disp, Contract Cliffs, Wave Schedule, Owners | §1.0, §3.2, §3.3, §11 | Evidence corpus (hash-sealed, CHK-051) | George Galindo | 07-Aug-2026 |
| Application Interface Details (IFD) full pass | §4.7, §4.10 | Evidence corpus (CHK-051) | GEHA | 12/24/25 |
| Matilda Discovery Assessment Summary | §4.1 | Evidence corpus (CHK-051) | GEHA | 08-Aug-2026 |
| Server_VM_Inventory (vCenter export) | §4.1.1 | Evidence corpus (CHK-051) | GEHA | — |
| SOW ZCON-18111 (signed 30-Jul-2026) — Exhibit C | §1.0 wave placement, §10.3 | Evidence corpus (CHK-051) | CitiusTech/GEHA | 30-Jul-2026 |
| Decision &amp; Evidence Register (Appendix A ref. REG-001..Appendix A ref. REG-030) | throughout — decisions are cited by REG id, not restated | Evidence corpus (CHK-051) | George Galindo | 13-Aug-2026 |

Table 1.6 — Attachment Register

# 2. Executive Summary

Utility moves out of the GEHA datacenter under the rehost disposition. Development sandboxes, PoCs, and utility environments can be migrated to Azure with a simple lift-and-shift approach. Cutover is planned for Thursday 03/18/27 in Wave 3 (BASELINE v2.1, plan of record 26 Aug 2026); no contract cliff is recorded against this application. Users see one planned outage at cutover; the window is agreed at the readiness review. Datacenter decommissioning, facility exit and hardware disposal are excluded from the current statement of work. The main threat to the date is late delivery of the information listed in Appendix B, tracked weekly with GEHA.

Scope is limited to Utility. The committed dates are those recorded in section 11, and every open item is tracked in Appendix B with the date it is needed.

As stated Utility application is one wave 1 – The migration scope includes eight active utility servers across the DEV, Test, and PROD environments. These servers operate primarily as shared jump boxes used by support teams to install administrative tools, perform support activities, and run sceduled jobs. The azure target will use windows server 2025 gen 2 virtual machines, UEFI boot, standard azure encrpytion and storage, and azure hybrid benefit where eligible. The environment does not require static IP addresses, load balancing, or utility specific network tunnels. The principal open items are team-specific software inventory, service and application accounts, certificates scheduled jobs, network access requirments, and the final disposition of the powered off legacy server LXENTUTl01.

# 3. Application Overview

## 3.1 Business Purpose

No business-context narrative for Utility was found (read: Wave Plan Tracker rev-3 Wave Schedule and App Disp tabs, BIA Application BIA 338 rows, GEHA discovery sessions 1-3).   (Source: Wave Plan Tracker (rev-3), as-of 07-Aug-2026)

## 3.2 Ownership & Stakeholders

Migration work stalls more often on unresolved ownership than on technical difficulty, so every role bearing on this application is resolved to a named individual here rather than to a team or a distribution list. The register covers business ownership, technical ownership, security, database and production control, network and DNS, batch scheduling, and the single person empowered to abort a cutover in progress. Where a recorded owner has left the organization, the vacancy is carried forward as an open item rather than quietly inherited by whoever is nearest. Each entry is confirmed with the individual concerned before the go/no-go gate, because a name that has never been verified is not an owner.

| Role | Name | Contact | Confirmed |
| --- | --- | --- | --- |
| Business / Application Owner | Not yet provided — role not resolved to a named individual (§10.4). Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Not yet provided — contact not on file. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Not confirmed |
| Technical Owner | Not yet provided — role not resolved to a named individual (§10.4). Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Not yet provided — contact not on file. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Not confirmed |
| Security Contact | Not yet provided — role not resolved to a named individual (§10.4). Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Not yet provided — contact not on file. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Not confirmed |
| DBA / Production Control | Not yet provided — role not resolved to a named individual (§10.4). Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Not yet provided — contact not on file. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Not confirmed |
| Network / DNS / Firewall | Not yet provided — role not resolved to a named individual (§10.4). Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Not yet provided — contact not on file. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Not confirmed |
| Scheduling / Batch Automation | Not yet provided — role not resolved to a named individual (§10.4). Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Not yet provided — contact not on file. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Not confirmed |
| Rollback Authority | Not yet provided — role not resolved to a named individual (§10.4). Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Not yet provided — contact not on file. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Not confirmed |
| On-call / Support (Admin / Support Manager) | Dale Gibson (Source: Wave Plan Tracker (rev-3) GEHA Application Owners tab, as-of 07-Aug-2026) | Not yet provided — contact not on file. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Not confirmed |
| Director (GEHA) | John Dean | Not yet provided — contact not on file. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Not confirmed |

Table 3.2 — Ownership & Stakeholders

## 3.3 Criticality & Service Levels

Not applicable

The service levels the business receives today are recorded here so that the target design can be measured against a documented reference rather than against recollection or aspiration. Current availability, recovery time and recovery point objectives are captured alongside the peak usage window and the calendar dates a cutover must avoid. Where the target design would deliver less than the current state, that shortfall becomes a gap requiring the application owner's explicit written acceptance rather than a technical footnote. These figures also frame the business conversation about acceptable downtime, which is far easier to hold before a date is committed than after.

| Business Criticality | Not yet provided — requested from GEHA, required by 2026-09-30 (Appendix B, item 12).Critical ☐ High ☐ Medium ☐ Low |
| --- | --- |
| Current Availability SLA | Not yet provided — requested from GEHA, required by 2026-09-30 (Appendix B, item 12). |
| RTO (Recovery Time Objective) | Not yet provided — requested from GEHA, required by 2026-09-30 (Appendix B, item 12). |
| RPO (Recovery Point Objective) | Not yet provided — requested from GEHA, required by 2026-09-30 (Appendix B, item 12). |
| Peak Usage Window | Not yet provided — requested from GEHA, required by 2026-09-30 (Appendix B, item 12). |
| Business Calendar Constraints | Open enrolment / open season — GEHA-wide constraint; confirm application-specific dates with the owner. Program blackouts: 1 Nov-14 Dec 2026 and 1 Nov-13 Dec 2027 (SOW: production cutovers barred; Christmas close 22 Dec-2 Jan). |
| Regulatory / Compliance Scope | Not yet provided — requested from GEHA, required by 2026-09-30 (Appendix B, item 12). |

Table 3.3 — Criticality & Service Levels

## 3.4 Performance Baseline

Performance complaints after go-live cannot be resolved against an undocumented baseline, so the application's present behavior is measured and recorded here before anything moves. Typical and worst-case response times for the most-used functions, elapsed times for significant batch jobs, observed peak concurrency and transaction volumes are all captured with the conditions under which they were measured. The measurement date matters as much as the figure: a baseline older than the last significant change to the application is not a baseline. These numbers become the exit criteria for performance testing, converting a subjective judgment into a pass or fail.

| Transaction / Screen Response | Not yet provided — requested from GEHA, required by 2026-09-30 (Appendix B, item 12). |
| --- | --- |
| Batch and Report Durations | Not yet provided — requested from GEHA, required by 2026-09-30 (Appendix B, item 12). |
| Peak Concurrency | Instance activity classified Low; CPU Low, memory Moderate, storage Moderate (Source: Matilda Discovery Assessment Summary (Host Details / Instance Assessment), as-of 08-Aug-2026) |
| Transaction Volume | Observed inbound connection rows by port — 111 — 2 rows; 49807 — 1 rows; 135 (RPC endpoint mapper) — 1 rows; 49707 — 1 rows (Source: Application Interface Details, full 451,897-row pass, as-of 12/24/25) |
| Measurement Source & Date | Matilda discovery assessment, as-of 08-Aug-2026; utilization bands, not absolute peaks (Source: Matilda Discovery Assessment Summary (Host Details / Instance Assessment), as-of 08-Aug-2026) |

Table 3.4 — Performance Baseline

# 4. Current State

What follows is a complete account of the application as it exists in the datacenter today, and it serves two purposes at once. It is the specification from which the Azure target is sized and designed, and it is the evidence of what was actually running when the estate was assessed — the record that datacenter exit is measured against. Every component, data store, account, certificate, scheduled job, interface and hardcoded value that the migration must address is captured here rather than discovered during the cutover window. Because this section is the exit evidence, it is not reducible even for low-complexity applications.   The utility environment consist of eight active servers across the development, test, and production environments. These servers operate primarily as shared jump boxes that various support use to install administrative tools, perform support activities, and run scheduled jobs that should not execute from users' laptops. The utility environment does not use load balancer, dedicated network tunnel, or peer connection, and it has no static IP dependency. Standard security agents are installed as required, while additional tools vary by team.

Link- https://lucid.app/lucidchart/e84a11a1-eb65-4751-978a-82ffc74bdb82/edit?viewport_loc=-985%2C69%2C7800%2C2906%2C42U8H5I2Zcsty&invitationId=inv_62a1f34e-fc33-410c-bd80-bfd3a5da28ed

4.0 Current State Diagram Flow

Currently we have eight active servers across two data centers, four in Lee Summit and four in Lenexa. These are shared servers that support teams' use for administrative tools, support tools, and scheduled jobs. Across both sites, we have one development server, two test server, and five production servers. At the top, the support teams and administrators access the utility environment to carry out their work. On the left is Lee summit and the two production servers are LSUTILPRD101 and SECAMUTLPRD101. Below them, EAUTILDEV201 is the development server and OIMST101 is the test server. The main connection shown here around LSUTILPRD101 and it receives inbound connections from the Remote Desktop License Server and SCCM. It also has outbound connection to Orion and ServiceNow. SCCM has another inbound connection to OIMTST101. Lenexa has three production servers LXUTILPRD101, MSCOREOSPRD101 and NETBACKUPPPRD101, and one test Server OIMTST101. LXUTILPRD101 has an outbound connection to Citrix, NETBACKUPPRD101 receives SSH connection from Ansible and the system identified as development in the document. That Server is shown in purple because it runs RHEL 9.0 and host containers. The other seven active servers run windows. As confirmed, the environment has no utility specific load balancer, dedicated tunnel, Peer connection, or static dependency.

## 4.0 Current State Architecture Diagram

The diagram presents the current deployment in a single view and acts as the visual counterpart to the registers that follow. Every server, integration, network object and identity flow recorded in this section should be locatable on it, and any component that appears on the diagram but is absent from the registers is by definition undocumented. It is drawn from evidenced sources — configuration exports, firewall rules, DNS records and discovery output — rather than from memory or from superseded architecture material. Its practical use is to walk the move-group boundaries and brief the cutover team on what exists today before anything is changed.

Not yet provided — INSERT CURRENT STATE ARCHITECTURE DIAGRAM HERE. To be supplied by GEHA (Appendix B).

| Diagram Name | — utility application |
| --- | --- |
| Description | Not yet provided — One or two sentences: what the diagram shows and the boundary it covers — which environments, which zones, what is delib. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). The diagram shows the current utility environment, consisting of eight jump servers across the DEV, TEST, And PROD enivironments at the lee Summit and Lenexa Data centers, It also shows the support teams and shared enterprise services that interace with the servers, No utility-specfic load balancer, network tunnel, or peer connection is in use |
| Use Case | Not yet provided — What this diagram is used for: verifying the §4 registers are complete, walking the §6.1 move-group boundaries, briefing. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). The diagram is used to validate the eight servers included in the utility migration scope, review existing connections and dependencies, support azure migration planning, and brief the migration and cutover teams |
| Source of Truth | Not yet provided — What the diagram was drawn from — config exports, firewall rules, discovery tooling — with the as-of date. A diagram wit. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Author & Date | TBD |
| Sign-Off | To be determined Not yet provided — Client approver — name, role, date. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). / Not yet provided — Vendor approver — name, role, date. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |

Table 4.0 — Diagram Record

## 4.1 Host Resource Specifications

| Server / Component | Role | OS / Version | Environment | Assessment Readiness | Holds Data? | CMDB / Asset ID |
| --- | --- | --- | --- | --- | --- | --- |
| EAUTILDEV201 | Web Server | Windows Server 2019 Standard | DEV | Active; OS support ends 01-09-2029 (Source: Matilda Discovery Assessment Summary (Host Details / Instance Assessment), as-of 08-Aug-2026) | No | Lee Summit |
| LSUTILPRD101 | Web Server | Windows Server 2019 Standard | PROD | Active; OS support ends 01-09-2029 (Source: Matilda Discovery Assessment Summary (Host Details / Instance Assessment), as-of 08-Aug-2026) | No | Lee Summit |
| LXUTILPRD101 | Infra | Windows Server 2019 Standard | PROD | Active; OS support ends 01-09-2029 (Source: Matilda Discovery Assessment Summary (Host Details / Instance Assessment), as-of 08-Aug-2026) | No | Lenexa |
| MSCOREOSPRD101 | Infra | Windows Server 2025 Standard | PROD | Active; OS support ends 10-15-2034 (Source: Matilda Discovery Assessment Summary (Host Details / Instance Assessment), as-of 08-Aug-2026) | No | Lenexa |
| NETBACKUPPRD101 | Container | RHEL 9.0 | PROD | Active; OS support ends 05-31-2035 (Source: Matilda Discovery Assessment Summary (Host Details / Instance Assessment), as-of 08-Aug-2026) | No | Lenexa |
| OIMTST101 | Infra | Windows Server 2019 Standard | TEST | Active; OS support ends 01-09-2029 (Source: Matilda Discovery Assessment Summary (Host Details / Instance Assessment), as-of 08-Aug-2026) | No | Lee Summit |
| OIMTST102 | Infra | Windows Server 2019 Standard | TEST | Active; OS support ends 01-09-2029 (Source: Matilda Discovery Assessment Summary (Host Details / Instance Assessment), as-of 08-Aug-2026) | No | Lenexa |
| SECADMUTLPRD101 | Infra | Windows Server 2022 Standard | PROD | Active; OS support ends 10-15-2031 (Source: Matilda Discovery Assessment Summary (Host Details / Instance Assessment), as-of 08-Aug-2026) | No | Lee Summit |
| LXENTUTL01 | Legacy EA Utility Server — unmapped, disposition required | Windows Server 2012 (64-bit) | Legacy | poweredOff; vCenter annotation "Owner: EA Engineers EA Utility Server" (Evidenced — Server_VM_Inventory, LX tab row 191). Unmapped in Matilda and absent from prior revisions of this playbook. Retire-or-ignore ruling required (register W3-UTIL-2). | Unknown | Lenexa (vCenter LX tab) |

Table 4.1 — Host Resource Specifications

### 4.1.1 Sizing & Utilization Baseline

Allocated capacity and measured utilization are recorded side by side, because the difference between them is where cloud cost is won or lost. Target sizing is derived from what the workload actually consumes rather than from what was provisioned for it, which is frequently several times larger. The observation window is stated with every figure, since a short sample will not capture cyclical peaks such as month-end or open-season processing. Where no measurement exists, that absence is recorded plainly and the associated sizing risk is carried into the risk register rather than hidden inside an estimate.

| Server | vCPU Allocated | Memory Allocated | Disks (Count / Size / Type) | Peak CPU % | Peak Memory % | Peak IOPS / Throughput | Network Throughput | Measurement Source & Window |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| EAUTILDEV201 | 2 | 8 GB | 2 disks / 210 GB | Low% average | Moderate% average | Moderate% storage utilization | Not yet provided — requested from GEHA, required by 2026-09-05, re-dated 26-Aug-2026 (was 2026-08-25, elapsed) (Appendix B, item 01). | Allocation from Server_VM_Inventory (vCenter export); utilization from Matilda Discovery Assessment Summary (Host Details / Instance Assessment), as-of 08-Aug-2026 |
| LSUTILPRD101 | 4 | 32 GB | 2 disks / 550 GB | Low% average | Moderate% average | Low% storage utilization | Not yet provided — requested from GEHA, required by 2026-09-05, re-dated 26-Aug-2026 (was 2026-08-25, elapsed) (Appendix B, item 01). | Allocation from Server_VM_Inventory (vCenter export); utilization from Matilda Discovery Assessment Summary (Host Details / Instance Assessment), as-of 08-Aug-2026 |
| LXUTILPRD101 | 4 | 32 GB | 2 disks / 280 GB | Low% average | Low% average | Low% storage utilization | Not yet provided — requested from GEHA, required by 2026-09-05, re-dated 26-Aug-2026 (was 2026-08-25, elapsed) (Appendix B, item 01). | Allocation from Server_VM_Inventory (vCenter export); utilization from Matilda Discovery Assessment Summary (Host Details / Instance Assessment), as-of 08-Aug-2026 |
| MSCOREOSPRD101 | 2 | 4 GB | 1 disks / 40 GB | High% average | Moderate% average | Moderate% storage utilization | Not yet provided — requested from GEHA, required by 2026-09-05, re-dated 26-Aug-2026 (was 2026-08-25, elapsed) (Appendix B, item 01). | Allocation from Server_VM_Inventory (vCenter export); utilization from Matilda Discovery Assessment Summary (Host Details / Instance Assessment), as-of 08-Aug-2026 |
| NETBACKUPPRD101 | 4 | 16 GB | 2 disks / 1330 GB | Low% average | Low% average | High% storage utilization | Not yet provided — requested from GEHA, required by 2026-09-05, re-dated 26-Aug-2026 (was 2026-08-25, elapsed) (Appendix B, item 01). | Allocation from Server_VM_Inventory (vCenter export); utilization from Matilda Discovery Assessment Summary (Host Details / Instance Assessment), as-of 08-Aug-2026 |
| OIMTST101 | 4 | 8 GB | 1 disks / 80 GB | Low% average | Moderate% average | High% storage utilization | Not yet provided — requested from GEHA, required by 2026-09-05, re-dated 26-Aug-2026 (was 2026-08-25, elapsed) (Appendix B, item 01). | Allocation from Server_VM_Inventory (vCenter export); utilization from Matilda Discovery Assessment Summary (Host Details / Instance Assessment), as-of 08-Aug-2026 |
| OIMTST102 | 2 | 8 GB | 1 disks / 80 GB | Low% average | Moderate% average | High% storage utilization | Not yet provided — requested from GEHA, required by 2026-09-05, re-dated 26-Aug-2026 (was 2026-08-25, elapsed) (Appendix B, item 01). | Allocation from Server_VM_Inventory (vCenter export); utilization from Matilda Discovery Assessment Summary (Host Details / Instance Assessment), as-of 08-Aug-2026 |
| SECADMUTLPRD101 | 2 | 32 GB | 1 disks / 100 GB | Low% average | Moderate% average | High% storage utilization | Not yet provided — requested from GEHA, required by 2026-09-05, re-dated 26-Aug-2026 (was 2026-08-25, elapsed) (Appendix B, item 01). | Allocation from Server_VM_Inventory (vCenter export); utilization from Matilda Discovery Assessment Summary (Host Details / Instance Assessment), as-of 08-Aug-2026 |

Table 4.1.1 — Sizing & Utilization Baseline

### 4.1.2 Operating System & Platform Readiness

The attributes recorded here determine whether a supported migration path exists at all and whether the machine will boot once it arrives in Azure. Operating system support status, boot type and partition style, architecture, clustering, static addressing, installed agents, licensing entitlement and any special storage are each confirmed against the running system rather than the inventory record. An out-of-support operating system is a decision for the business before it is a task for the migration team, and hardware-bound licensing can stop an application working the moment it moves. Several of these attributes also constrain the migration method chosen later, so they are settled before the method is fixed.

| OS Support Status | Active on all 8 hosts — per OS: Windows Server 2019 (EAUTILDEV201, LSUTILPRD101, LXUTILPRD101, OIMTST101/102) support ends 01-09-2029; Windows Server 2022 (SECADMUTLPRD101) ends 10-15-2031; Windows Server 2025 (MSCOREOSPRD101) ends 10-15-2034; RHEL 9.0 (NETBACKUPPRD101) ends 05-31-2035 (Evidenced — Matilda Host Details, as-of 08-Aug-2026). The prior single-value entry (Windows/2029) is corrected. |
| --- | --- |
| Boot Type & Partition Style | ☐ BIOS ☐ UEFI — Not yet provided — and MBR or GPT. This determines the supported migration path and the target disk configuration. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Architecture & Generation | Platform: Windows (7 hosts) plus RHEL 9.0 on NETBACKUPPRD101 — the Linux host changes the migration tooling path (Azure Migrate agent choice) and its docker workload carries a container-target recommendation (§5.1 conflict) (Evidenced — Matilda Host Details / Server_VM_Inventory LX tab) |
| Clustering / Shared Disk | ☐ None ☐ Failover cluster ☐ Shared disk — Not yet provided — clustered workloads need a specific target design, not a straight lift. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Static IP Dependency | ☐ Yes ☐ No — Not yet provided — anything hardcoded to this address elsewhere in the estate — see §4.7. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Installed Agents & Tooling | Not yet provided — requested from GEHA, required by 2026-09-15 (Appendix B, item 05). |
| Licensing & Hybrid Benefit Eligibility | Not yet provided — Windows Server and SQL Server licensing held, Software Assurance status, and whether Azure Hybrid Benefit applies — this. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Encryption / Special Storage | Not yet provided — Disk encryption, raw device mappings, pass-through disks, iSCSI or SAN-attached storage — each constrains the migration . Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |

Table 4.1.2 — Operating System & Platform Readiness

## 4.2 Application Software & Dependencies

The software layer is documented here in the terms that matter to a migration: exact installed version, whether the vendor supports that version on the target platform, and what else must travel with it. Scheduled jobs, file storage dependencies, license binding and client-side components are each recorded, because every one of them is a thing that silently stops working when the server underneath changes. License binding deserves particular attention: a license tied to a MAC address, host fingerprint or dongle will fail at the moment of cutover, and re-hosting it carries a vendor lead time. An unsupported configuration is a go/no-go item, not a hypercare issue.

| Application Version | Installed software observed on the hosts: /proc/916/exe; svchost.exe; ir_agent.exe; splunkd.exe; svchost.exe; rapid7_endpoint_broker.exe (Source: Application Interface Details, full 451,897-row pass, as-of 12/24/25) |
| --- | --- |
| Vendor Support Status of This Version | docker 29.1.1: Expired — Upgrade to Azure ACI container; iis 10.0: Active — Retain Service IIS version 10.0 (Source: Matilda Discovery Assessment Summary (Application Assessment Summary), as-of 08-Aug-2026)Supported ☐ Extended ☐ End of support — To be provided by GEHA |
| Software Vendor Support Position | Not yet provided — Whether the software vendor supports this application on the target platform, in the target configuration, at this versi. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Vendor Case or Reference | Not yet provided — Support case, account manager confirmation, or published compatibility statement evidencing the position above. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Scheduled Jobs & Batch | iis 10.0 (Web Server; Active); docker 29.1.1 (Container; Expired) (Source: services observed, Matilda Discovery Assessment Summary (Application Assessment Summary), as-of 08-Aug-2026) |
| File Storage Dependencies | Enterprise storage platform: (full capacity report in the corpus) (Source: Storage_Artifacts (Dell PowerFlex / Isilon capacity report)) |
| License Binding | ☐ Not bound ☐ MAC address ☐ Host ID / machine fingerprint ☐ Dongle or hardware key ☐ License server — Not yet provided — a license bound to hardware stops working the moment the application moves. Confirm with the software vendor before cuto. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Client-Side / Desktop Dependencies | Not yet provided — Desktop clients, browser add-ins, printer/scanner integrations, hardcoded IPs or URLs on end-user devices — each must be. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |

Table 4.2 — Application Software & Dependencies

## 4.3 Application Delivery & Client Access

How users reach the application determines how much of the cutover work is invisible to them and how much lands on their desks. Browser access, installed thick clients, published or virtualized delivery, desktop-image deployment and mobile access each carry different execution, dependency and decommission implications. Where a client sits inside a managed desktop image, the image rebuild and redeployment cadence becomes a program dependency rather than a task the migration team controls. Local configuration held on endpoints — cached credentials, mapped drives, hardcoded server names, printer bindings — is captured here because each item must be updated or removed at cutover.

| Primary Access Method | No browser, SMB or RDP listener observed on these hosts; access is via the services listed in the network section (Source: Application Interface Details, full 451,897-row pass, as-of 12/24/25) |
| --- | --- |
| Application URL(s) | Not yet provided — Entry point URLs, and where users hold them — bookmarks, intranet links, portal tiles, shortcuts. Each is a change at cu. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Installed Client Detail | Not yet provided — Client name and version, 32/64-bit, prerequisites and runtimes, install footprint, whether administrative rights are nee. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Present in a Desktop Image? | Not yet provided — Yes/No — which image, who owns it, and the rebuild and redeployment cadence. If yes, that cadence is a dependency, not a. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Deployment & Packaging Mechanism | Not yet provided — SCCM/Intune package, GPO, manual install, image only — and the team that owns the package. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Published / Virtualized Delivery | Not yet provided — Citrix, AVD or similar: farm or host pool, published application name, and the team that republishes or retires it. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| User Population by Access Method | — |
| Device Types | 8 distinct out-of-network endpoints observed communicating with these hosts (Source: Application Interface Details, full 451,897-row pass, as-of 12/24/25) |
| Location & Network Path | Observed inbound listeners: 111 — 2 rows; 49807 — 1 rows; 135 (RPC endpoint mapper) — 1 rows; 49707 — 1 rows (Source: Application Interface Details, full 451,897-row pass, as-of 12/24/25) |
| Local Configuration or Data on the Endpoint | Not yet provided — Config files, cached credentials, local databases, mapped drives, hardcoded server names or IPs, printer or scanner bind. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Client Removal Owner | Not yet provided — Who uninstalls the client or pulls it from the image after go-live. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |

Table 4.3 — Application Delivery & Client Access

## 4.4 Data & Database Tier

The data tier is documented here as the migration source: what exists, how much of it there is, how it will be extracted and what obligations survive the source system. Engine version, edition, collation and compatibility level are recorded because they gate whether a managed platform target is available or whether a straight lift is the only supported option. Volume is captured at database granularity rather than instance total, since the load window is driven by the largest objects and by unstructured attachments that are routinely underestimated. Retention and legal-hold obligations are recorded explicitly, as they outlive the server and must be satisfied somewhere after it is gone.

| Database Engine & Version | Not yet provided — requested from GEHA, required by 2026-09-15 (Appendix B, item 16).— determines export tooling |
| --- | --- |
| Data Volume | Total size and record counts by major object, |
| Attachments / Unstructured Data | Not yet provided — File count and volume held against records — this is routinely underestimated and drives the load window. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Export Method & Access | Not yet provided — How data is extracted, by whom, and what access is required — request lead time if access does not yet exist. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Historical Data & Retention | Not yet provided — How much history migrates, what archives read-only, and the retention or legal-hold obligation on the remainder. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Instance Sizing & Utilization | Not yet provided — vCPU, memory, and measured peak CPU, memory, IOPS and throughput with the observation window — the same standard as §4.1. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Database Count & Individual Sizes | To be provided by GEHA |
| High Availability Topology | Not yet provided — requested from GEHA, required by 2026-09-15 (Appendix B, item 16).Standalone ☐ Always On AG ☐ Failover cluster instance ☐ Log shipping / mirroring — Not yet provided — the topology, not just its presence. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Collation & Compatibility Level | Not yet provided — Both values. These gate a managed-instance or platform-as-a-service target and are the usual reason a straight move is n. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Encryption at Rest | ☐ TDE ☐ Column-level ☐ None — Not yet provided — with key location and custodian. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Scheduled Database Jobs | Not yet provided — SQL Agent jobs, maintenance plans, replication and their owners. Each is retired or re-pointed in §7.6. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Target Compatibility Assessment | Not yet provided — Result of the assessment tool run against this instance, its date, and the blocking findings. Record Not run as a findin. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Cross-Database / Linked Server Dependencies | Not yet provided — Systems that read this database directly. Each is an integration and belongs in §4.7. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |

Table 4.4 — Data & Database Tier

## 4.5 Identity & Access

Identity is documented here with particular care because it is the area most often assumed to transfer intact and the first to fail after a rehost. Authentication method, identity provider, account populations, privileged access and multi-factor enforcement are each recorded with counts rather than general descriptions. Group resolution, service-account authentication and credential paths all depend on directory decisions taken in the target design, so the current position must be precise before that design is fixed. Entries in the registers that follow must each resolve to a target decision; an unmapped group or an unaccounted service account is a post-cutover outage waiting to happen.

| Authentication Method | Enterprise position recorded at discovery: "van led a discussion on current user and app authentication methods, including the use of Entra ID, conditional access policies, service accounts, managed identities, and RBAC for security groups. + Tom and Dale confirmed that on-premises Active Directory groups replicate via AD Connect, and permiss" (ai notes - 2025.11.26 Identity and Access) ¦ "e groups. + Khurshid asked about single sign-on and guest access, and Tom clarified that Entra ID is used for SSO and guest access is supported. + Tom confirmed that single sign-on is managed through Entra ID, and guest access is supported for third-party vendors. + Dale explained that Octa is no lo" (ai notes - 2025.11.26 Identity and Access). Application-specific configuration still to be confirmed with the owner. (Source: GEHA Identity &amp; Access discovery session, 26-Nov-2025) |
| --- | --- |
| Identity Provider | Program record — "van led a discussion on current user and app authentication methods, including the use of Entra ID, conditional access policies, service accounts, managed identities, and RBAC for security groups. + Tom and Dale confirmed that on-premises Active Directory groups replicate via AD Connect, and permiss" (ai notes - 2025.11.26 Identity and Access) ¦ "e groups. + Khurshid asked about single sign-on and guest access, and Tom clarified that Entra ID is used for SSO and guest access is supported. + Tom confirmed that single sign-on is managed through Entra ID, and guest access is supported for third-party vendors. + Dale explained that Octa is no lo" (ai notes - 2025.11.26 Identity and Access) (Source: GEHA Identity &amp; Access discovery session, 26-Nov-2025)— name the product and version, not just the directory |
| Internal User Accounts | — |
| External / Partner Accounts | — |
| Access Governed By | Not yet provided — Active Directory security groups / direct AD user assignment / local application accounts / a mix — name the mechanism. . Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Privileged Access | Not yet provided — Admin accounts, PAM or vaulting in use, and who approves elevation. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| MFA in Use | ☐ Yes ☐ No — To be provided by GEHA |

Table 4.5 — Identity & Access

### 4.5.1 Single Sign-On

The single sign-on configuration in effect today is recorded here in enough detail to be reproduced or deliberately replaced. Integrated Windows Authentication and LDAP binds are not federated protocols, and they continue to function in Azure only where the target remains domain-joined with line of sight to a domain controller — which is a directory decision, not a networking one. Protocol, identity provider, trust configuration, signing certificates, claims released and the identifier that uniquely identifies a user are all captured, since an unstable identifier breaks user mapping in the target. Access paths that bypass single sign-on entirely are recorded too, because they survive an identity change unnoticed.

| Is Federated SSO in Use? | Program record — "van led a discussion on current user and app authentication methods, including the use of Entra ID, conditional access policies, service accounts, managed identities, and RBAC for security groups. + Tom and Dale confirmed that on-premises Active Directory groups replicate via AD Connect, and permiss" (ai notes - 2025.11.26 Identity and Access) ¦ "e groups. + Khurshid asked about single sign-on and guest access, and Tom clarified that Entra ID is used for SSO and guest access is supported. + Tom confirmed that single sign-on is managed through Entra ID, and guest access is supported for third-party vendors. + Dale explained that Octa is no lo" (ai notes - 2025.11.26 Identity and Access) (Source: GEHA Identity &amp; Access discovery session, 26-Nov-2025)Yes ☐ No ☐ Partially — Not yet provided — state which user populations are federated and which are not. If No, name the actual mechanism and stop here. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| --- | --- |
| Protocol | Not yet provided — SAML 2.0 / OIDC / WS-Federation / Kerberos or IWA / header-based. Kerberos and IWA are not federation — flag them as suc. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Identity Provider Product & Version | Not yet provided — ADFS farm and version, Entra ID, Okta, PingFederate — and whether it is on-premises or cloud-hosted. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| IdP Ownership | To be provided by GEHA |
| Trust / Relying Party Configuration | Not yet provided — Relying party trust or enterprise application name, entity ID or issuer, ACS or reply URL, and where the metadata is pub. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Signing & Encryption Certificates | Not yet provided — Certificate, thumbprint and expiry for both IdP and SP sides. Every certificate here must also appear in §4.8, and its e. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Claims / Attributes Released | Not yet provided — Attribute names and sources — UPN, email, employee ID, group claims. Note any attribute the application depends on that . Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| NameID Format & Unique Identifier | Not yet provided — What identifies a user to the application, and whether it is stable across a name change or email change. An unstable id. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| SSO Flow Supported | Not yet provided — IdP-initiated, SP-initiated, or both — and which one users actually use today, since that is the bookmark that changes a. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Session Lifetime & Timeout | Not yet provided — Token lifetime, idle timeout, and re-authentication behavior. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| MFA Enforcement Point | Not yet provided — At the IdP, at the application, or not enforced — and under which conditional access or policy rules. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Non-SSO Access Paths | Not yet provided — Local or emergency accounts, API keys, or service logins that bypass SSO entirely. These survive an SSO change and are r. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| IdP Migration Dependency | Not yet provided — Whether the identity provider is itself being migrated, upgraded or retired under another program workstream. If so, thi. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |

Table 4.5.1 — Single Sign-On

### 4.5.2 Authorization & Entitlement Model

Authorization is a separate question from authentication, and it is recorded here layer by layer: what the directory grants, what the application grants, and what the database grants independently of both. The authoritative permission store is named explicitly, together with the person able to export it, because a description of a role model is not an entitlement list. Data-scoping and field-level rules are captured with the mechanism that enforces them, since a rule the target platform cannot enforce becomes a risk rather than a configuration task. A current export of who holds what is the only way to prove after cutover that the target matches the source.

| Where Entitlement Is Determined | Not yet provided — Directory groups only / in-application roles only / both, with the directory granting entry and the application granting. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| --- | --- |
| Authoritative Permission Store | Not yet provided — The system that holds the definitive answer to “what can this user do” — AD, the application database, a config file, a . Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| In-Application Role Model | Not yet provided — Roles defined inside the application, what each confers, and how a user is assigned to one. Attach the export; a descrip. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Data Scoping / Record-Level Rules | Not yet provided — Restrictions on which records a user can see — by region, business unit, client, claim type, ownership. State the rule a. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Field-Level or Action-Level Restrictions | Not yet provided — Fields a role can view but not edit, actions gated by approval, dollar or volume thresholds. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Segregation of Duties Constraints | Not yet provided — Combinations of access that must not be held together, and what enforces the rule today. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Database-Level Permissions | Not yet provided — Direct database access held by users or tools outside the application — logins, roles, read access for reporting. These . Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Delegated Administration | Not yet provided — Who can grant access without going through IT, and what they can grant. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Access Request & Approval Workflow | Not yet provided — How a new user gets access today — ticket, manager approval, form, verbal. This process must exist for the target on day. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Access Review / Recertification | Not yet provided — Cadence, who attests, when it was last performed, and whether findings were remediated. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Documented Entitlement Baseline | Not yet provided — Whether a current export of who has what exists. If not, take one before cutover — it is the only way to prove the targe. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |

Table 4.5.2 — Authorization & Entitlement Model

### 4.5.3 Non-Interactive & Bypass Access

Mechanisms that operate outside interactive sign-on — API keys, tokens, certificates, key pairs, shared accounts, allowlists and vendor support access — are inventoried here because they persist unchanged through identity migrations and rarely appear in access reviews. The checklist is completed first so that each mechanism is positively confirmed present or absent, rather than left ambiguous by omission. Every entry records who or what uses it, where the credential is held, when it expires or rotates, and whether it bypasses single sign-on altogether. Anything that bypasses sign-on must be closed or formally retained by recorded decision before the go/no-go gate.

| Present | Mechanism | Present | Mechanism |
| --- | --- | --- | --- |
| ☐ | API key or static token | ☐ | OAuth client credentials |
| ☐ | Bearer or personal access token | ☐ | Mutual TLS client certificate |
| ☐ | SSH key pair for SFTP | ☐ | LDAP or directory bind account |
| ☐ | Shared or generic account | ☐ | Smartcard or certificate logon |
| ☐ | IP allowlist used as access control | ☐ | Direct database login |
| ☐ | Kerberos delegation or constrained delegation | ☐ | Local application administrator account |
| ☐ | Vendor or third-party support access | ☐ | Other — specify below |
| ☐ | Confirmed none present |  | Checked by / date: |

Table 4.5.3a — Step 1: Mechanism Checklist

| Mechanism | Who or What Uses It | Credential Type | Issued / Held By | Expiry or Rotation | Bypasses SSO? | Target Equivalent | Disposition |
| --- | --- | --- | --- | --- | --- | --- | --- |
| To be provided by GEHA | To be provided by GEHA | Not yet provided — Key, secret, certificate, key pair, password. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | To be provided by GEHA | ☐ Date: ☐ Interval: ☐ None | ☐ Yes ☐ No | Not yet provided — Target mechanism that replaces it, or None available. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | ☐ Replace ☐ Retain ☐ Revoke at cutover |

Table 4.5.3b — Step 2: Mechanism Register

### 4.5.4 Active Directory Security Group Register

Every Active Directory group that governs access to this application is registered here with its effective membership, its owner and its target mapping. Membership counts are taken after nested groups are expanded, because a count read from the group object understates real access and nesting is a common source of entitlement nobody intended to grant. Groups shared with other applications are identified explicitly, since they cannot be retired alongside this application and become coupling findings for the dependency register. Each group resolves either to a target role or to an explicit retirement decision; none may be left unmapped.

| Group Name (full DN) | Access It Grants | Effective Members | Nested Groups | Group Owner | How Membership Is Granted | Used By Other Applications? | Target Role Mapping |
| --- | --- | --- | --- | --- | --- | --- | --- |
| To be provided by GEHA | Not yet provided — Application role or permission set this group confers. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | — | Not yet provided — Groups nested inside this one, or None. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | To be provided by GEHA | Not yet provided — Access request workflow, manual add, automated from HR attribute. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | ☐ Yes — name them ☐ No — scoped to this application only | ☐ Target role: ☐ Retire |

Table 4.5.4 — Active Directory Security Group Register

### 4.5.5 Service & Application Account Register

Service and application accounts are registered here separately from user accounts, because they fail differently: nothing breaks at cutover, and then a scheduled job runs and fails silently hours later. Each account records what it authenticates to, where its credential is held, its expiry or rotation position, the rights it carries, and the job or integration that depends on it. Every account must trace to a scheduled job, an integration or an explicit retirement decision; an account tracing to none of these is recorded as an open item. Where a managed identity can replace an account in the target, that substitution is recorded, and where it cannot, the reason is stated.

| Account Name | Type | What It Authenticates To | Credential Holder / Vault | Password Policy & Expiry | Rights Held | Depends On / Used By | Disposition at Cutover |
| --- | --- | --- | --- | --- | --- | --- | --- |
| To be provided by GEHA | Not yet provided — AD service account / gMSA / local account / SQL login / application-internal account. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Not yet provided — Target system, share, database or endpoint. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | To be provided by GEHA | ☐ Expiry date: ☐ Non-expiring | Not yet provided — Interactive logon, log on as a service, SPN, group memberships, database roles. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Not yet provided — Scheduled job in §4.2 or integration in §4.7. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | ☐ Replaced by a target credential or managed identity in §5.7 ☐ Retained for another purpose ☐ Disabled and deleted |

Table 4.5.5 — Service & Application Account Register

## 4.6 Network

Only the network configuration that must change as a consequence of this migration is documented here; configuration unaffected by the move is deliberately out of scope to keep the record actionable. DNS records are captured with their current resolution, time-to-live values and owning team, because lowering time-to-live ahead of cutover is a lead-time activity rather than a cutover step. Firewall rules that exist solely for this application are identified so they can be removed at decommission rather than left standing indefinitely. External and partner connectivity is recorded separately, since changes at the far end run on someone else's change process and timetable.

| DNS Records | GEHA operates 144 DNS zones (read: DHCP_DNS_list DNS tab). The records for this application must be identified within them before cutover; per-record TTLs are not held in the export. (Source: DHCP_DNS_list (DNS tab)) |
| --- | --- |
| Firewall Rules to Remove | Not yet provided — requested from GEHA, required by 2026-09-01 (Appendix B, item 06). |
| External / Partner Connectivity | Observed outbound destination ports — 443 (HTTPS) — 85 rows; 9998 — 27 rows; 135 (RPC endpoint mapper) — 11 rows; 389 (LDAP) — 6 rows; 8089 — 4 rows; 49667 — 2 rows; 49669 — 2 rows; 49670 — 2 rows; 8 out-of-network endpoints (Source: Application Interface Details, full 451,897-row pass, as-of 12/24/25) |

Table 4.6 — Network

### 4.6.1 VPN & Remote Connectivity

To be determined Remote access and site-to-site connectivity are treated separately here because they behave differently after a move to Azure. Remote access requirements change rather than disappear, and the answer depends on the connectivity model chosen in the target design, including whether traffic to Azure endpoints is forced back through the corporate tunnel — a frequent and avoidable cause of post-cutover performance complaints. Site-to-site tunnels are jointly owned with external organizations, so their encryption domains, authentication material and far-end contacts are recorded with the lead time each partner's change process requires. Where this application was the only reason a population held VPN access, that access is reviewed rather than left in place.

| Is Remote Access VPN Required to Reach the Application? | Program record — "it ExpressRoute uplink as a potential risk for migration timelines, but stated that using VPNs or publicly reachable storage accounts can bypass this limitation. Firewall management and automation + Ron stated that Azure firewall rules are managed via bicep templates during app deployment, and noted" (ai notes - 2025.11.26 network and connectivity) ¦ "from on-premises infrastructure through edge switches, Palo Alto firewalls, Megaport, and ExpressRoute to Azure. + Ron explained that V hubs are deployed in each Azure region with secured hubs using Azure Firewall, all regions are directly peered, and on-premises ranges connect directly to the Xbox " (ai notes - 2025.11.26 network and connectivity) (Source: GEHA Network &amp; Connectivity discovery session, 26-Nov-2025)Yes ☐ No ☐ Only some populations — To be provided by GEHA |
| --- | --- |
| Solution & Client | Not yet provided — Product and version, client-based or clientless portal, and whether the client is part of the desktop build in §4.3. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Concentrator / Gateway | Not yet provided — Device or service terminating the connection, and the team that owns it. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Authentication to the VPN | Not yet provided — Directory, certificate, MFA — and whether this is a second authentication on top of the application login in §4.5. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Split Tunnel Behavior | Not yet provided — Whether all traffic or only corporate traffic traverses the tunnel. Traffic to Azure forced back through the tunnel adds. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| User Populations Dependent on It | — |
| Still Required After Cutover? | ☐ Yes ☐ No ☐ Only for other applications — Not yet provided — if this application was the only reason a population held VPN access, that access should be reviewed rather than left st. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |

Table 4.6.1a — Remote Access VPN

Each site-to-site tunnel is registered individually because changes at the far end are outside GEHA's control and run to the partner's timetable, not the program's. The register records what traffic the tunnel carries, its encryption domain, the device terminating it, the authentication material and its expiry, and a named contact at the far end together with their required notice period. Tunnels shared with other applications are identified explicitly so they are not retired alongside this one. Each tunnel resolves to retirement, retention or modification, and that disposition is agreed with the partner before the cutover window opens.

| Tunnel / Peer | Far-End Organization | Traffic Carried | Encryption Domain | Termination Device | Authentication & Expiry | Far-End Contact | Used by Other Applications? | Disposition |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| To be provided by GEHA | Not yet provided — Partner, vendor or other site. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Not yet provided — What flows across it, in which direction, and which interfaces in §4.7 depend on it. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Not yet provided — Local and remote subnets in scope. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Not yet provided — Firewall or gateway, and the owning team. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Not yet provided — Pre-shared key or certificate, with rotation or expiry date — add certificates to §4.8. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | To be provided by GEHA | ☐ Yes — name them ☐ No — carries only this application | ☐ Retire after cutover ☐ Retain for other traffic ☐ Modify encryption domain |

Table 4.6.1b — Site-to-Site Tunnels

| Incumbent Vendor Support Access | Not yet provided — How the current vendor or any third party reaches this environment for support — VPN, jump host, remote tool, standing a. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| --- | --- |
| Standing Versus On-Demand | Not yet provided — Whether that access is always available or requested per incident, and who approves it. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |

Table 4.6.1c — Vendor & Third-Party Access

### 4.6.2 Load Balancer Configuration

| Load Balancer in Use? | Not yet provided — requested from GEHA, required by 2026-09-01 (Appendix B, item 06).Yes ☐ No ☐ Partially — Not yet provided — if No, state how traffic reaches the application — direct DNS, reverse proxy, or client-side — and complete no further r. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| --- | --- |

Table 4.6.2a — Load Balancer Configuration

The load balancer configuration is recorded from an exported running configuration rather than from screen captures, because the settings that break applications — persistence profiles, health monitor strings, traffic policies, source address translation and client-IP preservation — are precisely the ones screenshots omit. Each virtual server is documented with its address, the hostnames it serves, its pool members, its balancing method and its TLS termination model. A virtual server that fronts more than one application cannot be retired with this application alone and is recorded as a coupling finding. Certificates presented by the load balancer are cross-referenced to the certificate register and their expiry checked against the cutover date rather than today's date.

| Platform & Version | Not yet provided — Vendor, model, software version, and whether physical or virtual appliance. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| --- | --- |
| Device Names & HA Model | Not yet provided — Device hostnames, active/standby or active/active pairing, and the failover mechanism. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Virtual Server / VIP | To be provided by GEHA |
| FQDNs Served by This VIP | Not yet provided — Every hostname resolving here, including SNI-based routing. A VIP serving more than one application is a coupling findin. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Pool & Members | Not yet provided — Pool name, each member as host and port, and their state. These are the servers in §4.1 — the two lists must agree. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Load Balancing Method | Not yet provided — Round robin, least connections, ratio, priority groups — and any member weighting. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Persistence / Session Affinity | Not yet provided — Source address, cookie, TLS session, or none — with timeout. Applications that hold session state in process depend on t. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Health Monitors | Not yet provided — Monitor type, interval, timeout, and the send and receive strings. A monitor that only checks a port open will not detec. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| TLS Termination Model | Not yet provided — Offload, re-encrypt or passthrough — this determines where certificates live and what the application sees. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Certificates on the Load Balancer | Not yet provided — Certificate names, subject and SAN entries, issuer and expiry. Each must also appear in §4.8, and expiry checked against. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Cipher Policy & TLS Versions | Not yet provided — Permitted protocol versions and cipher suites, and any client certificate authentication requirement. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Traffic Policies, iRules or Scripts | Not yet provided — Every rule, redirect and rewrite applied — HTTP to HTTPS redirects, path-based routing, header manipulation, maintenance. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| WAF / Security Policies | Not yet provided — Web application firewall, bot defence, rate limiting or DDoS policy applied to this virtual server, and who owns the pol. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| SNAT / Source Address Translation | Not yet provided — SNAT pool or automap, and the resulting source addresses seen by back-end servers. These addresses commonly appear in do. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Client IP Preservation | Not yet provided — Whether X-Forwarded-For or an equivalent header is inserted. Applications and downstream systems that log or authorize o. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Global / DNS-Based Load Balancing | Not yet provided — Whether a GSLB or DNS load balancing tier sits in front of this VIP across sites, and how it decides. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Configuration Export Held | Not yet provided — Type of export obtained, the date it was taken, and where it is stored. Record Not obtained as a finding rather than lea. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Configuration Owner & Change Lead Time | To be provided by GEHA |
| Disposition at Decommission | Not yet provided — Retire the virtual server, pool, monitors and certificates — or, where objects are shared with another application, iden. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |

Table 4.6.2b — Load Balancer Configuration

## 4.7 Integrations & Dependencies

Every integration this application participates in is inventoried here, in both directions, with the protocol, frequency and criticality of each. The team owning the far side of the interface is named, because that team controls when the change can be made and their lead time frequently exceeds the migration team's own. Implicit dependencies receive the same treatment as formal interfaces: scheduled jobs on other systems, license servers, mail relays and hardcoded addresses all fail in the same way and for the same reason. This inventory is the input to the target integration design and to the re-pointing tracker executed during the cutover window.

| System | Direction | Protocol / Method | Frequency | Owning Team (Far Side) | Criticality |
| --- | --- | --- | --- | --- | --- |
| ORION | Outbound | observed on ports 49847… (svchost) | 83 connection rows | Not yet provided — far-side owning team not on file (Appendix B item 05). Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Low |
| SCCM | Inbound | observed on ports 60640… (dllhost) | 7 connection rows | Not yet provided — far-side owning team not on file (Appendix B item 05). Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Low |
| REMOTE DESKTOP LICENSE SERVER | Inbound | observed on ports 64365… (svchost) | 2 connection rows | Not yet provided — far-side owning team not on file (Appendix B item 05). Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Low |
| SERVICENOW | Outbound | observed on ports 63634… (svchost) | 2 connection rows | Not yet provided — far-side owning team not on file (Appendix B item 05). Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Low |
| ANSIBLE | Inbound | observed on ports 55586… (sshd:) | 2 connection rows | Not yet provided — far-side owning team not on file (Appendix B item 05). Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Low |
| DEVELOPMENT | Inbound | observed on ports random/none… (sshd:) | 1 connection rows | Not yet provided — far-side owning team not on file (Appendix B item 05). Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Low |
| CITRIX | Outbound | observed on ports 59417… (svchost) | 1 connection rows | Not yet provided — far-side owning team not on file (Appendix B item 05). Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). Different teams on this application to be determined | Low |

Table 4.7 — Integrations & Dependencies

## 4.8 Certificates & Secrets

Every certificate and secret the application depends on is inventoried here, with expiry evaluated against the planned cutover date rather than against today. A certificate that is comfortably valid now but expires during the migration window will fail at the least convenient moment, and renewal frequently involves a third party with its own lead time. Each entry records its purpose, where the private material is held, who custodies it, and the action to be taken — renewal, retirement, or migration to a vault in the target. Certificates presented by load balancers and identity providers appear here as well as in their own sections, so that nothing depends on a reader cross-referencing two lists.

| Certificate / Secret | Purpose | Holder / Vault | Expiry | Expires Before Cutover? | Action |
| --- | --- | --- | --- | --- | --- |
| Not yet provided — requested from GEHA, required by 2026-09-01 (Appendix B, item 06). | — | — | — | — | — |

Table 4.8 — Certificates & Secrets

## 4.9 Data Classification

The sensitivity of the data this application holds, and the regulatory obligations that follow from it, are recorded here because they constrain target region, encryption, logging and retention decisions rather than merely describing them. Presence of protected health information, personally identifiable information or cardholder data is stated explicitly rather than implied by the application's business purpose. Residency constraints are captured because they determine not only where the workload runs but where its backups and diagnostic logs may be held. Current encryption at rest and in transit is recorded so the target can be shown to preserve or improve the position rather than quietly weaken it  The utility servers function as shared jump boxes uses by support teams to install administrative tools perform support activities and run sceduled jobs. They are not intended to store application or business data. Based on the information currently avaliable the enviroment is classfied as internal, and no PHI, PCI or data-residency requirments have been indentified. The current encryption methods for data at rest and data in transit- require confirmation from GEHA

| Data Sensitivity | ☐ Public ☐ Internal ☐ Confidential ☐ Restricted internal |
| --- | --- |
| PII / PHI / PCI Present | ☐ Yes ☐ No — NO – utility servers are jump boxes and are not intended to store application or business data |
| Data Residency Constraints |  |
| Current Encryption at Rest | ☐ Yes ☐ No — To be provided by GEHA |
| Current Encryption in Transit | To be provided by GEHA |

Table 4.9 — Data Classification

## 4.10 Environment Inventory

Every environment is inventoried here, not only production, because non-production estates carry real data, real integrations and real license obligations far more often than expected. Each environment records its purpose, its endpoint, the nature of the data it holds and the internal move group it belongs to. Non-production is migrated ahead of production deliberately, so that the process is proven on a system whose failure costs nothing. Environments that are dormant or unused are identified here as retirement candidates rather than migrated by default.

| Environment | Purpose | URL / Endpoint | Data Source | Migration Wave |
| --- | --- | --- | --- | --- |
| DEV | Development | Not yet provided — endpoint URL not on file (Appendix B item 05). Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Non-production data | 1 host-rows observed |
| PROD | Live business use | Not yet provided — endpoint URL not on file (Appendix B item 05). Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Live data | 5 host-rows observed |
| TEST | Pre-production validation | Not yet provided — endpoint URL not on file (Appendix B item 05). Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Non-production data | 2 host-rows observed |

Table 4.10 — Environment Inventory

## 4.11 Availability & Backup Position

Availability and backup posture is recorded here to the extent that it bears on the migration itself, rather than as a description of steady-state operations. Cluster and replication topology is captured because it determines which migration methods are available, and a verified restore point is captured because it is the only genuine protection across the cutover window. The recovery point the current configuration actually delivers is recorded alongside the objective the business believes it has, since the two frequently differ and the target should not be designed to an aspiration. Retention and legal-hold obligations, and any standby copy holding live data, are recorded because both outlive the source system.

| High Availability Topology | Not yet provided — requested from GEHA, required by 2026-09-15 (Appendix B, item 16).Standalone ☐ Clustered ☐ Replicated / mirrored ☐ Load-balanced pair — Not yet provided — per tier. Anything other than standalone changes the migration method — record which tier and what form. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| --- | --- |
| Known Single Points of Failure | Not yet provided — requested from GEHA, required by 2026-09-15 (Appendix B, item 05). |
| Backup Product & Schedule | Per-host vCenter backup policies on file: LSUTILPRD101 "8WK Backup, ansiblehost"; LXUTILPRD101, SECADMUTLPRD101, MSCOREOSPRD101 and NETBACKUPPRD101 "8WK Backup"; OIMTST101/102 and EAUTILDEV201 "2WK Backup" (Evidenced — Server_VM_Inventory (vCenter export), Backup Policy column, LS/LX tabs). Backup product and restore verification remain with GEHA (Appendix B item 17; register W3-UTIL-3). |
| Most Recent Verified Restore | Not on file — the vCenter export records backup policy but no restore-verification history; searched the full evidence pack (Appendix B note); requested from GEHA (Appendix B item 17; register W3-UTIL-3). |
| Retention & Legal Hold | Not yet provided — requested from GEHA, required by 2026-09-30 (Appendix B, item 12). |
| Achieved RPO Today | Not yet provided — requested from GEHA, required by 2026-09-15 (Appendix B, item 16). |
| DR Replica or Standby Copy | Not yet provided — requested from GEHA, required by 2026-09-15 (Appendix B, item 16).None ☐ Standby / replica exists — Not yet provided — if one exists, state whether it migrates, retires, or is left in place — a forgotten standby holds live data after go-li. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |

Table 4.11 — Availability & Backup Position

# 5. Target State

The target state is defined here decision by decision, with the reasoning recorded alongside each choice. Unlike a vendor-operated service, this environment is designed and operated by GEHA, so an undocumented rationale cannot be reviewed and will not survive the staff changes that occur across a program of this length. Each decision names what was chosen, what was rejected, and who accepted the resulting trade-off. Read against the current-state section, the difference between the two is the migration.

## 5.0 Target State Architecture Diagram

The diagram presents the application as it will run in Azure and serves as the visual counterpart to the design decisions recorded in this section. Subscription and resource-group boundaries, compute, data services, network segmentation and identity paths should all be locatable on it, and any component drawn without an owning subsection is undesigned rather than merely undocumented. It is used for design review and sign-off, for briefing the platform and network teams on what to build, and afterwards for verifying that what was built matches what was agreed. Read against the current-state diagram, the delta between the two is the scope of work.

Not yet provided — INSERT TARGET STATE ARCHITECTURE DIAGRAM HERE. To be supplied by GEHA (Appendix B).

| Diagram Name | — Target State on Azure |
| --- | --- |
| Description | Not yet provided — One or two sentences: what the diagram shows and the boundary it covers — which environments, which subscriptions, what . Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Use Case | Not yet provided — What this diagram is used for: design review and §12 sign-off, the §5.14 Well-Architected review, briefing the platform . Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Source of Truth | Not yet provided — The design decisions and IaC repository the diagram reflects, with the version or date it was last synchronized. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Author & Date | To be provided by GEHA |
| Sign-Off | Not yet provided — Client approver — name, role, date. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). / Not yet provided — Vendor approver — name, role, date. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |

Table 5.0 — Diagram Record

## 5.1 Migration Strategy

Migration strategy is settled per component rather than per application, because a single application routinely rehosts one tier, replatforms another and retires a third. Each component records its strategy, its target service, the reasoning behind the choice and the person who made it. Recording what was rejected matters as much as recording what was chosen, since the question is invariably revisited later by someone who was not in the room. The strategies chosen here determine the migration method, the achievable downtime and the rollback position described in the sections that follow.

| Component | Strategy | Target Service | Rationale | Decided By |
| --- | --- | --- | --- | --- |
| Utility — application tier | Rehost | target service not recorded in the Wave Plan Tracker | Rehost per the authoritative tracker (BASELINE v2.1 Reference -App Disp). CONFLICT logged, not resolved silently: Matilda Application Assessment Summary records UTILITY:PROD as Replatform (IaaS,PaaS) and marks the docker workload on NETBACKUPPRD101 "Upgrade to Azure ACI container" (Application Summary Details), while UTILITY:DEV/TEST are Rehost/IaaS. The tracker ruling stands; the Matilda recommendation is recorded for the NETBACKUPPRD101 container ruling (register DECISION W3-UTIL-D1). | Wave Plan Tracker rev-3 / Matilda assessment |

Table 5.1 — Migration Strategy

## 5.2 Landing Zone Placement

Landing zone placement records where this workload deploys and, just as importantly, what it inherits by deploying there. The management group, subscription, resource groups, region and paired region are captured together with the naming and tagging standards the workload must satisfy. Inherited policy is called out explicitly because it constrains deployments in ways invisible to the application team and is a frequent cause of failures that appear inexplicable at build time. Quota, SKU and zone availability in the target region are confirmed before design sign-off rather than discovered on the day of deployment.

| Management Group | GEHA tenant hierarchy holds 0 management groups and 95 subscriptions; the target group for this workload is a placement decision still open. (Source: Subscription_Management_Groups export) |
| --- | --- |
| Subscription Name & ID | Not yet provided — Target subscription. State whether it exists or must be provisioned, and the lead time if it must. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Resource Groups | Not yet provided — Resource groups to be created, and the lifecycle boundary each represents. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Primary Region & Paired Region | Program target — "¦ ¦ Minutes of Meeting — Azure Landing Zone Discovery Session ¦ +-----------------------------------------------------------------------+ 1. Meeting Details --------------- ------------------------------------------------------- Meeting Title Azure Landing Zone — Discove" (GEHA_LZ_Discovery_MoM_0702) ¦ "--------- ------------------------------------------------------- Meeting Title Azure Landing Zone — Discovery Session Date July 1, 2026 Duration Approximately 55 minutes Facilitator George (CitiusTech) Note-taker CitiusTech Delivery Team Distribution All participants + GEHA Cloud, Security, Network" (GEHA_LZ_Discovery_MoM_0702) (Source: GEHA Azure Landing Zone Discovery minutes of meeting, 01-Jul-2026) |
| Naming Standard | Not yet provided — The convention applied, and where it is published. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Tagging Requirements | Not yet provided — Mandatory tags and their values for this workload — owner, cost center, environment, criticality, data classification. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Inherited Policy Assignments | 42 policy assignments exist in the tenant and will apply at the scope this workload lands in. (Source: Policy_list (AssignmentListExport)) |
| Policy Exemptions Required | Not yet provided — Any exemption this workload needs, with the justification, the approver and an expiry date. An exemption without an expi. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| RBAC Scope for the Workload Team | Not yet provided — What the application team can do in this subscription, and what remains with the platform team. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Quota & Capacity Confirmation | Not yet provided — vCPU quota, SKU availability and zone availability confirmed in the target region — check before design sign-off, not at. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |

Table 5.2 — Landing Zone Placement

## 5.3 Compute

The target compute design is sized from measured utilization rather than from allocated capacity, so that the migration does not carry years of over-provisioning into a consumption-billed platform. Each server records its target SKU, the assessment output the recommendation came from, and the reasoning wherever a recommendation has been overridden. Availability design is stated with the uptime commitment it actually supports, so it can be compared honestly against the service level the business expects. Disk configuration is specified against measured throughput and latency requirements rather than replicating on-premises disk layouts by default.

| Target VM SKUs | Right-sizing input — 8 hosts across 3 environments (Evidenced — Matilda Application TCO Right Sizing rows 254-256, as-of 08-Aug-2026): DEV (EAUTILDEV201) 2 logical processors / 8 GB / 209.4 GB; TEST (OIMTST101/102) 6 / 16 GB / 158.9 GB; PROD (LSUTILPRD101, LXUTILPRD101, SECADMUTLPRD101, MSCOREOSPRD101, NETBACKUPPRD101) 16 / 115.3 GB / 2,455.1 GB. Totals 24 logical processors, 139.3 GB memory, 2,823.4 GB storage. The prior figure in revision 0.3 used the DEV row alone and is corrected. SKU selection is a design decision still open. |
| --- | --- |
| Assessment Report Reference | To be provided by GEHA |
| Right-Sizing Basis | Matilda assessment: migration type IaaS, complexity Low, priority Low, group GroupFive (Source: Matilda Discovery Assessment Summary (Application Assessment Summary), as-of 08-Aug-2026)Measured utilization ☐ Allocated capacity ☐ Vendor requirement — Not yet provided — if allocation was used, say why measurement was unavailable. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Availability Design | ☐ Availability zones ☐ Availability set ☐ Single instance — Not yet provided — with the uptime commitment each gives, compared against §3.3. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Disk Configuration | Not yet provided — Disk type and size per volume, with the IOPS and throughput each provides against the §4.1.1 measured peak. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Proximity & Latency Requirements | Not yet provided — Whether components must be co-located, and what breaks if they are not. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| VM Extensions & Agents | Not yet provided — Extensions to be installed — monitoring, backup, security, domain join, custom script — and who owns each. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Trusted Launch / Security Type | ☐ Trusted Launch ☐ Standard — Not yet provided — Trusted Launch requires a Gen2 UEFI source; confirm against the boot type in §4.1.2 and state the reason where Standard . Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Boot Diagnostics & Serial Access | Not yet provided — Enabled, and where diagnostics are stored — this is what makes a failed boot diagnosable. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Auto-Shutdown / Scheduling | Not yet provided — Applies to non-production; state the schedule and who can override it. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Scaling Approach | Not yet provided — Fixed size, scale set, or manual resize — and the trigger for a resize decision. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |

Table 5.3 — Compute

## 5.4 Data Platform

The target data service is recorded here together with the migration method that reaches it and the downtime that method implies. The compatibility assessment of the source instance is the input to this decision: collation, compatibility level and unsupported features determine whether a managed platform target is available or whether a lift to a virtual machine is the only supported path. Backup, retention and restore testing are defined as part of the design rather than deferred to operations. Every endpoint change is identified so that connection strings and downstream references can be updated in a controlled way rather than discovered by failure.

| Target Data Service | ☐ SQL on Azure VM ☐ SQL Managed Instance ☐ Azure SQL Database ☐ Other — Not yet provided — with the reason, referencing the §4.4 compatibility assessment. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| --- | --- |
| Service Tier & Sizing | Not yet provided — Tier, compute size and storage, sized from the §4.4 utilization figures. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| High Availability Design | Not yet provided — Target HA model and the availability commitment it carries. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Backup Configuration | Not yet provided — Backup frequency, retention, long-term retention, and where backups are held. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Restore Testing | Not yet provided — How and when a restore is proven — an untested backup is an assumption. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Migration Method | Not yet provided — Backup and restore, replication link, migration service, or export and import — with the expected downtime each implies. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Compatibility Blockers & Remediation | Not yet provided — Findings from the §4.4 assessment, and the fix or accepted change for each. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Connection String & Endpoint Changes | Not yet provided — New endpoints and every place a connection string must be updated — cross-reference §5.13. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |

Table 5.4 — Data Platform

## 5.5 Storage & File Services

The target storage design addresses not only capacity but the two things that most often break at cutover: how identity is presented to file shares, and whether permissions survive the copy. Each source location maps to a target service with a stated redundancy option and lifecycle rule aligned to the retention obligation recorded earlier. Copy duration is taken from the rehearsal rather than estimated, because a file copy that runs longer than the outage window is discovered too late to fix. Permission preservation is verified explicitly and the verification signed, since restored data that nobody can open has not been migrated.

| Target Storage Services | Current on-premises platform (source of the data to be moved): Storage ¦ Dell Powerﬂex/vxﬂex storage cluster ¦ LS – 262TB of capacity. 62% used. 3.09 data reduction. No snapshots or ¦ replication ¦ LX – 222TB of capacity. 58% used. 3.23 data reduction. No snapshots or ¦ replication ¦ Dell Isilon ¦ LS – 415TB of capacity. 68% used. SyncIQ is used for replication to LX ¦ LX – 415TB of capacity. 60% used. SyncIQ is used for replication to LS (Source: Storage_Artifacts (Dell PowerFlex / Isilon capacity report)) |
| --- | --- |
| Redundancy Option | Not yet provided — Local, zone or geo redundancy, and the reason. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Access Tier & Lifecycle | Not yet provided — Tiering and lifecycle rules, aligned to the retention obligation in §4.4. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Share Access Method | Not yet provided — SMB or NFS, and how identity is handled — this is where domain-joined file access commonly breaks. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Migration Method & Measured Duration | Not yet provided — Copy tooling, and elapsed time measured during the §6.4 test, not estimated. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Permissions Preservation | Not yet provided — Whether ACLs are carried, how they are verified, and who signs the verification. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |

Table 5.5 — Storage & File Services

## 5.6 Network

The target network design records the addressing, segmentation and connectivity the workload requires, together with every change users, integrations and partners must make to reach it. Address space is confirmed as non-overlapping with on-premises and peered ranges before anything is built. Security groups and route tables are derived from the on-premises rules being retired, so that the target reproduces the intended posture rather than inheriting an accumulation of exceptions. Private endpoints, DNS zones and load balancing are specified deliberately, including persistence, health probes and TLS termination, because carrying these across by default is a common source of intermittent failure. The utility servers will be deployed in the approved GEHA Azure virtual network and subnet. The servers do not require static IP addresses, loadbalancing, or utility specfic tunnel or peer connections. Connectivity will be limited to administartive access and required enterprise services, include Active Directory, DNS, Security agents, monitoring, pacthing, and team specific tools.

Not yet provided — INSERT TARGET NETWORK TOPOLOGY DIAGRAM HERE. To be supplied by GEHA (Appendix B).

| Virtual Network & Subnets | Not yet provided — VNet, address space, subnets and their purpose. Confirm no overlap with on-premises or peered ranges. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| --- | --- |
| IP Addressing | Not yet provided — Static or dynamic per component, and any address that must be reserved because something elsewhere depends on it — see §. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Connectivity to On-Premises | Program record — "it ExpressRoute uplink as a potential risk for migration timelines, but stated that using VPNs or publicly reachable storage accounts can bypass this limitation. Firewall management and automation + Ron stated that Azure firewall rules are managed via bicep templates during app deployment, and noted" (ai notes - 2025.11.26 network and connectivity) ¦ "from on-premises infrastructure through edge switches, Palo Alto firewalls, Megaport, and ExpressRoute to Azure. + Ron explained that V hubs are deployed in each Azure region with secured hubs using Azure Firewall, all regions are directly peered, and on-premises ranges connect directly to the Xbox " (ai notes - 2025.11.26 network and connectivity) (Source: GEHA Network &amp; Connectivity discovery session, 26-Nov-2025)ExpressRoute ☐ Site-to-site VPN ☐ None required — Not yet provided — with the circuit or gateway, its owner, and the change lead time. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Hub / Spoke Peering | Program target — "¦ ¦ Minutes of Meeting — Azure Landing Zone Discovery Session ¦ +-----------------------------------------------------------------------+ 1. Meeting Details --------------- ------------------------------------------------------- Meeting Title Azure Landing Zone — Discove" (GEHA_LZ_Discovery_MoM_0702) ¦ "--------- ------------------------------------------------------- Meeting Title Azure Landing Zone — Discovery Session Date July 1, 2026 Duration Approximately 55 minutes Facilitator George (CitiusTech) Note-taker CitiusTech Delivery Team Distribution All participants + GEHA Cloud, Security, Network" (GEHA_LZ_Discovery_MoM_0702) (Source: GEHA Azure Landing Zone Discovery minutes of meeting, 01-Jul-2026) |
| Network Security Groups & Application Security Groups | Not yet provided — Rules required, derived from the §4.6 rules being retired. Attach the rule set. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Route Tables & Forced Tunnelling | Not yet provided — User-defined routes, and whether egress is forced through an inspection point. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Firewall / Egress Control | Program target — "ly to align the network team before detailed Wave planning proceeds. Key Highlights - Azure Firewall Premium confirmed as cloud-side network security. No Palo Alto in Azure. - IDS/IPS active on Azure Firewall. TLS inspection and URL filtering NOT enabled on Azure Firewall. - Zscaler ZIA + ZPA in use" (GEHA_FW_Migration_MoM) ¦ "nfirmed as cloud-side network security. No Palo Alto in Azure. - IDS/IPS active on Azure Firewall. TLS inspection and URL filtering NOT enabled on Azure Firewall. - Zscaler ZIA + ZPA in use for user traffic only. Server egress goes through Azure Firewall. - F5 is a reverse proxy and GSLB — Akamai is" (GEHA_FW_Migration_MoM) (Source: GEHA Firewall Migration minutes of meeting) |
| Private Endpoints & Private DNS | Not yet provided — Platform services reached privately, the private DNS zones involved, and who owns zone records. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Load Balancing | Not yet provided — Load balancer, Application Gateway or Front Door — replacing the §4.6.2 configuration. Carry across persistence, health . Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Web Application Firewall | Not yet provided — Policy, mode (detection or prevention), and the owner. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| DNS Records | GEHA operates 144 DNS zones (read: DHCP_DNS_list DNS tab). The records for this application must be identified within them before cutover; per-record TTLs are not held in the export. (Source: DHCP_DNS_list (DNS tab)) |
| Certificates | Not yet provided — Certificates required in the target, where they are stored, and their expiry — add each to §4.8. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |

Table 5.6 — Network

## 5.7 Identity & Access

The target identity design must account for every entry in the current-state identity registers; unresolved entries are the single most common cause of access failure after cutover. The directory model is stated first, since it determines whether domain-joined authentication remains available or whether the application must move to a federated protocol. Group-to-role mapping is recorded one row per source group, with no group left unmapped, and service accounts resolve either to a managed identity or to a credential with a named rotation owner. Break-glass and privileged access are defined explicitly, including how their use is detected.

| Directory Model | Program identity position — "van led a discussion on current user and app authentication methods, including the use of Entra ID, conditional access policies, service accounts, managed identities, and RBAC for security groups. + Tom and Dale confirmed that on-premises Active Directory groups replicate via AD Connect, and permiss" (ai notes - 2025.11.26 Identity and Access) ¦ "e groups. + Khurshid asked about single sign-on and guest access, and Tom clarified that Entra ID is used for SSO and guest access is supported. + Tom confirmed that single sign-on is managed through Entra ID, and guest access is supported for third-party vendors. + Dale explained that Octa is no lo" (ai notes - 2025.11.26 Identity and Access) (Source: GEHA Identity &amp; Access discovery session, 26-Nov-2025)Domain-joined to on-premises AD ☐ Entra Domain Services ☐ Entra joined ☐ Mixed — Not yet provided — with the reason and what it requires from the platform team. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| --- | --- |
| Application Authentication | Not yet provided — Target authentication method, mapped from §4.5.1. If SSO is being introduced rather than carried, that is new work — siz. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Group-to-Role Mapping | Not yet provided — One row per group in §4.5.4, resolving to a target group or role, or to Retire. No group may be left unmapped. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Azure RBAC Assignments | Not yet provided — Role, scope and assignee for platform-level access — distinct from access inside the application. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Managed Identities | Not yet provided — Where a service account from §4.5.5 is replaced by a managed identity, and where it cannot be, with the reason. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Remaining Service Accounts | Not yet provided — Accounts that must persist, their credential store, rotation owner and rotation interval. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Secrets & Certificate Storage | Not yet provided — Key vault, access model, and who can read what. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Privileged Access | Not yet provided — Just-in-time elevation, approval requirement, and standing access that survives — standing administrative access should . Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Break-Glass Access | Not yet provided — Emergency access, who holds it, and how its use is detected. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Programmatic Access Paths | Not yet provided — Target equivalent for each row of §4.5.3 — API credentials, certificates, keys — with issuer, storage and rotation. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |

X

## 5.8 Security & Compliance

The controls protecting this workload in the target are recorded here, together with the obligations carried forward from the data classification. Posture management, endpoint protection, encryption at rest and in transit, log collection, vulnerability management and patching are each assigned to a named tool and a named owner rather than described in general terms. Where a control is inherited from the platform rather than configured per workload, that inheritance is stated so it is not duplicated or assumed. Data residency is confirmed for the workload, its backups and its logs, since the three do not always land in the same place.

| Cloud Security Posture Tooling | Program target — "ly to align the network team before detailed Wave planning proceeds. Key Highlights - Azure Firewall Premium confirmed as cloud-side network security. No Palo Alto in Azure. - IDS/IPS active on Azure Firewall. TLS inspection and URL filtering NOT enabled on Azure Firewall. - Zscaler ZIA + ZPA in use" (GEHA_FW_Migration_MoM) ¦ "nfirmed as cloud-side network security. No Palo Alto in Azure. - IDS/IPS active on Azure Firewall. TLS inspection and URL filtering NOT enabled on Azure Firewall. - Zscaler ZIA + ZPA in use for user traffic only. Server egress goes through Azure Firewall. - F5 is a reverse proxy and GSLB — Akamai is" (GEHA_FW_Migration_MoM) (Source: GEHA Firewall Migration minutes of meeting)’s configuration, and who acts on findings |
| --- | --- |
| Endpoint Protection | Not yet provided — Product on the target servers, and how it is deployed. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Encryption at Rest | ☐ Platform-managed keys ☐ Customer-managed keys — Not yet provided — with key custodian and rotation policy. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Encryption in Transit | Program target — "ly to align the network team before detailed Wave planning proceeds. Key Highlights - Azure Firewall Premium confirmed as cloud-side network security. No Palo Alto in Azure. - IDS/IPS active on Azure Firewall. TLS inspection and URL filtering NOT enabled on Azure Firewall. - Zscaler ZIA + ZPA in use" (GEHA_FW_Migration_MoM) ¦ "nfirmed as cloud-side network security. No Palo Alto in Azure. - IDS/IPS active on Azure Firewall. TLS inspection and URL filtering NOT enabled on Azure Firewall. - Zscaler ZIA + ZPA in use for user traffic only. Server egress goes through Azure Firewall. - F5 is a reverse proxy and GSLB — Akamai is" (GEHA_FW_Migration_MoM) (Source: GEHA Firewall Migration minutes of meeting) |
| Security Log Collection | Not yet provided — Which logs are collected, where they land, retention on each side, and how they reach the SIEM. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Vulnerability Management | Not yet provided — Scanning cadence, who remediates, and the agreed remediation window by severity. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Patching Approach | Not yet provided — Update mechanism, maintenance window, and who approves out-of-band patching. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Compliance Obligations | Not yet provided — Obligations carried from §4.8, and the control that satisfies each in the target. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Data Residency Confirmation | Not yet provided — Confirmed against the region selected in §5.2, including where backups and logs are held. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |

Table 5.8 — Security & Compliance

## 5.9 Resilience & Recovery

The target backup and recovery design is stated against the current service levels rather than in isolation, so that any regression is visible rather than buried. Backup policy, retention, verification and restore testing are defined as design decisions with owners, not as operational details to be settled later. A target recovery position weaker than the current state requires the application owner's written acceptance, recorded here rather than assumed. The disaster recovery design names its procedure and its owner, and an untested design is carried as an assumption until it has actually been exercised.

| Backup Policy | Not yet provided — Frequency, retention, long-term retention, and vault location. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| --- | --- |
| Backup Verification | Program record — "ion and clarifying details. - Backup Technologies and Storage: Matt explained that Cohesity is used for backups, with Lightspeed generating database BAK files that Cohesity then backs up. Backups are stored locally and at a remote data center for eight weeks, and long-term backups are kept in Azure " (ai notes - 2025.12.05 backup, dr, and continuity) ¦ "y is used for backups, with Lightspeed generating database BAK files that Cohesity then backs up. Backups are stored locally and at a remote data center for eight weeks, and long-term backups are kept in Azure Blob storage for three years. - Backup Retention Policies: Matt detailed that daily backup" (ai notes - 2025.12.05 backup, dr, and continuity) (Source: GEHA Backup, DR &amp; Continuity discovery session, 05-Dec-2025) |
| Restore Test | To be provided by GEHA |
| Target RTO / RPO | Not yet provided — Target values, against the §3.3 current values, with the gap stated. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Availability Commitment | Not yet provided — The uptime the target design supports, against the §3.3 SLA. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Disaster Recovery Design | ☐ Cross-region replication ☐ Backup restore only ☐ None — Not yet provided — with the recovery procedure and its owner. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| DR Test Plan | Not yet provided — When the DR design is exercised, and by whom. An untested DR design is an assumption in §10.2. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |

Table 5.9 — Resilience & Recovery

## 5.10 Monitoring & Operations

An Azure environment arrives with no monitoring, alerting or operational visibility beyond what is deliberately configured, which is a sharp contrast to a datacenter where a great deal is inherited from the surrounding estate. Workspace, diagnostic settings, platform and guest metrics, alert rules and action groups are each specified here with a named recipient, because an alert with no recipient is not an alert. Guest-level metrics require an agent and are the most frequently forgotten element of the design. Dashboards and update management are included so that the support team inherits a workload it can actually see.

| Log Analytics Workspace | Program monitoring position is recorded in the Wave Plan Tracker replacement column for the monitoring estate; this application inherits the platform standard. (Source: Wave Plan Tracker rev-3) |
| --- | --- |
| Diagnostic Settings | Not yet provided — Resources emitting diagnostics, and where they are sent. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Platform & Guest Metrics | Not yet provided — What is collected from the host and from inside the guest — guest metrics require an agent and are frequently missed. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Alert Rules | Not yet provided — Condition, threshold, severity and action group for each alert. An alert with no named recipient is not an alert. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Action Groups & On-Call Routing | Not yet provided — Who is notified, by what channel, and the escalation if unacknowledged. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Application Monitoring | Not yet provided — Availability tests, transaction monitoring, and integration failure detection. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Dashboards & Reporting | Not yet provided — What operations and the business see, and where. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Update Management | Not yet provided — How patching is scheduled and reported. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |

Table 5.10 — Monitoring & Operations

## 5.11 Cost & Licensing

The estimated run cost is recorded here together with the licensing position it depends on, because the two cannot be separated: hybrid benefit eligibility alone can move the figure substantially. The estimate names its date, its source tool and the assumptions behind it, so that it can be validated later rather than merely believed. Reservation and savings commitments are proposed but not made until the workload has run at steady state, since committing early locks in the over-provisioning the migration was meant to remove. Budgets, alert thresholds and chargeback tags are defined so that cost lands with the owner who can act on it.

| Estimated Monthly Run Cost | Assessment estimate — IaaS on-demand $799, 1-year reserved $498, 3-year reserved $345. (Source: Matilda Discovery Assessment Summary (Application TCO Right Sizing), as-of 08-Aug-2026) |
| --- | --- |
| Cost Comparison | Not yet provided — Against the current on-premises cost, stating what is and is not included on each side. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Reservations / Savings Commitments | Not yet provided — Whether a commitment is proposed, its term, and who approves it. Do not commit before the workload has run at steady sta. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Hybrid Benefit Applied | ☐ Yes ☐ No — Not yet provided — from the §4.1.2 licensing position. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Non-Production Cost Controls | Not yet provided — Scheduling, smaller SKUs, or scale-down outside business hours. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Budget & Alerts | Not yet provided — Budget set, threshold alerts, and who receives them. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Chargeback / Showback Tags | Not yet provided — Tags that route this cost to the right owner, matching §5.2. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |

Table 5.11 — Cost & Licensing

## 5.12 Deployment Method & Infrastructure as Code

How the target is deployed determines how easily it can be rebuilt, audited and recovered, so the method is recorded as a decision rather than left implicit. Manual deployment is an acceptable answer provided the associated configuration-drift risk is stated and accepted. Where infrastructure as code is used, the repository, pipeline and approval path are named, along with where deployment state and secrets are held and who can reach them. Drift detection is specified so that manual change after deployment is visible rather than silently divergent from the documented design.

| Deployment Approach | ☐ Infrastructure as code ☐ Portal / manual ☐ Mixed — Not yet provided — if manual, state why and what the drift risk is. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| --- | --- |
| Tooling & Repository | Not yet provided — Language and repository location, with access. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Pipeline & Approvals | Not yet provided — How a change reaches production, and who approves. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Environment Parity | Not yet provided — How non-production is kept representative of production, and where it deliberately differs. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Configuration Drift Detection | Not yet provided — What detects manual change after deployment, and who reviews it. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| State & Secret Handling | Not yet provided — Where deployment state and secrets live, and who can reach them. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |

Table 5.12 — Deployment Method & Infrastructure as Code

## 5.13 Hardcoded Values & Configuration Changes

Hardcoded values are the most frequent cause of an application that has migrated successfully in every technical sense and still does not work. Connection strings, hostnames, IP addresses, URLs, file paths, certificate references, mail relays, license servers and service accounts are identified from configuration files and source code rather than from recollection. Each entry records where the value lives, its current and target values, its owner, and whether it can be pre-staged before the outage window. Values that can be changed in advance are changed in advance, which shortens the window and reduces the number of decisions taken under time pressure.

| Change | Where It Lives | Current Value | Target Value | Owner | Pre-Stageable |
| --- | --- | --- | --- | --- | --- |
| Not yet provided — Connection string, hostname, IP, URL, file path, certificate reference, SMTP relay, license server, service account. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Not yet provided — File, registry key, database table, environment variable. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | To be provided by GEHA | To be provided by GEHA | To be provided by GEHA | ☐ Yes ☐ No |

Table 5.13 — Hardcoded Values & Configuration Changes

## 5.14 Well-Architected Review Record

Design decisions are recorded here against each Well-Architected pillar together with the trade-off accepted in making them, so that the reasoning remains visible to whoever inherits the design. Reliability, security, cost, operational excellence and performance are each addressed, and a trade-off accepted for cost or schedule is stated plainly rather than presented as a neutral choice. Each acceptance carries a named individual and a date. This record is what allows a future reviewer to distinguish a considered compromise from an oversight.

| Pillar | Key Decisions | Trade-Off Accepted | Accepted By |
| --- | --- | --- | --- |
| Reliability | Not yet provided — Availability design, redundancy, recovery. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |  | To be provided by GEHA |
| Security | Not yet provided — Identity, encryption, network isolation, logging. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | — | — |
| Cost Optimization | Not yet provided — Sizing, licensing, commitments, scheduling. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | — | — |
| Operational Excellence | Not yet provided — Deployment, monitoring, patching, runbooks. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | — | — |
| Performance Efficiency | Not yet provided — Sizing basis, scaling approach, latency. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | — | — |

Table 5.14 — Well-Architected Review Record

## 5.15 Scheduled Job & Batch Orchestration

Scheduled jobs are frequently assumed to travel with the server, which is true only where the scheduler runs locally. Where an enterprise scheduler triggers the job, every one requires its own endpoint change, credential and agent work carried out by the team that owns the scheduler, on their timetable. Each job recorded earlier resolves here to a target trigger, an owning team, an identity it runs as, and the date and time of its first execution after cutover together with the person confirming it succeeded. Time-zone differences between the source datacenter and the target region are checked, since a job scheduled for 02:00 local will not run at the same hour after the move.

| Job / Batch | Trigger Today | Target Trigger | Change Required | Owning Team | Runs As | First Run After Cutover |
| --- | --- | --- | --- | --- | --- | --- |
| To be provided by GEHA | Not yet provided — Enterprise scheduler, Task Scheduler, cron, SQL Agent, application-internal. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Not yet provided — Same scheduler re-pointed, target-native scheduling, or retired. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | Not yet provided — Endpoint, credential, agent installation, script path. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | To be provided by GEHA | Not yet provided — Account or managed identity from §5.7. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). | To be provided by GEHA |

Table 5.15a — Scheduled Job & Batch Orchestration

| Scheduler Agent Installation | Not yet provided — Whether a scheduling agent must be installed on the target and who installs it. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| --- | --- |
| Calendar and Time Zone | Whether the target region‘s time zone changes any job’s effective run time — a job scheduled for 02:00 local runs at a different hour if the target region differs |
| Job Dependencies and Sequence | Not yet provided — Jobs that must run in order or that depend on jobs on other systems, and how that sequence is preserved. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |
| Failure Alerting | Not yet provided — How a failed job is detected in the target and who receives the alert. A job that silently stops running is the most com. Not on file in the evidence pack (searched per the Appendix B source-exhaustion note, 26-Aug-2026); requested from GEHA (Appendix B; register W3-UTIL). |

Table 5.15b — Scheduled Job & Batch Orchestration

# 6. Migration Preparation

Everything that can be completed before the cutover window is completed before it, so that the window itself is reserved exclusively for work that genuinely cannot be pre-staged. Replication, rehearsal, testing, freeze arrangements, readiness confirmation and communications all belong here rather than on the night. The discipline is simple and repeatedly proven: the shorter the list of decisions taken under time pressure, the higher the probability the cutover completes without incident. Each preparation activity carries an owner and an exit condition, so readiness is demonstrated rather than asserted.

## 6.1 Move Groups & Sequencing

Move groups are sets of servers that must migrate together because they cannot function apart, and they are derived from observed dependency evidence rather than from application naming or organizational structure. Grouping by name is the most common source of a migration that completes technically and fails functionally, because two systems that share a database rarely share a naming convention. Each group records why it is grouped, what it depends on, and when it is planned. Non-production migrates ahead of production, beginning with the least complex group, so that the process is proven where failure is inexpensive.

| Move Group | Servers / Components | Why Grouped | Depends On | Planned Date |
| --- | --- | --- | --- | --- |
| Utility — primary | EAUTILDEV201; LSUTILPRD101; LXUTILPRD101; MSCOREOSPRD101; NETBACKUPPRD101; OIMTST101; OIMTST102; SECADMUTLPRD101 | Single application move group | G1 current-state validation 08/28/26 (BASELINE v2.1 Milestones UTIL-G1) | 03/18/27 (cutover — BASELINE v2.1) |

Table 6.1 — Move Groups & Sequencing

## 6.2 Migration Method per Component

The migration method for each component is recorded together with the rollback position that method actually supports, because the two are inseparable. Replication and failover, backup and restore, database migration services, file copy and rebuild each imply a different downtime profile and a different answer to the question of what happens if the cutover is aborted. Expected downtime is taken from the rehearsal rather than estimated. Where a method offers no rollback, that is stated plainly here rather than discovered during the window.

| Component | Method | Tool | Expected Downtime | Rollback Available? | Owner |
| --- | --- | --- | --- | --- | --- |
| Utility — all components | Azure Migrate | Azure Migrate | To be confirmed at rehearsal | Yes — source retained, powered off and bootable | To be provided by GEHA |

Table 6.2 — Migration Method per Component

## 6.3 Replication Build & Bandwidth

Replication is bandwidth-bound and is almost always the longest-running preparation activity, so it is planned and measured rather than assumed. The initial seed volume and its measured elapsed time are recorded, along with steady-state delta lag, throttling arrangements and who is alerted when replication fails. Cutover is not scheduled until delta lag is stable at or near zero, because a cutover that begins with outstanding lag begins with unquantified data loss. Where replication competes with production traffic for bandwidth, the sharing arrangement is agreed with the network team in advance.

| Replication Appliance / Service | Not yet provided — What performs replication, where it runs, and its sizing. To be supplied by GEHA (Appendix B). |
| --- | --- |
| Available Bandwidth | Not yet provided — Measured throughput available to replication, and whether it is shared with production traffic. To be supplied by GEHA (Appendix B). |
| Initial Seed Volume & Duration | 2823 GB observed across 8 host(s); this wave is outside the pre-seed window (Source: storage from Matilda Discovery Assessment, as-of 08-Aug-2026; dates computed by the wave engine) |
| Delta Replication Lag | Not yet provided — Observed steady-state lag. Cutover does not start until lag is at zero. To be supplied by GEHA (Appendix B). |
| Throttling / Scheduling | Not yet provided — Whether replication is throttled during business hours, and by whom. To be supplied by GEHA (Appendix B). |
| Monitoring & Failure Handling | Not yet provided — How replication failure is detected, and who is alerted. To be supplied by GEHA (Appendix B). |

Table 6.3 — Replication Build & Bandwidth

## 6.4 Migration Rehearsal

The rehearsal proves that the target boots, runs and is reachable, and it is executed in an isolated network so that it cannot affect the source under any circumstances. It is also the only legitimate source of the timings used in the cutover schedule; estimated durations are how outage windows are overrun. A minimum of two passes is planned — the first to find defects, the second to prove the corrections — and the last pass must be defect-free. Test resources are removed on completion, because retained ones incur cost and create ambiguity about which environment is authoritative on the night.

| Test Environment | Not yet provided — Isolated network used, and confirmation that it cannot reach production. To be supplied by GEHA (Appendix B). |
| --- | --- |
| Passes Planned | Not yet provided — Minimum two — the last must be defect-free. To be supplied by GEHA (Appendix B). |
| Validation Performed | Not yet provided — Boot, service start, application login, database connectivity, integration smoke tests, agent check-in. To be supplied by GEHA (Appendix B). |
| Timings Captured | Not yet provided — Elapsed time per step, carried into §7.3. To be supplied by GEHA (Appendix B). |
| Defects Raised & Cleared | Not yet provided — Reference to the defect log, with the count outstanding. To be supplied by GEHA (Appendix B). |
| Test Resources Cleaned Up | ☐ Yes ☐ No — To be provided by GEHA |
| Sign-Off | To be provided by GEHA |

Table 6.4 — Migration Rehearsal

## 6.5 Testing Strategy

The testing strategy defines what will be tested, by whom, and the conditions under which testing may start and must stop. Functional, data validation, integration, performance, security, backup and recovery testing each carry their own entry and exit criteria, expressed as conditions rather than as opinions. Performance exit criteria are set against the documented baseline recorded earlier, which converts an argument about whether the system feels slower into a measurement. Sign-off is by named individuals, because an untested assumption discovered after go-live is indistinguishable from a defect.

| Test Type | Scope | Owner | Entry Criteria | Exit Criteria |
| --- | --- | --- | --- | --- |
| Functional / UAT | Not yet provided — Core business workflows on the migrated system. To be supplied by GEHA (Appendix B). | To be provided by GEHA | To be provided by GEHA | Not yet provided — All P1 cases pass; no open Sev1/Sev2. To be supplied by GEHA (Appendix B). |
| Data Validation | Not yet provided — Record counts and integrity after migration. To be supplied by GEHA (Appendix B). | To be provided by GEHA | To be provided by GEHA | Not yet provided — Reconciliation within the §7.8 tolerance. To be supplied by GEHA (Appendix B). |
| Integration Testing | Not yet provided — Every interface in §4.7, both directions. To be supplied by GEHA (Appendix B). | To be provided by GEHA | Not yet provided — Endpoints reachable, credentials issued. To be supplied by GEHA (Appendix B). | To be provided by GEHA |
| Performance | Not yet provided — Response under peak load from §3.3. To be supplied by GEHA (Appendix B). | To be provided by GEHA | Not yet provided — Production-like sizing and data. To be supplied by GEHA (Appendix B). | Not yet provided — Response times and batch durations at or better than the §3.4 baseline. To be supplied by GEHA (Appendix B). |
| Security & Access | Not yet provided — RBAC, group mapping, network rules, privileged access. To be supplied by GEHA (Appendix B). | To be provided by GEHA | To be provided by GEHA | Not yet provided — Access matches design; no excess privilege. To be supplied by GEHA (Appendix B). |
| Backup & Restore | Not yet provided — Backup runs and a restore succeeds. To be supplied by GEHA (Appendix B). | To be provided by GEHA | To be provided by GEHA | Not yet provided — Restore proven, with evidence. To be supplied by GEHA (Appendix B). |
| Failover / DR | To be provided by GEHA | To be provided by GEHA | To be provided by GEHA | Not yet provided — Recovery within the stated RTO. To be supplied by GEHA (Appendix B). |

Table 6.5 — Testing Strategy

## 6.6 Change Freeze

The change freeze is the period during which both source and target stop changing so that what is tested is what is migrated. Patching and restarts are included in the freeze rather than exempted from it, because either can invalidate replication that has taken weeks to build. The freeze is enforced by a named individual through a stated mechanism rather than by request, and the authorizing change record is referenced here. The cutover date is checked against the program blackout calendar and the business calendar, and that check is recorded with the date it was performed.

| Source System Freeze Window | Program blackout windows: 1 Nov-14 Dec 2026 and 1 Nov-13 Dec 2027; production cutovers are barred in those windows under the SOW, and the Christmas close 22 Dec-2 Jan carries no CRs. (Source: SOW ZCON-18111, signed 30-Jul-2026) |
| --- | --- |
| Why Patching Is Included | Not yet provided — Patching and restarts during replication can invalidate it — confirm the exclusion with whoever owns patching. To be supplied by GEHA (Appendix B). |
| Target Configuration Freeze | Not yet provided — When target configuration stops changing ahead of cutover. To be supplied by GEHA (Appendix B). |
| Enforced By | To be provided by GEHA |
| Change Control Reference | Not yet provided — Change record authorizing the cutover. To be supplied by GEHA (Appendix B). |
| Blackout Window Check | SOW blackout clause — "vernance outcomes, and business constraints are confirmed. During blackout periods, production cutovers will not be scheduled unless specifically approved by G.E.H.A. Planning, design, build, testing, remediation, and non-production activities may continue. Waves Expectations 0 Application inventory va" (Source: SOW ZCON-18111, signed 30-Jul-2026) |

Table 6.6 — Change Freeze

## 6.7 Readiness Review

The readiness review is held before the go/no-go gate and confirms that every team with a part to play knows its role, holds tested access to the target, and has agreed what proves their step succeeded. It is emphatically not the first review of the plan; teams arriving unfamiliar with the runbook at this point is itself a finding. Access is tested rather than assumed, because credentials that have never been exercised fail at the least convenient moment. Rollback criteria are agreed here so that the decision to abort, if it comes, is a judgment against pre-agreed conditions rather than an argument at three in the morning.

| Review Date | To be provided by GEHA |
| --- | --- |
| Teams Represented | Not yet provided — Every team with a step in §7.3, each by a named attendee. To be supplied by GEHA (Appendix B). |
| Skills & Capability Confirmed | Each team’s experience with the target services, migration tooling, and cutover execution, with gaps identified. Where a gap exists, state the training or external support arranged and by when |
| Access Confirmed | Not yet provided — Each team has tested the access they need in the target — tested, not assumed. To be supplied by GEHA (Appendix B). |
| Verification Procedures Agreed | Not yet provided — Each team knows what proves their step succeeded. To be supplied by GEHA (Appendix B). |
| Rollback Criteria Agreed | Not yet provided — Each team knows what would trigger rollback and what their part in it is. To be supplied by GEHA (Appendix B). |
| Outstanding Actions | Not yet provided — Carried to §10.4 with owners and dates. To be supplied by GEHA (Appendix B). |

Table 6.7 — Readiness Review

## 6.8 Training, Communications & External Notification

The plan records what users will experience differently, when they will be told, and who supports them when the change lands. User-visible changes — a new address, a new client, altered performance — are identified from the configuration and access sections rather than assumed to be invisible. External parties are notified with the lead time their own change processes require, which is frequently measured in weeks and is outside GEHA's control. The service desk is briefed before go-live rather than after, so the first call is answered by someone who already knows what changed.

| User-Visible Change | Not yet provided — What users experience differently — new URL, new client, changed performance. From §5.13 and §4.3. To be supplied by GEHA (Appendix B). |
| --- | --- |
| Training Plan | Not yet provided — Audience, format and completion target. To be supplied by GEHA (Appendix B). |
| Communication Schedule | Not yet provided — Announcement, go-live notice, and where users go for help. To be supplied by GEHA (Appendix B). |
| External Party Notification | Not yet provided — Lead time required, owner, and what each party must change — tracked per party in §7.7. To be supplied by GEHA (Appendix B). |
| Support Desk Briefing | Not yet provided — When the service desk is briefed, and on what. To be supplied by GEHA (Appendix B). |

Table 6.8 — Training, Communications & External Notification

# 7. Cutover Runbook

## 7.1 Go / No-Go Gate

The go/no-go gate is the formal point at which cutover is authorized, and it is decided against documented evidence rather than confidence. It is scheduled with enough lead time that a no-go outcome can actually be acted upon, which means days rather than hours before the window. A single named individual owns the decision, the rule by which the decision is made is stated in advance, and the attendees whose absence would postpone it are named. Each criterion references the section that produces its evidence, so the gate is a review of facts already established rather than a fresh discussion.

| Gate Meeting Date & Time | To be provided by GEHA |
| --- | --- |
| Attendees Required | To be provided by GEHA |
| Decision Owner | Not yet provided — The single individual who says go or no-go. To be supplied by GEHA (Appendix B). |
| Decision Rule | SOW record — "rnance / design authority review, readiness validation, and go / no-go checks. The current high-level roadmap is shown below. Wave Est. Timing Classification Wave 0 Jun 15, 2026 - Jul 31, 2026 Mobilization and validation Wave 1 Aug 2026 - Dec 2026 Foundation and" (Source: SOW ZCON-18111, signed 30-Jul-2026) |
| Communication of Decision | Not yet provided — Who is told, by what channel, and by when. To be supplied by GEHA (Appendix B). |

Table 7.1a — Go / No-Go Gate

| Gate Criterion | Evidence Required | Owner | Status |
| --- | --- | --- | --- |
| Rehearsal complete and defect-free | To be provided by GEHA | To be provided by GEHA | ☐ R ☐ A ☐ G |
| Replication lag at zero and stable | To be provided by GEHA | To be provided by GEHA | ☐ R ☐ A ☐ G |
| UAT signed off | To be provided by GEHA | To be provided by GEHA | ☐ R ☐ A ☐ G |
| All integrations tested end to end | To be provided by GEHA | To be provided by GEHA | ☐ R ☐ A ☐ G |
| Identity, RBAC and group mapping verified | To be provided by GEHA | To be provided by GEHA | ☐ R ☐ A ☐ G |
| Backup policy applied and a restore proven | To be provided by GEHA | To be provided by GEHA | ☐ R ☐ A ☐ G |
| Monitoring and alerting live in the target | To be provided by GEHA | To be provided by GEHA | ☐ R ☐ A ☐ G |
| Readiness review held; actions closed | To be provided by GEHA | To be provided by GEHA | ☐ R ☐ A ☐ G |
| Change freeze in effect; change approved | To be provided by GEHA | To be provided by GEHA | ☐ R ☐ A ☐ G |
| Source retention and rollback position confirmed | To be provided by GEHA | To be provided by GEHA | ☐ R ☐ A ☐ G |
| External parties confirmed | To be provided by GEHA | To be provided by GEHA | ☐ R ☐ A ☐ G |
| Software vendor support position confirmed for the target configuration | To be provided by GEHA | To be provided by GEHA | ☐ R ☐ A ☐ G |
| Scheduled jobs re-pointed or retired; first-run owners named | To be provided by GEHA | To be provided by GEHA | ☐ R ☐ A ☐ G |
| Support and hypercare staffed | To be provided by GEHA | To be provided by GEHA | ☐ R ☐ A ☐ G |

Table 7.1b — Gate Criteria

## 7.2 Cutover Team & Bridge

The cutover team is named here individually, with a designated backup and a reachable telephone number for every role, because a role covered by a team name is a role nobody is holding at two in the morning. Availability is stated as hours rather than as intent. The bridge is live for the whole window, the status update cadence is fixed in advance, and the escalation path states who is woken and in what order. This section exists so that the window is worked by a team that knows its shape before the first step begins.

| Role | Name | Backup | Phone | Available From / To |
| --- | --- | --- | --- | --- |
| Cutover Lead | To be provided by GEHA | To be provided by GEHA | To be provided by GEHA | To be provided by GEHA |
| Migration / Replication | To be provided by GEHA | To be provided by GEHA | To be provided by GEHA | To be provided by GEHA |
| Database | To be provided by GEHA | To be provided by GEHA | To be provided by GEHA | To be provided by GEHA |
| Identity / Access | To be provided by GEHA | To be provided by GEHA | To be provided by GEHA | To be provided by GEHA |
| Network / DNS / Firewall | To be provided by GEHA | To be provided by GEHA | To be provided by GEHA | To be provided by GEHA |
| Integrations | To be provided by GEHA | To be provided by GEHA | To be provided by GEHA | To be provided by GEHA |
| Application Owner (acceptance) | To be provided by GEHA | To be provided by GEHA | To be provided by GEHA | To be provided by GEHA |
| Rollback Authority | To be provided by GEHA | To be provided by GEHA | To be provided by GEHA | To be provided by GEHA |

Table 7.2a — Cutover Team & Bridge

| Conference Bridge | Not yet provided — Dial-in and link — live for the whole window. To be supplied by GEHA (Appendix B). |
| --- | --- |
| Status Update Cadence |  |
| Escalation Path | Not yet provided — Who is woken, in what order, at what severity. To be supplied by GEHA (Appendix B). |

Table 7.2b — Bridge & Communications

## 7.3 Cutover Schedule

The cutover schedule is the executable document for the window, written to be used by staff who were not present at the design sessions. Absolute clock times with a stated time zone are used rather than relative durations, and every duration is taken from the rehearsal rather than estimated. Each step carries a named owner, a verification that confirms completion before the next step begins, and the condition that would trigger rollback. Cumulative elapsed time is shown so that the total is visible before the window is committed; if the total exceeds the agreed outage, the plan is not ready.

| # | Phase | Time (TZ) | Elapsed | Action | Owner (Named) | Verification | Rollback Trigger |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Pre-window | To be provided by GEHA | — | To be provided by GEHA | To be provided by GEHA | To be provided by GEHA | — |
| 2 | Pre-window | To be provided by GEHA | — | Not yet provided — Confirm replication lag at zero; confirm freeze in effect. To be supplied by GEHA (Appendix B). | To be provided by GEHA | Not yet provided — Lag reading and freeze record. To be supplied by GEHA (Appendix B). | — |
| 3 | Pre-window | To be provided by GEHA | — | Not yet provided — Pre-stage target configuration changes that do not require the source to be down. To be supplied by GEHA (Appendix B). | To be provided by GEHA | Not yet provided — Change list from §5.13 complete. To be supplied by GEHA (Appendix B). | — |
| 4 | Quiesce | To be provided by GEHA | — | Not yet provided — Stop application services and block user access on the source. To be supplied by GEHA (Appendix B). | To be provided by GEHA | Not yet provided — Sessions terminated; logins blocked. To be supplied by GEHA (Appendix B). | — |
| 5 | Quiesce | To be provided by GEHA | — | Not yet provided — Stop writes and quiesce the database. To be supplied by GEHA (Appendix B). | To be provided by GEHA | Not yet provided — No active sessions; last write timestamp recorded. To be supplied by GEHA (Appendix B). | — |
| 6 | Quiesce | To be provided by GEHA | — | Not yet provided — Final synchronization — confirm zero lag. To be supplied by GEHA (Appendix B). | To be provided by GEHA | Not yet provided — Sync timestamp later than the last source write. To be supplied by GEHA (Appendix B). | To be provided by GEHA |
| 7 | Migrate | To be provided by GEHA | — | Not yet provided — Perform the migration or failover. To be supplied by GEHA (Appendix B). | To be provided by GEHA | Not yet provided — Target resources created; no errors reported. To be supplied by GEHA (Appendix B). | To be provided by GEHA |
| 8 | Migrate | To be provided by GEHA | — | Not yet provided — Boot target and verify OS, disks and services. To be supplied by GEHA (Appendix B). | To be provided by GEHA | Not yet provided — All disks present; services started; event log clean. To be supplied by GEHA (Appendix B). | To be provided by GEHA |
| 9 | Migrate | To be provided by GEHA | — | Not yet provided — Apply post-migration configuration — IP, domain join, agents, extensions, licensing. To be supplied by GEHA (Appendix B). | To be provided by GEHA | Not yet provided — Agents checked in; domain join confirmed. To be supplied by GEHA (Appendix B). | — |
| 10 | Migrate | To be provided by GEHA | — | Not yet provided — Apply application configuration changes from §5.13. To be supplied by GEHA (Appendix B). | To be provided by GEHA | Not yet provided — Each change verified in place. To be supplied by GEHA (Appendix B). | — |
| 11 | Validate | To be provided by GEHA | — | Not yet provided — Data validation and reconciliation — see §7.8. To be supplied by GEHA (Appendix B). | To be provided by GEHA | Not yet provided — Control totals within tolerance. To be supplied by GEHA (Appendix B). | To be provided by GEHA |
| 12 | Validate | To be provided by GEHA | — | To be provided by GEHA | To be provided by GEHA | Not yet provided — Sample logins across each role succeed. To be supplied by GEHA (Appendix B). | To be provided by GEHA |
| 13 | Validate | To be provided by GEHA | — | Not yet provided — Re-point integrations — see §7.6. To be supplied by GEHA (Appendix B). | To be provided by GEHA | Not yet provided — Each interface passes its smoke test. To be supplied by GEHA (Appendix B). | To be provided by GEHA |
| 14 | Validate | To be provided by GEHA | — | To be provided by GEHA | To be provided by GEHA | Not yet provided — Resolution confirmed inside and outside the network. To be supplied by GEHA (Appendix B). | — |
| 15 | Validate | To be provided by GEHA | — | Not yet provided — Confirm monitoring, alerting and backup are live on the target. To be supplied by GEHA (Appendix B). | To be provided by GEHA | Not yet provided — Alerts firing to the right action group; first backup succeeded. To be supplied by GEHA (Appendix B). | — |
| 16 | Validate | To be provided by GEHA | — | To be provided by GEHA | To be provided by GEHA | To be provided by GEHA | To be provided by GEHA |
| 17 | Release | To be provided by GEHA | — | Not yet provided — Go / no-go on release to users. To be supplied by GEHA (Appendix B). | To be provided by GEHA | To be provided by GEHA | To be provided by GEHA |
| 18 | Release | To be provided by GEHA | — | Not yet provided — Release to users; go-live communication. To be supplied by GEHA (Appendix B). | To be provided by GEHA | Not yet provided — Notice sent; support desk briefed. To be supplied by GEHA (Appendix B). | — |

Table 7.3 — Cutover Schedule

## 7.4 Data Cut-Off

The data cut-off is the moment the source system stops accepting work, and it is stated as an exact time with a time zone rather than as a rough intention. Transactions already in flight at that moment need a defined treatment, as does business activity that occurs while the system is unavailable and must be re-entered afterwards. Batch files and feeds that arrive during the window are held somewhere deliberate rather than lost. Getting this wrong produces data that exists in neither system, which is the hardest category of migration defect to detect and to remedy.

| Cut-Off Timestamp | Cutover date of record: 03/18/27, Thursday (BASELINE v2.1 Plan Control; supersedes engine 02/14/28 and prior plan 01/08/28 — §11 already carries the rebaselined dates). Exact clock time to be set at the readiness review. (Source: wave engine; Wave Plan Tracker rev-3)— after which no transaction enters the source |
| --- | --- |
| In-Flight Transaction Handling | Not yet provided — What happens to work started before cut-off and not completed. To be supplied by GEHA (Appendix B). |
| Manual Capture During the Window | Not yet provided — How business activity is recorded while the system is unavailable, and who re-enters it. To be supplied by GEHA (Appendix B). |
| Late-Arriving Data | Not yet provided — Batch files or feeds that land during the window, and where they are held. To be supplied by GEHA (Appendix B). |

Table 7.4 — Data Cut-Off

## 7.5 Access Verification

Access is verified in the target account by account and group by group, rather than inferred from the fact that the design was implemented correctly. At least one member of each source group signs in, every service account authenticates and its dependent job is confirmed running, and every programmatic access path is shown to be replaced, retained or revoked as decided. Users who held access outside any group are handled explicitly, since they are invisible to group-based verification. Break-glass access is tested before the window opens, because the moment it is needed is the worst moment to discover it does not work.

| Group-to-Role Mapping Verified | Not yet provided — Tested per group from §4.5.4 — at least one member of each — and signed. To be supplied by GEHA (Appendix B). |
| --- | --- |
| Azure RBAC Assignments Verified | Not yet provided — Platform access matches §5.7; no excess assignment. To be supplied by GEHA (Appendix B). |
| Service Accounts & Managed Identities | Not yet provided — Each entry from §4.5.5 authenticating successfully in the target, with its dependent job confirmed running. To be supplied by GEHA (Appendix B). |
| Programmatic Access Paths | Not yet provided — Each row of §4.5.3 replaced, retained or revoked, with the decision recorded. To be supplied by GEHA (Appendix B). |
| Direct-Assignment Users Handled | Not yet provided — Users who held access outside any group, carried across or deliberately dropped. To be supplied by GEHA (Appendix B). |
| Break-Glass Verified | Not yet provided — Emergency access tested before the window opens. To be supplied by GEHA (Appendix B). |

Table 7.5 — Access Verification

## 7.6 Integration Re-Point

Each integration is re-pointed individually by the team that owns it, and this tracker records the change type, the named person executing it, whether it can be pre-staged, and the notice their process requires. Integrations are the most common cause of a cutover that appears successful and then degrades over the following hours as batch cycles begin to run. Implicit dependencies receive the same treatment as formal interfaces: scheduled jobs on other systems, license servers, mail relays and hardcoded addresses. Every entry carries evidence of a smoke test rather than an assertion that the change was made.

| Integration | Change Type | Executed By (Named) | Pre-Stageable | Lead Time | Window Slot | Test Evidence |
| --- | --- | --- | --- | --- | --- | --- |
| To be provided by GEHA | Not yet provided — Endpoint / credential / certificate / firewall rule / code change. To be supplied by GEHA (Appendix B). | To be provided by GEHA | ☐ Yes ☐ No | — | Not yet provided — Step # in §7.3, or Pre-staged. To be supplied by GEHA (Appendix B). | To be provided by GEHA |

Table 7.6 — Integration Re-Point

## 7.7 External Party Cutover Tracker

External parties operate on their own change calendars and cannot be compressed to suit the program, so each is tracked here individually from notification through confirmation to tested. A named contact is recorded for every party, not a generic mailbox, and the lead time their process requires is captured explicitly. The fallback position is stated for each party in case they are not ready on the night, since discovering that during the window leaves no room to manoeuvre. Partner readiness is a go/no-go criterion rather than a matter to be resolved during hypercare.

| Partner | Contact | Notified | Change Required Their Side | Confirmed | Tested | Fallback |
| --- | --- | --- | --- | --- | --- | --- |
| To be provided by GEHA | To be provided by GEHA | To be provided by GEHA | Not yet provided — Endpoint, credential, allowlist, tunnel. To be supplied by GEHA (Appendix B). | To be provided by GEHA | To be provided by GEHA | Not yet provided — What happens if they are not ready. To be supplied by GEHA (Appendix B). |

Table 7.7 — External Party Cutover Tracker

## 7.8 Reconciliation & Acceptance

Reconciliation compares the target against the source using control totals agreed before the window opens, and tolerance is expressed as a number rather than as a judgment. For financial and regulated objects that number is zero unless the application owner has accepted otherwise in writing. Record counts, financial totals, file counts and attachment volumes are each compared, and failed records go to a named queue with a named owner and a date by which they will be worked. Acceptance is given by the application owner at a recorded time, which is what converts a technical completion into a business one.

| Control Totals | Record counts and financial or volumetric totals by object, source versus target — |
| --- | --- |
| Tolerance | Not yet provided — The numeric threshold — state it. Zero for financial and regulated objects unless the Application Owner has accepted oth. To be supplied by GEHA (Appendix B). |
| File & Attachment Counts | — |
| Error Queue Handling | Not yet provided — Where failed records go, who works them, and by when. To be supplied by GEHA (Appendix B). |
| Acceptance Sign-Off | Not yet provided — Application Owner name, and the time acceptance was given. To be supplied by GEHA (Appendix B). |

Table 7.8 — Reconciliation & Acceptance

## 7.9 Rollback

Rollback for a replication-based migration to Azure is not a failback; replication runs in one direction only, so rollback means returning to the source system as it stood at the data cut-off. Work performed in the target after cutover is not recoverable to the source unless it is manually re-entered, and that treatment is decided in advance rather than improvised. The plan therefore depends on the source remaining intact, powered off and bootable for a stated retention period, with its storage and networking untouched. The point of no return is identified by step number, the decision deadline is set by clock time, and the duration of the rollback itself is measured during rehearsal rather than estimated.

| Rollback Trigger Criteria | Not yet provided — Objective conditions, tied to the verification failures in §7.3. To be supplied by GEHA (Appendix B). |
| --- | --- |
| Rollback Decision Deadline | Not yet provided — The clock time by which rollback must be invoked to complete before the business day. To be supplied by GEHA (Appendix B). |
| Rollback Steps | Not yet provided — Power the source back on, revert DNS and endpoints, restore integrations, re-enable access, notify partners and users. To be supplied by GEHA (Appendix B). |
| Rollback Duration | Not yet provided — Measured during the §6.4 test, not estimated. To be supplied by GEHA (Appendix B). |
| Point of No Return | Not yet provided — The specific step number in §7.3 after which rollback is no longer viable, and why. To be supplied by GEHA (Appendix B). |
| Source Preserved | Source remains intact, powered off and bootable through hypercare; migration method Azure Migrate is unidirectional, so rollback means reverting to the source as at data cut-off. (Source: wave engine; program migration method)Yes ☐ No — Not yet provided — the source must remain intact, powered off and bootable, with its storage and networking unchanged, for the retention pe. To be supplied by GEHA (Appendix B). |
| Data Entered After Cutover | Not yet provided — The treatment of transactions entered in the target if rollback is invoked — re-keyed into the source or lost. Determine. To be supplied by GEHA (Appendix B). |
| Rehearsed | ☐ Yes ☐ No — To be provided by GEHA |
| Rollback Authority | To be provided by GEHA |

Table 7.9 — Rollback

# 8. Post-Cutover & Service Handover

The post-cutover period is treated as a defined stage with entry and exit conditions rather than as an indefinite settling-in. Hypercare, verification of operational controls in production, decommissioning of the source and the review that feeds the next migration each have their own criteria. Every stage exits on documented evidence rather than on elapsed time, because a quiet fortnight is not the same thing as a stable service. Handled properly, this section is where a migration becomes an operational reality rather than a completed project.

## 8.1 Hypercare

Hypercare is the period of heightened support immediately after go-live, and it is defined here with a named roster, coverage hours and an escalation path rather than an assumption that the migration team remains available. Its exit criteria are objective — a stated number of consecutive days without severity one or two incidents, with backup and monitoring proven in steady state — so that the end of hypercare is a demonstrated condition rather than a date in a plan. The steady-state support owner is named, and the handover to them is explicit. Issues raised during hypercare are triaged through a defined route so that nothing depends on knowing which individual to telephone.

| Hypercare Period | SOW record — ", communication plan, service desk readiness checklist, and hypercare approach. 1 Software Development Units are registered with Special Economic Zones or Software Technology Parks. G.E.H.A. Data Center Transition and Cloud Migration SOW 3 Scope of Services • Program Management: Establish and manage the integrated project plan, assumptions log," (Source: SOW ZCON-18111, signed 30-Jul-2026) |
| --- | --- |
| Hypercare Roster | To be provided by GEHA |
| Steady-State Support Owner | To be provided by GEHA |
| Issue Triage Process | Not yet provided — How issues are logged, triaged and routed. To be supplied by GEHA (Appendix B). |
| Escalation Path | Not yet provided — Sev1 and Sev2 contacts, with response expectations. To be supplied by GEHA (Appendix B). |
| Exit Criteria | Objective — |

Table 8.1 — Hypercare

X

| Monitoring & Alerting Proven | Not yet provided — An alert has fired and reached the right person — test it rather than assume it. To be supplied by GEHA (Appendix B). |
| --- | --- |
| Backup Running & Restore Proven | Not yet provided — First backups succeeded, and a restore has been performed from the target. To be supplied by GEHA (Appendix B). |
| Patching Enrolled | Not yet provided — The workload appears in the patching schedule, with the first cycle date. To be supplied by GEHA (Appendix B). |
| Log Export to SIEM Confirmed | Not yet provided — Logs arriving, with retention set on both sides. To be supplied by GEHA (Appendix B). |
| Cost Baseline Captured | Not yet provided — First full period of actual cost, against the §5.11 estimate, with variance explained. To be supplied by GEHA (Appendix B). |
| Right-Sizing Review Scheduled | To be provided by GEHA |
| Scheduled Jobs Confirmed Running | Not yet provided — Every job in §5.15 has completed a successful scheduled execution in the target, with the date of each first run recorde. To be supplied by GEHA (Appendix B). |
| Support Runbook Published | Not yet provided — Where the steady-state operational procedure lives. To be supplied by GEHA (Appendix B). |
| Known Issues Carried Into Service | Not yet provided — Accepted gaps and workarounds that support must be briefed on. To be supplied by GEHA (Appendix B). |
| Configuration Baseline Recorded | Not yet provided — Deployed state captured in code or exported, so drift can be detected. To be supplied by GEHA (Appendix B). |

Table 8.2 — Operational Readiness

## 8.3 Decommission

Decommissioning is a sequence of verifications rather than a single act of deletion, and the source is not removed until the rollback retention period has expired and no remaining dependency on it can be found. Absence of active users, jobs and integrations is confirmed over a stated period, retention and legal-hold obligations are confirmed satisfied in the target, and a final archive is taken and restore-tested. Access, service accounts, security groups, load balancer objects, tunnels, firewall rules, DNS records and certificates are each retired in turn, with shared objects identified and deliberately left in place. Licences are reclaimed and assets removed from the configuration management database, which is what converts a migration into a realized saving.

| Source Retention Period | Not yet provided — How long the source stays intact, powered off and bootable after go-live, and who authorises its release. Rollback is un. To be supplied by GEHA (Appendix B). |
| --- | --- |
| Retention Expiry Date | To be provided by GEHA |
| Released By | To be provided by GEHA |

Table 8.3a — Source Retention

| Step | Action | Owner | Verification |
| --- | --- | --- | --- |
| 1 | Not yet provided — Confirm no active users, jobs or integrations on the source for N days. To be supplied by GEHA (Appendix B). | To be provided by GEHA | Not yet provided — Access and traffic logs reviewed. To be supplied by GEHA (Appendix B). |
| 2 | Not yet provided — Confirm retention and legal-hold obligations are met in the target. To be supplied by GEHA (Appendix B). | To be provided by GEHA | Not yet provided — Sign-off from records or compliance owner. To be supplied by GEHA (Appendix B). |
| 3 | Not yet provided — Confirm the rollback retention period has expired and been released. To be supplied by GEHA (Appendix B). | To be provided by GEHA | To be provided by GEHA |
| 4 | Not yet provided — Final archive of source data taken and restore-tested. To be supplied by GEHA (Appendix B). | To be provided by GEHA | Not yet provided — Archive location, retention, and a successful test restore. To be supplied by GEHA (Appendix B). |
| 5 | Not yet provided — Revoke access; disable service accounts and credentials marked for retirement in §4.5. To be supplied by GEHA (Appendix B). | To be provided by GEHA | Not yet provided — Disabled for N days with no failure raised, then deleted. To be supplied by GEHA (Appendix B). |
| 6 | Not yet provided — Retire application-scoped security groups. To be supplied by GEHA (Appendix B). | To be provided by GEHA | Not yet provided — Only groups marked as unshared in §4.5.4; shared groups left in place and recorded. To be supplied by GEHA (Appendix B). |
| 7 | Not yet provided — Retire the source virtual server, pool, monitors and certificates. To be supplied by GEHA (Appendix B). | To be provided by GEHA | Not yet provided — Only objects marked as unshared in §4.6.2. To be supplied by GEHA (Appendix B). |
| 8 | Not yet provided — Retire tunnels marked for retirement; remove source subnets from encryption domains that remain. To be supplied by GEHA (Appendix B). | To be provided by GEHA | Not yet provided — Far end reports no loss; shared tunnels still carrying other traffic. To be supplied by GEHA (Appendix B). |
| 9 | Not yet provided — Remove firewall rules, DNS records and certificates. To be supplied by GEHA (Appendix B). | To be provided by GEHA | Not yet provided — §4.6 and §4.8 items closed out. To be supplied by GEHA (Appendix B). |
| 10 | Not yet provided — Decommission source infrastructure and reclaim licenses. To be supplied by GEHA (Appendix B). | To be provided by GEHA | Not yet provided — Assets removed from CMDB; licenses returned or reallocated. To be supplied by GEHA (Appendix B). |

Table 8.3b — Decommission Steps

## 8.4 Post-Migration Review

What worked and what did not is recorded here while the detail is still recoverable, so that the next application in the program benefits rather than repeats. Root causes are recorded rather than symptoms, and steps whose actual duration differed materially from plan are corrected for future playbooks. Changes to the rollback procedure are captured whether or not rollback was invoked, since a plan that was never exercised is still a plan that can be improved. A review that produces no change to the next playbook or to the program process has not been completed.

| What Worked | Not yet provided — Practices to repeat, stated specifically enough to be reused. To be supplied by GEHA (Appendix B). |
| --- | --- |
| What Did Not | Not yet provided — Steps that failed, ran long, or were discovered late — with the root cause, not the symptom. To be supplied by GEHA (Appendix B). |
| Rollback Procedure Corrections | Not yet provided — Changes to the §7.9 rollback steps, triggers, or timings arising from this migration, whether or not rollback was invoke. To be supplied by GEHA (Appendix B). |
| Schedule Corrections | Not yet provided — Steps in §7.3 whose actual duration differed materially from plan, with the corrected figure for future playbooks. To be supplied by GEHA (Appendix B). |
| Template or Process Changes | Not yet provided — Changes required to this playbook template or the program process, with the owner who will make them. To be supplied by GEHA (Appendix B). |
| Reviewed By & Date | To be provided by GEHA |

Table 8.4 — Post-Migration Review

# 9. Roles & Responsibilities

Responsibility across the migration lifecycle is assigned here using the RACI model, with exactly one accountable owner for each task. The distinction between responsible and accountable matters most at the two points where migrations stall: the go/no-go decision and the rollback decision. Consulted and informed parties are recorded so that teams learn of changes affecting them before rather than after the event. Where this matrix and the ownership register disagree, the ownership register governs and the discrepancy is corrected here.

| Task | App Owner | Migration Team | Platform / Cloud | Security | End Users | Admin / Support Manager Dale Gibson |
| --- | --- | --- | --- | --- | --- | --- |
| Landing zone placement | I | C | A/R | C | I | I |
| Target design | C | A/R | C | C | I | C |
| Sizing & cost model | C | R | A | I | I | C |
| Replication build | I | A/R | C | I | I | I |
| Identity & RBAC | C | R | C | A | I | C |
| Migration rehearsal | C | A/R | C | I | I | C |
| Integration re-point | I | R | C | C | I | A |
| Go / no-go decision | A | R | C | C | I | C |
| Cutover execution | A | R | C | I | I | C |
| Reconciliation & acceptance | A | R | I | I | C | C |
| Rollback decision | A | R | C | I | I | C |
| Operational readiness | C | R | A | C | I | C |
| Decommission | A | R | C | C | I | C |

Table 9 — Roles & Responsibilities

# 10. Risks, Assumptions, Dependencies & Open Items

Four distinct records are maintained here, and keeping them distinct is what makes them useful. A risk is an event that may occur; an assumption is a reliance not yet verified; a dependency is a requirement controlled by someone outside this migration; and an open item is a question with an owner and a due date. Collapsing them into a single list, which is the usual habit, obscures the fact that they need entirely different treatment. Each record is maintained live through execution rather than completed once at authoring and left to age.

## 10.1 Risks

The risk register records potential events only. An event that has already occurred is an issue and is managed as one, and a reliance not yet verified is an assumption and belongs in the register that follows; keeping the boundary sharp is what stops the register becoming a list of everything anyone is uneasy about. Each risk carries a likelihood, an impact, a mitigation expressed as an action rather than an intention, and a named owner. Risks are reviewed at each program checkpoint rather than at authoring time alone.

| Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| Engine flag "achievable 2028-02-14 vs plan cutover 2028-01-08 (+37d late)" — superseded by BASELINE v2.1 plan of record 03/18/27; withdrawn 26-Aug-2026. Live risk: NETBACKUPPRD101 (RHEL 9 + docker) carries a Matilda container-replatform recommendation against the Rehost ruling — rule before design sign-off (W3-UTIL-D1) | — | — | Rule the NETBACKUPPRD101 container workload at the Wave 3 design gate; track on the program wave board | John Dean (Director, GEHA Application Owners row 39 — Owner cell vacant) |

Table 10.1 — Risks

## 10.2 Assumptions

Every assumption carries an owner and a date by which it must be confirmed or converted into a risk, because an assumption that is never tested becomes a defect at cutover. What is being taken as true is stated plainly alongside what breaks if it proves false, which is what allows the assumption to be prioritized rather than merely listed. Assumptions confirmed by evidence are marked as such with their source, and those that fail are escalated rather than quietly amended. This register is reviewed at the readiness review and again at the go/no-go gate.

| Assumption | Why It Matters | Confirm By | Owner | Status |
| --- | --- | --- | --- | --- |
| Ruled effort size S = 6 weeks; 4 parallel migration tracks | Drives the cutover date and wave capacity | To be confirmed by GEHA | GEHA PMO | Open |
| Wave window 2026-08-01 onward per the program wave plan | Cutover must fall inside the wave window | Confirmed in the Wave Plan Tracker | CitiusTech | Confirmed |

Table 10.2 — Assumptions

## 10.3 Dependencies

Dependencies are requirements controlled outside this migration and therefore outside the migration team's ability to accelerate. Subscription provisioning, quota increases, circuit changes, policy exemptions, desktop image cadence and the readiness of other waves are typical, and each runs to a schedule owned by someone else. Every entry names an owner, the date by which it is needed and its current status, so that a slipping dependency is visible while there is still time to act. Dependencies at risk are escalated to the program rather than absorbed silently into the application's own float.

| Dependency | Type | Owner | Needed By | Status |
| --- | --- | --- | --- | --- |
| G1 — current state validated, playbook sections 3-4 complete (UTIL-G1, BASELINE v2.1 Milestones) | Platform | CitiusTech / GEHA | 2026-08-28 — IMMINENT (2 days from 26-Aug-2026) | On track |
| Azure landing zone and target subscription confirmed | Platform | GEHA cloud platform team | To be agreed | At risk |

Table 10.3 — Dependencies

## 10.4 Open Items

Every unresolved question and unassigned ownership raised anywhere in this playbook is collected here, so that nothing depends on a reader noticing a gap buried in a distant section. Each item carries an owner, a due date and a status, and items are closed with the answer recorded rather than simply removed. This register is the practical agenda for the recurring working session with GEHA. An item still open at the go/no-go gate is a decision for the gate rather than an administrative loose end.

| Item | Raised | Owner | Due | Status |
| --- | --- | --- | --- | --- |
| Appendix B item 01 — Azure Migrate project access / first discovery export | 13-Aug-2026 | GEHA (request not yet sent) | 09/05/26 (re-dated; original elapsed) | Open — OVERDUE at 26-Aug-2026 review |
| Appendix B item 02 — Formal G-1 gate completion date | 13-Aug-2026 | GEHA (request not yet sent) | 09/05/26 (re-dated; original elapsed) | Open — OVERDUE at 26-Aug-2026 review |
| Appendix B item 06 — Owner reassignments (5 departed) + OnBase director ruling | 13-Aug-2026 | GEHA (request not yet sent) | 09/01/26 | Open |
| Appendix B item 10 — Capacity parameters: tracks, freeze calendar, LZ readiness | 13-Aug-2026 | GEHA (request not yet sent) | 09/05/26 (re-dated; original 08/31/26 imminent) | Open |
| Appendix B item 12 — Backup policy export + per-app protection groups (Cohesity) | 13-Aug-2026 | GEHA (request not yet sent) | 09/30/26 | Open |
| Appendix B item 14 — Current DNS zone + firewall rule exports (refresh) | 13-Aug-2026 | GEHA (request not yet sent) | 09/30/26 | Open |
| Engine flag: achievable 2028-02-14 vs plan cutover 2028-01-08 — superseded by BASELINE v2.1 (03/18/27); withdrawn 26-Aug-2026 | 13-Aug-2026 | CitiusTech migration lead | — | Closed |

Table 10.4 — Open Items

# 11. Timeline & Milestones

The milestone dates this playbook commits to are recorded here, each traceable to the section that produces its supporting evidence. Dates are stated rather than implied, and the contract cliff is shown as a hard date so that available float is visible at a glance rather than calculated by the reader. Where a milestone has both an achievable date and a planned date, both are shown and the difference is left visible rather than reconciled away. This table is the schedule of record for the application and is reconciled with the program wave plan at every checkpoint.

| Milestone | Target Date | Status |
| --- | --- | --- |
| Landing zone and subscription confirmed | — | Not started |
| Target design signed off | 02/25/27 — design accepted (BASELINE v2.1) | Not started |
| G1 — current state validated (UTIL-G1, BASELINE v2.1) | 08/28/26 — imminent (2 days from 26-Aug-2026) | Not started |
| Build start (engine) | 02/25/27 — build follows design acceptance (BASELINE v2.1) | Not started |
| GEHA plan — design start | 02/11/27 (BASELINE v2.1) | Not started |
| GEHA plan — build start | 02/25/27 (BASELINE v2.1) | Not started |
| GEHA plan — test start | Before the playbook freeze (03/12/27) — BASELINE v2.1 | Not started |
| Rehearsal pass 2 complete and defect-free | — | Not started |
| UAT sign-off | — | Not started |
| Readiness review held | 03/15/27 — playbook approval (BASELINE v2.1) | Not started |
| Go / no-go gate | 03/17/27 — CAB Wednesday (BASELINE v2.1) | Not started |
| Production cutover (engine-achievable) | 03/18/27, Thursday (BASELINE v2.1) | Not started |
| GEHA plan — cutover | 03/18/27 (BASELINE v2.1; supersedes 01/08/28) | Not started |
| Hypercare ends | 04/06/27 (BASELINE v2.1) | Not started |
| Source retention released | — | Not started |
| Source decommissioned | — | Not started |

Table 11 — Timeline & Milestones

## 11.1 Effort & Duration Record

Planned and actual effort are recorded side by side, together with elapsed duration, so that later waves are planned from observed velocity rather than from estimate. Authoring, discovery, build, testing, cutover and hypercare are measured separately, because they scale differently and the ratio between them is what makes an estimate transferable. Variance is recorded with its cause rather than as a number alone. Reporting these figures to the program is what allows the datacenter exit date to be planned against evidence instead of optimism.

| Measure | Planned | Actual | Variance & Cause |
| --- | --- | --- | --- |
| Playbook authoring effort (person-days) | — | — | — |
| Assessment and discovery effort (person-days) | — | — | — |
| Build and configuration effort (person-days) | — | — | — |
| Testing and rehearsal effort (person-days) | — | — | — |
| Cutover window (elapsed hours) | — | — | — |
| Hypercare (elapsed days) | — | — | — |
| Total elapsed time, kickoff to decommission (days) | — | — | — |

Table 11.1a — Effort & Duration Record

| Complexity Classification | Matilda migration complexity: Low; priority Low (Source: Matilda Discovery Assessment Summary (Application Assessment Summary), as-of 08-Aug-2026)Low ☐ Medium ☐ High — Not yet provided — the classification used to plan this playbook; state whether the actuals support it. To be supplied by GEHA (Appendix B). |
| --- | --- |
| Reported to Program | ☐ Yes ☐ No — To be provided by GEHA |

Table 11.1b — Effort & Duration Record

# 12. Sign-Off

Approval to execute is recorded here, and each signatory is a named individual accountable for the sections relevant to their role rather than a representative of a team. Signing confirms that the target design, the cutover plan and the rollback position documented in this playbook are approved for execution as written. Signatures are obtained before the go/no-go gate rather than retrospectively. A playbook signed on this basis is the authority under which the cutover proceeds.

By signing below, stakeholders confirm that the target design, cutover plan and rollback position documented in this playbook are approved for execution.

| Name | Role | Date |
| --- | --- | --- |
| To be provided by GEHA | Application Owner |  |
| To be provided by GEHA | Migration / Technical Lead |  |
| George Galindo — Cloud Architect, CitiusTech | Platform / Cloud Lead |  |
| To be provided by GEHA | Security |  |
| Christy Ammel (DBA / Production Control — program record) | DBA / Production Control |  |
| To be provided by GEHA | Network |  |

Table 12 — Sign-Off

CONFIDENTIAL — Prepared by Citius Healthcare Consulting. This document contains confidential and proprietary information and is intended solely for the named recipient. It may not be copied, disclosed or distributed, in whole or in part, without the prior written consent of Citius Healthcare Consulting.

# Appendix A — Program Decision References

This playbook does not restate program decisions. Each reference below points to the entry in the CitiusTech Decision & Evidence Register, the append-only historical record in which the decision, its evidence class, its source and the checkpoint it was made under are held. The register is available to GEHA on request.

Ref. REG-001 — Palo Alto Firewall. Recorded 2026-08-08; evidence class: Attested.

Ref. REG-017 — LiteSpeed scope confirmed; Azure Backup withdrawn. Recorded 2026-08-11; evidence class: Confirmed (GEHA-verbal).

Ref. REG-030 — Comprehensive review: display defects found and fixed. Recorded 2026-08-11; evidence class: Derived — audit.

# Appendix B — Information Requested from GEHA

Fields shown in this playbook as “not yet provided” correspond to the items below. Each is a specific request to GEHA with the date by which it is needed to keep this application on its planned wave. Items marked blocking prevent the affected section from being completed at all.

Source-exhaustion pass, 26-Aug-2026: every field marked “Not yet provided” or “To be supplied by GEHA” was re-tested against the full evidence pack — searched Server_VM_Inventory (LS/LX), Matilda Discovery Assessment Summary (7 visible tabs, as-of 08-Aug-2026), GEHA_SQLServers_DBDetails_Inventory (visible tabs), DBA_Migration_Artifacts (DEV/TEST/PRE-PROD/PROD), Discovery Report Inventory v1.0 (visible tabs), BIA_Applications_20251113 and BIA_Capability (Application BIA), Applications Sessions 1-3 responses (visible tabs), DHCP_DNS_list, Policy_list, Key_Vault_Certs, Subscription_Management_Groups and vmware_hosts_DRS. Values found were written into the owning sections with citations; the fields still open after that pass are confirmed not on file in those sources and are carried, re-dated, in the program information request register (fragment W3, refs W3-UTIL-n). Operational and runbook fields (§6–§9, §12) are completed at design and readiness, not from discovery evidence, and are excluded from the absence claims.

Item 01 — Azure Migrate project access / first discovery export  ·  Category: Tool access  ·  Required by: 2026-09-05 (re-dated 26-Aug-2026; was 2026-08-25, elapsed)  ·  BLOCKING

Why it is needed: Corroborates attested 26-Jul deployment; starts IFD reconciliation; gates G-1 close

Item 02 — Formal G-1 gate completion date  ·  Category: Schedule  ·  Required by: 2026-09-05 (re-dated 26-Aug-2026; was 2026-08-18, elapsed)  ·  BLOCKING

Why it is needed: Wave 3 build planning; G1 (current state validated) falls 28-Aug-2026 per BASELINE v2.1 Milestones UTIL-G1

Item 05 — Vendor portal logins: Progress, Cohesity, Archer  ·  Category: Tool access  ·  Required by: 2026-09-15

Why it is needed: Gated [L]-class artifact retrieval

Item 06 — Owner reassignments (5 departed) + OnBase director ruling  ·  Category: Ownership  ·  Required by: 2026-09-01  ·  BLOCKING

Why it is needed: Playbook sign-off + cutover approvals (C7/CF-12)

Item 10 — Capacity parameters: tracks, freeze calendar, LZ readiness  ·  Category: Schedule  ·  Required by: 2026-09-05 (re-dated 26-Aug-2026; was 2026-08-31, elapsed)  ·  BLOCKING

Why it is needed: 3-track assumption drives all wave loads + W3/W4 overloads

Item 12 — Backup policy export + per-app protection groups (Cohesity)  ·  Category: Config export  ·  Required by: 2026-09-30

Why it is needed: Per-workload re-protection steps in each wave (REG-008)

Item 14 — Current DNS zone + firewall rule exports (refresh)  ·  Category: Config export  ·  Required by: 2026-09-30

Why it is needed: DNS/firewall updates at each cutover; corpus copies stale

Item 16 — Table-level write audit: per-DB object permissions + SQL Audit/Query Store capture of writes by login  ·  Category: Config export  ·  Required by: 2026-09-15

Why it is needed: Shared-TABLE writers not captured by any source (F-DB-1); changes cutover grouping + rollback design

Item 17 — Cohesity DataProtect support confirmation for every migrating SQL instance (OS/SQL version/config vs Cohesity requirements)  ·  Category: Backup / DR  ·  Required by: 2026-09-15  ·  BLOCKING

Why it is needed: Azure Backup withdrawn per REG-017 — a non-supported instance now has NO fallback protection path at cutover