# Application Migration Playbook - Datacenter to Azure Migration

CyberArk PAS

Version 0.2

Document Control

Document Information

| Field | Value |
| --- | --- |
| Platform Name | CyberArk PAS |
| Document Name | CyberArk PAS Application Migration Playbook |
| Document Type | Application Migration Playbook - Datacenter to Azure Migration |
| Product Version | Version of the product/application being documented |
| Release Version | 0.2 |
| Effective Date | <Date on which the document becomes effective for use by the intended audience.> |
| Classification | Public/Internal / Confidential / Restricted |
| Status | Draft |

Revision History

| Document Version # | Revision Date | Prepared By | Summary of Changes |
| --- | --- | --- | --- |
| 0.2 | 14-Aug-26 | George Galindo, CitiusTech | Prepared for GEHA technical review. Evidenced fields cite their source and as-of date; fields GEHA has not yet supplied are shown as dated requests in Appendix B. Program decisions are not restated in the body; they are cited in Appendix A. |
| 0.3 | 08/15-09/15/2026 | Syed Ahmed | Various changes throughout the document. |

Approval Matrix

| Role | Name | Signature | Approval Date |
| --- | --- | --- | --- |
| Application Owner | Eric Ullmann |  | Click here to enter a date. |
| Application Administrator | Phil Costanzo |  |  |
| Security Lead | Phil Costanzo |  |  |
| Cloud Architect - CitiusTech Healthcare Consulting | George Galindo |  |  |
| Migration & Platform Lead - CitiusTech Healthcare Consulting | Saikat Majumdar |  |  |
| Enterprise Architect, G.E.H.A. | Scott Schultz |  |  |

Copyright

Copyright © 2026 . All Rights Reserved.
This document contains confidential and proprietary information belonging to CitiusTech, the Client, and/or their respective owners and is protected by applicable intellectual property and confidentiality laws. It is intended solely for authorized recipients. Any unauthorized use, reproduction, distribution, disclosure, or modification of this document, in whole or in part, is strictly prohibited without prior written consent of the applicable rights holder.

Table of Contents

1	Application Snapshot	11

2	Executive Summary	12

3	Application Overview	14

3.1	Business Purpose	14

3.2	Ownership & Stakeholders	14

3.3	Criticality & Service Levels	15

4	Current State	16

4.1	Summary	16

4.2	Service Overview	16

4.3	Servers	18

4.3.1	CyberArk Servers in vCenter	19

4.3.2	Components by Server	20

4.4	Network connections	20

4.5	Load Balancer Configuration	22

4.6	Integrations	24

4.7	Sizing, Utilization, and Protection	25

4.8	Items for Confirmation	26

4.9	Network Connection Register	28

4.10	Sources	33

4.11	Vendor References	34

4.12	Infrastructure & Connectivity	36

4.12.1	Connector Host Inventory	36

4.12.2	Primary Connectivity and Data Flows	36

4.13	Session Recording Configuration	38

4.14	CCP Application Registrations (AIM)	38

4.15	Service Accounts	39

4.16	Component Versions	39

4.16.1	Host Resource Specifications	39

4.16.2	Operating System & Platform Readiness	40

4.16.3	Application Software & Dependencies	40

4.17	Data & Database Tier	41

4.17.1	Single Sign-On	41

4.17.2	Active Directory Security Group Register	41

4.18	Service & Application Account Register	41

4.19	Network	41

4.20	Environment Inventory	42

4.21	Availability & Backup Position	42

5	Design Overview	43

5.1	How to Read the Tables	45

5.2	Landing Zone Placement	45

5.3	Resources Build Table	47

5.4	Hub Firewall Rule Set	55

5.5	Internal Load Balancer Parameters	61

5.6	Host Configuration	62

5.7	Application Configuration	64

5.8	Operations	68

5.9	Tags	71

5.10	Inputs from GEHA	72

5.11	Migration Strategy	78

5.12	Landing Zone Placement	78

5.13	Compute	79

5.14	Data Platform	81

5.15	Storage and File Services	81

5.16	Network	81

5.17	Identity and Access	83

5.18	Security and Compliance	84

5.19	Resilience and Recovery	85

5.20	Monitoring and Operations	87

5.21	Cost and Licensing	88

5.22	Deployment Method	89

6	Post-Migration Test and Validation Plan	90

6.1	Purpose and Scope	92

6.2	Roles	92

6.3	Entry criteria	93

6.4	Test cases	95

6.4.1	Group A: Platform Build Verification	95

6.4.2	Group B: Network Path Verification	98

6.4.3	Group C: Tenant Registration	101

6.4.4	Group D: Brokered Sessions to Migrated Targets	103

6.4.5	Group E: Parallel Run and Separation	106

6.4.6	Group F: Operations Evidence	108

6.4.7	Group G: Disaster Recovery	109

6.5	Schedule	112

6.6	Exit Criteria	112

6.7	Cutover Day Validation and Rollback	112

6.8	Deferred items	113

Appendix A: Workflow description	114

A.1  Swimlanes	114

A.2  Phases and Gates	114

A.3  Decision Points	115

Appendix A: Roles & Responsibilities	117

7.	Sign Off	118

List of Figures

Figure 4-1: On-Premises Current State Production Environment	16

Figure 5-1: Target State Architecture Diagram	43

Figure 6-1: Post-Migration Test and Validation workflow	90

List of Tables

Table 1-1: Key Information	10

Table 3-1: Ownership & Stakeholders	13

Table 3-2: Criticality & Service Levels	14

Table 4-1: Servers	17

Table 4-2: Servers Named in the F5 Pools	18

Table 4-3: Components by Server	19

Table 4-4: Network Connections	20

Table 4-5: F5 Virtual Servers. Full member addresses are provided in the Current State Build Tables	22

Table 4-6: Integrations	23

Table 4-7: Utilization	25

Table 4-8: Protection	25

Table 4-9:  Items for Confirmation	26

Table 4-10: Network Connection Register	27

Table 4-11: Sources	33

Table 4-12: Vendor References	34

Table 4-13: Connector Host Inventory	36

Table 4-14: Primary Connectivity and Data Flows	37

Table 4-15: Session Recording Configuration	38

Table 4-16: CCP Application Registrations (AIM)	39

Table 4-17: Component Versions	39

Table 4-18: Host Resource Specifications	40

Table 5-1: Landing Zone Placement	45

Table 5-2: Hub Firewall Rule Set	55

Table 5-3: Hub Firewall Rules, Production	57

Table 5-4: Internal Load Balancer Parameters	61

Table 5-5: Host Configuration	62

Table 5-6: Application Configuration	65

Table 5-7: Operations	69

Table 5-8: Migration Strategy Per Component	74

Table 5-9: Landing Zone Placement	75

Table 5-10: Compute	76

Table 5-11: Network	78

Table 5-12: Identity and Access	81

Table 5-13: Security and Compliance	82

Table 5-14: Resilience and Recovery	84

Table 5-15: Monitoring and Operations	85

Table 5-16: Cost and Licensing	86

Table 5-17: Deployment Method	87

Table 6-1: Roles Used in the Case Tables	91

Table 6-2: Entry Criteria	92

Table 6-3: Group A: 12 cases, about 2.3 hours of execution	94

Table 6-4: Group B: 10 cases, about 2.4 hours of execution	97

Table 6-5: Group C: 6 cases, about 0.8 hours of execution.	100

Table 6-6: Group D: 10 cases, about 3.8 hours of execution	101

Table 6-7: Group E: 5 cases, About 2 hours of Execution	104

Table 6-8: Group F: 3 cases, About 1.3 Hours of Execution	105

Table 6-9: Group G: 9 cases, About 3.8 Hours of Execution, Plus the Initial Replication Before Day 4	106

Table 6-10: Exit Criteria	110

Table 6-11: Cutover Day Steps	110

Table 6-12: Phases, Tasks, and Gates	112

Table 6-13: Decision Points	113

Table 6-14: Roles & Responsibilities	116

Table 6-15: Sign-Off	118

# Application Snapshot

CyberArk PAS is GEHA's Privileged Access Management platform and a foundational dependency for the entire migration program.

Everything a reader needs to orient themselves on this application is gathered here in a single view so that no one has to hunt through later sections for a date, an owner, or a target platform. Each field is owned by the section named beside it, and that owning section remains the authoritative source; this table is corrected to match it rather than the other way around. The scheduling fields, including wave placement, migration strategy, cliff date, cliff driver, and target cutover date, are recorded here in structured form and narrated in the executive summary that follows. Reading this table alone should be enough to understand what is moving, when it must move, and what forces the timing.

Table 1-1: Key Information

| Field | Value |
| --- | --- |
| Playbook Index ID | GEHA-DCM-CYBERARK-PAS-v0.1 |
| Application Version |  |
| Wave Placement | W1 |
| Migration Strategy | Parallel deployment. No migration. |
| Target Cutover Date | 10-01-2026 |
| User Access Method |  |
| Key Dependencies |  |
| Target Subscription & Landing Zone |  |
| Target Region & Paired Region | Central US, primary. East US, paired. |
| Application Tier | 24h |
| RTO and RPO | 24h |
| Load Balancer | Internal load balancer. Cyberark.geha.com 10.110.12.39 / 10.100.12.39 |
| Deployment Pattern | 4 host(s) across 2 environment(s) |

# Executive Summary

GEHA's privileged access platform, CyberArk, is being extended into Azure to ensure that servers migrating from the data center remain subject to the same privileged-access controls from the day they arrive. The CyberArk vault and service are already cloud-hosted; the components GEHA operates today are the connector servers in the data center that record administrator sessions, broker privileged access to Windows and Linux servers, and manage the credentials on those servers. Because the vault is a cloud service, no credential data is moved. This deployment introduces an equivalent pair of connectors in the Azure production landing zone. It is the first application workload deployed in GEHA's Azure landing zone and establishes the pattern that subsequent applications will follow.

CyberArk is being deployed first because the wave plan identifies it as a foundational dependency for the entire program. Every migrated server's service accounts and privileged credentials must be vaulted in CyberArk, and the connectors serving a server must reside alongside it. If a server moves to Azure while its connector remains in the data center, session recording and brokered access to that server are disrupted. The Azure connectors must therefore be operational before the applications in Waves 2 through 4 are migrated. The credential provider used by on-premises applications is the only exception; it remains on premises with those applications and is retired with them.

The migration follows a parallel-run model rather than a cutover model. The Azure connectors manage only the servers that have migrated, while the data-center connectors continue to manage those that have not. As each application migrates within its assigned wave, its servers are reassigned to the Azure connectors within the CyberArk service and can be reassigned back if a wave is rolled back. The data-center connectors are decommissioned only after the final server has migrated in Wave 4.

The production design consists of two connector servers, one deployed in each of two availability zones, behind an internal load balancer in a dedicated subnet within the Corp production landing zone in Central US. Administrators access the service through a single name, cyberark-prd.GEHA.com, from on-premises workstations, Azure Virtual Desktop, and Zscaler Private Access. All inbound and outbound traffic passes through the Central US hub firewall, which is the only network control on the subnet, as required by the landing-zone standard. The servers are deployed from GEHA's CIS Level 2 Windows Server 2025 image with the CyberArk hardening policy, patched through MECM, monitored through Splunk, and backed up by Cohesity. Non-production and disaster-recovery environments are implemented separately.

The deployment is defined in build tables that identify every resource, rule, and setting. GEHA Cloud Platform engineers and CHC Azure engineers deploy the servers from GEHA's Bicep module library through the Azure DevOps pipeline. Firewall rules are deployed through the GEHA firewall pipeline as a standard change. GEHA's CyberArk administrators install the CyberArk components and register them with the tenant. A test plan validates the deployment and the first brokered sessions before any server is assigned to the new connectors.

The deployed solution resides in subscription CIP-PRD, the Corp production landing zone in Central US. It consists of one workload resource group containing two Windows Server 2025 virtual machines, AZPASPCCPRD101 and AZPASPCCPRD102, and an internal load balancer; one subnet within the production landing-zone network created by the Cloud Platform Team; one DNS name; one rule collection group within the Central US hub firewall policy; and, within GEHA's CyberArk tenant, a session manager farm and a password manager for the Azure estate. All other dependencies, including the hub, ExpressRoute, domain controllers, Splunk, MECM, and Cohesity, already exist and are used without modification.

# Application Overview

This section provides an overview of CyberArk PAS, including its business purpose, ownership, stakeholders, and operational requirements. The information presented here establishes the context for understanding the application's current-state environment, target-state architecture, migration approach, and service-level expectations. Together, these details define the role of CyberArk PAS within the GEHA migration program and the requirements that must be maintained throughout the migration lifecycle.

## Business Purpose

CyberArk PAS is GEHA's enterprise Privileged Access Management (PAM) platform and a foundational dependency for the migration program. All migrated servers must have privileged credentials, service accounts, and application credentials managed through CyberArk. Because of this dependency, CyberArk support for Azure-hosted workloads must be established before the majority of application migrations can occur.

CyberArk is currently delivered as a SaaS-based solution, with cloud-hosted Vault and Central Policy Manager (CPM) services providing privileged access management, secure credential management, credential rotation, and RDP session monitoring and recording. These capabilities are required to satisfy GEHA's operational, security, and audit requirements for both existing and migrated workloads.

To extend CyberArk services to Azure, new CyberArk connector servers will be deployed within Azure to support migrated workloads while existing connectivity continues to support servers that remain in the datacenter. This dual-site operating model allows CyberArk services to be maintained across both environments throughout the migration program.

The Azure connector servers are a prerequisite for workload migration because they provide the communication path between Azure-hosted systems and the CyberArk SaaS platform. Without these connectors, migrated servers would not be able to leverage CyberArk for privileged access management, credential management, or session recording. As a result, the Azure connector deployment must be completed and operational before the associated application and server migrations can proceed.

Although Microsoft Entra Privileged Identity Management (PIM) has been identified as a potential alternative for certain privilege-elevation functions, it does not provide equivalent session-recording capabilities. Therefore, CyberArk will remain a required component of the target-state architecture to support GEHA's privileged access management, auditing, and compliance requirements.

## Ownership & Stakeholders

This section identifies the individuals responsible for the ownership, administration, and support of CyberArk PAS. These stakeholders provide business, operational, and technical oversight for the application and serve as key contacts during migration planning, implementation, testing, and post-migration support.

Table 3-1: Ownership & Stakeholders

| Role | Name |
| --- | --- |
| Business / Application Owner | Eric Ullmann |
| On-call / Support (Admin / Support Manager) | Phil Costanzo |
| Administrator delegate / primary operations support resource | James Edwards |

## Criticality & Service Levels

This section captures the application's service-level and operational requirements, including availability targets, Recovery Time Objectives (RTOs), Recovery Point Objectives (RPOs), peak business operating periods, and migration scheduling constraints. These requirements establish the baseline for evaluating the target-state architecture and developing the migration approach.

Table 3-2: Criticality & Service Levels

| Business Criticality | Tier 2 |
| --- | --- |
| RTO (Recovery Time Objective) | 24 Hours |
| RPO (Recovery Point Objective) | undefined |
| Business Calendar Constraints | Open enrollment / open season - GEHA-wide constraint; program blackouts: 2026-11, 2027-11 |
| Regulatory / Compliance Scope | Business impact: If the application were unavailable, the impact could result in the loss of certain privileged access management services. |

# Current State

This section describes the CyberArk components that run in the Lee's Summit and Lenexa data centers today: the servers, their roles, the network connections they make, the load-balancer configuration, the systems they integrate with, and how they are sized and protected. It is the current-state baseline for the migration. It does not describe the target design.

The content is drawn from the program's discovery data: the vCenter server inventory, a network connection capture, the F5 load-balancer exports, the Matilda assessment, the application register, and the discovery sessions held with GEHA. The Sources table lists the sources. Where the data indicates something without recording it directly, the text states so, and each such point is listed in the Items for Confirmation.

## Summary

GEHA uses CyberArk Privilege Cloud. CyberArk hosts the vault, the portal, and the tenant services. The components that remain on premises support privileged-session access and recording, password management, and application credential retrieval.

vCenter holds nine servers whose notes name a CyberArk role: two connector servers, four credential-provider servers (two of them in the DMZ), and two PSM proxy servers.

In the network capture, both connector servers and two of the credential-provider servers connect to 54.82.114.164 on TCP 1858, the CyberArk vault port. The connector servers also connect over HTTPS to CyberArk services and query the domain controllers, and PASPCCPRD101 sends data to the security syslog server. The F5 load balancers publish RDP and SSH session access inside the network, and credential retrieval over HTTPS 443 both inside the network and from the DMZ.

## Service Overview

GEHA delivers privileged access through CyberArk Privilege Cloud, a software-as-a-service offering. GEHA has confirmed that CyberArk hosts the vault and CPM service and that no vault data is held in GEHA's data centers.

GEHA describes three purposes for the on-premises components: recording RDP sessions, providing privileged access over RDP, and managing application credentials. The Identity and Access discovery session recorded that CyberArk was being integrated to manage privileged accounts, including domain administrator accounts, with credentials stored and passwords rotated automatically. GEHA has stated that CyberArk will be retained because its session-recording capability is unique.

Both connector servers run the session manager (PSM). PASPCCPRD101 also runs the password manager (CPM) and the account-discovery scanner; the capture shows these on no other server. The connector servers connect to the vault on TCP 1858 and, over HTTPS 443, to public addresses. The processes that make these connections reside in the installation folders CyberArk Identity Connector, Management Agent, DPAConnector, and PrivilegeCloudSecureTunnel, which correspond to the Identity Connector, Connector Management, Dynamic Privileged Access, and Secure Tunnel components. The credential-provider servers PASCCPPRD101 and PASCCPPRD102 run the Application Password Provider, which also connects to the vault.

GEHA describes the two connector servers as active-active behind the F5 load balancer and open to all data-center servers: a session reaches the load balancer, which routes it to one of the two connectors. The F5 session pool also names six further servers, PASPSMPRD101 to PASPSMPRD106, listed with the servers. The CyberArk Automation Server is not deployed.

The migration approach recorded with GEHA is a parallel run. New connector servers are built in Azure, and, as servers migrate, their connector configuration moves to the Azure connectors. The on-premises connectors continue to serve the remaining servers until GEHA decommissions them after the final wave. GEHA has noted that a connector must not be retired before the servers it serves have moved, or session recording for those servers stops. The program records the disposition as "Rehost - Connector Servers Only," with the vault and CPM service out of scope.

GEHA rates CyberArk as Criticality Tier 2, with a Recovery Time Objective (RTO) of 24 hours, and the application register classifies its data as Confidential.

Figure 4-1: On-Premises Current State Production Environment

## Servers

All nine servers are virtual machines in the Flex Prod clusters, each with one network adapter and one disk. Memory and disk capacity are shown in GiB. The role is the note recorded for each server in vCenter; the Components table lists the components found running.

Table 4-1: Servers

| Server | Role (vCenter note) | Site | IP address | Network | Operating system | vCPU / memory / disk | Backup policy |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PASPCCPRD101 | Identity Connector | LX | 10.0.4.55 | ACI-Prod | Windows Server 2022 | 08-08-1980 | 8WK Backup |
| PASPCCPRD102 | Identity Connector | LS | 10.0.2.91 | ACI-Prod | Windows Server 2022 | 08-08-1980 | 8WK Backup |
| PASCCPPRD101 | Core Credential Provider | LX | 10.0.4.150 | ACI-Prod | Windows Server 2019 | 02-04-1980 | 2WK Backup |
| PASCCPPRD102 | Core Credential Provider | LS | 10.0.1.9 | ACI-Prod | Windows Server 2019 | 02-04-1980 | 2WK Backup |
| PASCCPPRD103 | Core Credential Provider | LX | 172.16.110.140 | DMZ-VL507 | Windows Server 2019 | 02-04-1980 | 2WK Backup |
| PASCCPPRD104 | Core Credential Provider | LS | 172.16.1.140 | DMZ-VL7 | Windows Server 2019 | 02-04-1980 | 2WK Backup |
| PASPROXYPRD201 | PSM Proxy Server | LX | 10.0.4.83 | ACI-Prod | Red Hat Enterprise Linux 8 | 04-08-1940 | 8WK Backup |
| PASPROXYPRD202 | PSM Proxy Server | LS | 10.0.2.98 | ACI-Prod | Red Hat Enterprise Linux 8 | 04-08-1940 | 8WK Backup |

### CyberArk Servers in vCenter

PASPTAPRD101-OLD runs CentOS 7, which has reached end of life. The four credential-provider servers carry the vCenter note: "Power Off CR - CHG0080381 (Powered back on and removed from decommissions)."

Servers Named in the F5 Pools

The following servers are referenced in the F5 load-balancer pools but do not appear in the vCenter inventory, Matilda assessment, DNS export, or network capture.

Table 4-2: Servers Named in the F5 Pools

| Server | Address | Pool |
| --- | --- | --- |
| pasproxyprd101 | 10.0.4.190 | pas-ssh, port 22 |
| pasproxyprd102 | 10.0.0.190 | pas-ssh, port 22 |
| paspsmprd101 | 10.0.4.191 | pas-rdp, port 3389 |
| paspsmprd102 | 10.0.4.192 | pas-rdp, port 3389 |
| paspsmprd103 | 10.0.4.193 | pas-rdp, port 3389 |
| paspsmprd104 | 10.0.0.191 | pas-rdp, port 3389 |
| paspsmprd105 | 10.0.0.192 | pas-rdp, port 3389 |
| paspsmprd106 | 10.0.0.193 | pas-rdp, port 3389 |

### Components by Server

Table 4-3: Components by Server

| Server | Components |
| --- | --- |
| PASPCCPRD101 | Session manager (PSM), password manager (CPM), account discovery scanner, Identity Connector, Connector Management agent, Dynamic Privileged Access connector and Secure Tunnel, identified from the process paths in the network capture |
| PASPCCPRD102 | As PASPCCPRD101, without the password manager and the account discovery scanner |
| PASCCPPRD101, PASCCPPRD102 | Application Password Provider, from the process path. Matilda records IIS 10.0 and server type Web Server on both. The Central Credential Provider web service does not appear in the capture |
| PASCCPPRD103, PASCCPPRD104 | vCenter role Core Credential Provider. No CyberArk process appears in the capture |
| PASPROXYPRD201, PASPROXYPRD202 | vCenter role PSM Proxy Server. Members of the F5 SSH pool. No network activity in the capture |
| PASPTAPRD101-OLD | vCenter role Privileged Threat Analytics. No network activity in the capture |

## Network connections

The network capture records 130 connections involving the nine server addresses. As the capture reflects activity at a specific point in time, it may not represent all possible connections. Peer names are not included for outbound connections initiated by the CyberArk servers; the names shown have been derived from corresponding address lookups in vCenter. No connections to CyberArk virtual addresses hosted on the F5 load balancers were captured. As a result, user sessions and credential requests processed through the load balancers are not represented in the dataset. The Network Connections table summarizes the captured traffic, and the Network Connection Register provides the detailed record of all captured connections.

Table 4-4: Network Connections

| From | To | Port | Process and note |
| --- | --- | --- | --- |
| PASPCCPRD101, PASPCCPRD102 | 54.82.114.164 | TCP 1858 | Session manager on both; password manager on PASPCCPRD101. 1858 is the CyberArk vault port |
| PASCCPPRD101, PASCCPPRD102 | 54.82.114.164 | TCP 1858 | Application Password Provider |
| PASPCCPRD101, PASPCCPRD102 | Public addresses, in the connection register | TCP 443 | Identity Connector, Connector Management, Dynamic Privileged Access and Secure Tunnel processes; account discovery scanner from PASPCCPRD101 only |
| PASPCCPRD101, PASPCCPRD102 | LSDC01 to 04, LXDC03, LXDC04 | TCP 389, 3268 | Identity Connector process, to all six domain controllers |
| PASPCCPRD101, PASPCCPRD102 | LSDC01, LSDC02, LSDC03, LSDC04, LXDC03, LXDC04 | TCP 49667, 49669, 49670 | Identity Connector process: 49667 to LSDC01, LSDC04, LXDC03 and LXDC04; 49669 to LSDC02; 49670 to LSDC03 |
| PASPCCPRD101 | lssyslog01, 10.100.12.174 | TCP 49550 | Secure Tunnel process |
| PASPCCPRD101, 102; PASCCPPRD101, 102 | lssplunkindex01, 02; lxsplunkindex01, 02 | TCP 9998 | Splunk forwarder |
| PASPCCPRD101, PASCCPPRD101 | spldepprd101 | TCP 8089 | Splunk forwarder to the deployment server |
| PASPCCPRD101, 102; PASCCPPRD101, 102 | Public addresses, in the connection register | TCP 443 | Rapid7 Insight Agent and endpoint broker processes |
| PASPCCPRD101, 102; PASCCPPRD102 | Public addresses, in the connection register | TCP 80 | Windows service host process (svchost.exe); purpose not recorded |
| MECMSITEPRD101 | All six Windows CyberArk servers | One port per server, 50442 to 65398 | SCCM site server, dllhost.exe |
| PASCCPPRD103, PASCCPPRD104 | MECMSITEPRD101 | TCP 10123 | Recorded by the SCCM site server. 10123 is the SCCM client notification port |
| SNMIDPRD301 | PASPCCPRD102 | TCP 135 | ServiceNow MID server. 135 is the RPC endpoint mapper |
| SNMIDTST201 | PASCCPPRD104 | TCP 443 | ServiceNow test MID server; the only HTTPS request to a credential provider server in the capture |
| ORIONMWSPRD101; ORIONAPEPRD101 | PASCCPPRD102; PASCCPPRD103 | One port each, 59426 and 49815 | SolarWinds job engine |

## Load Balancer Configuration

The CyberArk virtual servers are hosted on lsmbigipp01 and lxabigipp01. Both exports identify the devices as "Online (Standby)"; therefore, the active units and the configurations running on them are not included in the available data.

The LDAPS and syslog virtual servers are hosted on lsbigip02 and lxbigip02. Both exports identify these devices as "Online (Active)".

The exports include details of virtual servers, pools, and pool members only. They do not provide information on load-balancing methods, health monitors, or persistence settings.

Each CyberArk pool contains inventoried servers from both data centers.

Table 4-5: F5 Virtual Servers. Full member addresses are provided in the Current State Build Tables

| Virtual server | Addresses (LS; LX) | Port | Pool members |
| --- | --- | --- | --- |
| pas-rdp | 10.100.12.39; 10.110.12.39 | 3389 | PASPCCPRD101, PASPCCPRD102, paspsmprd101 to 106 |
| pas-ssh | 10.100.12.39; 10.110.12.39 | 22 | pasproxyprd101, pasproxyprd102, PASPROXYPRD201, PASPROXYPRD202 |
| pas-http | 10.110.12.39 (LX only) | 80 | No pool; redirects to HTTPS |
| cyberark-ccp-prd-vs, internal | 10.100.10.63; 10.110.10.63 | 443 | PASCCPPRD101, PASCCPPRD102 |
| cyberark-ccp-prd-vs, DMZ | 172.16.1.66; 172.16.110.66 | 443 | PASCCPPRD103, PASCCPPRD104 |
| LDAPS_vs | 10.100.12.109; 10.110.12.109 | 636 | The six domain controllers and 10.140.5.100, 10.140.5.101 |
| Syslog, syslog-tcp | 10.100.12.16; 10.110.12.16 | Any | lssyslog01, lssyslog02 (LS); lxsyslog01, lxsyslog02 (LX) |
| Virtual server | Addresses (LS; LX) | Port | Pool members |

The network capture shows the connector servers querying the domain controllers directly on ports 389 and 3268. It also shows PASPCCPRD101 sending traffic directly to lssyslog01 on port 49550.

No connections from any CyberArk server to the LDAPS or syslog virtual servers appear in the capture. However, the capture does record other servers using the syslog virtual addresses.

## Integrations

The following integrations were identified during discovery.

Table 4-6: Integrations

| System | Relationship |
| --- | --- |
| Active Directory | Both connector servers query the six domain controllers |
| Splunk | Forwarder on the connector servers and the internal credential provider servers |
| Security syslog | lssyslog01 receives a connection from the Secure Tunnel process on PASPCCPRD101. CyberArk documents the Secure Tunnel as the path for Privilege Cloud to reach a SIEM |
| Rapid7 | Insight Agent on the connector servers and the internal credential provider servers |
| SCCM | The SCCM site server connects to all six Windows CyberArk servers. Matilda lists SCCM as the dependent application of the four servers it assessed |
| ServiceNow | MID servers SNMIDPRD301 and SNMIDTST201 connect to PASPCCPRD102 and PASCCPPRD104 |
| SolarWinds Orion | The Orion job engine connects to PASCCPPRD102 and PASCCPPRD103 |
| Devolutions Remote Desktop Manager | Recorded in the business impact analysis as needed for the CyberArk session manager |
| Remote Desktop Services licensing | The session manager runs on RDS; GEHA holds about 200 RDS licences under its Microsoft agreement |
| Axonius | The application register lists CyberArk as an upstream dependency of Axonius; the Axonius questionnaire names the connected adapter as CyberArk EPM |
| CyberArk EPM | A separate SaaS product used on desktops and laptops only; no migration is required |
| CyberArk DNA | A discovery and audit tool, recorded in the business impact analysis as run on an ad hoc basis |
| Venafi | The register proposes a move to Venafi SaaS (CyberArk Machine Id Security). No Venafi server appears in the capture with the CyberArk servers |
| Password Manager Pro (PMP) | A separate password manager, used for the LiteSpeed backup passwords. No link to CyberArk is recorded |

## Sizing, Utilization, and Protection

Utilization data is derived from the Matilda assessment. The remaining five servers were not assessed.

Table 4-7: Utilization

| Server | vCPU | Memory GB | Average CPU % | CPU P95 | Average memory % | Memory P95 | Storage used % |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PASPCCPRD101 | 8 | 8 | 2.78 | 6.00% | 66.85 | 68.25% | 53.44 |
| PASPCCPRD102 | 8 | 8 | 1.79 | 3.75% | 65.79 | 66.62% | 66.93 |
| PASCCPPRD101 | 2 | 4 | 5.94 | 7.00% | 78.16 | 79.25% | 71.24 |
| PASCCPPRD102 | 2 | 4 | 6.44 | 4.00% | 75.43 | 76.50% | 67.45 |

Table 4-8: Protection

| Area | Current state |
| --- | --- |
| Backup | vCenter records the 8WK Backup policy on the connector and PSM proxy servers, and 2WK Backup on the credential provider and PTA servers. GEHA uses Cohesity for backup, with daily jobs and retention periods of two weeks, three years and eight weeks; daily backups are kept for eight weeks, locally and at the remote data center. The data does not state which product the two vCenter policies belong to. |
| Disaster recovery | The application register records disaster recovery as "SaaS Platform". No recovery arrangement specific to the on-premises servers is recorded. GEHA has decided to keep on-premises disaster recovery in place during the migration warranty period. |
| High availability | Two connector servers, one in each data center, in the F5 pas-rdp pool. The password manager appears in the capture on PASPCCPRD101 only. |
| Clusters | LS and LX Flex Prod clusters. The DRS export records DRS as fully automated. |

## Items for Confirmation

The following items could not be confirmed from the discovery data. Each item includes the available evidence and the specific confirmation requested from GEHA. Outcomes are to be recorded in the Program Decision Register.

Table 4-9:  Items for Confirmation

| # | Item | What the records show | Confirmation requested |
| --- | --- | --- | --- |
| 2 | F5 pool members | paspsmprd101 to 106 and pasproxyprd101 and 102 appear in the F5 pools only. | Whether these servers exist, and their site and role. |
| 5 | Meaning of "CCP" | The session minutes describe the CCP as one of the two connectors, responsible for password rotation, and state that only one CCP can exist at a time. In CyberArk terms, password rotation is performed by the CPM, which appears on PASPCCPRD101; the Central Credential Provider is a separate credential provider web service, and the vCenter role Core Credential Provider is recorded on the PASCCPPRD servers. | Which component the term refers to, and what the one-at-a-time constraint applies to. |
| 6 | Password manager | Records describe the CPM as SaaS. The CPM engine appears in the capture on PASPCCPRD101 only. | Where password rotation runs, and whether a second CPM exists. |
| 15 | Directory protocol | The connector servers use LDAP 389 and global catalog 3268 in the capture; no LDAPS 636 connection appears. | Whether the target should use LDAPS. |
| 16 | Audit feed | The Secure Tunnel connection to lssyslog01 appears from PASPCCPRD101 only. | Where the audit feed runs and whether PASPCCPRD102 also carries it. |
| 18 | DNS names | The DNS export holds zones and scopes but no host records. | The DNS names clients use for each CyberArk virtual server. |
| 20 | HTTP 80 traffic | PASPCCPRD101, 102 and PASCCPPRD102 make outbound HTTP 80 connections from the Windows service host process. | The purpose of this traffic. |
| 21 | Integration settings | Configuration for ServiceNow, SolarWinds, Devolutions RDM, Axonius and Venafi is not recorded. | The settings that reference CyberArk server names or addresses. |
| 22 | RDS licensing | vCenter holds RDSLICPRD301 (10.0.2.104). No connection between it and a CyberArk server appears in the capture. | The licensing server the session manager uses. |
| 23 | Backup policies | The 8WK and 2WK policies are recorded in vCenter. GEHA uses Cohesity. | That both are Cohesity policies, and the recovery arrangement for these servers. |
| 25 | Azure integration | Direct integration between CyberArk and Azure was raised during discovery as needing investigation. | Whether CyberArk must manage Azure accounts or resources. |

## Network Connection Register

The network connection capture contains 53 connection groups and 130 records, all using TCP. Names have been derived from vCenter address lookups. The two records from PASCCPPRD103 and PASCCPPRD104 on port 10123 were recorded by MECMSITEPRD101; therefore, the originating process was not captured.

Table 4-10: Network Connection Register

| # | From | Process | To | Name | Port | Records |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | PASPCCPRD101 | CACPMScanner.exe | 54.243.179.151 | Public address | 443 | 1 |
| 2 | PASPCCPRD101 | CAPSM.exe | 54.82.114.164 | Public address | 1858 | 1 |
| 3 | PASPCCPRD101 | PMEngine.exe | 54.82.114.164 | Public address | 1858 | 1 |
| 4 | PASPCCPRD101 | PrivilegeCloudSecureTunnel.exe | 100.28.105.160 | Public address | 443 | 1 |
| 5 | PASPCCPRD101 | PrivilegeCloudSecureTunnel.exe | 10.100.12.174 | lssyslog01 | 49550 | 1 |
| 6 | PASPCCPRD101 | ProxyHost.exe | 10.100.10.8, 10.100.10.9, 10.100.10.10, 10.100.10.12, 10.110.10.10, 10.110.10.12 | LSDC03, LSDC04, LSDC01, LSDC02, LXDC03, LXDC04 | 389 | 6 |
| 7 | PASPCCPRD101 | ProxyHost.exe | 44.206.149.120, 52.1.175.164, 52.3.199.216, 52.4.223.91 | Public addresses | 443 | 4 |
| 8 | PASPCCPRD101 | ProxyHost.exe | 10.100.10.8, 10.100.10.9, 10.100.10.10, 10.100.10.12, 10.110.10.10, 10.110.10.12 | LSDC03, LSDC04, LSDC01, LSDC02, LXDC03, LXDC04 | 3268 | 6 |
| 9 | PASPCCPRD101 | ProxyHost.exe | 10.100.10.9, 10.100.10.10, 10.110.10.10, 10.110.10.12 | LSDC04, LSDC01, LXDC03, LXDC04 | 49667 | 4 |
| 10 | PASPCCPRD101 | ProxyHost.exe | 10.100.10.12 | LSDC02 | 49669 | 1 |
| 11 | PASPCCPRD101 | ProxyHost.exe | 10.100.10.8 | LSDC03 | 49670 | 1 |
| 12 | PASPCCPRD101 | component-manager-client.exe | 67.202.56.0 | Public address | 443 | 1 |
| 13 | PASPCCPRD101 | connector.exe | 3.81.198.213 | Public address | 443 | 1 |
| 14 | PASPCCPRD101 | ir_agent.exe | 34.226.68.35, 34.236.161.191, 52.203.25.223, 54.144.111.231, 193.149.136.16, 193.149.136.101, 193.149.136.107, 193.149.136.134, 193.149.136.168 | Public addresses | 443 | 9 |
| 15 | PASPCCPRD101 | rapid7_endpoint_broker.exe | 34.236.161.191, 52.203.25.223 | Public addresses | 443 | 2 |
| 16 | PASPCCPRD101 | splunkd.exe | 10.100.12.145 | spldepprd101 | 8089 | 1 |
| 17 | PASPCCPRD101 | splunkd.exe | 10.100.12.172, 10.100.12.173, 10.110.12.172, 10.110.12.173 | lssplunkindex01, lssplunkindex02, lxsplunkindex01, lxsplunkindex02 | 9998 | 4 |
| 18 | PASPCCPRD101 | svchost.exe | 146.75.82.172, 199.232.214.172 | Public addresses | 80 | 2 |
| 19 | PASPCCPRD102 | CAPSM.exe | 54.82.114.164 | Public address | 1858 | 1 |
| 20 | PASPCCPRD102 | PrivilegeCloudSecureTunnel.exe | 100.28.105.160 | Public address | 443 | 1 |
| 21 | PASPCCPRD102 | ProxyHost.exe | 10.100.10.8, 10.100.10.9, 10.100.10.10, 10.100.10.12, 10.110.10.10, 10.110.10.12 | LSDC03, LSDC04, LSDC01, LSDC02, LXDC03, LXDC04 | 389 | 6 |
| 22 | PASPCCPRD102 | ProxyHost.exe | 52.44.252.222 | Public address | 443 | 1 |
| 23 | PASPCCPRD102 | ProxyHost.exe | 10.100.10.8, 10.100.10.9, 10.100.10.10, 10.100.10.12, 10.110.10.10, 10.110.10.12 | LSDC03, LSDC04, LSDC01, LSDC02, LXDC03, LXDC04 | 3268 | 6 |
| 24 | PASPCCPRD102 | ProxyHost.exe | 10.100.10.9, 10.100.10.10, 10.110.10.10, 10.110.10.12 | LSDC04, LSDC01, LXDC03, LXDC04 | 49667 | 4 |
| 25 | PASPCCPRD102 | ProxyHost.exe | 10.100.10.12 | LSDC02 | 49669 | 1 |
| 26 | PASPCCPRD102 | ProxyHost.exe | 10.100.10.8 | LSDC03 | 49670 | 1 |
| 27 | PASPCCPRD102 | component-manager-client.exe | 52.205.147.46, 54.86.151.37 | Public addresses | 443 | 2 |
| 28 | PASPCCPRD102 | connector.exe | 3.227.38.104, 34.205.145.5 | Public addresses | 443 | 2 |
| 29 | PASPCCPRD102 | ir_agent.exe | 34.226.68.35, 34.236.161.191, 52.203.25.223, 54.144.111.231, 193.149.136.16, 193.149.136.101, 193.149.136.134, 193.149.136.168 | Public addresses | 443 | 8 |
| 30 | PASPCCPRD102 | splunkd.exe | 10.100.12.172, 10.100.12.173, 10.110.12.172, 10.110.12.173 | lssplunkindex01, lssplunkindex02, lxsplunkindex01, lxsplunkindex02 | 9998 | 4 |
| 31 | PASPCCPRD102 | svchost.exe | 92.223.96.6 | Public address | 80 | 1 |
| 32 | PASCCPPRD101 | AppProvider.exe | 54.82.114.164 | Public address | 1858 | 1 |
| 33 | PASCCPPRD101 | ir_agent.exe | 34.236.161.191, 193.149.136.16, 193.149.136.101, 193.149.136.107, 193.149.136.134, 193.149.136.142, 193.149.136.160, 193.149.136.168 | Public addresses | 443 | 8 |
| 34 | PASCCPPRD101 | rapid7_endpoint_broker.exe | 34.226.68.35, 52.203.25.223, 54.144.111.231 | Public addresses | 443 | 3 |
| 35 | PASCCPPRD101 | splunkd.exe | 10.100.12.145 | spldepprd101 | 8089 | 1 |
| 36 | PASCCPPRD101 | splunkd.exe | 10.100.12.172, 10.100.12.173, 10.110.12.172, 10.110.12.173 | lssplunkindex01, lssplunkindex02, lxsplunkindex01, lxsplunkindex02 | 9998 | 4 |
| 37 | PASCCPPRD102 | AppProvider.exe | 54.82.114.164 | Public address | 1858 | 1 |
| 38 | PASCCPPRD102 | ir_agent.exe | 34.226.68.35, 34.236.161.191, 52.203.25.223, 54.144.111.231, 193.149.136.16, 193.149.136.101, 193.149.136.134, 193.149.136.168 | Public addresses | 443 | 8 |
| 39 | PASCCPPRD102 | rapid7_endpoint_broker.exe | 34.226.68.35, 34.236.161.191 | Public addresses | 443 | 2 |
| 40 | PASCCPPRD102 | splunkd.exe | 10.100.12.172, 10.100.12.173, 10.110.12.172, 10.110.12.173 | lssplunkindex01, lssplunkindex02, lxsplunkindex01, lxsplunkindex02 | 9998 | 4 |
| 41 | PASCCPPRD102 | svchost.exe | 23.53.127.170 | Public address | 80 | 1 |
| 42 | PASCCPPRD103 | Not recorded | 10.0.1.185 | MECMSITEPRD101 | 10123 | 1 |
| 43 | PASCCPPRD104 | Not recorded | 10.0.1.185 | MECMSITEPRD101 | 10123 | 1 |
| 44 | MECMSITEPRD101 | dllhost.exe | 172.16.1.140 | PASCCPPRD104 | 50442 | 1 |
| 45 | MECMSITEPRD101 | dllhost.exe | 10.0.1.9 | PASCCPPRD102 | 51371 | 1 |
| 46 | MECMSITEPRD101 | dllhost.exe | 10.0.2.91 | PASPCCPRD102 | 53771 | 1 |
| 47 | MECMSITEPRD101 | dllhost.exe | 10.0.4.55 | PASPCCPRD101 | 60115 | 1 |
| 48 | MECMSITEPRD101 | dllhost.exe | 172.16.110.140 | PASCCPPRD103 | 62604 | 1 |
| 49 | MECMSITEPRD101 | dllhost.exe | 10.0.4.150 | PASCCPPRD101 | 65398 | 1 |
| 50 | ORIONAPEPRD101 | SWJobEngineWorker2.exe | 172.16.110.140 | PASCCPPRD103 | 49815 | 1 |
| 51 | ORIONMWSPRD101 | SWJobEngineWorker2.exe | 10.0.1.9 | PASCCPPRD102 | 59426 | 1 |
| 52 | SNMIDPRD301 | svchost.exe | 10.0.2.91 | PASPCCPRD102 | 135 | 1 |
| 53 | SNMIDTST201 | java.exe | 172.16.1.140 | PASCCPPRD104 | 443 | 1 |

## Sources

The following sources were used to establish the current-state baseline.

Table 4-11: Sources

| Source | Content used |
| --- | --- |
| vCenter server inventory (Server_VM_Inventory.xlsx), DRS export (vmware_hosts_DRS.xlsx) | Server names, roles, addresses, sizing, operating systems, backup policies, clusters |
| Network connection capture (Application_Interface_Details) | 451,897 records, 130 involving the CyberArk servers |
| F5 exports (lsmbigipp01, lxabigipp01, lsbigip02, lxbigip02) | Virtual servers, pools, members and device status |
| Matilda Discovery Assessment Summary | Utilization, IIS and dependent application for four CyberArk servers |
| Discovery Report Inventory v1.0; BIA Applications | Register record, criticality, recovery objective, integrations |
| GEHA wave plan tracker; Application Owners | Owners, disposition, scope, discovery session minutes |
| CyberArk session minutes; SIEM and IAM minutes; Cohesity and LiteSpeed minutes | Components, migration approach, PTA status, RDS licensing, backup scheme |
| Discovery session notes: Identity and Access; Cloud Platform; Applications and Integrations; Backup, DR and Continuity | Account management, disaster recovery decision, connector description, Cohesity retention |
| Applications session 1 and 2 responses; Databases questionnaire | CyberArk, EPM, Axonius, ServiceNow and PMP answers |
| NAT Rules, DHCP and DNS list | NAT and DNS checks |

Sources: Evidence supporting each value is recorded in the Current State Build Tables and the associated validation log.

## Vendor References

Table 4-12: Vendor References

| Reference | Link |
| --- | --- |
| CentOS Linux 7 end of life | https://www.redhat.com/en/topics/linux/centos-linux-eol |
| Privilege Cloud network requirements, including TCP 1858 to the vault | https://docs.cyberark.com/privilege-cloud-standard/latest/en/content/privilege%20cloud/privcloud-sys-req-networks.htm |
| Central Credential Provider | https://docs.cyberark.com/credential-providers/latest/en/content/ccp/the-central%20-credential-provider.htm |
| Automatic password management by the CPM | https://docs.cyberark.com/privilege-cloud-shared-services/latest/en/content/pasimp/configuring-accounts-for-automatic-management.htm |
| Connecting Privilege Cloud to a SIEM through the Secure Tunnel | https://docs.cyberark.com/privilege-cloud-standard/latest/en/content/privilege%20cloud/privcloud-connect-siem.htm |
| Secure Tunnel supported versions | https://docs.cyberark.com/end-of-life-policy/latest/en/content/eol-saas-products.htm |
| SCCM client notification port TCP 10123 | https://learn.microsoft.com/en-us/intune/configmgr/core/plan-design/hierarchy/ports |

## Infrastructure & Connectivity

This section describes the current CyberArk PAS infrastructure and the connectivity patterns that support privileged access management, credential retrieval, and communication with the CyberArk SaaS platform. It identifies the deployed hosts, their roles, and the primary data flows that enable application and administrative functions.

### Connector Host Inventory

The CyberArk environment includes Privileged Session Manager (PSM) and Central Credential Provider (CCP/AIM) servers that support privileged session management, credential retrieval, and integration with consuming applications. The inventory below summarizes the currently deployed connector hosts and their assigned roles.

Table 4-13: Connector Host Inventory

| Host | Role | vCPU | Memory | Disk | Notes |
| --- | --- | --- | --- | --- | --- |
| PASPCCPRD101 | PSM (session broker) | 8 | 8 GB | 80 GB |  |
| PASPCCPRD102 | PSM (session broker) | 8 | 8 GB | 80 GB | Load-balanced pair |
| PASCCPPRD101 | CCP / AIM | 2 | 4 GB | 80 GB | Load-balanced pair |
| PASCCPPRD102 | CCP / AIM | 2 | 4 GB | 80 GB |  |
| PASCCPPRD103 | CCP / AIM | — | — | — | Sizing not supplied (D2) |
| PASCCPPRD104 | CCP / AIM | — | — | — | Sizing not supplied (D2) |

### Primary Connectivity and Data Flows

CyberArk supports two primary access patterns within the GEHA environment: privileged user access and application credential retrieval.

For privileged user access, administrators connect through a load balancer that distributes traffic across the CyberArk Privileged Session Manager (PSM) servers (PASPCCPRD101 and PASPCCPRD102). The PSM servers broker connections to target production servers, eliminating the need for direct administrative access. All privileged sessions are monitored and recorded, with session recordings stored in the CyberArk cloud recording vault and retained for 180 days in accordance with operational and compliance requirements.

For machine-to-machine authentication, applications retrieve credentials dynamically from CyberArk rather than storing privileged credentials locally. Current consumers include Venafi, Nexpose, UiPath Orchestrator, and ServiceNow, which obtain credentials through the CyberArk Central Credential Provider (CCP) servers (PASCCPPRD101-104). This approach reduces credential exposure and centralizes password management within the CyberArk platform.

CyberArk connector servers and the systems they support reside within the same on-premises production network, eliminating the need for firewall traversal between the connectors and their target systems. The primary controlled network path is the outbound connection from the CyberArk connector servers to the CyberArk Privileged Cloud tenant through the Palo Alto perimeter firewalls. This communication is established over TCP 1858 and TCP 443 and enables connectivity between the on-premises components and the CyberArk SaaS platform.

In addition, CyberArk components communicate with Active Directory to perform directory and identity-related functions using LDAP (TCP 389) and Global Catalog (TCP 3268) services. These directory integrations support authentication, user lookup, and authorization workflows across the CyberArk environment.

Table 4-14: Primary Connectivity and Data Flows

| Source | Destination | Data Flow / Purpose | Protocol / Port | Comments |
| --- | --- | --- | --- | --- |
| Administrators | Load Balancer | Initiate privileged administrative access sessions | HTTPS / RDP-related traffic | Entry point for privileged user access |
| Load Balancer | PSM Servers (PASPCCPRD101, PASPCCPRD102) | Distribute privileged session traffic | Internal Application Traffic | Provides load balancing and high availability for PSM services |
| PSM Servers | Production Target Servers | Broker privileged access sessions and record administrator activity | RDP | All privileged sessions are recorded and audited |
| PSM Servers | CyberArk Recording Vault (SaaS) | Transfer and store session recordings | TCP 443 | Session recordings are retained for 180 days |
| Venafi | CCP Servers (PASCCPPRD101-104) | Runtime credential retrieval | HTTPS | Credentials are retrieved dynamically rather than stored locally |
| Nexpose | CCP Servers (PASCCPPRD101-104) | Runtime credential retrieval | HTTPS | Credentials are retrieved dynamically rather than stored locally |
| UiPath Orchestrator | CCP Servers (PASCCPPRD101-104) | Runtime credential retrieval | HTTPS | Credentials are retrieved dynamically rather than stored locally |
| ServiceNow | CCP Servers (PASCCPPRD101-104) | Runtime credential retrieval | HTTPS | Credentials are retrieved dynamically rather than stored locally |
| CyberArk Connector Servers | CyberArk Privileged Cloud (SaaS) | Connector-to-cloud communication | TCP 1858, TCP 443 (Outbound) | Required for CyberArk SaaS connectivity and service operations |
| CyberArk Connector Servers | Active Directory | Authentication, directory lookups, and authorization services | LDAP (TCP 389), Global Catalog (TCP 3268) | Supports Active Directory integration |
| CyberArk Connector Servers | Managed Target Servers | Privileged access and credential management communications | Internal Network Traffic | Connectors and targets reside in the same production network. No firewall traversal is required |

## Session Recording Configuration

This section documents the current session-recording configuration used by CyberArk Privileged Session Manager. Session recording supports monitoring, auditing, and compliance requirements for privileged administrative activities.

Table 4-15: Session Recording Configuration

| Configuration Item | Value |
| --- | --- |
| PSM Servers Defined | PASPCCPRD101, PASPCCPRD102 |
| Load Balancing | Load-balanced pair |
| Recording Retention | 180 days |
| Recording Storage | Recording vault, cloud-hosted |

## CCP Application Registrations (AIM)

This section identifies applications currently consuming credentials through the CyberArk Central Credential Provider (CCP) infrastructure. These integrations support dynamic credential retrieval and reduce the need for locally stored credentials.

Table 4-16: CCP Application Registrations (AIM)

| Configuration Item | Value |
| --- | --- |
| Consuming applications | Venafi, Nexpose, UiPath_Orchestrator, ServiceNow |
| CCP hosts | PASCCPPRD101, 102, 103, 104 |

## Service Accounts

This section identifies the service accounts currently associated with the CyberArk PAS environment. Additional account ownership, permissions, and dependency details are documented later in the Service & Application Account Register.

Service Accounts:

Svcnexpose

SvcCMDBdc

SvcAutoQA

SVCVenafi

## Component Versions

This section records the currently identified CyberArk platform and component versions. These versions establish the baseline for target-state planning, compatibility assessment, and migration readiness activities.

Table 4-17: Component Versions

| Component | Version |
| --- | --- |
| CyberArk Privileged Cloud | 14.9 |
| Management Agent | 3 |
| Password Manager | 15 |
| Central Policy Manager (CPM) | 15 |
| Privileged Session Manager (PSM) | 15 |

### Host Resource Specifications

This section records the host-level resource specifications and inventory attributes currently available for the CyberArk PAS servers. These details support migration readiness assessments, target-state sizing validation, and infrastructure planning activities. Where information has not yet been provided, the gap is recorded to support follow-up and data collection.

Table 4-18: Host Resource Specifications

| Server / Component | Role | OS / Version | Environment | Assessment Readiness | Holds Data? | CMDB / Asset ID |
| --- | --- | --- | --- | --- | --- | --- |
| PASCCPPRD101 | application/server host | Not yet provided —. | — | Not assessed — no Azure Migrate export on file (Appendix B item 01) | No | CMDB ID not recorded |
| PASCCPPRD102 | application/server host | Not yet provided — ). | — | Not assessed — no Azure Migrate export on file (Appendix B item 01) | No | CMDB ID not recorded |
| PASPCCPRD101 | application/server host | Not yet provided —. | — | Not assessed — no Azure Migrate export on file (Appendix B item 01) | No | CMDB ID not recorded |
| PASPCCPRD102 | application/server host | Not yet provided — | — | Not assessed — no Azure Migrate export on file (Appendix B item 01) | No | CMDB ID not recorded |

### Operating System & Platform Readiness

This section captures the operating system and platform attributes that determine migration feasibility and target-state compatibility. Operating system support status, architecture, boot configuration, networking, clustering, installed agents, licensing dependencies, and storage characteristics are validated against the running systems because these attributes directly affect migration options and post-migration operability. Any unsupported operating system or hardware-dependent licensing requirement may require remediation before migration activities can proceed.

### Application Software & Dependencies

This section documents the application software stack and supporting dependencies that must be evaluated during migration planning. Key considerations include installed versions, platform supportability, scheduled tasks, file storage dependencies, licensing constraints, and client-side components. These dependencies are reviewed to identify any conditions that could affect application functionality following migration. Where software licensing is tied to host-specific attributes, the dependency is documented to support migration planning and cutover readiness assessments.

## Data & Database Tier

Not Applicable.

### Single Sign-On

Not Applicable.

### Active Directory Security Group Register

Not Applicable.

## Service & Application Account Register

This section documents service and application accounts used by CyberArk PAS and its supporting integrations. Each account should identify its purpose, credential ownership, password management approach, assigned privileges, dependent services, and planned disposition at cutover. The information supports migration planning, operational readiness, and post-migration validation activities. Accounts that cannot be traced to a defined service, integration, or retirement decision should be treated as open items requiring further review.

| Account Name | Type | What It Authenticates To | Credential Holder / Vault | Password Policy & Expiry | Rights Held | Depends On / Used By | Disposition at Cutover |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Cyberarkpc rec@geha.com | Not yet provided | Not yet provided | To be provided by GEHA | ☐ Expiry date: ☐ Non-expiring | Not yet provided | Not yet provided | ☐ Replaced by a target credential or managed identity in Section 5.9 ☐ Retained for another purpose ☐ Disabled and deleted |

## Network

CyberArk currently uses an on-premises F5 load balancer to provide access through the DNS name cyberark.geha.com. The DNS currently resolves to 10.110.12.39 and 10.100.12.39. Because the on-premises F5 environment will be retired, an Azure load-balancing solution will be required for the future-state CyberArk environment. The connector servers use outbound TCP 1858 and TCP 443 to the SaaS tenant. The connector servers are in the same network as their targets, so there is no firewall between them.

Host

PASCCPPRD101

PASCCPPRD102

PASCCPPRD103

PASCCPPRD104

## Environment Inventory

Not applicable

## Availability & Backup Position

Not applicable

# Design Overview

Figure 5-1: Target State Architecture Diagram

CyberArk Privileged Access Security is a software-as-a-service platform. CyberArk hosts and operates the vault, web portal, policy engine, and session recording store. None of these components move. GEHA operates the connector tier: the servers that broker privileged sessions, rotate the credentials held in the vault, and hold the outbound tunnel to the tenant. The connector tier is the component that moves to Azure.

CyberArk will be deployed to Azure using a parallel deployment pattern. Two new Microsoft Windows Server 2022 servers will be deployed for production and two for non-production, for a total of four servers. All four servers will be deployed from the approved GEHA server image through the Bicep module library. The existing on-premises connectors will not be migrated and will remain in service throughout the program so that privileged access never depends on a single estate. As each application migrates, its credentials will be re-pointed from the on-premises connectors to the Azure connectors. GEHA will decommission the on-premises connectors after the final wave, once no on-premises targets remain.

Each environment will consist of a pair of Standard_D8ls_v5 servers with eight virtual processors and sixteen gigabytes of memory, with one server deployed in Availability Zone 1 and the other in Availability Zone 2 in the Central US region. The servers will sit behind a standard internal load balancer. The load balancer holds client affinity to the same server for the life of a session, which the CyberArk brokering handshake requires. Both servers run the Privileged Session Manager and the Secure Tunnel. Credential rotation runs active on the first server and passive on the second, allowing rotation to survive the loss of either server. The Connector Management Agent, Identity Connector, and Dynamic Access Connector run on both servers.

The environment will be deployed in the two security landing zone subscriptions, CIP-PRD and CIP-DEV, beneath Landing Zones and Corp. Each environment will use a /27 subnet within the landing zone virtual network that already serves its subscription. No dedicated network will be built. No connector will have a public address. All traffic will transit Azure Firewall Premium in the Central US secured hub, where it is inspected and, where outbound, translated. This includes inbound administrator sessions, brokered sessions to migrated servers, directory authentication and log forwarding to the data centers over ExpressRoute, and outbound traffic to the CyberArk tenant. Administrative access to the operating systems will be provided through Azure Bastion only.

One firewall rule establishes the boundary that makes the parallel deployment pattern safe. The Azure connectors are denied brokered access to on-premises targets that have not yet migrated. Directory authentication and log forwarding to those same networks remain permitted, so the rule operates by service rather than by address. An application is served by only one connector estate at a time. The change that moves an application is a configuration change within the CyberArk platform, not a cutover of a running server.

The design is stateless. The connectors hold no database, application data, or persistent copy of any credential. Session recordings are uploaded to the tenant and are not stored locally. Recovery from the loss of a server, an availability zone, or the region is achieved through redeployment from the approved image and re-registration with the tenant rather than through restoration. This is also what keeps the migration low risk. Nothing is copied. Nothing is transformed. Reversing an application requires the same configuration change applied in the opposite direction.

## How to Read the Tables

Status in the Resource Table takes one of two values:

Net new: The object does not exist in any Azure export contained in the program source files, and this build creates it.

Pre-existing: The object exists and is evidenced in the program source files identified in the Evidence column.

Scope is stated in Parameters. Resource references R-01 to R-40 belong to this edition. PH-01 to PH-04 identify placeholder addresses. RE-01 to RE-07 identify values that exist in the estate or are supplied by a named owner. Input numbers refer to the Inputs Table.

The Parent column in the Resource Table identifies either the resource group of a built resource or the object that contains a platform, governance, or external item. Network attachment is stated in Parameters.

The production architecture drawing shows a single resource group, rg-sec-cyberark-prd, enclosing the network for readability. The build creates the workload objects in rg-sec-cyberark-prd and consumes the network and subnet from the platform resource group rg-alz-centralus-vnet-cip-cus-prd-01, as stated in the Placement and Resource Tables.

## Landing Zone Placement

This section records the subscription, resource groups, network, and subnet that contain the build. Platform objects are owned by the Cloud Platform Team and are consumed without modification.

Table 5-1: Landing Zone Placement

| Scope | Parent | Detail |
| --- | --- | --- |
| Connectivity, Central US | Platform | subscription f0bacc2a-12d2-4cd5-86f8-80d5a18fa89e · Virtual WAN az-c-vwan-p-01 · secured hub az-c-hub-01 · AzureFirewall_az-c-hub-01 · firewall policy DefaultFirewallPolicy · resource group vWAN-01 |
| Subscription CIP-PRD | GEHA › Landing Zones › Corp | 87c9e9d1-06a7-4b33-87e0-5f04bcbfbfae · Central US |
| Resource group rg-alz-centralus-vnet-cip-cus-prd-01 | CIP-PRD | Platform, owned by the Cloud Platform Team |
| Virtual network vnet-cip-cus-prd-01 | rg-alz-centralus-vnet-cip-cus-prd-01 | address space RE-01 · inside the Central US hub range 10.9.0.0/16 |
| Subnet snet-sec-cyberark-cus-prd-01 | vnet-cip-cus-prd-01 | /27 · 10.9.250.0/27 (PH-01) · created by the Cloud Platform Team network automation |
| Resource group rg-sec-cyberark-prd | CIP-PRD | Workload, owned by GEHA Security; application owner Eric Ullmann |

## Resources Build Table

One row is provided for each resource.

The subnet resides in the platform resource group rg-alz-centralus-vnet-cip-cus-prd-01 and is created by the Cloud Platform Team through its network automation, which connects the network to the hub. All other objects listed in the workload section are created in rg-sec-cyberark-prd from the GEHA Bicep module library through the Azure DevOps pipeline and are attached to the subnet.

| Ref | Resource name | Azure type | Parent | Parameters | Status | Evidence |
| --- | --- | --- | --- | --- | --- | --- |
| Production, net new |  |  |  |  |  |  |
| R-01 | rg-sec-cyberark-prd | Resource group | CIP-PRD | Central US / workload owned by GEHA Security, application owner Eric Ullmann / tags per the tag table | Net new | Not in the Azure exports |
| R-02 | snet-sec-cyberark-cus-prd-01 | Subnet | vnet-cip-cus-prd-01 in rg-alz-centralus-vnet-cip-cus-prd-01 | /27 · 10.9.250.0/27 (PH-01) / created by the Cloud Platform Team in the platform group / no network security group; the hub firewall is the control / no delegation, no service endpoints / route table by the platform | Net new | Not in the Azure exports |
| R-03 | lbi-sec-cyberark-cus-prd-01 | Load balancer, internal | rg-sec-cyberark-prd | front end in snet-sec-cyberark-cus-prd-01 / parameters per the load balancer table / front end 10.9.250.7 (PH-02), fourth usable address of the subnet / backend pool: both connector NICs | Net new | Not in the Azure exports |
| R-04 | nic-sec-cyberark-cus-prd-01 | Network interface | rg-sec-cyberark-prd | attached to snet-sec-cyberark-cus-prd-01 / static private IP 10.9.250.8 (PH-03), fifth usable / accelerated networking enabled / attached to vm-sec-cyberark-cus-prd-01 | Net new | Not in the Azure exports |
| R-05 | nic-sec-cyberark-cus-prd-02 | Network interface | rg-sec-cyberark-prd | attached to snet-sec-cyberark-cus-prd-01 / static private IP 10.9.250.9 (PH-04), sixth usable / accelerated networking enabled / attached to vm-sec-cyberark-cus-prd-02 | Net new | Not in the Azure exports |
| R-06 | vm-sec-cyberark-cus-prd-01 | Virtual machine | rg-sec-cyberark-prd | AZPASPCCPRD101 · zone 1 / Standard_D8ls_v5 · 8 vCPU · 16 GB / Windows Server 2025, CIS Level 2 image / PSM · CPM active / Connector Management agent / Identity Connector · DPA Connector | Net new | Not in the Azure exports |
| R-07 | vm-sec-cyberark-cus-prd-02 | Virtual machine | rg-sec-cyberark-prd | AZPASPCCPRD102 · zone 2 / Standard_D8ls_v5 · 8 vCPU · 16 GB / Windows Server 2025, CIS Level 2 image / PSM · CPM passive / Connector Management agent / Identity Connector · DPA Connector | Net new | Not in the Azure exports |
| R-08 | disk-sec-cyberark-cus-prd-01-os | Managed disk | rg-sec-cyberark-prd | 128 GB premium solid state / read-only host caching / attached to vm-sec-cyberark-cus-prd-01 | Net new | Not in the Azure exports |
| R-09 | disk-sec-cyberark-cus-prd-02-os | Managed disk | rg-sec-cyberark-prd | 128 GB premium solid state / read-only host caching / attached to vm-sec-cyberark-cus-prd-02 | Net new | Not in the Azure exports |
| R-10 | cyberark-prd.geha.com | DNS A record | geha.com zone | points to the load balancer front end 10.9.250.7 (PH-02) / created in the platform-owned geha.com zone by GEHA DNS | Net new | Not in the Azure exports |
| Platform, pre-existing and consumed |  |  |  |  |  |  |
| R-11 | AzureFirewall_az-c-hub-01 | Firewall | Connectivity, vWAN-01 | Premium / east-west inspection / egress translation / DefaultFirewallPolicy, rules per the firewall rule table / egress public address RE-04 | Pre-existing | Azure resource export, 25-Aug-2026 |
| R-12 | ExpressRoute circuits | ExpressRoute circuit | Connectivity | MegaPort-Chicago · North Central US / MegaPort-Dallas · South Central US / 2 circuits, 1 Gbps each | Pre-existing | Azure resource export, 25-Aug-2026 |
| R-13 | IP address groups | IP group | Connectivity, vwan-01 | IP_Group_Geha_Onprem_PrivIPs / IP_Group_Geha_Azure_PrivIPs / IP_Group_Zscaler_Clients / new groups per the IP group table | Pre-existing | Azure resource export, 25-Aug-2026 |
| R-14 | DNS private resolvers | DNS private resolver | Connectivity | pr-tio-ncus-01 / pr-tio-scus-01 / geha.com zone, platform owned / hybrid model: Azure resolves through the on-premises domain controllers | Pre-existing | Azure resource export, 25-Aug-2026 |
| R-15 | vnet-cip-cus-prd-01 | Virtual network | rg-alz-centralus-vnet-cip-cus-prd-01 | holds the production subnet / address space RE-01 / connected to az-c-hub-01 / holds the 2fauth and Veracore private endpoints | Pre-existing | Azure resource export, 25-Aug-2026 |
| Governance, pre-existing and applied automatically |  |  |  |  |  |  |
| R-16 | Corp landing zone denials | Policy assignment | alz-landingzones-corp | no public IP on a network interface / no workload gateway resource / no private DNS zone | Pre-existing | Policy assignment export |
| R-17 | Landing Zones controls | Policy assignment | Landing Zones | management port from the internet blocked / backup enrollment to a policy-created vault unless the exclusion tag is present, the tag table / Allowed locations at the GEHA management group | Pre-existing | Policy assignment export |
| R-18 | Diagnostic settings | Policy assignment | GEHA | applied by policy to every resource / Deploy-Resource-Diag | Pre-existing | Policy assignment export |
| R-19 | alz-log-analytics | Log Analytics workspace | rg-alz-logging, Management subscription | Central US / landing zone platform workspace / Defender for Cloud configuration deployed by policy | Pre-existing | Azure resource export, 25-Aug-2026; Policy assignment export |
| External endpoints and retained estate, pre-existing |  |  |  |  |  |  |
| R-20 | CyberArk vault | SaaS endpoint | Cloud service | session manager and password manager · TCP 1858 / vault host name from the tenant export (Input 5) / current address 54.82.114.164 | Pre-existing | Interface capture, Dec-2025 |
| R-21 | Privilege Cloud tenant | SaaS endpoint | Cloud service | identity, connector management and dynamic access services · TCP 443 / *.cyberark.cloud and the vendor domains in the firewall rule table | Pre-existing | Interface capture, Dec-2025 |
| R-22 | Connector management | SaaS endpoint | Cloud service | component lifecycle · TCP 443 / object storage, message broker and component registry endpoints, the firewall rule table | Pre-existing | Interface capture, Dec-2025 |
| R-23 | Account discovery | SaaS endpoint | Cloud service | account discovery scanner · TCP 443 / current address 54.243.179.151 | Pre-existing | Interface capture, Dec-2025 |
| R-24 | Active Directory | On-premises service | On premises | 6 domain controllers, LSDC01 to 04, LXDC03, LXDC04 / 10.100.10.8, .9, .10, .12 · 10.110.10.10, .12 / directory, Kerberos, DNS, domain membership, time | Pre-existing | VM inventory; Interface capture, Dec-2025 |
| R-25 | Splunk indexers | On-premises service | On premises | 4 indexers · TCP 9998 / 10.100.12.172, .173 · 10.110.12.172, .173 | Pre-existing | Interface capture, Dec-2025 |
| R-26 | Rapid7 Insight platform | SaaS endpoint | Cloud service | Rapid7 Insight agent and endpoint broker · TCP 443 / endpoint.ingress.rapid7.com · *.endpoint.ingress.rapid7.com · *.insight.rapid7.com | Pre-existing | Interface capture, Dec-2025 |
| R-27 | PASPCCPRD101 / PASPCCPRD102 | Retained server | On premises | 10.0.4.55 · 10.0.2.91 / Windows Server 2022 connectors / serve the unmigrated estate during the parallel run | Pre-existing | VM inventory |
| R-28 | Unmigrated target servers | Retained estate | On premises | served only by the on-premises connectors until their own wave | Pre-existing | VM inventory |
| R-29 | F5 BIG-IP pair | Retained appliance | On premises | lxabigipp01 · lsmbigipp01 / fronts the on-premises tier only / pas-rdp 3389: PASPCCPRD101, PASPCCPRD102, paspsmprd101 to 106 / pas-ssh 22: pasproxyprd101, 102, PASPROXYPRD201, 202 | Pre-existing | F5 configuration exports |
| R-30 | Corp landing zones | Target group | Landing zones | internal workloads · TCP 3389, 22 / a server enters when its platform is assigned to Azure-PSM-PRD | Pre-existing | Subscription export |
| R-31 | Online landing zones | Target group | Landing zones | internet-facing workloads | Pre-existing | Subscription export |
| R-32 | Credential provider tier | Retained tier | On premises | PASCCPPRD101 to 104 / remains on premises for its consumers; retires with them or at data center close / Input 19 | Pre-existing | VM inventory |
| R-33 | Secure shell proxy tier | Out of scope | Out of scope | PASPROXYPRD201, 202 / no disposition recorded / Input 19 | Pre-existing | VM inventory |
| R-34 | DMZ environment | Out of scope | Out of scope | no Azure network exists | Pre-existing | VM inventory |
| R-35 | Secure Tunnel | Out of scope | Out of scope | not installed by this build / the audit feed it carries today, PASPCCPRD101 to lssyslog01 on TCP 49550, is re-pointed before decommission, Input 18 | Pre-existing | Interface capture, Dec-2025 |
| R-36 | SCCM site server MECMSITEPRD101 | On-premises service | On premises | 10.0.1.185 · inbound TCP 135, 445, dynamic RPC / client installation and management / management point on this address (RE-06) | Pre-existing | VM inventory; Interface capture, Dec-2025 |
| R-37 | ServiceNow MID server SNMIDPRD301 | On-premises service | On premises | 10.0.1.226 · inbound TCP 135, dynamic / discovery / interim address (RE-07) | Pre-existing | VM inventory; Interface capture, Dec-2025 |
| R-38 | Splunk deployment server spldepprd101 | On-premises service | On premises | 10.100.12.145 · TCP 8089 / forwarder management | Pre-existing | Interface capture, Dec-2025 |
| R-39 | Remote desktop licensing server RDSLICPRD301 | On-premises service | On premises | 10.0.2.104 · TCP 135, 445, dynamic RPC / client access license issue | Pre-existing | VM inventory |
| R-40 | Cohesity backup service | SaaS service | Cloud service | agentless snapshots of the managed disks through Azure Resource Manager / no agent on the connectors / connection to the subscription per Input 25 | Pre-existing | Azure resource export, 25-Aug-2026 |

## Hub Firewall Rule Set

The hub firewall is the only network control applied to the connector subnet. No network security group is deployed. The GEHA landing-zone standard uses Azure Firewall in place of network security groups.

The rules are implemented in DefaultFirewallPolicy on AzureFirewall_az-c-hub-01 as a single rule collection group, rcg-sec-cyberark, through the GEHA firewall pipeline. Adding rules is a standard change requiring security approval.

Collection priorities are presented as an order. GEHA Network assigns the actual priority values within the policy. The deny collection is evaluated first.

Network rules that reference fully qualified domain names require DNS proxy to be enabled on the policy and do not support wildcards. The vault rule references the exact host name supplied in the tenant export. Application rules use the domains published by the vendors.

Load-balancer health probes originate from the Azure platform and do not traverse the firewall.

Traffic between subnets within vnet-cip-cus-prd-01 does not traverse the hub and is not filtered. The network contains the 2fauth and Veracore private endpoints and no other endpoints. No rule is created for this traffic (Input 20).

IP groups referenced by the firewall rules. New groups follow the existing IP_Group_ naming pattern.

Table 5-2: Hub Firewall Rule Set

| IP group | Status | Members | Source of the members |
| --- | --- | --- | --- |
| IP_Group_Geha_Onprem_PrivIPs | Pre-existing | On-premises private ranges, held in the firewall policy | GEHA Network |
| IP_Group_Geha_Azure_PrivIPs | Pre-existing | Azure private ranges, held in the firewall policy | GEHA Network |
| IP_Group_Zscaler_Clients | Pre-existing | Zscaler client source ranges, held in the firewall policy (RE-03) | GEHA Network |
| IP_Group_Geha_CyberArk_PRD | Net new | 10.9.250.0/27 (PH-01) | This build |
| IP_Group_Geha_CyberArk_LB | Net new | 10.9.250.7/32 (PH-02), the load balancer front end | This build |
| IP_Group_Geha_AVD_Clients | Net new | Prefixes of vnet-ds-entapps-avd-prd-01, -02, -03 and vnet-entapps-avd-prd-04 (RE-02) | Cloud Platform Team |
| IP_Group_Geha_Admin_Ranges | Net new | Administrative workstation ranges (RE-05) | GEHA Security |
| IP_Group_Geha_DomainControllers | Net new | 10.100.10.8/32, 10.100.10.9/32, 10.100.10.10/32, 10.100.10.12/32, 10.110.10.10/32, 10.110.10.12/32 | The domain controllers the current connectors use |
| IP_Group_Geha_Splunk | Net new | 10.100.12.172/32, 10.100.12.173/32, 10.110.12.172/32, 10.110.12.173/32, 10.100.12.145/32 | The Splunk indexers and deployment server the current connectors use |
| IP_Group_Geha_SCCM_MID | Net new | 10.0.1.185/32 (site server and management point), 10.0.1.226/32 (MID, interim); distribution point addresses (RE-06) | The SCCM site server and ServiceNow MID server that reach the current connectors |
| IP_Group_Geha_RDSLicensing | Net new | 10.0.2.104/32 | RDSLICPRD301 |

Table 5-3: Hub Firewall Rules, Production

| Collection | Type | Order | Rule | Source | Destination | Protocol and ports | Action | Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| net-cyberark-deny | Network | 1, first | deny-brokered-to-onprem | IP_Group_Geha_CyberArk_PRD | IP_Group_Geha_Onprem_PrivIPs | TCP 3389, 22 | Deny | Keeps the Azure connectors off unmigrated targets. Evaluated before every allow. |
| net-cyberark-inbound | Network | 2 | allow-session-from-clients | IP_Group_Geha_Onprem_PrivIPs; IP_Group_Geha_AVD_Clients; IP_Group_Zscaler_Clients | IP_Group_Geha_CyberArk_LB | TCP 3389 | Allow | Administrator sessions to the load balancer front end from on-premises workstations, AVD hosts and Zscaler private access. |
| net-cyberark-inbound | Network | 2 | allow-admin-rdp | IP_Group_Geha_Admin_Ranges | IP_Group_Geha_CyberArk_PRD | TCP 3389 | Allow | Operating system administration to the connector addresses. |
| net-cyberark-inbound | Network | 2 | allow-sccm-mid-inbound | IP_Group_Geha_SCCM_MID | IP_Group_Geha_CyberArk_PRD | TCP 135, 445, 49152-65535 | Allow | Client push, management and discovery. |
| net-cyberark-onprem | Network | 3 | allow-directory | IP_Group_Geha_CyberArk_PRD | IP_Group_Geha_DomainControllers | TCP 389, 636, 3268, 3269, 445, 135, 49152-65535; TCP and UDP 88, 464, 53; UDP 389, 123 | Allow | Directory, Kerberos, name resolution, domain membership, time. |
| net-cyberark-onprem | Network | 3 | allow-splunk | IP_Group_Geha_CyberArk_PRD | IP_Group_Geha_Splunk | TCP 9998, 8089 | Allow | Forwarder to indexers; management to the deployment server. |
| net-cyberark-onprem | Network | 3 | allow-sccm-client | IP_Group_Geha_CyberArk_PRD | IP_Group_Geha_SCCM_MID | TCP 80, 443, 10123 | Allow | Client to management point (80, 443, client notification 10123) and distribution point (80, 443), per the Microsoft port table. |
| net-cyberark-onprem | Network | 3 | allow-rds-licensing | IP_Group_Geha_CyberArk_PRD | IP_Group_Geha_RDSLicensing | TCP 135, 445, 49152-65535 | Allow | Client access license issue. |
| net-cyberark-azure | Network | 4 | allow-brokered-and-rotation | IP_Group_Geha_CyberArk_PRD | IP_Group_Geha_Azure_PrivIPs | TCP 3389, 22, 445, 1433 | Allow | Brokered sessions and credential rotation to migrated targets. |
| net-cyberark-vault | Network | 5 | allow-vault-1858 | IP_Group_Geha_CyberArk_PRD | FQDN: the vault host name from the tenant export, under *.cyberark.cloud | TCP 1858 | Allow | Exact host name, no wildcard; requires DNS proxy on the policy. |
| app-cyberark-cloud | Application | 6 | allow-cyberark-services | IP_Group_Geha_CyberArk_PRD | *.cyberark.cloud; *.idaptive.app; *.id.cyberark.cloud; *.idap.co; *.my.idaptive.app | https 443 | Allow | Tenant, identity and dynamic access services. |
| app-cyberark-cloud | Application | 6 | allow-connector-management | IP_Group_Geha_CyberArk_PRD | *-REGION.s3.amazonaws.com; *.REGION.amazonaws.com; component-registry-store-490081306957.s3.amazonaws.com; *.s3.REGION.amazonaws.com | https 443 | Allow | REGION is the AWS region token from the tenant export. Installation files, component registry, IoT communication, Dynamic Privileged Access binaries. |
| app-cyberark-cloud | Application | 6 | allow-revocation | IP_Group_Geha_CyberArk_PRD | ocsp.verisign.com; ocsp.globalsign.com; crl.globalsign.com; secure.globalsign.com; privacy-policy.truste.com; *.amazontrust.com; ocsp.digicert.com | http 80; https 443 | Allow | Certificate revocation, plain HTTP by design. |
| app-cyberark-cloud | Application | 6 | allow-rapid7 | IP_Group_Geha_CyberArk_PRD | endpoint.ingress.rapid7.com; *.endpoint.ingress.rapid7.com; *.insight.rapid7.com | https 443 | Allow | Insight agent and endpoint broker. The apex name is listed because a wildcard does not match it. |
| app-cyberark-platform | Application | 7 | allow-windows-update; allow-defender; allow-monitor | IP_Group_Geha_CyberArk_PRD | FQDN tag WindowsUpdate; Microsoft Defender for Endpoint and Azure Monitor endpoints as published by Microsoft | https 443; http 80 | Allow | Written unless GEHA Network confirms that DefaultFirewallPolicy already covers these endpoints for corporate virtual machines (Input 11). |

## Internal Load Balancer Parameters

The load balancer distributes traffic by hash and uses no session persistence. The 30-second probe interval follows the CyberArk load-balancer example.

An Azure HTTPS probe accepts only HTTP status code 200. Therefore, the PSM health check operates in CodeBased mode, which returns HTTP 503 when the server is unhealthy.

The probes originate from the Azure platform and do not require a corresponding firewall rule.

Table 5-4: Internal Load Balancer Parameters

| Parameter | Value |
| --- | --- |
| SKU and tier | Standard, Regional |
| Front end | lbi-sec-cyberark-cus-prd-01-fe · private · static · 10.9.250.7 (PH-02), fourth usable address of the subnet · zone-redundant |
| Backend pool | lbi-sec-cyberark-cus-prd-01-pool · nic-sec-cyberark-cus-prd-01, nic-sec-cyberark-cus-prd-02 |
| Probe 1 | probe-rdp · TCP · port 3389 · interval 30 s · unhealthy threshold 3 |
| Probe 2 | probe-psm-health · HTTPS · port 443 · path /psm/api/health · interval 30 s · unhealthy threshold 3 · PSM health check mode CodeBased |
| Rule | rule-rdp · TCP · front end 3389 to backend 3389 · probes: both · session persistence None · idle timeout 20 minutes · TCP reset enabled · floating IP disabled · HA ports disabled |
| Outbound | None. An internal load balancer provides no outbound path; egress leaves through the hub firewall. |
| Diagnostics | Applied by Deploy-Resource-Diag to the platform workspace. |

## Host Configuration

Unless otherwise stated, the configuration applies to both connector servers.

The installation sequence follows the CyberArk prerequisite order.

Table 5-5: Host Configuration

| Item | Value |
| --- | --- |
| Image | The GEHA CIS Level 2 Windows Server 2025 image, deployed by the Bicep module through the ADO pipeline. CyberArk lists Windows Server 2025 as a supported connector operating system for both PSM and CPM. Bicep module and repository: Input 4. ADO pipelines: Don Maraski. |
| Hardening | One policy. The CyberArk Privilege Cloud Connector Unified Hardening GPO, downloaded from the CyberArk Marketplace, imported into Active Directory and linked to the connector organizational unit by GEHA Identity before install step 4, is the only hardening policy deployed to the connectors. The CIS Level 2 image supplies the operating system baseline; no CIS baseline policy is applied in addition. The connector installer does not apply hardening itself. Customizations to the CyberArk GPO, including any GEHA groups added to it, are re-applied after every connector upgrade. CyberArk publishes no position on its GPO over a CIS Level 2 image; the combination is proven in non-production first (Input 21). |
| Endpoint protection | Agent per GEHA Security (Input 22): CrowdStrike Falcon is the GEHA endpoint platform of record; the Microsoft Defender for Endpoint agent is deployed to Azure virtual machines by policy. Per CyberArk, third-party antivirus and threat protection agents are disabled while the connector components are installed or upgraded and re-enabled afterwards with CyberArk's exclusions applied. |
| Computer names | AZPASPCCPRD101, AZPASPCCPRD102. |
| Domain | GEHA.com, joined over ExpressRoute against the six domain controllers in the IP group table. |
| Organizational unit | The connector organizational unit in the application configuration table (Input 16). |
| Local administrators | The group named in the application configuration table (Input 16) and the installation account. |
| Session manager accounts | The PSMConnect and PSMAdminConnect pair for each connector, per the application configuration table; created before install step 4. |
| Remote Desktop Services | Session Host role installed. License server RDSLICPRD301, set by domain policy where the policy scope covers the connectors and locally on each host otherwise (Input 17). Client access license scheme per GEHA licensing. |
| Network level authentication | Disabled for the connector installation, as the CyberArk connector requirements state. Enabling it afterwards follows the CyberArk NLA procedure and is GEHA Security's decision (Input 9). |
| Web server | IIS role and the ASP.NET Core Runtime 8.0 hosting bundle, required by the PSM health check. Site binding HTTPS on 443 with a certificate per the GEHA certificate standard. |
| CyberArk components, install order | 1 domain join into the connector organizational unit; the CyberArk hardening GPO applies through the unit, the only hardening policy over the CIS Level 2 image. 2 RDS role and license server pointer. 3 IIS and hosting bundle. 4 Privilege Cloud connector installer through Connector Management, which installs the CPM before the PSM: both on each connector; CPM active on 01, passive on 02. 5 PSM health check component. 6 Connector Management agent, then Identity Connector and DPA Connector from the tenant. 7 Splunk universal forwarder, registered with spldepprd101. 8 Endpoint protection agent enabled with CyberArk exclusions; monitoring agents as carried by the image. |
| Not installed | Secure Tunnel. Credential provider. PSM for SSH. Cohesity agent; backup is agentless. |
| Time | Domain hierarchy, UDP 123 to the domain controllers. |
| Backup exclusion tag | Key and value per Input 3. Applied in the deployment template so the enrollment policy does not bind at create time. |
| Tenant objects | Session manager farm Azure-PSM-PRD and password manager AZ-CPM-PRD-01, per the application configuration table. |

## Application Configuration

This section records the directory objects, tenant objects, and backup arrangements required by the connectors.

The Value column identifies the configuration that the build creates or consumes. The Basis column identifies the vendor requirement or program source. The Supplied By column identifies the input that provides the GEHA value when the value is not present in the program files.

The configuration export agreed with GEHA Security on 4 August 2026 (Input 23) provides the account names, service identities, and directory groups referenced in this section.

Table 5-6: Application Configuration

| Item | Value | Basis | Supplied by |
| --- | --- | --- | --- |
| Active Directory objects |  |  |  |
| Organizational unit | A dedicated organizational unit for the Azure connectors, holding AZPASPCCPRD101 and AZPASPCCPRD102, with the CyberArk hardening GPO linked to it and no other hardening policy. Placed under the unit that holds the on-premises connectors where GEHA keeps them in one tree. | CyberArk requires the connector servers under a dedicated organizational unit so that its GPO applies to them. The on-premises connector unit is not recorded in the program files. | Input 16 |
| Computer objects | AZPASPCCPRD101 and AZPASPCCPRD102, created by the domain join in install step 1 and moved into the connector unit before the installer runs. | Host configuration install order. | None |
| Session manager accounts | Four domain accounts: PSMConnect and PSMAdminConnect for connector 01 and a second pair for connector 02, named to the GEHA service account convention. Pre-Windows 2000 logon name under 20 characters; password never expires; Log On To restricted to the two connectors; each pair a member of Remote Desktop Users on its own connector only; Allow log on through Remote Desktop Services restricted to the two accounts and the maintenance administrators. Created before install step 4; passwords managed by the password manager after install. | CyberArk requires domain users where the RDS licence is per user or sessions run past one hour, and recommends a separate pair of applicative users per PSM server for redundancy. The on-premises names and the GEHA convention are not in the program files. | Input 23 |
| Installation account | A domain account with full local administrator rights on both connectors, used for the installation only. The administrator signs in to Connector Management with a CyberArk Identity user in the System Administrator or Connector Management Admin role, and the installer authenticates with the Installeruser service user from Identity Administration, Users, Service Users. | CyberArk connector installation through Connector Management: local administrator with full rights, a domain user for in-domain deployments; Installeruser is the built-in Identity Administration user for installing on-premises components. | GEHA CyberArk administration |
| Component services | The PSM, CPM and Connector Management services run under the identities the CyberArk installer and hardening set; this build creates no service account for them. | The configuration export records the service accounts in use on premises; the build changes none of them. | Input 23 |
| Security groups |  |  |  |
| Local Administrators | The GEHA server administration group of the server standard, plus the installation account. Any GEHA group added to the CyberArk GPO is recorded, because the addition is re-applied after every connector upgrade. | GEHA server standard not in the program files. CyberArk: groups and user objects added to its GPO are re-applied after upgrade. | Input 16 |
| Remote Desktop Users | On each connector its own PSMConnect and PSMAdminConnect pair and no other member. Operating system administration is by the local Administrators group from IP_Group_Geha_Admin_Ranges. | CyberArk domain user requirements; firewall rule allow-admin-rdp. | None |
| Groups configured for the connectors | The directory groups configured for the on-premises connectors, from the configuration export, reused for the Azure unit. No new group is created unless the export shows none. | Tracker, discovery session 4 August 2026, item C-11: groups configured for the connector are in the agreed export. Not in the program files. | Input 23 |
| Tenant roles | Unchanged. Roles and safe membership are held in the Privilege Cloud tenant and mapped to GEHA directory groups through the Identity Connector; the Azure connectors join the existing tenant. The safe and role model export is the record. | Inferred from the tenant model: the connectors hold no credential or role data (tracker, 21 July 2026). Test: the export shows no connector-specific role. | Input 23 |
| Tenant objects |  |  |  |
| Session manager farm | Azure-PSM-PRD, the session manager both connectors register under. Platforms of migrated servers are assigned to it at their wave; platforms of unmigrated servers stay on the on-premises session manager. | CyberArk: session manager assignment is per platform. | None |
| Password manager | AZ-CPM-PRD-01, active on connector 01. The passive installation on connector 02 is started for recovery only. Safes of migrated servers are reassigned to it at their wave. | CyberArk: password manager assignment is per safe; a passive password manager is a manual recovery instance. | Input 7 |
| Allowlist entry | The hub firewall egress address (RE-04) in the tenant IP allowlist before the first connector registers. | CyberArk allowlist requirement, Input 10. | Input 10 |
| Backup |  |  |  |
| Platform | Cohesity, agentless snapshots of the two managed disks through Azure Resource Manager. No agent on the connectors. Azure Backup enrollment is excluded by the tag in the host configuration table. | Cohesity is the GEHA backup platform (discovery session 5 December 2025); the LS-Cohesity01 and LX-Cohesity01 archive containers exist in the Azure estate (tag export); Cohesity SaaS is the confirmed LiteSpeed replacement (tracker). | None |
| Protection policy | The 8-week policy the on-premises connector carries: daily snapshot retained 8 weeks locally and at the remote site, monthly copy retained 3 years in Azure Blob. The Azure policy mirrors the on-premises policy, as GEHA stated in discovery. | PASPCCPRD102 carries 8WK Backup in the VM inventory; the inventory records no policy for PASPCCPRD101. Reading 8WK Backup as the daily eight-week retention GEHA described on 5 December 2025 is an inference that the Cohesity policy export confirms (Input 25). The 3-year retention awaits GEHA compliance sign-off (tracker action, GEHA Legal). | Input 25 |
| Scope and recovery | Operating system disk of each connector. The connectors hold no credential data. A failed connector is restored from its latest snapshot or rebuilt from the image and re-registered with the tenant, whichever is faster; the other connector carries sessions meanwhile. | Tracker, 21 July 2026: all CyberArk credential data resides in the cloud vaults. Recovery order is the design position. | Input 25 |
| Backup exclusion tag | Per the host configuration table; key and value per Input 3. | Landing Zones enrollment assignment (policy assignment export). | Input 3 |

## Operations

This section describes how the connectors are changed, patched, upgraded, monitored, and operated after deployment.

The arrangements are derived from the GEHA change process, the GEHA operational tooling on record, and the CyberArk upgrade procedure. Schedule-related values are provided as inputs.

Table 5-7: Operations

| Item | Arrangement | Basis |
| --- | --- | --- |
| Change control |  |  |
| Change window | Production changes go through CAB: submit by end of business Friday, review Wednesday, deploy after Wednesday. Maintenance windows are Thursday evening or weekends, with exceptions by arrangement; expedited changes on 48 hours' notice; emergency changes are break-fix only. The rule collection group in the firewall rule table is a standard change with security approval and deploys in business hours. The build touches production in three other places, each under the change process of that system: the DNS record cyberark-prd.geha.com (R-10), the tenant allowlist entry (Input 10) and the registration of the two connectors in the production tenant. | GEHA firewall migration minutes, 9 July 2026, sections 4.10 and 4.11. |
| Change freezes | Open Season 28 September to 15 December; Thanksgiving 23 November to 1 December; year-end 14 December to 5 January. The freezes bind cutovers in the wave plan; whether they bind the firewall change is confirmed with GEHA Network at CAB submission. | Wave plan tracker, 10 September 2026. GEHA PMO owes the full list of freeze windows (tracker action, open). |
| Patching |  |  |
| Windows updates | MECM, through the client installed by push from MECMSITEPRD101 over the firewall rules. The connectors form a maintenance window collection of their own so the two hosts patch on different nights: connector 02 first, connector 01 the following night. Monthly, in the CAB maintenance window. | GEHA patches servers with SCCM and Intune (cloud platform discovery session, 25 November 2025). A monthly Windows update cadence is recorded for the SQL estate only (SQL inventory questionnaire). Collection and schedule: Input 24. |
| Order and effect | One connector at a time. Sessions on the connector being patched end at its reboot; new sessions go to the other connector through the load balancer probes. A reboot of connector 01 pauses password rotation for its duration; the passive password manager on connector 02 is not started for patching. | Load balancer probes. CyberArk: a passive password manager is a manual recovery instance. |
| Session manager and password manager upgrades | Started by GEHA CyberArk administration in Connector Management when a version is offered; these two components are not upgraded automatically. Order per CyberArk: update the hardening GPO from the Marketplace, disable the endpoint protection agent, upgrade the password manager and session manager, restart the connector, re-enable the agent, re-apply GPO customizations. Downtime is a few minutes per connector; one connector at a time, in the maintenance window. | CyberArk: upgrade the Privilege Cloud connector using Connector Management; upgrade connector components. |
| Agent automatic upgrades | The Management Agent upgrades itself: on by default for new environments, in the SLA service maintenance window, starting only when the connector is idle; the window can be set to a custom schedule or the automatic upgrade opted out. The Identity Connector updates itself by default, with a schedulable time window. Both windows are set to the CAB maintenance window, or opted out, per Input 26. | CyberArk: Management Agent automatic upgrade; manage the Identity Connector. |
| Operating |  |  |
| Monitoring | Splunk universal forwarder to the on-premises indexers over the firewall rules; Splunk is the monitoring and alerting tool for Azure. Resource diagnostics go to the platform workspace by policy. | Cloud platform discovery session, 25 November 2025; Deploy-Resource-Diag (policy assignment export). |
| Certificates | The HTTPS binding certificate on each connector, used by the session manager health probe, is issued and renewed under the GEHA certificate standard and tracked in Venafi. The load balancer probe requires a SHA-256 chain and Microsoft documents no expiry check, so renewal is a tracked date, not a probe-detected failure. | Load balancer table; Microsoft load balancer health probe documentation. Venafi Trust Protection Platform manages GEHA TLS certificates (tracker). |

## Tags

Tags are applied to every resource created by the deployment template.

The keys listed in this section are currently used within the GEHA Azure estate, which does not enforce a single tag schema. This build is the first workload to carry the complete tag set.

Table 5-8: Tags

| Key | Value | Basis |
| --- | --- | --- |
| Environment | prd | Environment key values prd and dev are in use in the estate and match the resource names. |
| Owner | Security@geha.com | Owner values Security and Security@geha.com are in use. |
| ApplicationName | CyberArk PAS | Key in use; value per the GEHA application inventory. |
| Migrate Project | Datacenter-Transformation | Key and value in use for this program. |
| DataClassification | Confidential | CyberArk data classification in the application register. |
| BusinessUnit | Input 16, GEHA Security | Precedent values EISD, IT, Shared. |
| CostCenter | Input 16, GEHA Security | Precedent values 1006, 1073. |
| Criticality | Input 16, GEHA Security | Precedent values Critical, High, Business unit-critical, low. |
| DR | Essential | Values Essential and na are in use. Disaster recovery for the production pair is a separate edition. |
| Backup exclusion tag | Input 3, Cloud Platform Team | The tag the Landing Zones enrollment assignment tests for; not present in the tag export. |
| Key | Value | Basis |

## Inputs from GEHA

The build can be completed only after the inputs listed in this section are provided.

Each input identifies the owning team and the tables it affects. Address-related inputs are tracked in the Address Register. All other outcomes are recorded in the Program Decision Register.

Table 5-9: Inputs from GEHA

| # | Input | Applies to | Owner |
| --- | --- | --- | --- |
| 1 | Address space of vnet-cip-cus-prd-01 (RE-01) and the allocated subnet prefix. The placeholder subnet deploys as written when the address space contains it; otherwise the Cloud Platform Team adds the /27 as a second address prefix or allocates the prefix and the register is updated. | The placement table; R-02 to R-05, R-10; the IP group table; the load balancer table | Cloud Platform Team |
| 2 | Zonal availability of Standard_D8ls_v5 and the physical zone mapping of subscription CIP-PRD, both read from the subscription: az vm list-skus --location centralus --size Standard_D8ls_v5 --zone (a Restrictions value closes a zone to the subscription) and az account list-locations --query "[?availabilityZoneMappings]". Microsoft sells the size in Central US and publishes no per-zone list; the logical-to-physical mapping is assigned per subscription and differs between subscriptions | R-06, R-07 | Cloud Platform Team |
| 3 | Backup exclusion tag key and value, read from the parameters of the Landing Zones assignment "Configure backup on virtual machines without a given tag to a new recovery services vault with a default policy" | R-17; the host configuration, application configuration and tag tables | Cloud Platform Team |
| 4 | Bicep module and repository for the virtual machine, load balancer and network interface deployments, and the pipeline that runs them | The host configuration table | Cloud Platform Team |
| 5 | Tenant configuration export: tenant subdomain, vault host name, AWS region token and tenant type. The firewall rules are written for a Privilege Cloud tenant on CyberArk Shared Services (*.cyberark.cloud); a Standard tenant uses *.privilegecloud.cyberark.com. | The firewall rule table; R-20 to R-23 | GEHA CyberArk administration |
| 6 | Peak concurrent sessions and number of managed passwords, to confirm Standard_D8ls_v5 against the CyberArk sizing tiers | R-06, R-07 | GEHA CyberArk administration |
| 7 | Password manager placement: active on connector 01, passive on connector 02 | R-06, R-07; the host configuration table | GEHA Security |
| 8 | Load balancing: the Azure load balancer distributes by hash; CyberArk recommends least-connections routing and routing live session monitoring to the server that holds the session | The load balancer table | GEHA Security |
| 9 | Network Level Authentication: disabled for installation per CyberArk; enabled afterwards only on GEHA Security's decision | The host configuration table | GEHA Security |
| 10 | Hub firewall outbound public address, Central US (RE-04), entered in the Privilege Cloud IP allowlist. CyberArk requires the allowlist for the PSM and CPM to communicate with the tenant; it is set in the tenant at Setup › Settings › Advanced Settings › IP allowlist, holds 200 entries, and accepts ranges from /22 to /32 | R-11; tenant allowlist | GEHA Network; GEHA CyberArk administration |
| 11 | Whether DefaultFirewallPolicy already carries Windows Update, Defender for Endpoint and Azure Monitor rules for corporate virtual machines; the app-cyberark-platform collection is written unless it does | The firewall rule table | GEHA Network |
| 12 | Administrative workstation ranges (RE-05) | IP_Group_Geha_Admin_Ranges | GEHA Security |
| 13 | AVD network prefixes (RE-02), and confirmation that Zscaler private access sessions to Azure originate from members of IP_Group_Zscaler_Clients (RE-03) | IP_Group_Geha_AVD_Clients; allow-session-from-clients | Cloud Platform Team; GEHA Network |
| 14 | SCCM distribution point addresses (RE-06) and the client installation ports the site server uses | IP_Group_Geha_SCCM_MID | GEHA SCCM owner |
| 15 | ServiceNow MID server address (RE-07) once the Azure MID servers exist; 10.0.1.226 is interim | IP_Group_Geha_SCCM_MID; R-37 | ServiceNow MID owner |
| 16 | Organizational unit, local administrators group, and the BusinessUnit, CostCenter and Criticality tag values | the host configuration, application configuration and tag tables | GEHA Identity; GEHA Security |
| 17 | Remote Desktop licensing server policy scope | The host configuration table | GEHA Identity |
| 18 | Audit feed target in place of the Secure Tunnel feed to lssyslog01 | R-35 | GEHA Security |
| 19 | Confirmation that the credential provider tier remains on premises for its consumers and retires with them or at data center close, and the owner of that retirement; disposition of the PSM SSH proxy servers | R-32, R-33 | GEHA Security |
| 20 | Acceptance of unfiltered traffic between subnets inside vnet-cip-cus-prd-01, or a network security group on the connector subnet as defence in depth | R-02; the firewall rule table | GEHA Network; GEHA Security |
| 21 | Proof that the CyberArk connector hardening GPO, applied as the only hardening policy to a non-production connector built from the CIS Level 2 Windows Server 2025 image, passes the CyberArk connector prerequisite check and a brokered session test | The host configuration table; R-06, R-07 | GEHA Security; CHC build team |
| 22 | Endpoint protection agent on the connectors: CrowdStrike Falcon, the Microsoft Defender for Endpoint agent deployed by policy, or both, with CyberArk's exclusions and the install-time disable and re-enable step | The host configuration table | GEHA Security |
| 23 | Configuration export agreed on 4 August 2026 (tracker item C-11): component versions, tenant URL, safe and role model, directory groups configured for the connectors, and service accounts. It supplies the account names, service identities and groups in the application configuration table | The application configuration table | GEHA CyberArk administration; Eric Ullmann |
| 24 | MECM maintenance window collection and deployment schedule for the two connectors, and confirmation that Azure clients register with MECMSITEPRD101 over ExpressRoute | The operations table | GEHA Cloud Services, MECM owner |
| 25 | Cohesity protection policy for the Azure connectors: policy name, retention, the Cohesity connection to subscription CIP-PRD, and whether Cohesity SaaS connectors are deployed in the subscription for it | The application configuration table; R-40 | Cohesity owner Matthew Lathrom; Dale Gibson |
| 26 | Automatic upgrade settings for the Management Agent and the Identity Connector on the Azure connectors: opt in or out, and the time window, aligned with the CAB maintenance window | The operations table | GEHA CyberArk administration |

## Migration Strategy

This section documents the migration approach for each major CyberArk PAS component. It identifies the target service and the planned disposition of each component as part of the migration program.

This is a build rather than a move. There is no cutover of a running server and no data transfer. A target server joins the Azure estate when its platform is assigned to the Azure session manager group; the rotation engine assignment follows once its placement is confirmed by GEHA Security. The production connectors are replicated to East US 2 by Azure Site Recovery for disaster recovery.

## Landing Zone Placement

This section records the target landing-zone placement, subscription assignments, governance controls, and access model for the CyberArk PAS deployment in Azure.

Table 5-11: Landing Zone Placement

| Field | Production | Non-production |
| --- | --- | --- |
| Management Group | GEHA › Landing Zones › Corp | GEHA › Landing Zones › Corp |
| Subscription Name and ID | CIP-PRD 87c9e9d1-06a7-4b33-87e0-5f04bcbfbfae | CIP-DEV e657afbe-61e4-4a5f-b6cb-cfbba50fd3a6 |
| Resource Groups | rg-sec-cyberark-prd. Workload lifecycle, created for this deployment. rg-alz-centralus-vnet-cip-cus-prd-01. Platform lifecycle, holds the network. | rg-sec-cyberark-dev. Workload lifecycle, created for this deployment. rg-alz-centralus-vnet-cip-cus-dev-01. Platform lifecycle, holds the network. |
| Primary Region | Central US | Central US |
| Paired Region | None. The connectors hold no state and are rebuilt rather than recovered. | As production |
| Naming Standard | Security workload resource groups follow rg-sec-workload-environment. Virtual networks and subnets follow the platform convention for the region and environment. | As production |
| Tagging | Environment, Owner, ApplicationName, Migrate Project, DataClassification, BusinessUnit, CostCenter, Criticality, DR and the backup exclusion tag, applied at deployment by the Bicep module per the CyberArk PAS Azure Tag Plan v1.0. | As production |
| Inherited Policy Assignments | Corp scope: public IP on a network interface denied; workload gateway resources denied; private DNS zone creation denied; public network access disabled for platform services. Landing Zones scope: management port access from the internet blocked. GEHA management group: Allowed locations; Azure Compute Security Baseline compliance auditing. | As production |
| Policy Exemptions | Proposed: two exemptions against the compute security baseline, scoped to the connector servers, covering the two operating system settings the product requires at 5.3. Raising them is a build step; no exemption exists today. | As production |
| Role-Based Access Control | The workload team operates within rg-sec-cyberark-prd. Network, subnet and private endpoint provisioning remain with Cloud and Platform Services. Role assignment and privileged identity management remain with Security. | As production. |

## Compute

The connector servers are deployed from the approved GEHA Windows Server image through the Bicep module library. Operating system version and edition, hardening, security type, boot configuration, the installed agent set, endpoint protection and the patching mechanism are carried by that image. The table below records the values specific to this workload.

Table 5-12: Compute

| Field | Production | Non-production |
| --- | --- | --- |
| Source Image | The approved GEHA Windows Server image, deployed by Bicep module. | As production |
| Virtual Machine Size | Standard_D8ls_v5, 8 virtual processors and 16 GB memory. Two servers. | Standard_D8ls_v5, 8 virtual processors and 16 GB memory. Two servers. |
| Sizing Basis | Eight processors is the CyberArk small tier for the session manager and matches the current connector allocation. Observed utilization on the current connectors is 3.75 to 6 per cent processor and 66 to 68 per cent memory at the ninety-fifth percentile against 8 GB; memory is doubled accordingly. | As production |
| Availability Design | Availability zones. One server in zone 1, one in zone 2. The physical zone behind each logical number is recorded in the build record. | As production |
| Disk Configuration | Operating system disk only, 128 GB premium solid state. No data disk. Session recordings are uploaded to the tenant and are not retained on the connector. | As production |
| Operating System Configuration | The Remote Desktop Services role is enabled; the session manager runs on it. Network level authentication is disabled on the session manager listener, as the product requires. The listener is reachable only through the internal load balancer from the on-premises client ranges. Both settings are covered by the proposed exemptions at 5.2. | As production |
| Client Access Licensing | Remote Desktop Services client access licenses are required for the session host role; the scheme and source are with GEHA licensing. The session manager service accounts are created as domain accounts, which the vendor requirements call for on Server 2022. The license server route is recorded in the flow document. | As production |
| Agents and Extensions | Monitoring, endpoint security, log forwarding and domain join are carried by the approved image. The CyberArk components are installed by the vendor connector installer following deployment. | As production |
| Proximity and Latency | No co-location requirement. The two servers are deliberately separated across zones; session brokering tolerates inter-zone latency; a connection stays on one node for its life under the five tuple hash. | As production |
| Scheduling | No scheduled shutdown. The connectors must be reachable whenever a privileged session is requested. | No scheduled shutdown, on the same basis |
| Scaling | Fixed size, two servers per environment. A further connector is added by deploying an additional server from the same image into the same subnet and joining it to the farm; the subnet is sized to accommodate this. | As production |

## Data Platform

Not applicable.

The connectors hold no database and no persistent application data. Credentials, safes, policies, audit records and session recordings are held in the CyberArk Privilege Cloud tenant. A connector that fails is redeployed and re-registered; there is nothing to restore.

## Storage and File Services

Not applicable.

No file share, object storage or attached data volume is required. The only storage is the operating system disk recorded at 5.3 and the managed storage account used for boot diagnostics. Session recordings transit the connector and are written to the tenant.

## Network

This section records the target-state network design, including connectivity, routing, load balancing, security controls, and supporting network services.

Table 5-13: Network

| Field | Production | Non-production |
| --- | --- | --- |
| Virtual Network | vnet-cip-cus-prd-01, in rg-alz-centralus-vnet-cip-cus-prd-01. | vnet-cip-cus-dev-01, in rg-alz-centralus-vnet-cip-cus-dev-01 |
| Subnet | snet-sec-cyberark-cus-prd-01, a /27 within the landing zone address space, allocated by Cloud and Platform Services. | snet-sec-cyberark-cus-dev-01, a /27 within the landing zone address space, allocated by Cloud and Platform Services |
| IP Addressing | Static on all three addresses. The load balancer front end takes the fourth usable address in the subnet, connector 01 the fifth and connector 02 the sixth. Three of twenty-seven usable addresses are consumed. | As production |
| Connectivity to On-Premises | ExpressRoute. Two redundant circuits at 1 Gbps each, per the landing zone record of 01-Jul-2026, attached to the virtual wide area network; the hub each lands on is not an exported object. | As production |
| Hub Attachment | Both landing zone networks attach to the virtual wide-area network hub. No workload peering is created. | As production |
| Network Security Group | nsg-sec-cyberark-cus-prd-01, associated to the subnet. Inbound: TCP 3389 from the on-premises client and administrative ranges, since the load balancer preserves the client address; the platform probe tag on both probe ports; TCP 135, 445 and the dynamic range from the SCCM site server and the ServiceNow MID server. Outbound: as permitted by the hub firewall rule set. | nsg-sec-cyberark-cus-dev-01, on the same terms |
| Routing | No user-defined route. Egress is directed through the hub firewall by the platform route. | As production |
| Firewall and Egress Control | Azure Firewall in the Central US secured hub performs east-west inspection and outbound translation. Eight rules govern this workload: administrator session inbound; connector to Azure target; connector to the CyberArk tenant; connector to directory services; connector to the log platform; connector to endpoint security; site server and discovery inbound; and a deny on brokered sessions from the Azure connectors to on-premises targets that have not yet migrated. | As production |
| Private Endpoints and Private DNS | None required. No platform service is consumed privately by this workload. | As production |
| Load Balancing | lbi-sec-cyberark-cus-prd-01, standard internal, no public address. Distribution is by the platform default five tuple hash and no session persistence is configured. The vendor requires persistence only where automatic session reconnection is enabled, and that feature is off unless turned on; this build leaves it off. Two health probes are configured, both taken from the vendor worked example: a transport check on TCP 3389 and a service check against the session manager health endpoint, each at a thirty second interval with an unhealthy threshold of three, the Azure form of the vendor values. Idle timeout twelve hundred seconds. TCP reset on idle enabled. The backend pool contains both connector interfaces. | lbi-sec-cyberark-cus-dev-01, on the same terms |
| Web Application Firewall | Not applicable. No web application is published by this workload. | As production |
| DNS Records | cyberark-prd.geha.com, an A record resolving to the load balancer front end, placed in the geha.com zone by the platform team. Azure networks resolve through the on-premises domain controllers. | cyberark-dev.geha.com, on the same terms |
| Certificates | The session manager health endpoint requires a web server binding with a certificate on each connector; its issuer follows the GEHA certificate standard and is set at build. The connectors validate the tenant certificate outbound. | As production |

## Identity and Access

This section records the identity, authentication, authorization, and privileged-access requirements for the target-state environment.

Table 5-14: Identity and Access

| Field | Production | Non-production |
| --- | --- | --- |
| Directory Model | On-premises Active Directory Domain Services, reached over ExpressRoute. Six domain controllers across the two data centers. The connectors bind domain services directly. | As production |
| Application Authentication | Unchanged. Administrators authenticate to the CyberArk platform, which brokers the session. No new authentication method is introduced. | As production |
| Group-to-Role Mapping | Unchanged. The Active Directory groups governing platform access are not affected by the connector build; access is granted at the platform, not at the connector. | As production |
| Azure Role Assignments | Proposed. Workload team: Contributor within rg-sec-cyberark-prd. Platform team: Network Contributor at the network resource group. Security team: role assignment and privileged identity management at subscription scope. No standing Owner assignment. | As production |
| Managed Identities | As required by the approved image and the platform agents. The CyberArk service accounts are not replaced by managed identities; the product authenticates to its own tenant. | As production |
| Service Accounts | The existing connector service accounts are reused rather than replaced, so safe permissions and audit history remain continuous. Credential custody, rotation owner and rotation interval are unchanged. | As production |
| Secrets and Certificate Storage | No workload secret is stored in Azure. The connector holds its registration credential locally as the product requires; all other credentials are held in the CyberArk vault. | As production |
| Privileged Access | Administrative access to the connector operating system is by remote desktop from the GEHA administrative address ranges to the connector private address, over ExpressRoute. The network security group on the connector subnet permits those ranges and denies all other inbound management traffic. No connector holds a public address, and management port access from the internet is blocked by policy. Elevation follows the existing privileged identity management model. | As production |
| Break-Glass Access | Per the landing zone standard; break glass exclusions sit in the conditional access policy list per the landing zone record of 01-Jul-2026. No workload-specific break-glass account is created. | As production |
| Programmatic Access Paths | The identity connector binds the directory for the platform. The dynamic access connector is carried forward with its existing target inventory and policies. | As production |

## Security and Compliance

This section records the security controls, monitoring requirements, compliance considerations, and operational security standards applicable to the target-state deployment.

Table 5-15: Security and Compliance

| Field | Production | Non-production |
| --- | --- | --- |
| Cloud Security Posture | Microsoft Defender for Cloud, applied at the tenant root. | As production |
| Endpoint Protection | Carried by the approved image. Reports outbound on TCP 443 through the hub firewall. | As production |
| Encryption at Rest | Platform-managed keys. The connectors hold no persistent, sensitive data. | As production |
| Encryption in Transit | All traffic is encrypted in transit: session brokering on TCP 3389, tenant traffic on TCP 443, vault protocol on TCP 1858 and directory traffic over the standard signed channels. | As production |
| Security Log Collection | Operating system and application logs are forwarded to the four log platform indexers on TCP 9998, with forwarder management on TCP 8089 to the Splunk deployment server. The program log platform target is Datadog forwarded to Exabeam, per the SIEM and IAM discovery record of 10-Jul-2026; the connector forwarding destination follows that program decision and is open item O-07 in the design. The tenant audit feed that reaches the GEHA syslog collector through the on-premises Secure Tunnel today is re-pointed before decommission, open item O-18. Platform diagnostics are collected to the platform workspace by policy. Session recordings are held in the CyberArk tenant. | As production |
| Vulnerability Management | Carried by the approved image, under the existing scanning cadence, remediation ownership and remediation window by severity. | As production |
| Patching | Carried by the approved image and the platform update mechanism. Maintenance is staggered so that a patch never takes both servers in an environment at once. | As production |
| Compliance | Data residency within the continental United States. The regional policy assignment restricts deployment to approved United States regions and the design lands in Central US. Compute, disks, diagnostics and the log platform are all within the United States. | As production |

## Resilience and Recovery

This section records the availability, backup, disaster-recovery, and recovery requirements for the target-state environment.

Figure 5-2: Disaster Recovery Environment

Table 5-16: Resilience and Recovery

| Field | Production | Non-production |
| --- | --- | --- |
| Backup | Backup is provided by Cohesity, the GEHA enterprise backup service, by agentless snapshots of the managed disks; no agent is installed. The connector servers carry the backup exclusion tag from deployment so that the native Azure enrollment policy does not bind them. The only Recovery Services vault is the Site Recovery vault in East US 2, which holds replication and no backup items. | As production |
| Recovery Method | Redeployment from the approved image and re-registration with the tenant. The connectors hold no state, so recovery is a rebuild rather than a restore. | As production |
| Recovery Objectives | Recovery time is bounded by redeployment and re-registration. A single server failure carries no recovery objective, as the surviving server continues to serve. No recovery point objective applies; no state is held on the connector. | As production |
| Availability Commitment | Two servers across two availability zones behind a zone-redundant internal load balancer. Loss of a single zone removes one server and sessions continue on the survivor. | As production |
| Disaster Recovery Design | Azure Site Recovery replication of both production connectors from Central US to East US 2 (Recovery Services vault rsv-sec-cyberark-eus2-dr-01 *, recovery plan rp-sec-cyberark-prd-01 *, replica disks only until failover). At failover the replicas start in East US 2 zones 1 and 2 with the same host names, join the DR load balancer lbi-sec-cyberark-eus2-dr-01 *, and GEHA DNS re-points cyberark-prd.geha.com. The DR virtual network reaches the East US hub by cross-region connection, pending confirmation by GEHA Network. Failback and the full procedure are in the Rollback Plan v1.0. | Not replicated. Non-production is rebuilt from the pipeline. |
| Disaster Recovery Test | Connector loss and zone loss at build validation (test plan cases D-04 and D-05); replication status, a test failover into an isolated East US 2 network, replica start and registration, DR load balancer, DNS re-point rehearsal, tenant allowlist and cleanup on test day 4 (cases G-01 to G-09); failback rehearsed at the first annual GEHA DR exercise. | As production |

## Monitoring and Operations

This section records the monitoring, alerting, logging, and operational-management requirements for the target-state solution.

Table 5-17: Monitoring and Operations

| Field | Production | Non-production |
| --- | --- | --- |
| Log Analytics Workspace | The platform workspace. No workload workspace is created. | As production |
| Diagnostic Settings | Applied automatically to every resource by policy assignment. | As production |
| Platform and Guest Metrics | Platform metrics by default. Guest metrics through the monitoring agent carried by the approved image. | As production |
| Alert Rules | Proposed. Six workload alerts in addition to the platform standard: connector unreachable; session manager service stopped; credential rotation engine stopped; connector management agent unregistered; load balancer probe failure on both servers; operating system disk above eighty-five per cent. | As production, at a lower severity on each. |
| Action Groups and Routing | Proposed: the existing platform action group and its escalation path. | As production |
| Application Monitoring | Connector health and component status are reported in the CyberArk tenant, which is the authoritative view of whether a connector is serving. | As production |
| Dashboards and Reporting | Connector status is read from the CyberArk tenant; platform health from the standard Azure workbooks. No workload dashboard is required. | As production |
| Update Management | Carried by the approved image and the platform update mechanism, against the staggered maintenance at 5.8. | As production |

## Cost and Licensing

This section records the cost, licensing, and financial considerations associated with the target-state deployment.

Table 5-18: Cost and Licensing

| Field | Production | Non-production |
| --- | --- | --- |
| Cost Model | Run cost for the connector estate is carried in the program cost model against the sizes at 5.3 and Central US pricing. It is not restated here. | As production |
| Cost Profile During Migration | Both estates run in parallel until the final wave, so the program carries the on-premises connectors and the Azure connectors concurrently. The reduction is realized at decommission. | As production |
| Reservations and Commitments | None. The workload runs at on-demand pricing until it reaches steady state and the estate has stopped growing. | As production |
| Windows Licensing | Azure Hybrid Benefit applicability is open item O-08 in the design, with GEHA licensing. | As production |
| Remote Desktop Services Licensing | Client access licenses for the session host role; scheme and source with GEHA licensing. | As production |
| Cost Controls | No scheduled shutdown applies. The connectors must be reachable whenever a privileged session is requested. | As production |
| Attribution | Cost is attributed by the tags applied at 5.2, with a budget and threshold alerts set at deployment. | As production |

## Deployment Method

This section records the deployment approach, tooling, configuration-management practices, and release processes used for the target-state solution.

Table 5-19: Deployment Method

| Field | Production | Non-production |
| --- | --- | --- |
| Deployment Approach | Infrastructure as code. The servers are deployed from the approved GEHA Windows Server image through the Bicep module library and the existing release pipeline. | As production |
| Tooling and Repository | Bicep modules from the vetted GEHA module library, deployed through Azure DevOps pipelines. | As production |
| Pipeline and Approvals | The existing release pipeline and its approval gates. Production change control follows the GEHA standard. | The existing release pipeline and its approval gates. |
| Environment Parity | Both environments are deployed from the same image and one parameterized module. They differ only in subscription, network, name tokens and alert severity. | As production |
| Configuration Drift | Pipeline redeployment corrects infrastructure drift. Operating system drift is answered by redeployment from the approved image rather than in-place remediation. Connector component versions are managed from the CyberArk tenant by the connector management agent. | As production |
| State and Secret Handling | Deployment state and pipeline secrets are held in Azure Key Vault, the GEHA standard for secrets per the landing zone record of 01-Jul-2026, under the existing access model. Service principals are used for pipeline authentication. | As production |

# Post-Migration Test and Validation Plan

Summary

This section provides a high-level overview of the purpose, scope, execution approach, and key validation objectives of the post-migration test and validation plan.

What We Are Testing

Two new CyberArk Privilege Cloud connectors in Azure, sitting behind an internal load balancer at cyberark-prd.geha.com. Nothing is being moved or switched off. The on-premises connectors continue serving every server that has not migrated, and the vault, portal, and discovery components remain in the CyberArk tenant exactly as they are today. This creates a parallel-run model, and the test plan is designed to demonstrate that both estates can coexist safely.

How the Test Is Organized

Seven groups are executed across four days. Day 1 confirms that the Azure build matches the build parameters (Group A), every network path opens and every deny path refuses (Group B), and both connectors register cleanly in the tenant alongside the on-premises pair (Group C). Days 2 and 3 execute real sessions through the Azure connectors, distribute them across both servers, and remove one server to validate failover (Group D). Day 3 also validates the controls that keep the two estates separated (Group E) and confirms that backup, alerting, and patching services recognize the new servers (Group F). Day 4 validates replication to East US 2 and confirms that the connectors can be started during a test failover (Group G).

The Two Tests That Matter Most

Group E is the key validation point. It moves an account so that an Azure connector is instructed to reach a server that has not migrated. The expected result is a refusal logged at the hub firewall. If the session reaches the target, testing stops and no cutover request proceeds until the rule is corrected and the test case is rerun successfully.

The second critical validation is the failover pair in Group D: stop the session manager on one connector, remove an entire availability zone, and confirm that users continue operating through the surviving connector without interruption.

How a Case Passes

Every test case identifies the execution steps, responsible role, evidence to capture, and expected result. A case passes only when the required evidence is present in the evidence repository and matches the expected outcome. Any activity without supporting evidence is recorded as not run and never as passed. The evidence pack is submitted to GEHA Security and Enterprise Architecture for acceptance before the CAB agenda request.

Who Is Involved

A CitiusTech build engineer runs the build and network test cases and assembles the evidence pack. The GEHA CyberArk administrator owns tenant configuration and validation activities. The GEHA Cloud Platform Team owns the firewall policy and provides addressing information. A GEHA test user executes the test sessions. Service owners for Splunk, SCCM, ServiceNow, RDS Licensing, Cohesity, Rapid7, and DNS confirm that their services can detect and support the new servers.

The estimated effort is approximately 12.6 hours across Days 1 through 3 and approximately 3.8 hours on Day 4, excluding configuration-refresh waits, CPM cycles, and initial replication.

Cutover and Rollback

Cutover is a tenant configuration change rather than an infrastructure change. The first production platform is pointed to the Azure group, one session is executed in each direction, and both groups are confirmed active. If any validation fails, the platform is pointed back to the on-premises group and the same checks are repeated.

Rollback takes less than 30 minutes, and no system is taken out of service. The rollback decision belongs to Phil Costanzo, GEHA's Admin and Support Manager for CyberArk. Cutover approval is provided jointly by Security, Enterprise Architecture, and CAB. The companion Rollback Plan contains the complete rollback procedure.

Open Items

Four items remain outside the scope of this test cycle and are tracked in the program decision register with an owner and target date: rotation-engine placement, Secure Tunnel audit-feed re-pointing, credential-provider decommissioning, and a direct monitoring route if live session monitoring cannot pass through the load balancer.

Disaster recovery introduces one additional open item: how the tenant handles a replica that starts with the same name as its production connector, which Day 4 testing is designed to determine.

Workflow at a Glance

Figure 6-1: Post-Migration Test and Validation workflow

Validation workflow: roles as lanes, phases as columns, gates G0 to G9 on the phase boundaries, decision points along the bottom, and the evidence store every case feeds. Appendix A describes the same workflow in table form.

## Purpose and Scope

This plan validates the two new Privilege Cloud connector servers built in the CIP-PRD subscription, vm-sec-cyberark-cus-prd-01 and vm-sec-cyberark-cus-prd-02 (computer names AZPASPCCPRD101 and AZPASPCCPRD102), behind the internal load balancer cyberark-prd.geha.com, and their recovery in East US 2. The deployment follows a parallel model: the on-premises connectors, PASPCCPRD101 and PASPCCPRD102, continue serving on-premises servers, while the vault, portal, and account discovery remain unchanged within the Privilege Cloud tenant.

Sessions are routed to a connector group by platform. The Azure connector pair is registered in the tenant as a single Configured PSM Server whose address is the load balancer name, and a platform sends its accounts to that group by carrying the group ID. A migrated server is served by the Azure group when its account resides on a platform that carries the Azure ID, while unmigrated servers remain on platforms that carry the on-premises ID.

The plan validates five key outcomes in sequence: that the Azure estate is built as specified (Group A), that its network paths function correctly (Group B), that both connectors are registered in the tenant alongside the on-premises pair (Group C), that a migrated server can be brokered through the Azure group with failover across both zones (Group D), and that the two estates remain isolated from one another (Group E). Group F validates that the platform services responsible for operating the servers can recognize and manage them. Group G validates that the connectors replicate to East US 2 and can be started during a test-failover scenario.

Non-production is validated using the same test cases and procedures, using the corresponding development environment names, after production testing is completed. Performance testing under production load and the ServiceNow change record are outside the scope of this plan. Open items are documented using descriptive names, while ownership and target dates are maintained within the program decision register.

## Roles

Table 6-1: Roles Used in the Case Tables

| Code | Role | Responsibility |
| --- | --- | --- |
| BE | Build engineer | CitiusTech. Deploys and configures the Azure resources, the connector software and the Site Recovery objects; captures build evidence. |
| CA | CyberArk administrator | GEHA Security. Owns the Privilege Cloud tenant configuration: Configured PSM Servers, platforms, safes, accounts, tenant allowlist. |
| CP | Cloud Platform Team | GEHA. Supplies subnet and address values; owns the hub firewall policy, the landing zone networks and the East US 2 landing zone. |
| TU | Test user | A GEHA privileged user working from the administrative ranges, with membership of the test safes. |
| SO | Service owner | GEHA owner of the platform service under test (Splunk, SCCM, ServiceNow, RDS licensing, Cohesity, Rapid7, DNS). |
| SR | Security and EA reviewers | GEHA Security and Enterprise Architecture. Accept the evidence pack at the presentation. |

## Entry criteria

Testing starts when every row below is true. Each row names who confirms it. E-11 applies to day 4 only.

Table 6-2: Entry Criteria

| Ref | Criterion | Detail |
| --- | --- | --- |
| E-01 | Build complete | Every Built row of Azure Build Parameters Table 2 exists; the values in Table 8 have been supplied by the Cloud Platform Team and applied. |
| E-02 | Domain and service accounts | Both connectors joined to GEHA.com; PSMConnect and PSMAdminConnect exist as domain accounts and are used by the PSM services. |
| E-03 | Network rules | Rule collection group rcg-sec-cyberark applied to DefaultFirewallPolicy; the NSG rule set applied to nsg-sec-cyberark-cus-prd-01; IP groups created. |
| E-04 | Connector software | Connector Management, Identity Connector, Privileged Session Manager and the dynamic access connector installed on both servers in that order, both at the same PSM version; each server restarted after the PSM install; PSM hardening run in the In Domain mode. The rotation engine is installed only once GEHA Security has confirmed its placement. |
| E-05 | Installer ownership | The account used for the second PSM install is not a direct owner of the PSMUnmanagedSessionAccounts safe. |
| E-06 | Certificates | Each connector holds a certificate from GEHA internal PKI whose subject alternative names include the server name and cyberark-prd.geha.com, bound to the PSM listener. |
| E-07 | Tenant configuration | Configured PSM Servers holds an entry for the Azure group, created by copying an existing entry so that PSMProtocolVersion is retained, with ID equal to the Azure group name and Address cyberark-prd.geha.com. A test platform cloned from the production Windows platform, and one from the Linux platform, carry the Azure group ID under UI and Workflows, Privileged Session Management. |
| E-08 | Test targets | One migrated Windows server and one migrated Linux server in the Corp landing zone, each with an account onboarded to a test safe on the matching test platform. One unmigrated on-premises server with an account on a production platform that carries the on-premises group ID. |
| E-09 | Test users | One test user with the Use Accounts and List Accounts permissions on the test safes and Initiate CPM account management operations; one reviewer with Monitor and View Audit permissions. |
| E-10 | Evidence store | A folder under the program workspace for this test cycle, one subfolder per case, receiving screenshots, exports and logs as each case closes. |
| E-11 | Disaster recovery ready | Replication enabled on both connectors at least one day before day 4 and both replicated items Protected; the East US 2 landing zone, DR subnet, NSG and load balancer built per Azure Build Parameters Table 2; the recovery plan created; an isolated test-failover virtual network in East US 2 provided by the Cloud Platform Team. |

## Test cases

Each case lists the steps in order, the evidence to capture, the expected result, the role that runs it and an estimated duration. A case passes only when the evidence is in the evidence store and matches the expected result. Durations are for one environment and exclude waiting on external teams.

### Group A: Platform Build Verification

Day 1, morning. Proves the Azure estate exists as specified before any connector test runs. All cases are read only.

Table 6-3: Group A: 12 cases, about 2.3 hours of execution

| Ref | Case | Steps | Evidence | Expected result | Role | Min |
| --- | --- | --- | --- | --- | --- | --- |
| A-01 | Resource inventory | - Run az resource list for rg-sec-cyberark-prd and export to CSV. - Compare each row with Azure Build Parameters Table 2, Built rows. - Record any resource present but not in Table 2. | CSV export; marked-up copy of Table 2 | Every Built row present with the name, type, SKU, zone and location in Table 2; no extra resources | BE | 20 |
| A-02 | Network placement | - Run az network nic show for nic-sec-cyberark-cus-prd-01 and 02. - Confirm the subnet reference and the private address of each. - Run az network vnet subnet show for snet-sec-cyberark-cus-prd-01 and confirm the NSG association. | Command output for both NICs and the subnet | Both NICs in snet-sec-cyberark-cus-prd-01 with the addresses from Table 8; nsg-sec-cyberark-cus-prd-01 associated with the subnet | BE | 15 |
| A-03 | Load balancer configuration | - Open lbi-sec-cyberark-cus-prd-01 in the portal. - Record the front end address, backend pool members, load balancing rule and both health probes. | Portal screenshots of each blade | Front end at the Table 8 address; both NICs in the pool; TCP 3389 rule with five tuple hash and no session persistence; probes on TCP 3389 and HTTPS 443, interval 30 seconds, unhealthy threshold 3 | BE | 15 |
| A-04 | Policy compliance | - Open Azure Policy, Compliance, filter to rg-sec-cyberark-prd. - Export the compliance state. | Compliance export | No non-compliant resource against the Corp landing zone assignments | BE | 10 |
| A-05 | Diagnostic settings | - Open Diagnostic settings on the load balancer, the NSG and both virtual machines. - Record the destination workspace. | Screenshots | Diagnostic settings present on all four resources and sent to the platform workspace named in the design | BE | 10 |
| A-06 | Domain membership and time | - On each connector run nltest /dsgetdc:geha.com and w32tm /query /status. - Run whoami /upn as the build engineer. | Command output | Secure channel to a GEHA.com domain controller; time source is a domain controller; offset under five minutes | BE | 10 |
| A-07 | PSM service accounts and NLA | - Open Services on each connector and record the logon account of the CyberArk Privileged Session Manager service. - Open System Properties, Remote, and record the Network Level Authentication setting. | Screenshots | Service runs as the GEHA.com PSMConnect account; Network Level Authentication disabled on both servers | BE | 10 |
| A-08 | Hardening applied | - Open Local Security Policy, AppLocker, and confirm rules exist for executables and DLLs. - Read the RDS SecurityLayer and MinEncryptionLevel registry values. - Confirm SMB1 is disabled (Get-WindowsOptionalFeature). | Screenshots and command output | AppLocker rules present; SecurityLayer and MinEncryptionLevel set by the hardening; SMB1 disabled | BE | 15 |
| A-09 | Probe health after hardening | - After A-08, open the load balancer backend pool health. - If a probe reads unhealthy, inspect the Windows firewall rule added by hardening for 168.63.129.16. | Screenshot of backend health | Both servers Healthy on both probes. If the hardening rule blocks inbound probes from 168.63.129.16, add an inbound exception and record the change against the build | BE | 10 |
| A-10 | Health endpoint | - From a client in the subnet, request https://CONNECTOR/psm/api/health on each server, substituting the connector name. - Request the same path through cyberark-prd.geha.com. | Response captures | HTTP 200 from each server and through the load balancer name | BE | 10 |
| A-11 | Certificate binding | - In IIS on each connector open the site binding for 443 and export the certificate details. - From a client in the administrative ranges, browse to https://cyberark-prd.geha.com/psm/api/health and inspect the certificate. | Certificate details and browser capture | Subject alternative names include the server name and cyberark-prd.geha.com; issuer is GEHA internal PKI; chain trusted; not expired | BE | 10 |
| A-12 | Tags | - Run az resource list with tag output for rg-sec-cyberark-prd. | Export | Every resource carries the keys and values in Azure Build Parameters Table 7 | BE | 5 |
| A-13 | Endpoint protection | - On each connector record the endpoint protection agent installed, its state and its last check-in with the console. 2. Confirm the CyberArk exclusions are applied. 3. Confirm the agent was re-enabled after the connector install. | Screenshots; console record | The agent GEHA Security named under build tables input 22 is installed and enabled on both with the CyberArk exclusions; both servers present in its console | BE, SO | 15 |

### Group B: Network Path Verification

Day 1, afternoon. One case per path in Network Data Flows Table 2.1. Run from each connector unless the step says otherwise.

Table 6-4: Group B: 10 cases, about 2.4 hours of execution

| Ref | Case | Steps | Evidence | Expected result | Role | Min |
| --- | --- | --- | --- | --- | --- | --- |
| B-01 | Vault protocol | - On each connector run Test-NetConnection VAULTHOST -Port 1858, substituting the vault host from the tenant export. - Pull the hub firewall log entry for the connection. | Command output; firewall log line | TcpTestSucceeded True on both; the log shows allow-vault-1858 matched on the exact host name | BE, NW | 10 |
| B-02 | Tenant and connector management services | - On each connector run Test-NetConnection on port 443 to one host in each FQDN set in Azure Build Parameters Table 3. - Run the same test to a host not in any set (for example a public news site). 3. Run the revocation host tests on port 80. | Command output for every host | Every listed host succeeds; the unlisted host is refused; the firewall log shows the application rule matched for each success | BE, NW | 20 |
| B-03 | Rapid7 agent | - On each connector confirm the Insight agent service is running. - In the Insight console locate both servers and record the last check in. | Service screenshot; console screenshot | Both servers registered; last check in within 15 minutes; allow-rapid7 matched in the log | BE, SO | 10 |
| B-04 | Domain controllers | - On each connector run klist purge, then klist get krbtgt. - Run nslookup geha.com and nslookup of the vault host. - Run w32tm /resync. | Command output | Ticket granting ticket issued; DNS answers from a GEHA.com domain controller; time resync succeeds; allow-directory matched | BE | 10 |
| B-05 | Splunk forwarding | - On each connector run splunk list forward-server. - In Splunk search index=* host=CONNECTOR earliest=-15m. - In the deployment server console confirm both servers appear. | Command output; search results; console screenshot | Forwarder connected to an indexer on 9998; events from both servers present; both listed under spldepprd101 on 8089 | BE, SO | 15 |
| B-06 | MECM client | - Push the client from MECMSITEPRD101 to both connectors. - In the SCCM console open the device record for each. - On each connector open Configuration Manager in Control Panel and run Machine Policy Retrieval. | Console screenshots; client log extract | Client installed over allow-sccm-mid-inbound; device record active with a management point assignment; policy retrieval and client notification succeed over allow-sccm-client; both devices in the connector maintenance window collection | SO | 30 |
| B-07 | ServiceNow discovery | - Run a discovery schedule from SNMIDPRD301 that includes the connector subnet. - Open the resulting CI records. | Discovery status; CI screenshots | A CI exists for each connector with the correct name, addresses and operating system | SO | 20 |
| B-08 | Remote desktop licensing | - On each connector run Get-RDLicenseConfiguration. - Open Event Viewer, TerminalServices-Licensing, after the first brokered session in D-01. | Command output; event log extract | RDSLICPRD301 listed as the license server; a client access license issued on first session over allow-rds-licensing | BE, SO | 10 |
| B-09 | Administrator entry | - From a workstation in the GEHA administrative ranges, RDP to cyberark-prd.geha.com and to each connector name. - From an on-premises workstation outside those ranges, repeat. | Connection results | Succeeds from the administrative ranges (allow-admin-rdp); refused from outside them, with the firewall log showing no matching rule | TU, NW | 15 |
| B-10 | Session path from each client group | - RDP to cyberark-prd.geha.com from an on-premises workstation, from an Azure Virtual Desktop session host and from a Zscaler private access client. - GEHA Network pulls the log line for each. | Connection results; firewall log lines | All three reach the load balancer front end; each log line shows allow-session-from-clients matched with the expected source group | TU, NW | 20 |
| B-11 | Inbound from another landing zone network | - From a server in a landing zone network other than vnet-cip-cus-prd-01, run Test-NetConnection CONNECTOR -Port 3389. - From a server in another subnet of vnet-cip-cus-prd-01, repeat and record the result. | Command output | Refused from the other network, with no matching rule in the log. The result from inside vnet-cip-cus-prd-01 is recorded as is; traffic inside the network is not filtered (build tables input 20) | BE, NW | 10 |
| B-12 | Platform endpoints | - On each connector run Test-NetConnection on port 443 to a Windows Update host, a Defender for Endpoint host and an Azure Monitor host as published by Microsoft. | Command output | All succeed, through app-cyberark-platform or the existing policy rules GEHA Network named under Input 11 | BE, NW | 10 |

### Group C: Tenant Registration

Day 1, end of day. The vendor verification steps for a new connector, applied to both servers.

Table 6-5: Group C: 6 cases, about 0.8 hours of execution.

| Ref | Case | Steps | Evidence | Expected result | Role | Min |
| --- | --- | --- | --- | --- | --- | --- |
| C-01 | Connector Management status | - In the Privilege Cloud portal open Connector Management, Connectors. - Select the row for each Azure connector and open the component list. - Record the status of every component and its version. - Repeat for PASPCCPRD101 and PASPCCPRD102. | Screenshots of each component list | Every component on both Azure connectors shows an active status with no failed component; both on-premises connectors unchanged | CA | 15 |
| C-02 | System health | - Open the system health dashboard in the portal. - Record the entries for both Azure connectors. | Screenshot | Both Azure connectors present and healthy | CA | 5 |
| C-03 | Identity Connector | - On each connector open the Identity Connector Configuration program, Status tab. - Record the last connection time and result, and the auto-update setting and window. | Screenshots | Last connection recent and successful on both; both registered under the same customer ID; auto-update set as GEHA decided under Input 26 | CA | 10 |
| C-04 | Session manager service and farm entry | - On each connector confirm the CyberArk Privileged Session Manager service is running. - In the portal open Configured PSM Servers and record the Azure-PSM-PRD entry and the on-premises entry. | Screenshots | Service running on both; the Azure entry shows ID Azure-PSM-PRD, Address cyberark-prd.geha.com and the PSM credential object; the on-premises entry unchanged | CA | 10 |
| C-05 | Dynamic access connector | - In the portal open the dynamic access connector pool and record both connectors. | Screenshot | Both connectors registered and online in the designed pool | CA | 5 |
| C-06 | Password manager | - In Connector Management record the password manager component on each Azure connector and its state. - In the portal confirm AZ-CPM-PRD-01 is listed. | Screenshots | Component present on both; running on connector 01 as AZ-CPM-PRD-01; installed and not started on connector 02 (the passive instance). If GEHA Security rules otherwise under Input 7, the recorded state is the ruled one | CA | 10 |
| C-07 | Management Agent upgrade window | - In Connector Management open the automatic upgrade setting for the Management Agent and record whether it is on, and the window. | Screenshot | Set as GEHA decided under Input 26: the CAB maintenance window, or opted out | CA | 5 |

### Group D: Brokered Sessions to Migrated Targets

Days 2 and 3. Proves the Azure group serves a migrated server end to end, distributes across both connectors and survives the loss of one.

Table 6-6: Group D: 10 cases, about 3.8 hours of execution

| Ref | Case | Steps | Evidence | Expected result | Role | Min |
| --- | --- | --- | --- | --- | --- | --- |
| D-01 | RDP session through the Azure farm | - Test user signs in to the portal from the administrative ranges. - Opens the Windows test account (test platform carrying the Azure group ID) and clicks Connect. - Runs one command on the target that leaves a trace (for example creates a file). - Ends the session. - Reviewer opens the session in Monitoring and records the PSM server name. | Session record with PSM server name; recording; target evidence | Session brokered by AZPASPCCPRD101 or 102 over allow-brokered-and-rotation; recording complete and playable; the trace exists on the target | TU, CA | 20 |
| D-02 | SSH session through the Azure farm | - As D-01 with the Linux test account. | As D-01 | As D-01 on TCP 22 | TU, CA | 15 |
| D-03 | Distribution across connectors | - Open ten sessions in succession to the Windows test target, closing each before the next. - Record the PSM server for each session. | Session list export | Sessions land on both connectors; no run of sessions pinned to one server. The distribution is by hash; the result is recorded against Input 8 | TU, CA | 30 |
| D-04 | Connector failure | - Stop the CyberArk Privileged Session Manager service on connector 01. - Note the time; watch the load balancer backend health. - Open three sessions. - Start the service; watch backend health return. | Timestamps; backend health screenshots; session records | Connector 01 marked unhealthy within 90 seconds through probe-psm-health; all three sessions brokered by 02 with no user error; 01 returns to Healthy after restart | BE, TU | 30 |
| D-05 | Zone loss | - Deallocate vm-sec-cyberark-cus-prd-01 (zone 1). - Repeat D-01 and D-06. 3. Start the virtual machine and confirm C-01 status returns. | Portal screenshots; session record | Sessions continue on connector 02; recordings retrievable; 01 rejoins with all components active | BE, TU, CA | 40 |
| D-06 | Recording retrieval | - Reviewer retrieves the D-01 and D-02 recordings from the portal and plays each to the end. | Playback screenshots | Both recordings complete, with the session end visible | CA | 10 |
| D-07 | Live session monitoring | - Test user opens a session as in D-01 and keeps it open. - Reviewer opens live monitoring of that session from the portal. - Record whether monitoring connects and to which server. | Screenshots | Monitoring connects to the connector running the session. If it fails, record it against Input 8: CyberArk routes live monitoring to the server that holds the session, which the hash-distributed load balancer cannot guarantee | TU, CA | 20 |
| D-08 | Concurrent sessions | - Five test users, or one user with five accounts, open sessions in parallel to the test targets and hold them for ten minutes. - Record CPU and memory on both connectors from Azure Monitor. | Session list; metrics charts | All sessions brokered; CPU and memory within headroom for Standard_D8ls_v5, recorded against Input 6 | TU, BE | 30 |
| D-09 | Password manager verification | - In the portal open the Windows test account, Overview, Last Verified, and click Verify. - Wait one CPM cycle. - Record the compliance status and which CPM performed the verification. | Screenshots | Account verified by AZ-CPM-PRD-01 from connector 01 over allow-brokered-and-rotation | CA | 25 |
| D-10 | Account discovery | - Run a discovery that includes the migrated test target. - Confirm the target is found. | Discovery results | Target discovered through the tenant scanner; no dependency on the Azure connectors | CA | 15 |

### Group E: Parallel Run and Separation

Day 3. The controls that make the parallel run safe: the on-premises estate is unchanged, and no session can cross from the Azure group to an unmigrated server.

Table 6-7: Group E: 5 cases, About 2 hours of Execution

| Ref | Case | Steps | Evidence | Expected result | Role | Min |
| --- | --- | --- | --- | --- | --- | --- |
| E-01 | On-premises estate unchanged | - Test user opens a session to the unmigrated test target (account on a production platform carrying the on-premises group ID). - Reviewer records the PSM server. | Session record | Brokered by PASPCCPRD101 or 102; recording playable | TU, CA | 15 |
| E-02 | No session from Azure to an unmigrated server | - CyberArk administrator moves the unmigrated target account to the test platform carrying the Azure group ID. - Wait one configuration refresh (ConfigurationRefreshInterval, default 600 seconds). - Test user attempts a session. - Administrator moves the account back and waits one refresh. - Repeat E-01. | Session attempt result; firewall log; E-01 repeat record | The attempt fails to reach the target; the hub firewall log shows the deny (no rule from the connector subnet to on-premises server ranges); E-01 succeeds again after the move back | CA, TU, CP | 40 |
| E-03 | Platform re-point rehearsal | - Move the migrated Windows test account from the test platform (Azure ID) to a platform carrying the on-premises ID. - Wait one refresh; open a session; record the PSM server. - Move it back; wait one refresh; open a session; record the PSM server. | Two session records; account property export before and after | Sessions follow the platform on the next connection; no account property lost | CA, TU | 40 |
| E-04 | Secure Tunnel and audit feed unaffected | - On PASPCCPRD101 confirm the Secure Tunnel service is running. - In the SIEM confirm audit events from the tenant are still arriving. | Service screenshot; SIEM search | Running; events arriving. The re-point of this feed is a separate item and is not part of this test | CA, SO | 10 |
| E-05 | Credential provider consumers | - Pull the IIS logs from the four PASCCP hosts for the test window. - Filter for source addresses in the migrated test target set. | Log extract | No requests from any migrated test target | CA | 15 |

### Group F: Operations Evidence

Day 3. Confirms the platform services that run the servers after cutover see them.

Table 6-8: Group F: 3 cases, About 1.3 Hours of Execution

| Ref | Case | Steps | Evidence | Expected result | Role | Min |
| --- | --- | --- | --- | --- | --- | --- |
| F-01 | Backup protection and restore | - In the Cohesity console open the protection status of both virtual machines. - Confirm a snapshot completed after build. - Restore one disk to an isolated resource group, or schedule the restore and record the date. | Console screenshots; restore job record | Both protected by the policy confirmed under Input 25 (the 8-week policy of the on-premises connector); snapshot present; restore succeeds or is scheduled; no Azure Backup enrollment | SO | 30 |
| F-02 | Alerting | - Stop the PSM service on one connector for two minutes. - Record the alert received and its route. | Alert record | The Splunk alert the Splunk owner configured for the connectors fires and reaches the named route | BE, SO | 15 |
| F-03 | Patching | - Deploy one approved update to both connectors through MECM in the connector maintenance window collection, connector 02 first and connector 01 the following night. - Confirm installation and reboot of each. - Confirm sessions continued on the other connector during each reboot. | MECM deployment status; session records | Installed on both; reboots completed one at a time; C-01 status active afterwards; no session interruption on the connector not being patched | SO, TU | 40 |
| F-04 | Agent upgrade windows | - Record the Management Agent automatic upgrade setting and window (C-07) and the Identity Connector auto-update window (C-03) against the CAB maintenance window. | Screenshots | Both set as GEHA decided under Input 26; neither can start outside the agreed window unless opted out | CA | 10 |

### Group G: Disaster Recovery

Day 4, after day 3 closes and before hypercare exit. Proves the connectors replicate to East US 2 and start there. The test failover uses an isolated virtual network so that production, the DR subnet and the tenant registration of the production pair are untouched; G-09 proves production is unaffected while it runs.

Table 6-9: Group G: 9 cases, About 3.8 Hours of Execution, Plus the Initial Replication Before Day 4

| Ref | Case | Steps | Evidence | Expected result | Role | Min |
| --- | --- | --- | --- | --- | --- | --- |
| G-01 | Replication status | - In the portal open the Recovery Services vault, Replicated items, and record both connectors with status, RPO and last recovery point. - Record the time from enable replication to Protected. | Screenshots; timing note | Both items Protected; RPO within the replication policy; recovery points present for both | BE, CP | 15 |
| G-02 | Replication paths | - On each connector run Test-NetConnection on port 443 to the cache storage account blob endpoint, to login.microsoftonline.com and to the Site Recovery service host for the vault region. | Command output | All succeed on both connectors (NSG rules 210 to 240 and the allow-site-recovery firewall rule in Azure Build Parameters Tables 3 and 4) | BE | 15 |
| G-03 | Test failover | - Open the recovery plan and run Test failover with the latest processed recovery point into the isolated test-failover virtual network. - Record start and completion times. - Record both test virtual machines with zone, size and tags. | Job record; screenshots; timing note | Both replicas running in East US 2, zone 1 and zone 2, Standard_D8ls_v5; the plan completes without error; tags recorded against the Azure Tag Plan, including the backup exclusion tag | BE, CA | 60 |
| G-04 | Replica start and registration | - From a jump host in the isolated network, on each test virtual machine record the computer name, domain membership and the state of the CyberArk Privileged Session Manager service. - In Connector Management record what the tenant shows for the replica while it runs. | Screenshots | Computer names AZPASPCCPRD101 and 102; PSM service running. The tenant behavior for a second instance of a registered connector is recorded, whatever it is; a conflict or duplicate entry becomes a recovery-plan action owned by GEHA Security | CA, BE | 30 |
| G-05 | DR load balancer | - Open lbi-sec-cyberark-eus2-dr-01 and record the front end, probes and rule. - Add the two test virtual machine NICs to the backend pool and record health. - Remove them after G-08. | Screenshots | Parameters match Azure Build Parameters Table 5; both test virtual machines Healthy on both probes | BE | 20 |
| G-06 | DNS re-point rehearsal | - GEHA DNS creates cyberark-drtest.geha.com pointing at the DR front end address. - From the isolated network run nslookup and request https://cyberark-drtest.geha.com/psm/api/health. - Record the time to change and propagate; remove the record after G-08. | Command output; timing note | The record resolves; HTTP 200 through the DR load balancer; change time recorded | CP, SO | 30 |
| G-07 | Tenant allowlist | - Cloud Platform Team provides the East US egress public address. - CyberArk administrator confirms it is on the tenant allowlist. | Screenshot | Address present on the allowlist before any real failover | CA, CP | 15 |
| G-08 | Cleanup | - Run Cleanup test failover on the recovery plan with notes. - Confirm the test virtual machines are removed and replication remains Protected. | Job record; screenshot | Test virtual machines removed; both items Protected | BE | 20 |
| G-09 | Production unaffected | During G-03 and after G-08 repeat D-01 against production. Reviewer records the PSM server and the Connector Management status of the production pair. | Session records; screenshots | Brokered by AZPASPCCPRD101 or 102 both times; the production pair active throughout | TU, CA | 20 |

## Schedule

The cases total about 12.6 hours of execution across the three test days and about 3.8 hours on day 4: groups A, B and C on day 1, group D on days 2 and 3, groups E and F on day 3, group G on day 4. Waiting time for configuration refresh (600 seconds per platform change), CPM cycles, initial replication and service owner actions is additional. Day 3 closes with the evidence pack and the summary sheet for the Security and Enterprise Architecture presentation; day 4 evidence is added to the pack before hypercare exit.

## Exit Criteria

The following criteria must be satisfied before testing is considered complete and the solution is approved to progress through the migration lifecycle.

Table 6-10: Exit Criteria

| Ref | Criterion |
| --- | --- |
| X-01 | Groups A, B and C pass, or each failure has a named owner and a fix date before the CAB agenda request. |
| X-02 | D-01 to D-07 pass. D-08 passes or the sizing is re-examined before cutover. |
| X-03 | E-01, E-02 and E-04 pass with no exception. |
| X-04 | F-01 shows both connectors protected. |
| X-05 | Deferred items are recorded with an owner and a date: rotation engine placement, Secure Tunnel audit feed re-point, credential provider decommission, live monitoring route. |
| X-06 | The evidence pack is complete: one subfolder per case, each holding the evidence named in the case, and a signed summary sheet. |
| X-07 | Before hypercare exit: G-01, G-03, G-07, G-08 and G-09 pass; the G-04 result is recorded with any recovery-plan action and its owner; the G-06 change time is recorded. |

## Cutover Day Validation and Rollback

Cutover for this application is the first production platform, or set of production accounts, pointed at the Azure group. The steps below run on the cutover day in order; CV-06 runs only if rollback is invoked. Cutover is approved by GEHA Security, Enterprise Architecture and CAB together; the rollback decision belongs to Phil Costanzo, application admin and support manager, on the recommendation of the CyberArk administrator. The Roll Back Plan holds the full procedure

Table 6-11: Cutover Day Steps

| Ref | Step | Detail | Role | Min |
| --- | --- | --- | --- | --- |
| CV-01 | Pre-cutover check | Morning of cutover: repeat A-09, A-10, C-01 and C-02, and confirm G-01 shows both replicated items Protected. | BE, CA | 30 |
| CV-02 | Production re-point | Apply the Azure group ID to the first production platform, or move the first production accounts to the Azure platform, per the platform assignment model. Wait one configuration refresh. | CA | 20 |
| CV-03 | Production session check | Repeat D-01 and D-02 against one production target per platform re-pointed. | TU, CA | 30 |
| CV-04 | On-premises check | Repeat E-01 for one unmigrated production target. | TU, CA | 15 |
| CV-05 | Both groups active | Confirm the tenant session list shows sessions on both the Azure and the on-premises groups. | CA | 10 |
| CV-06 | Rollback, if invoked | Restore the on-premises group ID on the platform, or move the accounts back. Wait one refresh. Repeat CV-03 against the on-premises group. No infrastructure change is needed. | CA | 30 |

## Deferred items

The following are outside this test cycle and carry an owner and a date in the program decision register: the rotation engine on the Azure connectors; the credential provider tier, which decommissions with the on-premises connectors; the Secure Tunnel audit feed re-point; a direct monitoring route to each connector if D-07 shows the load balancer cannot carry live monitoring; and any recovery-plan action recorded at G-04.

Appendix A: Workflow description

This appendix describes the validation workflow drawn in Figure 1 as swimlanes, phases, tasks, gates and decisions. Task identifiers are the case references in section 4; gate identifiers are new.

A.1  Swimlanes

Six lanes, top to bottom: Cloud Platform Team (CP), Build engineer (BE), CyberArk administrator (CA), Test user (TU), Service owners (SO), Security and EA reviewers (SR). The evidence store is drawn as a data store at the right edge, receiving an artifact from every task.

A.2  Phases and Gates

Table 6-12: Phases, Tasks, and Gates

| Phase | Lane | Tasks in order | Gate at the end | Gate rule |
| --- | --- | --- | --- | --- |
| 0 Entry | CP, BE, CA | E-01 to E-10 in Table 2 | G0 Ready to test | All ten entry criteria confirmed; otherwise return to the owner of the failed criterion |
| 1 Platform build (day 1 am) | BE | A-01 to A-12, sequential; A-09 follows A-08 directly | G1 Built as specified | No failed case, or every failure has an owner and a fix date; A-09 unhealthy sends a firewall exception task to BE before G1 |
| 2 Network paths (day 1 pm) | BE, CP, SO, TU | B-01 to B-10; B-03, B-05, B-06, B-07 may run in parallel with the service owners | G2 Paths open | All paths pass; a refused path returns to CP for the rule collection |
| 3 Tenant registration (day 1 close) | CA | C-01 to C-06 in order | G3 Registered | C-01 to C-05 active on both connectors; C-06 recorded as present or deferred |
| 4 Brokered sessions (days 2 and 3) | TU, CA, BE | D-01, D-02, D-06, D-03, D-04, D-05, D-07, D-08, D-09, D-10 | G4 Serves migrated targets | D-01 to D-07 pass; D-08 pass or sizing review; a D-07 failure opens the live monitoring route item and a decision |
| 5 Parallel run (day 3) | CA, TU, CP, SO | E-01, E-02, E-03, E-04, E-05 | G5 Estates separated | E-01, E-02 and E-04 pass with no exception; an E-02 session that reaches the target is a stop: cutover cannot be requested |
| 6 Operations (day 3) | SO, BE | F-01, F-02, F-03 | G6 Operable | F-01 protected; F-02 and F-03 pass or deferred with owner |
| 7 Acceptance | BE, SR | Assemble evidence pack and summary sheet; one hour presentation to Security and EA | G7 Accepted | Both teams accept; playbook status set to Finalized; CAB agenda request submitted the Friday before CAB |
| 8 Cutover day | BE, CA, TU | CV-01 to CV-05; CV-06 on rollback | G8 Cut over | CV-03, CV-04 and CV-05 pass; otherwise CV-06 and a return to G7 for the next CAB |
| 9 Disaster recovery (day 4, before hypercare exit) | BE, CP, CA, TU, SO | E-11, then G-01, G-02, G-03, G-04, G-09 during G-03, G-05, G-06, G-07, G-08, G-09 after G-08 | G9 Recoverable | G-01, G-03, G-07, G-08 and G-09 pass; G-04 recorded with any recovery-plan action and owner; G-06 change time recorded |

A.3  Decision Points

Table 6-13: Decision Points

| Decision | Where | Yes path | No path |
| --- | --- | --- | --- |
| Probes healthy after hardening? | After A-09 | A-10 | Add inbound exception for 168.63.129.16, rerun A-09 |
| All tenant paths open? | After B-02 | B-03 | Return to CP: rule collection fix, rerun B-01 and B-02 |
| Rotation engine present? | C-06 | D-09 verifies through the Azure engine | D-09 verifies through the existing CPM; record against the rotation engine placement item |
| Live monitoring reaches the host? | D-07 | Continue | Open the live monitoring route item; decide a direct monitoring route before G4 |
| Session from Azure reaches an unmigrated server? | E-02 | Stop: firewall finding to CP; no cutover request until rerun passes | Continue to E-03 |
| Evidence accepted by Security and EA? | G7 | Finalize playbook, submit CAB agenda request | Address findings, re-present |
| Production sessions pass on cutover day? | CV-03 to CV-05 | Hypercare begins | CV-06 rollback; return to G7 for the next CAB |
| Replica registers with the tenant? | G-04 | Continue to G-05 | Record a re-registration step as a recovery-plan action owned by GEHA Security; continue to G-05 |
| Test failover cleaned up and replication Protected? | G-08 | G-09, then G9 | Remove the test resources by hand, record, rerun G-01 |

Appendix A: Roles & Responsibilities

Responsibility across the migration lifecycle is assigned here using the RACI model, with exactly one accountable owner for each task. The distinction between responsible and accountable matters most at the two points where migrations stall: the go/no-go decision and the rollback decision. Consulted[SA4.1] and informed parties are recorded so that teams learn of changes affecting them before rather than after the event. Where this matrix and the ownership register disagree, the ownership register governs and the discrepancy is corrected here.

Table 6-14: Roles & Responsibilities

| Task | App Owner | Migration Team | Platform / Cloud | Security | End Users | Admin / Support Manager |
| --- | --- | --- | --- | --- | --- | --- |
| Landing zone placement | I | C | A/R | C | I | I |
| Target design | C | A/R | C | C | I | C |
| Sizing & cost model | C | R | A | I | I | C |
| Replication build | I | A/R | C | I | I | I |
| Identity & RBAC | C | R | C | A | I | C |
| Migration rehearsal | C | A/R | C | I | I | C |
| Integration re-point | I | R | C | C | I | A |
| Go / no-go decision | A | R | C | C | I | C |
| Cutover execution | A | R | C | I | I | C |
| Reconciliation & acceptance | A | R | I | I | C | C |
| Rollback decision | A | R | C | I | I | C |
| Operational readiness | C | R | A | C | I | C |
| Decommission | A | R | C | C | I | C |

- Sign Off

Approval to execute is recorded here, and each signatory is a named individual accountable for the sections relevant to their role rather than a representative of a team. Signing confirms that the target design, the cutover plan and the rollback position documented in this playbook are approved for execution as written. Signatures are obtained before the go/no-go gate rather than retrospectively. A playbook signed on this basis is the authority under which the cutover proceeds.

By signing below, stakeholders confirm that the target design, cutover plan and rollback position documented in this playbook are approved for execution.

Table 6-15: Sign-Off

| Name | Role | Date |
| --- | --- | --- |
| To be prov TBD | Application Owner |  |
| To be provided by GEHA TBD | Migration / Technical Lead |  |
| To be provided by GEHATBD | Platform / Cloud Lead |  |
| To be provided by GEHA TBD | Security | T |
| To be provided by GEHATBD | DBA / Production Control |  |
| To be provided by GEHATBD | Network |  |