Application Migration Playbook Venafi Datacenter to SaaS Replacement v0.5 — DRAFT, FOR GEHA REVIEW

Venafi Trust Protection Platform (TPP) manages all TLS certificates across GEHA's infrastructure

Architecture

Prepared for: G.E.H.A.

Eric Ullmann (Application Owner); Eric Ullmann (Director); Phil Costanzo (Admin / Support Manager)

Prepared by: Citius Healthcare Consulting

George Galindo, Cloud Architect

Peer Reviewer:Not yet assigned

Document Status:☒ DRAFT ☐ RELEASE CANDIDATE ☐ PUBLISHED

Date:26-Aug-2026

| Field | Value |
| --- | --- |
| Application Name | Venafi |
| Playbook Index ID | GEHA-DCM-VENAFI-v0.5 |
| Application Version | Installed software observed on the hosts: sqlservr.exe; svchost.exe; VPlatform.exe; ir_agent.exe; splunkd.exe; rapid7_endpoint_broker.exe (Evidenced — Application Interface Details, full 451,897-row pass, as-of 12/24/25) Venafi TPP 24.1; components in use: Aperture, WebAdmin, Database; no remote agents |
| Wave Placement | Wave 1 |
| Migration Strategy | Repurchase → Venafi SaaS |
| Target Cutover Date | 12/17/26, Thursday (BASELINE v2.1) — SQLCOTS shared-instance night. CR Friday 12/11/26; CAB Wednesday 12/16/26; playbook frozen 12/11/26 (VENA-SUB) — the CR and the freeze fall on the same Friday; both stated. |
| Application Owner | Eric Ullmann — Application Owner (GEHA) |
| Cliff Date | 12/19/26 |
| Cliff Date Driver | Contract/license end — Contract Cliffs tab; annual renewal $126,961 (Evidenced — Wave Plan Tracker (rev-3), as-of 07-Aug-2026) |
| User Access Method | Not on file |
| Key Dependencies | ARCHER; ARCHER APP; AVAYA; BREAKROOM MONITOR SOFTWARE; CES; CONTROL-M; DBA; ERWIN |
| Target SaaS Product | Venafi SaaS |
| Vendor | Venafi |
| Vendor Contact | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA, required by 2026-09-15 (Appendix B, item 05). |

Table 1.0 — Key Information

Contents

# 1. Document Control

## 1.1 Approvers

| Name | Role | Approval Date |
| --- | --- | --- |
| Eric Ullmann | Application Owner |  |
| Phil Costanzo | Application Administrator |  |
| - | Security Lead |  |
| - | Vendor — Point of Contact |  |
| George Galindo | Cloud Architect — Citius Healthcare Consulting |  |
| - | Migration & Platform Lead (CHC) |  |

Table 1.2 — Approvers

## 1.2 Attachment Register

| Attachment | Referenced By |
| --- | --- |
| Wave Plan Tracker (rev-3) — App Disp, Contract Cliffs, Wave Schedule, Owners | §1.0, §3.2, §3.3, §11 |
| Application Interface Details (IFD) full pass | §4.7, §4.10 |
| Matilda Discovery Assessment Summary | §4.1 |
| Server_VM_Inventory (vCenter export) | §4.1.1 |
| GEHA_SQLServers_DBDetails_Inventory + DBA Migration Artifacts | §4.4, §4.11 |
| SOW ZCON-18111 (signed 30-Jul-2026) — Exhibit C | §1.0 wave placement, §10.3 |
| Decision &amp; | throughout — decisions are cited by REG id, not restated |

Table 1.6 — Attachment Register

# 2. Executive Summary

Venafi moves out of the GEHA datacenter under the repurchase disposition; it provides a certificate management solution to help GEHA achieve a modern and holistic view of certificates within the environment. The capability moves to Venafi SaaS; the on-premises installation retires once the target is in service. Cutover is planned for 12/17/26 in Wave 2 (BASELINE v2.1, 26 Aug 2026), on the SQLCOTS shared-instance night, against a binding contract cliff of 12/19/26, met with 2 days of margin. Users see one planned outage at cutover; the window is agreed at the readiness review. Datacenter decommissioning, facility exit and hardware disposal are excluded from the current statement of work. The main threat to the date is late delivery of the information listed in Appendix B, tracked weekly with GEHA.

Scope is limited to Venafi. The committed dates are those recorded in section 11, and every open item is tracked in Appendix B with the date it is needed.

# 3. Application Overview

## 3.1 Business Purpose

Venafi Trust Protection Platform (TPP) manages all TLS certificates across GEHA's infrastructure. The disposition is Repurchase to Venafi SaaS (rebranded as CyberArk Machine Identity Security after the CyberArk acquisition of Venafi). The SaaS migration means GEHA no longer manages the TPP server infrastructure — certificate policies, CA integrations, and auto-renewal workflows move to the cloud platform. Key risks are certificate continuity during migration and ensuring all certificate-consuming systems (web servers, load balancers, applications) are re-pointed to use the SaaS-managed certificates.
Post Discovery:
4 on-prem servers (2 DMZ, 2 internal). Used for network certificate discovery and scanning local network for cert validity.
UNCLEAR. If Azure environment moves to full PaaS, Azure APIs may cover certificate management, removing the need for on-prem scanning servers. Security cameras and similar on-prem-adjacent devices may still require local scanning. GEHA internal decision needed before scope can be confirmed.  Should be included in migration  ||  GEHA comment: will verify databases piece -- believe this is already SaaS. Will need to plug into the databases as they move.
There is an on-prem piece today. Should be included in migration  ||  Business capabilities served: 0 (Evidenced — Wave Plan Tracker (rev-3), as-of 07-Aug-2026)  Host-count reconciliation (26-Aug-2026): the vCenter export records four Venafi-named VMs — VENAFIPRD101 and VENAFIPRD102 (internal app servers), VENAFIPRD103 (DMZ discovery host, DNS VENAFIPRD103.DMZ.ext, annotation RITM0126683) and VENAFIPOC101 (POC box per annotation RITM0115793 — retirement candidate); Discovery Report App ID 74 records a server count of 5, which reaches five only by counting the shared SQLCOTS pair; the “2 DMZ, 2 internal” split is a GEHA verbal — only one host carries a DMZ DNS suffix in the export. Deltas logged, not resolved (Appendix B; register W2-VENA-1).

## 3.2 Ownership & Stakeholders

Migration work stalls more often on unresolved ownership than on technical difficulty, so every role bearing on this application is resolved to a named individual here rather than to a team or a distribution list. The register covers business ownership, technical ownership, security, database and production control, network and DNS, batch scheduling, and the single person empowered to abort a cutover in progress. Where a recorded owner has left the organization, the vacancy is carried forward as an open item rather than quietly inherited by whoever is nearest. Each entry is confirmed with the individual concerned before the go/no-go gate, because a name that has never been verified is not an owner.

| Role | Name |
| --- | --- |
| Business / Application Owner | Eric Ullmann |
| Technical Owner |  |
| Security Contact |  |
| DBA / Production Control | DBA team (per DBA Migration Artifacts) |
| Network / DNS / Firewall | - |
| Scheduling / Batch Automation | vm |
| Rollback Authority | - |
| On-call / Support (Admin / Support Manager) | Phil Costanzo |
| Director (GEHA) | Eric Ullmann |

Table 3.2 — Ownership & Stakeholders

## 3.3 Criticality & Service Levels

The service levels the business receives today are recorded here so that the target design can be measured against a documented reference rather than against recollection or aspiration. Current availability, recovery time and recovery point objectives are captured alongside the peak usage window and the calendar dates a cutover must avoid. Where the target design would deliver less than the current state, that shortfall becomes a gap requiring the application owner's explicit written acceptance rather than a technical footnote. These figures also frame the business conversation about acceptable downtime, which is far easier to hold before a date is committed than after.

| Business Criticality | Tier 3 — 2 - Medium (Evidenced — BIA_Capability and Application_DC Migration (Application BIA), as-of 13-Nov-2025) |
| --- | --- |
| Current Availability SLA | Na |
| RTO (Recovery Time Objective) | 24 Hours (Evidenced — BIA_Capability and Application_DC Migration (Application BIA), as-of 13-Nov-2025) |
| RPO (Recovery Point Objective) |  |
| Peak Usage Window | 6500 certificates, Peak issuance and renewal activity typically occurs during our annual geha.com certificate renewal cycle (Evidenced — GEHA application discovery sessions 1-3 (responses workbooks)) |
| Business Calendar Constraints | Open enrolment / open season — GEHA-wide constraint; confirm application-specific dates with the owner. Program blackouts: 2026-11, 2027-11 (SOW: production cutovers barred). |
| Regulatory / Compliance Scope | Business impact: Impact to the application may result in the loss of certificate management. (Evidenced — BIA_Capability and Application_DC Migration (Application BIA), as-of 13-Nov-2025) |

Table 3.3 — Criticality & Service Levels

## 3.4 Performance Baseline

Performance complaints after go-live cannot be resolved against an undocumented baseline, so the application's present behavior is measured and recorded here before anything moves. Typical and worst-case response times for the most-used functions, elapsed times for significant batch jobs, observed peak concurrency and transaction volumes are all captured with the conditions under which they were measured. The measurement date matters as much as the figure: a baseline older than the last significant change to the application is not a baseline. These numbers become the exit criteria for performance testing, converting a subjective judgment into a pass or fail.

| Transaction / Screen Response | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA, required by 2026-09-30 (Appendix B, item 12). |
| --- | --- |
| Batch and Report Durations | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA, required by 2026-09-30 (Appendix B, item 12). |
| Peak Concurrency | Instance activity classified High; CPU Moderate, memory High, storage Moderate (Evidenced — Matilda Discovery Assessment Summary (Host Details / Instance Assessment), as-of 08-Aug-2026) |
| Transaction Volume | Observed inbound connection rows by port — 64070 — 28 rows; 8883 — 9 rows; 135 (RPC endpoint mapper) — 2 rows; 49774 — 2 rows; 49768 — 2 rows; 49711 — 1 rows (Evidenced — Application Interface Details, full 451,897-row pass, as-of 12/24/25) |
| Measurement Source & Date | Matilda discovery assessment, as-of 08-Aug-2026; utilization bands, not absolute peaks (Evidenced — Matilda Discovery Assessment Summary (Host Details / Instance Assessment), as-of 08-Aug-2026) |

Table 3.4 — Performance Baseline

# 4. Current State

What follows is a complete account of the application as it exists in the datacenter today, and it serves two purposes at once. It is the specification from which the Azure target is sized and designed, and it is the evidence of what was actually running when the estate was assessed — the record that datacenter exit is measured against. Every component, data store, account, certificate, scheduled job, interface and hardcoded value that the migration must address is captured here rather than discovered during the cutover window. Because this section is the exit evidence, it is not reducible even for low-complexity applications.

## 4.0 Current State Architecture Diagram

The diagram presents the current deployment in a single view and acts as the visual counterpart to the registers that follow. Every server, integration, network object and identity flow recorded in this section should be locatable on it, and any component that appears on the diagram but is absent from the registers is by definition undocumented. It is drawn from evidenced sources — configuration exports, firewall rules, DNS records and discovery output — rather than from memory or from superseded architecture material. Its practical use is to walk the move-group boundaries and brief the cutover team on what exists today before anything is changed.

1. How to read the diagram

The diagram covers two sites. Lee’s Summit holds the whole working estate - the internal application tier, the DMZ discovery host, the certificate estate those hosts act on, and the shared database instance - with the perimeter firewall on its right edge. Lenexa holds only the log-shipping secondary. Shared enterprise services sit along the bottom on the internal LAN rather than on point-to-point links, because none of them belongs to this application.

| Element on the diagram | Where it sits | What it represents |
| --- | --- | --- |
| Administrators / operators | Corporate network | Certificate and PKI administrators, plus application and server teams raising requests. Aperture and WebAdmin are the only human-facing surfaces. |
| VENAFIPRD101 / 102 | Internal application tier, LS | The TPP application nodes. PRD101 is the primary: private keys provisioned through Venafi are stored and encrypted on it. No HSM is in use. |
| VENAFIPOC101 | Internal application tier, LS | A POC host carried in the vCenter export (RITM0115793, resource pool Sand). Drawn dashed - a retirement candidate rather than part of the production service. |
| VENAFIPRD103 | DMZ segment DMZ-VL7, LS | The DMZ web server used for network certificate discovery and administration. The only host in the export carrying a DMZ DNS suffix. |
| Certificate estate | LS | What the platform acts on: on-premises web servers and F5 load balancers that hold provisioned certificates, and the internal ranges, DMZ hosts and on-prem-adjacent devices that are scanned for certificate validity. |
| ENTSQL35\SQLCOTS and venafi_tpp | Database tier, LS | The shared SQL Server 2019 Enterprise instance and the single application database on it. The database, not the servers, is what carries the service. |
| Co-tenant applications | Database tier, LS | Twelve further applications observed against the same instance host. Drawn dashed because they are not Venafi flows - but they share the instance. |
| LXENTSQL35\SQLCOTS | Lenexa (LX) datacenter | The log-shipping secondary holding the DR copy of venafi_tpp. The only cross-site element in the current state. |
| Palo Alto NGFW | LS perimeter | The boundary every outbound server session crosses. Certificate traffic to the public CA and to external endpoints passes through it; discovery and provisioning inside the estate do not. |
| DigiCert, Akamai, Azure Key Vault, Rapid7 | Internet / external | The out-of-network parties: the public CA that issues certificates, two endpoints that consume them, and the vulnerability-management platform the agents report to. |

Table 4.0b - Elements shown on the current state diagram

The structural fact that shapes everything else Venafi does not simply hold certificates - it reaches out and installs them. With no remote agents deployed, every issuance and every installation is a remote, credentialed operation initiated from the TPP nodes to a CA, a web server, a load balancer or an external endpoint. What must survive the migration is therefore a set of network paths and service credentials, not agent software.

2. The certificate lifecycle, step by step

Steps 1 to 8 follow a certificate from the moment the estate is scanned to the moment its record is replicated to Lenexa and backed up. They occur in the order given, and every one of them is a flow that has to exist somewhere after the move to SaaS - which makes this sequence, rather than the server list, the real statement of scope.

Step 1 · F9 - The DMZ host discovers what certificates exist

| Path | VENAFIPRD103 (DMZ, DMZ-VL7) → on-premises and DMZ network ranges |
| --- | --- |
| Protocol / port | Network certificate discovery scanning |
| What happens | The DMZ host scans the network for certificates and checks their validity. This is what makes an on-premises footprint necessary at all: a cloud platform cannot see certificates sitting on internal hosts, DMZ servers and on-prem-adjacent devices. The scope note records that security cameras and similar devices may still require local scanning even after the rest of the estate moves. |

Step 2.F1 - An administrator requests or approves a certificate

| Path | Administrators and requesting teams → VENAFIPRD101 / VENAFIPRD102 (Aperture, WebAdmin) |
| --- | --- |
| Protocol / port | HTTPS, browser-based; Entra ID SSO |
| What happens | Interactive administration of the platform: certificate policy, CA connectors, provisioning workflows and the request queue. RBAC is applied on the Venafi back end behind the SSO, so directory group membership grants entry while Venafi itself decides what a signed-in user may do. There is no thick client and no desktop dependency. |

Step 3.F5 - Internal certificates are issued by GEHA’s own CA

| Path | TPP → internal ADCS (Microsoft enterprise CA) |
| --- | --- |
| Protocol / port | Certificate enrolment against the AD-integrated CA |
| What happens | Internal certificates come from GEHA’s own ADCS and are delivered to consumers by Venafi. The CA is enterprise infrastructure rather than part of this application, so it stays exactly where it is: what changes at migration is which platform asks it for certificates, not the CA itself. |

Step 4.F6 - Public certificates are issued by DigiCert

| Path | TPP → DigiCert (public CA) |
| --- | --- |
| Protocol / port | 443/TCP outbound, through the Palo Alto perimeter |
| What happens | Public certificates - the geha.com estate among them - are issued and renewed against DigiCert over an outbound session that crosses the perimeter. Peak issuance and renewal load falls in the annual geha.com renewal cycle. |

Step 5.F7 - Certificates are installed onto on-premises consumers

| Path | TPP → on-premises web servers and F5 load balancers |
| --- | --- |
| Protocol / port | Agentless provisioning; no remote agents are deployed |
| What happens | Issued certificates and their private keys are installed onto the consuming systems by the platform itself. Because no remote agents exist, every installation is a remote, credentialed operation from the TPP nodes. The private keys involved are held encrypted on the primary node; root and intermediate keys do not exist on the Venafi servers, and no HSM is in use. |

Step 6.F8 - Certificates are pushed to endpoints outside the datacenter

| Path | TPP → Akamai and Azure Key Vault |
| --- | --- |
| Protocol / port | 443/TCP outbound, through the perimeter |
| What happens | Consuming endpoints outside the datacenter receive certificates over the same egress path. They are drawn because they consume certificates today, not because they are part of the target design. |

Step 7.F2 - Everything the platform knows is written to the shared database

| Path | TPP nodes (and the DMZ node) → ENTSQL35\SQLCOTS |
| --- | --- |
| Protocol / port | TCP 64070 - the named-instance port, cname csqlcotsVENAFI\SQLCOTS |
| What happens | Every certificate object, policy, workflow and log entry lives in venafi_tpp on the shared SQLCOTS instance. The application nodes are stateless by comparison - apart from the encrypted private keys on the primary - so the database, not the servers, is what carries the service. Port 64070 appears on both sides of the interface pass because the same port serves the hosts as clients and the instance as a listener. |

Step 8.F3 and F4 - The record is replicated to Lenexa and backed up

| Path | ENTSQL35\SQLCOTS → LXENTSQL35\SQLCOTS (Lenexa); LiteSpeed → both instances; vCenter policies → all Venafi-named VMs |
| --- | --- |
| Protocol / port | SQL Server log shipping; daily full plus 15-minute transaction log backups, encrypted |
| What happens | The DR copy of venafi_tpp is maintained at Lenexa by log shipping, supported by daily full restore and a manual full restore procedure. Database protection runs at 15-minute log granularity with retention of eight weeks daily, one year weekly and three years monthly, and monthly restore validation. At the VM layer the export records 8WK Backup on PRD101 (crash consistent), PRD102, PRD103 and LXENTSQL35, and 2WK Backup on POC101. |

3. Platform flows - running underneath the lifecycle

These seven flows are not part of the certificate lifecycle. They are the scheduling, management, logging, identity, virtualization and shared instance paths the hosts sit inside simply by existing in the datacenter. Every one of them has an owning team outside the migration team, and each must be either re-established, retired or handed over deliberately.

Flow.F10 - Control-M reaches the instance host

| Path | Control-M → the SQLCOTS instance host |
| --- | --- |
| Protocol / port | Observed inbound on 64070 (ctmsca_service), 535 connection rows |
| What happens | Enterprise scheduling traffic arriving on the same port the platform uses. Because that port is the shared SQL listener rather than a Venafi service port, this is database-client traffic, and it may belong to a co-tenant application rather than to Venafi. |

Flow.F11 - SCCM manages the Windows build

| Path | Microsoft SCCM → the Venafi hosts |
| --- | --- |
| Protocol / port | Observed inbound on 49608/TCP (dllhost), 4 connection rows |
| What happens | Patch delivery, software distribution and configuration-compliance reporting for the Windows build - the standard inbound management path, and one that breaks quietly rather than visibly when a host changes network position. |

Flow.F12 - Splunk forwarders ship the logs off the hosts

| Path | splunkd.exe on the hosts → Splunk indexing tier |
| --- | --- |
| Protocol / port | 9998/TCP outbound, 20 rows observed |
| What happens | Forwarder shipping of Windows event, service and security logs into the enterprise logging platform. The forwarder initiates outbound; nothing connects in to it. |

Flow.F13 - Rapid7 agents report to the Insight platform

| Path | ir_agent.exe / rapid7_endpoint_broker.exe → Rapid7 Insight platform |
| --- | --- |
| Protocol / port | 443/TCP outbound, via the endpoint broker |
| What happens | Vulnerability-management agent telemetry. The broker relays the traffic, so the egress relationship belongs to the broker rather than to each host. |

Flow.F14 - The hosts authenticate against Active Directory and resolve names

| Path | The Venafi hosts → AD DS domain controllers and internal DNS |
| --- | --- |
| Protocol / port | Kerberos 88, LDAP 389 / 636, SMB 445, DNS 53 |
| What happens | Domain-joined authentication, Group Policy and name resolution. On-premises AD groups replicate to Entra ID through AD Connect, and SSO is delivered by Entra ID. Internal DNS holds 144 zones and the records for this application have not yet been identified within them. |

Flow.F15 - vCenter owns every host in the picture

| Path | VMware vCenter / ESXi → all five Venafi-named VMs and the shared SQL pair |
| --- | --- |
| Protocol / port | vSphere management plane |
| What happens | Every host on this diagram is a virtual machine. vCenter owns power state, VM configuration and disk placement, and is the source of both the allocation figures and the backup-policy column quoted throughout. It is also the source of the host-count reconciliation: four Venafi-named VMs in the export against a server count of five in the Discovery Report, which reaches five only by counting the shared SQL pair. |

Flow.F16 - Twelve other applications share the same database instance

| Path | Co-tenant applications → ENTSQL35\SQLCOTS |
| --- | --- |
| Protocol / port | Observed on 59012 (sqlservr), roughly 512 connection rows each |
| What happens | ARCHER APP, AVAYA, BREAKROOM MONITOR SOFTWARE, FINGER PRINT PRO, UIPATH, ITSM, SECURITY CAMERAS, UNIT ASSISTANT and others were observed against the same instance host. These are not Venafi flows and they are drawn dashed for that reason, but they are the reason the database cannot be treated as this application’s alone. |

## 4.1 Host Resource Specifications

| Server / Component | Role | OS / Version | Environment |
| --- | --- | --- | --- |
| ENTSQL35 | Database | Windows Server 2019 Standard | PROD |
| LXENTSQL35 | Database | Windows Server 2019 Standard | PROD |
| VENAFIPOC101 | Web Server | Windows Server 2019 Standard | POC — vCenter annotation RITM0115793 “Venafi Windows Server for POC”, resource pool Sand; retirement candidate, delta with the prior PROD label logged |
| VENAFIPRD101 | Web Server | Windows Server 2019 Standard | PROD |
| VENAFIPRD102 | Web Server | Windows Server 2019 Standard | PROD |
| VENAFIPRD103 | Web Server — DMZ certificate discovery and administration (Evidenced — Server_VM_Inventory LS tab, poweredOn, annotation RITM0126683) | Windows Server 2019 Standard | PROD (DMZ — DNS VENAFIPRD103.DMZ.ext, network DMZ-VL7) |

Table 4.1 — Host Resource Specifications

### 4.1.1 Sizing

Allocated capacity and measured utilization are recorded side by side, because the difference between them is where cloud cost is won or lost. Target sizing is derived from what the workload actually consumes rather than from what was provisioned for it, which is frequently several times larger. The observation window is stated with every figure, since a short sample will not capture cyclical peaks such as month-end or open-season processing. Where no measurement exists, that absence is recorded plainly and the associated sizing risk is carried into the risk register rather than hidden inside an estimate.

| Server | vCPU Allocated | Memory Allocated | Disks (Count / Size / Type) |
| --- | --- | --- | --- |
| ENTSQL35 | 4 | 32 GB | 5 disks / 2498 GB |
| LXENTSQL35 | 4 | 32 GB | 5 disks / 2498 GB |
| VENAFIPOC101 | 4 | 16 GB | 1 disks / 100 GB |
| VENAFIPRD101 | 4 | 16 GB | 1 disks / 180 GB |
| VENAFIPRD102 | 4 | 16 GB | 1 disks / 100 GB |
| VENAFIPRD103 | 4 | 12 GB | 1 disks / 100 GB |

Table 4.1.1 — Sizing

### 4.1.2 Operating System & Platform Readiness

The platform characteristics of the outgoing on-premises estate are captured here even though the destination is a vendor-operated tenant, because the source environment determines how much work stands between today and cutover. An unsupported or end-of-life operating system narrows the window in which the legacy system can safely continue to run in parallel, while clustering, hardware-bound license keys and SAN-attached storage each add a distinct thread of unwind work that has to be sequenced rather than simply switched off. Recording these attributes also establishes what has to be extracted, and from where, before the vendor can load anything. Where an attribute is inherited from shared infrastructure rather than owned by this application, that is noted so the effort is attributed to the correct workstream. The values below describe the current state; the target state for each is the vendor's platform and is therefore not restated.

| OS Support Status | Active |
| --- | --- |
| Architecture & Generation | Platform: Windows (Evidenced — Matilda Discovery Assessment Summary (Host Details / Instance Assessment), as-of 08-Aug-2026) |
| Clustering / Shared Disk | ☐ None ☐ Failover cluster ☐ Shared disk — Not on file — clustered workloads need a specific target design, not a straight lift. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Static IP Dependency | ☐ Yes ☐ No — Not on file — anything hardcoded to this address elsewhere in the estate — see §4.7. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Installed Agents & Tooling | Observed on the hosts: sqlservr.exe; svchost.exe; VPlatform.exe (Venafi TPP); ir_agent.exe (Rapid7); splunkd.exe (Splunk); rapid7_endpoint_broker.exe (Evidenced — Application Interface Details, full 451,897-row pass, as-of 12/24/25). A full agent/tooling inventory per host is not on file — requested from GEHA (Appendix B, item 05). |
| Encryption / Special Storage | Not on file —No Disk encrypted, . |

Table 4.1.2 — Operating System & Platform Readiness

## 4.2 Application Software & Dependencies

The software layer is documented here in the terms that matter to a migration: exact installed version, whether the vendor supports that version on the target platform, and what else must travel with it. Scheduled jobs, file storage dependencies, license binding and client-side components are each recorded, because every one of them is a thing that silently stops working when the server underneath changes. License binding deserves particular attention: a license tied to a MAC address, host fingerprint or dongle will fail at the moment of cutover, and re-hosting it carries a vendor lead time. An unsupported configuration is a go/no-go item, not a hypercare issue.

| Application Version | Isqlservr.exe; svchost.exe; VPlatform.exe; ir_agent.exe; splunkd.exe; rapid7_endpoint_broker.exe |
| --- | --- |
| Vendor Support Status of This Version | iis 10.0: Active — Retain Service IIS version 10.0; mssql 2019-Enterprise Edition: Active — Upgrade to Azure Database SQL for managed solution ( |
| Scheduled Jobs & Batch | mssql 2019-Enterprise Edition (Database; Active); iis 10.0 (Web Server; Active) (Evidenced — services observed, Matilda Discovery Assessment Summary (Application Assessment Summary), as-of 08-Aug-2026) |
| File Storage Dependencies | Enterprise storage platform: (full capacity report in the corpus) (Evidenced — Storage_Artifacts (Dell PowerFlex / Isilon capacity report)) |
| License Binding | ☐ Not bound ☐ MAC address ☐ Host ID / machine fingerprint ☐ Dongle or hardware key ☐ License server — Not on file — a license bound to hardware stops working the moment the application moves. Confirm with the software vendor before cuto. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |

Table 4.2 — Application Software & Dependencies

## 4.3 Application Delivery & Client Access

How users reach the application determines how much of the cutover work is invisible to them and how much lands on their desks. Browser access, installed thick clients, published or virtualized delivery, desktop-image deployment and mobile access each carry different execution, dependency and decommission implications. Where a client sits inside a managed desktop image, the image rebuild and redeployment cadence becomes a program dependency rather than a task the migration team controls. Local configuration held on endpoints — cached credentials, mapped drives, hardcoded server names, printer bindings — is captured here because each item must be updated or removed at cutover.

| Primary Access Method | No browser, SMB or RDP listener observed on these hosts; access is via the services listed in the network section |
| --- | --- |
| Application URL(s) | Not on file — Entry point URLs, and where users hold them — bookmarks, intranet links, portal tiles, shortcuts. Each is a change at cu. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Installed Client Detail | Not on file — Client name and version, 32/64-bit, prerequisites and runtimes, install footprint, whether administrative rights are nee. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Present in a Desktop Image? | Not on file — Yes/No — which image, who owns it, and the rebuild and redeployment cadence. If yes, that cadence is a dependency, not a. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Deployment & Packaging Mechanism | Not on file — SCCM/Intune package, GPO, manual install, image only — and the team that owns the package. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Published / Virtualized Delivery | Not on file — Citrix, AVD or similar: farm or host pool, published application name, and the team that republishes or retires it. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| User Population by Access Method | — |
| Device Types | 8 distinct out-of-network endpoints observed communicating with these hosts (Evidenced — Application Interface Details, full 451,897-row pass, as-of 12/24/25) |
| Location & Network Path | Observed inbound listeners: 64070 — 28 rows; 8883 — 9 rows; 135 (RPC endpoint mapper) — 2 rows; 49774 — 2 rows; 49768 — 2 rows; 49711 — 1 rows (Evidenced — Application Interface Details, full 451,897-row pass, as-of 12/24/25) |
| Local Configuration or Data on the Endpoint | Not on file — Config files, cached credentials, local databases, mapped drives, hardcoded server names or IPs, printer or scanner bind. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Client Removal Owner | Not on file — Who uninstalls the client or pulls it from the image after go-live. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |

Table 4.3 — Application Delivery & Client Access

## 4.4 Data & Database Tier

The data tier is documented here as the migration source: what exists, how much of it there is, how it will be extracted and what obligations survive the source system. Engine version, edition, collation and compatibility level are recorded because they gate whether a managed platform target is available or whether a straight lift is the only supported option. Volume is captured at database granularity rather than instance total, since the load window is driven by the largest objects and by unstructured attachments that are routinely underestimated. Retention and legal-hold obligations are recorded explicitly, as they outlive the server and must be satisfied somewhere after it is gone.

| Database Engine & Version | SQL Server 2019 (Enterprise Edition (64-bit)) (Evidenced — GEHA_SQLServers_DBDetails_Inventory) |
| --- | --- |
| Data Volume | venafi_tpp: 15,304 MB allocated / 11,182.88 MB used data + 10,568 MB log (Evidenced — GEHA_SQLServers_DBDetails_Inventory, DB_Sizes tab, as-of 01-Dec-2025). DBA Migration Artifacts PROD tab records 21,584 MB on the primary (ENTSQL35) and 16,144 MB on the secondary (LXENTSQL35) — a later observation; the figures differ by as-of date and are reported as a reconciled pair, not resolved. GEHA discovery response: “~15.5 GB” (Session 1 responses). Size refresh requested before seeding (Appendix B, item 16). |
| Attachments / Unstructured Data | Not on file — no attachment or unstructured-data store recorded for venafi_tpp; searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA, required by 2026-09-15 (Appendix B, item 16). |
| Export Method & Access | Not on file — no export-method record; searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA, required by 2026-09-15 (Appendix B, item 16). Target is Venafi SaaS — vendor-led configuration export expected; to be confirmed with the vendor. |
| Historical Data & Retention | Backup retention recorded for the SQLCOTS databases: daily 8 weeks, weekly 1 year, monthly 3 years; backups encrypted using LiteSpeed; monthly restore validation (Evidenced — Discovery Report Inventory v1.0, Data and Databases). Legal-hold obligations not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B, item 12). |
| Instance Sizing & Utilization | Instance hosts sized in §4.1.1 from the vCenter export (ENTSQL35 / LXENTSQL35: 4 vCPU / 32 GB / 5 disks / 2,498 GB each). Disk utilization per instance: ENTSQL35 60.85%, LXENTSQL35 18.82% (Evidenced — Discovery Report Inventory v1.0, Data and Databases; Server_VM_Inventory). |
| Database Count & Individual Sizes | One database: venafi_tpp — Prod on ENTSQL35\SQLCOTS (log-shipping primary, 21,584 MB) with DR copy on LXENTSQL35\SQLCOTS (secondary, 16,144 MB); recorded as “New DB on SQLCOTS”, cname csqlcotsVENAFI\SQLCOTS : 64070, owner Jason Pucilowski (Evidenced — GEHA_SQLServers_DBDetails_Inventory, SQLCOTS tab; DBA Migration Artifacts, PROD tab). |
| High Availability Topology | Daily Full Restore; LogShipping; Manual Full Restore (Evidenced — DBA Migration Artifacts) |
| Collation & Compatibility Level | Not on file — collation and compatibility level are not recorded in any evidence source; searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA, required by 2026-09-15 (Appendix B, item 16). |
| Encryption at Rest | Not Encrypted (Evidenced — DBA Migration Artifacts, PROD tab); “No encryption at DB level” (Evidenced — Discovery Report Inventory v1.0, Data and Databases). No TDE or column-level encryption on file. Note: private keys provisioned through Venafi are stored and encrypted locally on the primary node at the application layer (Session 1 responses). |
| Scheduled Database Jobs | Index management daily/weekly, managed by the application; quarterly SQL Server updates and monthly Windows updates recorded for the instance (Evidenced — Discovery Report Inventory v1.0, Data and Databases). A job-level SQL Agent export is not on file — requested from GEHA (Appendix B, item 16). |
| Target Compatibility Assessment | Not run — no assessment export on file (Appendix B item 01). Engine estate evidenced as SQL 2017/2019/2022 on WS2016/2019/2022 (Appendix A ref. REG-018), inside the supported range. |
| Cross-Database / Linked Server Dependencies | Not on file — no cross-database or linked-server dependency recorded for venafi_tpp; searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA, required by 2026-09-15 (Appendix B, item 16). |

Table 4.4 — Data & Database Tier

## 4.5 Identity & Access

Identity is documented here with particular care because it is the area most often assumed to transfer intact and the first to fail after a rehost. Authentication method, identity provider, account populations, privileged access and multi-factor enforcement are each recorded with counts rather than general descriptions. Group resolution, service-account authentication and credential paths all depend on directory decisions taken in the target design, so the current position must be precise before that design is fixed. Entries in the registers that follow must each resolve to a target decision; an unmapped group or an unaccounted service account is a post-cutover outage waiting to happen.

| Authentication Method | — |
| --- | --- |
| Identity Provider | — |
| Internal User Accounts | — |

Table 4.5 — Identity & Access

### 4.5.1 Single Sign-On

The single sign-on configuration in effect today is recorded here in enough detail to be reproduced or deliberately replaced. Integrated Windows Authentication and LDAP binds are not federated protocols, and they continue to function in Azure only where the target remains domain-joined with line of sight to a domain controller — which is a directory decision, not a networking one. Protocol, identity provider, trust configuration, signing certificates, claims released and the identifier that uniquely identifies a user are all captured, since an unstable identifier breaks user mapping in the target. Access paths that bypass single sign-on entirely are recorded too, because they survive an identity change unnoticed.

| Is Federated SSO in Use? | Program record — "van led a discussion on current user and app authentication methods, including the use of Entra ID, conditional access policies, service accounts, managed identities, and RBAC for security groups. + Tom and Dale confirmed that on-premises Active Directory groups replicate via AD Connect, and permiss" (ai notes - 2025.11.26 Identity and Access) ¦ "e groups. + Khurshid asked about single sign-on and guest access, and Tom clarified that Entra ID is used for SSO and guest access is supported. + Tom confirmed that single sign-on is managed through Entra ID, and guest access is supported for third-party vendors. + Dale explained that Octa is no lo" (ai notes - 2025.11.26 Identity and Access) (Evidenced — GEHA Identity &amp; Access discovery session, 26-Nov-2025) |
| --- | --- |
| Protocol | Not on file — SAML 2.0 / OIDC / WS-Federation / Kerberos or IWA / header-based. Kerberos and IWA are not federation — flag them as suc. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Identity Provider Product & Version | Not on file — ADFS farm and version, Entra ID, Okta, PingFederate — and whether it is on-premises or cloud-hosted. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| IdP Ownership | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) |
| Trust / Relying Party Configuration | Not on file — Relying party trust or enterprise application name, entity ID or issuer, ACS or reply URL, and where the metadata is pub. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Signing & Encryption Certificates | Not on file — Certificate, thumbprint and expiry for both IdP and SP sides. Every certificate here must also appear in §4.8, and its e. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Claims / Attributes Released | Not on file — Attribute names and sources — UPN, email, employee ID, group claims. Note any attribute the application depends on that. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| NameID Format & Unique Identifier | Not on file — What identifies a user to the application, and whether it is stable across a name change or email change. An unstable id. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| SSO Flow Supported | Not on file — IdP-initiated, SP-initiated, or both — and which one users actually use today, since that is the bookmark that changes a. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Session Lifetime & Timeout | Not on file — Token lifetime, idle timeout, and re-authentication behavior. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| MFA Enforcement Point | Not on file — At the IdP, at the application, or not enforced — and under which conditional access or policy rules. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Non-SSO Access Paths | Not on file — Local or emergency accounts, API keys, or service logins that bypass SSO entirely. These survive an SSO change and are r. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| IdP Migration Dependency | Not on file — Whether the identity provider is itself being migrated, upgraded or retired under another program workstream. If so, thi. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |

Table 4.5.1 — Single Sign-On

### 4.5.2 Authorization & Entitlement Model remove whole sec

Authorization is a separate question from authentication, and it is recorded here layer by layer: what the directory grants, what the application grants, and what the database grants independently of both. The authoritative permission store is named explicitly, together with the person able to export it, because a description of a role model is not an entitlement list. Data-scoping and field-level rules are captured with the mechanism that enforces them, since a rule the target platform cannot enforce becomes a risk rather than a configuration task. A current export of who holds what is the only way to prove after cutover that the target matches the source.

| Data Scoping / Record-Level Rules | Not on file — Restrictions on which records a user can see — by region, business unit, client, claim type, ownership. State the rule a. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| --- | --- |
| Field-Level or Action-Level Restrictions | Not on file — Fields a role can view but not edit, actions gated by approval, dollar or volume thresholds. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Segregation of Duties Constraints | Not on file — Combinations of access that must not be held together, and what enforces the rule today. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Database-Level Permissions | Not on file — Direct database access held by users or tools outside the application — logins, roles, read access for reporting. These. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Delegated Administration | Not on file — Who can grant access without going through IT, and what they can grant. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Access Request & Approval Workflow | Not on file — How a new user gets access today — ticket, manager approval, form, verbal. This process must exist for the target on day. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Access Review / Recertification | Not on file — Cadence, who attests, when it was last performed, and whether findings were remediated. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Documented Entitlement Baseline | Not on file — Whether a current export of who has what exists. If not, take one before cutover — it is the only way to prove the targe. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |

Table 4.5.2 — Authorization & Entitlement Model

### 4.5.3 Non-Interactive & Bypass Access

Mechanisms that operate outside interactive sign-on — API keys, tokens, certificates, key pairs, shared accounts, allowlists and vendor support access — are inventoried here because they persist unchanged through identity migrations and rarely appear in access reviews. The checklist is completed first so that each mechanism is positively confirmed present or absent, rather than left ambiguous by omission. Every entry records who or what uses it, where the credential is held, when it expires or rotates, and whether it bypasses single sign-on altogether. Anything that bypasses sign-on must be closed or formally retained by recorded decision before the go/no-go gate.

| Present | Mechanism | Present | Mechanism |
| --- | --- | --- | --- |
| ☐ | API key or static token | ☐ | OAuth client credentials |
| ☐ | Bearer or personal access token | ☐ | Mutual TLS client certificate |
| ☐ | SSH key pair for SFTP | ☐ | LDAP or directory bind account |
| ☐ | Shared or generic account | ☐ | Smartcard or certificate logon |
| ☐ | IP allowlist used as access control | ☐ | Direct database login |
| ☐ | Kerberos delegation or constrained delegation | ☐ | Local application administrator account |
| ☐ | Vendor or third-party support access | ☐ | Other — specify below |
| ☐ | Confirmed none present |  | Checked by / date: |

Table 4.5.3a — Step 1: Mechanism Checklist

| Mechanism | Who or What Uses It | Credential Type | Issued / Held By | Expiry or Rotation | Bypasses SSO? | Target Equivalent | Disposition |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | Not on file — Key, secret, certificate, key pair, password. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | ☐ Date: ☐ Interval: ☐ None | ☐ Yes ☐ No | Not on file — Vendor mechanism that replaces it, or None available. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | ☐ Replace ☐ Retain ☐ Revoke at cutover |

Table 4.5.3b — Step 2: Mechanism Register

### 4.5.4 Active Directory Security Group Register

Every Active Directory group that governs access to this application is registered here with its effective membership, its owner and its target mapping. Membership counts are taken after nested groups are expanded, because a count read from the group object understates real access and nesting is a common source of entitlement nobody intended to grant. Groups shared with other applications are identified explicitly, since they cannot be retired alongside this application and become coupling findings for the dependency register. Each group resolves either to a target role or to an explicit retirement decision; none may be left unmapped.

| Group Name (full DN) | Access It Grants | Effective Members | Nested Groups | Group Owner | How Membership Is Granted | Used By Other Applications? | Target Role Mapping |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | Not on file — Application role or permission set this group confers. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | — | Not on file — Groups nested inside this one, or None. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | Not on file — Access request workflow, manual add, automated from HR attribute. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | ☐ Yes — name them ☐ No — scoped to this application only | ☐ Target role: ☐ Retire |

Table 4.5.4 — Active Directory Security Group Register

### 4.5.5 Service & Application Account Register

Service and application accounts are registered here separately from user accounts, because they fail differently: nothing breaks at cutover, and then a scheduled job runs and fails silently hours later. Each account records what it authenticates to, where its credential is held, its expiry or rotation position, the rights it carries, and the job or integration that depends on it. Every account must trace to a scheduled job, an integration or an explicit retirement decision; an account tracing to none of these is recorded as an open item. Where a managed identity can replace an account in the target, that substitution is recorded, and where it cannot, the reason is stated.

| Account Name | Type | What It Authenticates To | Credential Holder / Vault | Password Policy & Expiry | Rights Held | Depends On / Used By | Disposition at Cutover |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | Not on file — AD service account / gMSA / local account / SQL login / application-internal account. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Not on file — Target system, share, database or endpoint. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | ☐ Expiry date: ☐ Non-expiring | Not on file — Interactive logon, log on as a service, SPN, group memberships, database roles. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Not on file — Scheduled job in §4.2 or integration in §4.7. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | ☐ Replaced by a target credential in §5.6 ☐ Retained for another purpose ☐ Disabled and deleted |

Table 4.5.5 — Service & Application Account Register

## 4.6 Network

Only the network configuration that must change as a consequence of this migration is documented here; configuration unaffected by the move is deliberately out of scope to keep the record actionable. DNS records are captured with their current resolution, time-to-live values and owning team, because lowering time-to-live ahead of cutover is a lead-time activity rather than a cutover step. Firewall rules that exist solely for this application are identified so they can be removed at decommission rather than left standing indefinitely. External and partner connectivity is recorded separately, since changes at the far end run on someone else's change process and timetable.

| DNS Records | GEHA operates 144 DNS zones (read: DHCP_DNS_list DNS tab). The records for this application must be identified within them before cutover; per-record TTLs are not held in the export. (Evidenced — DHCP_DNS_list (DNS tab)) |
| --- | --- |
| Firewall Rules to Remove | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA, required by 2026-09-01 (Appendix B, item 06). |
| External / Partner Connectivity | Observed outbound destination ports — 443 (HTTPS) — 52 rows; 9998 — 20 rows; 64070 — 11 rows; 8883 — 9 rows; 58320 — 4 rows; 59046 — 4 rows; 58919 — 4 rows; 58828 — 4 rows; 8 out-of-network endpoints (Evidenced — Application Interface Details, full 451,897-row pass, as-of 12/24/25) |

Table 4.6 — Network

### 4.6.1 VPN & Remote Connectivity

Remote access and site-to-site connectivity are treated separately here because they behave differently after a move to Azure. Remote access requirements change rather than disappear, and the answer depends on the connectivity model chosen in the target design, including whether traffic to Azure endpoints is forced back through the corporate tunnel — a frequent and avoidable cause of post-cutover performance complaints. Site-to-site tunnels are jointly owned with external organizations, so their encryption domains, authentication material and far-end contacts are recorded with the lead time each partner's change process requires. Where this application was the only reason a population held VPN access, that access is reviewed rather than left in place.

| Is Remote Access VPN Required to Reach the Application? | Program record — "it ExpressRoute uplink as a potential risk for migration timelines, but stated that using VPNs or publicly reachable storage accounts can bypass this limitation. Firewall management and automation + Ron stated that Azure firewall rules are managed via bicep templates during app deployment, and noted" (ai notes - 2025.11.26 network and connectivity) ¦ "from on-premises infrastructure through edge switches, Palo Alto firewalls, Megaport, and ExpressRoute to Azure. + Ron explained that V hubs are deployed in each Azure region with secured hubs using Azure Firewall, all regions are directly peered, and on-premises ranges connect directly to the Xbox " (ai notes - 2025.11.26 network and connectivity) (Evidenced — GEHA Network &amp; Connectivity discovery session, 26-Nov-2025) |
| --- | --- |
| Solution & Client | Not on file — Product and version, client-based or clientless portal, and whether the client is part of the desktop build in §4.3. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Concentrator / Gateway | Not on file — Device or service terminating the connection, and the team that owns it. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Authentication to the VPN | Not on file — Directory, certificate, MFA — and whether this is a second authentication on top of the application login in §4.5. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Split Tunnel Behavior | Not on file — Whether all traffic or only corporate traffic traverses the tunnel. Tenant traffic forced back through the tunnel adds l. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| User Populations Dependent on It | — |
| Still Required After Cutover? | ☐ Yes ☐ No ☐ Only for other applications — Not on file — if this application was the only reason a population held VPN access, that access should be reviewed rather than left st. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |

Table 4.6.1a — Remote Access VPN

Each site-to-site tunnel is registered individually because changes at the far end are outside GEHA's control and run to the partner's timetable, not the program's. The register records what traffic the tunnel carries, its encryption domain, the device terminating it, the authentication material and its expiry, and a named contact at the far end together with their required notice period. Tunnels shared with other applications are identified explicitly so they are not retired alongside this one. Each tunnel resolves to retirement, retention or modification, and that disposition is agreed with the partner before the cutover window opens.

| Tunnel / Peer | Far-End Organization | Traffic Carried | Encryption Domain | Termination Device | Authentication & Expiry | Far-End Contact | Used by Other Applications? | Disposition |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | Not on file — Partner, vendor or other site. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Not on file — What flows across it, in which direction, and which interfaces in §4.7 depend on it. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Not on file — Local and remote subnets in scope. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Not on file — Firewall or gateway, and the owning team. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Not on file — Pre-shared key or certificate, with rotation or expiry date — add certificates to §4.8. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | ☐ Yes — name them ☐ No — carries only this application | ☐ Retire after cutover ☐ Retain for other traffic ☐ Modify encryption domain |

Table 4.6.1b — Site-to-Site Tunnels

| Incumbent Vendor Support Access | Not on file — How the current vendor or any third party reaches this environment for support — VPN, jump host, remote tool, standing a. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| --- | --- |
| Standing Versus On-Demand | Not on file — Whether that access is always available or requested per incident, and who approves it. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |

Table 4.6.1c — Vendor & Third-Party Access

### 4.6.2 Load Balancer Configuration

| Load Balancer in Use? | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA, required by 2026-09-01 (Appendix B, item 06). |
| --- | --- |

Table 4.6.2a — Load Balancer Configuration

The load balancer configuration is recorded from an exported running configuration rather than from screen captures, because the settings that break applications — persistence profiles, health monitor strings, traffic policies, source address translation and client-IP preservation — are precisely the ones screenshots omit. Each virtual server is documented with its address, the hostnames it serves, its pool members, its balancing method and its TLS termination model. A virtual server that fronts more than one application cannot be retired with this application alone and is recorded as a coupling finding. Certificates presented by the load balancer are cross-referenced to the certificate register and their expiry checked against the cutover date rather than today's date.

| Platform & Version | Not on file — Vendor, model, software version, and whether physical or virtual appliance. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| --- | --- |
| Device Names & HA Model | Not on file — Device hostnames, active/standby or active/active pairing, and the failover mechanism. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Virtual Server / VIP | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) |
| FQDNs Served by This VIP | Not on file — Every hostname resolving here, including SNI-based routing. A VIP serving more than one application is a coupling findin. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Pool & Members | Not on file — Pool name, each member as host and port, and their state. These are the servers in §4.1 — the two lists must agree. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Load Balancing Method | Not on file — Round robin, least connections, ratio, priority groups — and any member weighting. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Persistence / Session Affinity | Not on file — Source address, cookie, TLS session, or none — with timeout. Applications that hold session state in process depend on t. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Health Monitors | Not on file — Monitor type, interval, timeout, and the send and receive strings. A monitor that only checks a port open will not detec. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| TLS Termination Model | Not on file — Offload, re-encrypt or passthrough — this determines where certificates live and what the application sees. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Certificates on the Load Balancer | Not on file — Certificate names, subject and SAN entries, issuer and expiry. Each must also appear in §4.8, and expiry checked against. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Cipher Policy & TLS Versions | Not on file — Permitted protocol versions and cipher suites, and any client certificate authentication requirement. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Traffic Policies, iRules or Scripts | Not on file — Every rule, redirect and rewrite applied — HTTP to HTTPS redirects, path-based routing, header manipulation, maintenance. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| WAF / Security Policies | Not on file — Web application firewall, bot defence, rate limiting or DDoS policy applied to this virtual server, and who owns the pol. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| SNAT / Source Address Translation | Not on file — SNAT pool or automap, and the resulting source addresses seen by back-end servers. These addresses commonly appear in do. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Client IP Preservation | Not on file — Whether X-Forwarded-For or an equivalent header is inserted. Applications and downstream systems that log or authorize o. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Global / DNS-Based Load Balancing | Not on file — Whether a GSLB or DNS load balancing tier sits in front of this VIP across sites, and how it decides. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Configuration Export Held | Not on file — Type of export obtained, the date it was taken, and where it is stored. Record Not obtained as a finding rather than lea. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Configuration Owner & Change Lead Time | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) |
| Disposition at Decommission | Not on file — Retire the virtual server, pool, monitors and certificates — or, where objects are shared with another application, iden. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |

Table 4.6.2b — Load Balancer Configuration

## 4.7 Integrations & Dependencies

Every integration this application participates in is inventoried here, in both directions, with the protocol, frequency and criticality of each. The team owning the far side of the interface is named, because that team controls when the change can be made and their lead time frequently exceeds the migration team's own. Implicit dependencies receive the same treatment as formal interfaces: scheduled jobs on other systems, license servers, mail relays and hardcoded addresses all fail in the same way and for the same reason. This inventory is the input to the target integration design and to the re-pointing tracker executed during the cutover window.

Dependencies are requirements controlled outside this migration and therefore outside the migration team's ability to accelerate. Subscription provisioning, quota increases, circuit changes, policy exemptions, desktop image cadence and the readiness of other waves are typical, and each runs to a schedule owned by someone else. Every entry names an owner, the date by which it is needed and its current status, so that a slipping dependency is visible while there is still time to act. Dependencies at risk are escalated to the program rather than absorbed silently into the application's own float.

Table 10.3 — Dependencies

| System | Direction | Protocol / Method | Frequency | Owning Team (Far Side) | Criticality |
| --- | --- | --- | --- | --- | --- |
| ERWIN | Outbound | observed on ports 64070… (EstServer) | 3018 connection rows | Not on file — far-side owning team not on file (Appendix B item 05). searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | High |
| CES | Outbound | observed on ports 64070… (EstServer) | 1307 connection rows | Not on file — far-side owning team not on file (Appendix B item 05). searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | High |
| CONTROL-M | Inbound | observed on ports 64070… (ctmsca_service) | 535 connection rows | Not on file — far-side owning team not on file (Appendix B item 05). searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Medium |
| ONBASE | Inbound | observed on ports 64070… (Hyland.Core.Scheduler.NTService) | 521 connection rows | Not on file — far-side owning team not on file (Appendix B item 05). searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Medium |
| VERACORE | Inbound | observed on ports 64070… (VeraCore.WindowsServices) | 521 connection rows | Not on file — far-side owning team not on file (Appendix B item 05). searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Medium |
| ARCHER APP | Inbound | observed on ports 59012… (sqlservr) | 512 connection rows | Not on file — far-side owning team not on file (Appendix B item 05). searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Medium |
| BREAKROOM MONITOR SOFTWARE | Inbound | observed on ports 59012… (sqlservr) | 512 connection rows | Not on file — far-side owning team not on file (Appendix B item 05). searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Medium |
| AVAYA | Inbound | observed on ports 59012… (sqlservr) | 512 connection rows | Not on file — far-side owning team not on file (Appendix B item 05). searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Medium |
| FINGER PRINT PRO | Inbound | observed on ports 59012… (sqlservr) | 512 connection rows | Not on file — far-side owning team not on file (Appendix B item 05). searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Medium |
| UIPATH | Inbound | observed on ports 59012… (sqlservr) | 512 connection rows | Not on file — far-side owning team not on file (Appendix B item 05). searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Medium |
| ITSM | Inbound | observed on ports 59012… (sqlservr) | 512 connection rows | Not on file — far-side owning team not on file (Appendix B item 05). searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Medium |
| SECURITY CAMERAS | Inbound | observed on ports 59012… (sqlservr) | 512 connection rows | Not on file — far-side owning team not on file (Appendix B item 05). searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Medium |
| UNIT ASSISTANT | Inbound | observed on ports 59012… (sqlservr) | 512 connection rows | Not on file — far-side owning team not on file (Appendix B item 05). searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Medium |
| GENETEC | Outbound | observed on ports 49468… (sqlservr) | 315 connection rows | Not on file — far-side owning team not on file (Appendix B item 05). searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Medium |
| DBA | Outbound | observed on ports 49731… (sqlservr) | 103 connection rows | Not on file — far-side owning team not on file (Appendix B item 05). searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Medium |
| ARCHER | Outbound | observed on ports 51572… (sqlservr) | 94 connection rows | Not on file — far-side owning team not on file (Appendix B item 05). searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Low |
| GSI | Outbound | observed on ports 65322… (sqlservr) | 72 connection rows | Not on file — far-side owning team not on file (Appendix B item 05). searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Low |
| SCALA | Outbound | observed on ports 57181… (sqlservr) | 47 connection rows | Not on file — far-side owning team not on file (Appendix B item 05). searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Low |
| SCCM | Inbound | observed on ports 49608… (dllhost) | 4 connection rows | Not on file — far-side owning team not on file (Appendix B item 05). searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Low |
| CITRIX | Outbound | observed on ports 62269… (sqlservr) | 3 connection rows | Not on file — far-side owning team not on file (Appendix B item 05). searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Low |
| ORION | Inbound | observed on ports 135… (svchost) | 1 connection rows | Not on file — far-side owning team not on file (Appendix B item 05). searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Low |

Table 4.7 — Integrations & Dependencies

## 4.8 Certificates & Secrets

Every certificate and secret the application depends on is inventoried here, with expiry evaluated against the planned cutover date rather than against today. A certificate that is comfortably valid now but expires during the migration window will fail at the least convenient moment, and renewal frequently involves a third party with its own lead time. Each entry records its purpose, where the private material is held, who custodies it, and the action to be taken — renewal, retirement, or migration to a vault in the target. Certificates presented by load balancers and identity providers appear here as well as in their own sections, so that nothing depends on a reader cross-referencing two lists.

| Certificate / Secret | Purpose | Holder / Vault | Expiry | Expires Before Cutover? | Action |
| --- | --- | --- | --- | --- | --- |
| geha.com - 2 | TLS / service certificate | Microsoft Azure (b7c537d8-4835-4261-b3ad-6a6d8cbb84b2) (b7c537d8-4835-4261-b3ad-6a6d8cbb84b2) | 2026-06-13 00:00:00 | — | — |
| testing.com | TLS / service certificate | Microsoft Azure (b7c537d8-4835-4261-b3ad-6a6d8cbb84b2) (b7c537d8-4835-4261-b3ad-6a6d8cbb84b2) | 2026-06-13 00:00:00 | — | — |

Table 4.8 — Certificates & Secrets

## 4.9 Data Classification

The sensitivity of the data this application holds, and the regulatory obligations that follow from it, are recorded here because they constrain target region, encryption, logging and retention decisions rather than merely describing them. Presence of protected health information, personally identifiable information or cardholder data is stated explicitly rather than implied by the application's business purpose. Residency constraints are captured because they determine not only where the workload runs but where its backups and diagnostic logs may be held. Current encryption at rest and in transit is recorded so the target can be shown to preserve or improve the position rather than quietly weaken it.

| Data Sensitivity | Criticality tier 3 (2 - Medium). Business impact: Impact to the application may result in the loss of certificate management. (Evidenced — BIA_Capability and Application_DC Migration (Application BIA), as-of 13-Nov-2025) |
| --- | --- |
| PII / PHI / PCI Present | ☐ Yes ☐ No — Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) |
| Data Residency Constraints |  |
| Current Encryption at Rest | ☐ Yes ☐ No — Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) |
| Current Encryption in Transit | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) |

Table 4.9 — Data Classification

## 4.10 Environment Inventory

Every environment is inventoried here, not only production, because non-production estates carry real data, real integrations and real license obligations far more often than expected. Each environment records its purpose, its endpoint, the nature of the data it holds and the internal move group it belongs to. Non-production is migrated ahead of production deliberately, so that the process is proven on a system whose failure costs nothing. Environments that are dormant or unused are identified here as retirement candidates rather than migrated by default.

| Environment | Purpose | URL / Endpoint | Data Source | Migration Wave |
| --- | --- | --- | --- | --- |
| PROD | Live business use | Not on file — endpoint URL not on file (Appendix B item 05). searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Live data | 5 host-rows observed |

Table 4.10 — Environment Inventory

## 4.11 Availability & Backup Position

Availability and backup posture is recorded here to the extent that it bears on the migration itself, rather than as a description of steady-state operations. Cluster and replication topology is captured because it determines which migration methods are available, and a verified restore point is captured because it is the only genuine protection across the cutover window. The recovery point the current configuration actually delivers is recorded alongside the objective the business believes it has, since the two frequently differ and the target should not be designed to an aspiration. Retention and legal-hold obligations, and any standby copy holding live data, are recorded because both outlive the source system.

| High Availability Topology | Daily Full Restore; LogShipping; Manual Full Restore (Evidenced — DBA Migration Artifacts) |
| --- | --- |
| Known Single Points of Failure | Not on file as an analysis — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B, item 05). Observed: a single production database (venafi_tpp) with one log-shipped secondary; a single DMZ discovery host (VENAFIPRD103). |
| Backup Product & Schedule | Database: LiteSpeed — daily full + 15-minute log backups; retention daily 8 weeks / weekly 1 year / monthly 3 years; backups encrypted using LiteSpeed (Evidenced — Discovery Report Inventory v1.0, Data and Databases). VM level (vCenter export, Backup Policy column): VENAFIPRD101 “8WK Backup - Crash Consistent”; VENAFIPRD102 and VENAFIPRD103 “8WK Backup”; VENAFIPOC101 “2WK Backup”; LXENTSQL35 “8WK Backup”; no policy recorded for ENTSQL35 — absence recorded (Evidenced — Server_VM_Inventory LS/LX). Target protection: Cohesity DataProtect (Appendix A ref. REG-017). |
| Most Recent Verified Restore | Monthly restore validation/testing is the recorded regime for the SQLCOTS databases (Evidenced — Discovery Report Inventory v1.0, Data and Databases); no dated last-restore record on file — requested from GEHA (Appendix B, item 17). |
| Retention & Legal Hold | Backup retention: daily 8 weeks, weekly 1 year, monthly 3 years (Evidenced — Discovery Report Inventory v1.0, Data and Databases). Legal-hold obligations not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B, item 12). |
| Achieved RPO Today | RTO 6 hours / RPO 15–30 minutes recorded at the database tier for the SQLCOTS instance (Evidenced — Discovery Report Inventory v1.0, Data and Databases). GEHA response for the Venafi service itself: SLA/RTO/RPO “Not defined” (Session 1 responses). |
| DR Replica or Standby Copy | Daily Full Restore; LogShipping; Manual Full Restore (Evidenced — DBA Migration Artifacts) |

Table 4.11 — Availability & Backup Position

# 5. Target State

## 5.0 Target State Architecture Diagram

## 5.1 Compliance & Security Verification

Assurance for a vendor-operated service rests on evidence the organization has actually obtained and read, and this section records that evidence rather than the vendor's claims about it. Each artifact — an audit report, penetration test summary, certification, or architecture attestation — is logged with its issue date, expiry date, the reviewer who assessed it and the findings that assessment produced. Expiry dates are recorded because an assurance artifact that lapses mid-contract leaves an evidentiary gap that has to be refreshed on a schedule. Findings are captured even when they are accepted, so that residual risk is visible to the approvers rather than filtered out during review. A certification asserted in marketing material but not backed by an obtained artifact is treated as unevidenced and is recorded as such.

| Artifact | Obtained | Report Date | Valid Until | Reviewed By | Exceptions / Findings | Accepted By |
| --- | --- | --- | --- | --- | --- | --- |
| Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | ☐ Y ☐ N | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) |
| Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | ☐ Y ☐ N | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | — | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | — | — |
| Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | ☐ Y ☐ N | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | — | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | — | — |
| Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | ☐ Y ☐ N | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | — | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | — | — |

Table 5.5 — Compliance & Security Verification**

## 5.6 Identity & Access

The target identity design must account for every entry in the current-state identity registers; unresolved entries are the single most common cause of access failure after cutover. The directory model is stated first, since it determines whether domain-joined authentication remains available or whether the application must move to a federated protocol. Group-to-role mapping is recorded one row per source group, with no group left unmapped, and service accounts resolve either to a managed identity or to a credential with a named rotation owner. Break-glass and privileged access are defined explicitly, including how their use is detected.

| Is SSO In Scope for the Target? | ☐ Yes ☐ No — Not on file — if the current state in §4.5.1 is not federated, this is new work with its own build, test and IdP change control — size. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| --- | --- |
| Federation Protocol | Not on file — SAML 2.0 / OIDC — as supported by the vendor on the edition purchased. Confirm the edition includes it; SSO is frequentl. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Identity Provider | Entra id Program record — "van led a discussion on current user and app authentication methods, including the use of Entra ID, conditional access policies, service accounts, managed identities, and RBAC for security groups. + Tom and Dale confirmed that on-premises Active Directory groups replicate via AD Connect, and permiss" (ai notes - 2025.11.26 Identity and Access) ¦ "e groups. + Khurshid asked about single sign-on and guest access, and Tom clarified that Entra ID is used for SSO and guest access is supported. + Tom confirmed that single sign-on is managed through Entra ID, and guest access is supported for third-party vendors. + Dale explained that Octa is no lo" (ai notes - 2025.11.26 Identity and Access) (Evidenced — GEHA Identity &amp; Access discovery session, 26-Nov-2025) |
| Metadata Exchange, Claims / Attribute Mapping | Not on file — Not on file — Source attribute to vendor-expected claim, one row per claim. Compare against what the IdP releases today in §4.5. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Entity ID, ACS and Sign-Out URLs | Not on file — |
| Signing Certificate & Rotation | Not on file — Certificate in use, expiry, who is notified before rotation, and what breaks if it lapses. Add it to the §4.8 register. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| SSO Flow & User Entry Point | Not on file — IdP-initiated tile or SP-initiated URL — this determines what users are told in §5.11 and §6.6. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Fallback If Federation Fails | Not on file — Whether local authentication exists, who holds it, and how it is controlled — see break-glass below. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Provisioning Method | Not on file — SCIM automated / API / manual / CSV import — this determines the effort in §7.5. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Target Authorization Model | Not on file — How entitlement is determined in the tenant — federated group claims, in-app roles assigned per user, or both. State whi. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Entitlement Mechanisms Without a Target Equivalent | Not on file — Anything from the §4.5.2 authorization model the vendor cannot reproduce — data scoping, field-level rules, segregation. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Programmatic Access Design | Not on file — Target equivalent for each row of the §4.5.3 non-interactive and bypass access register — API credentials, certificates,. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Access Request & Approval Process | Not on file — The joiner, mover and leaver process for the tenant, named owner, and the date it becomes operational. It must be live b. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Access Review / Recertification | Not on file — Cadence, attester, and how an entitlement export is obtained from the vendor — confirm the export exists before committi. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Group-to-Role Mapping | Not on file — One row per source group from the §4.5.4 register to its target role. Attach the mapping table; a description is not a m. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Groups Required in the Target | Not on file — Whether new groups must be created, who creates them, and their naming standard. State whether existing groups are reuse. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Users With Access Not Governed by a Group | Not on file — Direct assignments found during the §4.5.2 review, and whether each is carried across or removed. This is the usual sour. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| External / Partner Access | Not on file — How non-employee accounts authenticate, and who sponsors each. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| MFA Enforcement | Not on file — Enforced at IdP or vendor-native. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Service & API Accounts | Not on file — Target-side credential for each account in the §4.5.5 service account register — auth method, secret storage, rotation o. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Break-Glass Access | Not on file — Emergency administrative access if federation fails, and who holds it. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |

Table 5.6 — Identity & Access

## 5.8 Integrations

dependency on Archer (shares same backend database instance, plan is to unpin database for Venafi freeing shared database configuration)

| System | Direction | Method & Endpoint | Authentication | Vendor Limits | Owning Team (Far Side) |
| --- | --- | --- | --- | --- | --- |
| Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | Not on file — REST / webhook / iPaaS / SFTP. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Not on file — OAuth client, key, certificate. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Not on file — Rate limit, payload cap, batch window. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) |

Table 5.8 — Integrations

| Dependency | Type | Owner | Needed By | Status |
| --- | --- | --- | --- | --- |
| Not on file — Other application, wave, project, vendor commitment or infrastructure change. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). | ☐ Internal ☐ Other wave ☐ Vendor ☐ External | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | ☐ On track ☐ At risk ☐ Blocked |

## 5.9 Network Connectivity

Reaching a vendor-hosted tenant is a network design problem even when no infrastructure is being built, and this section defines that path for each class of consumer. It records how interactive users reach the service, how server-side integrations authenticate and egress, and how external partners connect, since these three routes frequently differ in both protocol and control point. The organization-side changes required to enable that access are enumerated explicitly — firewall rules, egress allow-lists, proxy exceptions, DNS entries, certificate trust and any private connectivity — because each is a change request with its own lead time and approver. IP allow-listing on the vendor side is captured where it applies, together with who maintains that list after go-live. Anything requiring a change to a shared network control is flagged so that its owner outside this application is identified before the cutover window is fixed.

| Connectivity Model | Not on file — Public internet over TLS, or a private connectivity option if the vendor offers one. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| --- | --- |
| Vendor Endpoints to Allow | Not on file — FQDNs and ports required outbound, including any regional variants. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Our Egress IPs for Vendor Allowlisting | Not on file — Addresses the vendor must allow, and who provides them. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| DNS Changes | Not on file — Records to create, change or retire, with owning team and TTL plan. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Client-Side Access | Not on file — Proxy, VPN or filtering changes needed for end users to reach the tenant. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| VPN Still Required? | Not on file — Whether users need the corporate VPN to reach the tenant at all. If not, say so plainly — it is a visible improvement an. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Split Tunnel / Proxy Treatment of Vendor Endpoints | Not on file — Whether vendor FQDNs are excluded from the tunnel or from proxy inspection, who makes that change, and its lead time. Te. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Partner Connectivity to the Vendor | Not on file — How external parties reach the tenant once the tunnel in §4.6 no longer carries them — internet with allowlisting, vendo. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |

Table 5.9 — Network Connectivity

## 5.12 Scheduled Job & Batch Orchestration

Scheduled jobs are frequently assumed to travel with the server, which is true only where the scheduler runs locally. Where an enterprise scheduler triggers the job, every one requires its own endpoint change, credential and agent work carried out by the team that owns the scheduler, on their timetable. Each job recorded earlier resolves here to a target trigger, an owning team, an identity it runs as, and the date and time of its first execution after cutover together with the person confirming it succeeded. Time-zone differences between the source datacenter and the target region are checked, since a job scheduled for 02:00 local will not run at the same hour after the move.

| Job / Batch | Kick off time |
| --- | --- |
| Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) | Not on file — Enterprise scheduler, Task Scheduler, cron, SQL Agent, application-internal. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |

Table 5.12a — Scheduled Job & Batch Orchestration

## 6.3 Migration Rehearsal

The rehearsal is the only activity in this playbook that produces measured facts rather than planned intentions, which is why it governs the cutover plan rather than informing it. A full rehearsal exercises the complete sequence — extract, transform, load, validate and functional check — against production-representative volumes, so that the timings it produces can be relied upon when the window is fixed. Each rehearsal is recorded with its date, the data set used, the durations observed at each stage, the defects raised and their resolution. A rehearsal is not complete when the load finishes; it is complete when its output has been reconciled against the source and the discrepancies have been explained or corrected. Where a rehearsal is repeated, the results of each pass are retained so that improvement between passes is visible and the final timings are traceable.

| Rehearsal Scope | Not on file — Full extract, transform and load, or a defined subset — state what is excluded and why. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| --- | --- |
| Environment | Not on file — Which tenant, and how closely its data resembles production. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Number of Passes Planned | Not on file — Minimum two — the last must be defect-free. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Success Criteria | Not on file — Load completes within the cutover window, reconciliation passes at the §7.8 tolerance, no open Sev1 or Sev2 defects. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Timings Captured | Not on file — Elapsed time per step, carried into the §7.3 schedule. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Defects Raised & Cleared | Not on file — Reference to the defect log, with the count outstanding. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Rollback Rehearsed | ☐ Yes ☐ No — Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) |
| Sign-Off | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) |

Table 6.3 — Migration Rehearsal

## 6.4 Testing Strategy

The testing strategy defines what will be tested, by whom, and the conditions under which testing may start and must stop. Functional, data validation, integration, performance, security, backup and recovery testing each carry their own entry and exit criteria, expressed as conditions rather than as opinions. Performance exit criteria are set against the documented baseline recorded earlier, which converts an argument about whether the system feels slower into a measurement. Sign-off is by named individuals, because an untested assumption discovered after go-live is indistinguishable from a defect.

## 6.5 Change Freeze

The application migration is going to follow the constraints defined by GEHA's blackout calendar like current change freeze dates

# 7. Cutover Runbook

## 7.1 Go / No-Go Gate

The go/no-go gate is the formal point at which cutover is authorized, and it is decided against documented evidence rather than confidence. It is scheduled with enough lead time that a no-go outcome can actually be acted upon, which means days rather than hours before the window. A single named individual owns the decision, the rule by which the decision is made is stated in advance, and the attendees whose absence would postpone it are named. Each criterion references the section that produces its evidence, so the gate is a review of facts already established rather than a fresh discussion.

## 7.2 Cutover Team & Bridge

The cutover team is named here individually, with a designated backup and a reachable telephone number for every role, because a role covered by a team name is a role nobody is holding at two in the morning. Availability is stated as hours rather than as intent. The bridge is live for the whole window, the status update cadence is fixed in advance, and the escalation path states who is woken and in what order. This section exists so that the window is worked by a team that knows its shape before the first step begins.

## 7.3 Cutover Schedule

The cutover schedule is the executable document for the window, written to be used by staff who were not present at the design sessions. Absolute clock times with a stated time zone are used rather than relative durations, and every duration is taken from the rehearsal rather than estimated. Each step carries a named owner, a verification that confirms completion before the next step begins, and the condition that would trigger rollback. Cumulative elapsed time is shown so that the total is visible before the window is committed; if the total exceeds the agreed outage, the plan is not ready.

## 7.4 Data Cut-Off

The data cut-off is the moment the source system stops accepting work, and it is stated as an exact time with a time zone rather than as a rough intention. Transactions already in flight at that moment need a defined treatment, as does business activity that occurs while the system is unavailable and must be re-entered afterwards. Batch files and feeds that arrive during the window are held somewhere deliberate rather than lost. Getting this wrong produces data that exists in neither system, which is the hardest category of migration defect to detect and to remedy.

## 7.5 Account & Access Migration

Access is what makes a tenant a service, and this section defines how identities, entitlements and access paths transition at cutover. It records the source of identity for the target product, the provisioning mechanism, how groups and roles map from the legacy model, and how privileged access is established and controlled. The work is deliberately split into what can be pre-staged — accounts created, groups populated, federation configured and tested — and what must occur inside the window, which is usually only enablement and a verification pass. This split is what keeps the outage short, since bulk provisioning performed during the window is a predictable cause of overrun. The section also states how access to the legacy application is withdrawn and when, so that two live access paths do not persist after cutover.

## 7.9 Rollback

Rollback is defined in advance because the moment it is needed is the worst moment to design it. This section states the conditions under which rollback is invoked, who holds the authority to make that call, and the point in the cutover sequence beyond which return to the legacy application is no longer practical. The procedure itself is recorded step by step, including how access is restored, how integrations are repointed and how any data created in the target tenant during the failed cutover is preserved or discarded. The time required to execute rollback is stated, because it must fit inside the agreed outage window alongside the forward path. Where rollback is genuinely not available after a defined point, that is recorded plainly so the go/no-go decision is made with that constraint understood.

| Rollback Trigger Criteria | Not on file — Objective conditions, tied to the verification failures in §7.3. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| --- | --- |
| Rollback Decision Deadline | Not on file — The clock time by which rollback must be invoked to complete before the business day — after this, the decision is made. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Rollback Steps | Not on file — Re-enable legacy access, revert DNS, restore integrations, notify partners and users. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Rollback Duration | Not on file — Measured in rehearsal, not estimated. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Point of No Return | Not on file — The specific step number in §7.3 after which rollback is no longer viable, and why. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Data Entered After Cutover | Not on file — The treatment of transactions entered in the tenant if rollback is invoked — extracted and re-keyed, or lost. Determine. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Rehearsed | ☐ Yes ☐ No — Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) |
| Rollback Authority | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) |

Table 7.9 — Rollback

# 8. Post-Cutover & Service Handover

The post-cutover period is treated as a defined stage with entry and exit conditions rather than as an indefinite settling-in. Hypercare, verification of operational controls in production, decommissioning of the source and the review that feeds the next migration each have their own criteria. Every stage exits on documented evidence rather than on elapsed time, because a quiet fortnight is not the same thing as a stable service. Handled properly, this section is where a migration becomes an operational reality rather than a completed project.

## 8.1 Hypercare

Hypercare is the period of heightened support immediately after go-live, and it is defined here with a named roster, coverage hours and an escalation path rather than an assumption that the migration team remains available. Its exit criteria are objective — a stated number of consecutive days without severity one or two incidents, with backup and monitoring proven in steady state — so that the end of hypercare is a demonstrated condition rather than a date in a plan. The steady-state support owner is named, and the handover to them is explicit. Issues raised during hypercare are triaged through a defined route so that nothing depends on knowing which individual to telephone.

| Hypercare Period | SOW record — ", communication plan, service desk readiness checklist, and hypercare approach. 1 Software Development Units are registered with Special Economic Zones or Software Technology Parks. G.E.H.A. Data Center Transition and Cloud Migration SOW 3 Scope of Services • Program Management: Establish and manage the integrated project plan, assumptions log," (Evidenced — SOW ZCON-18111, signed 30-Jul-2026) |
| --- | --- |
| Hypercare Roster | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) |
| Steady-State Support Owner | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) |
| Issue Triage Process | Not on file — How issues are logged, triaged, and routed between our team and the vendor. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Escalation Path | Not on file — Sev1 and Sev2 contacts, internal and vendor, with response expectations. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Exit Criteria | Objective — |

Table 8.1 — Hypercare

## 8.2 Operational Readiness

8.3 Decommission

## 8.4 Post-Migration Review

What worked and what did not is recorded here while the detail is still recoverable, so that the next application in the program benefits rather than repeats. Root causes are recorded rather than symptoms, and steps whose actual duration differed materially from plan are corrected for future playbooks. Changes to the rollback procedure are captured whether or not rollback was invoked, since a plan that was never exercised is still a plan that can be improved. A review that produces no change to the next playbook or to the program process has not been completed.

| What Worked | Not on file — Practices to repeat, stated specifically enough to be reused. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| --- | --- |
| What Did Not | Not on file — Steps that failed, ran long, or were discovered late — with the root cause, not the symptom. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Rollback Procedure Corrections | Not on file — Changes to the §7.9 rollback steps, triggers, or timings arising from this migration, whether or not rollback was invoke. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Schedule Corrections | Not on file — Steps in §7.3 whose actual duration differed materially from plan, with the corrected figure for future playbooks. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Template or Process Changes | Not on file — Changes required to this playbook template or the program process, with the owner who will make them. searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B). |
| Reviewed By & Date | Not on file — searched the full evidence pack — Server_VM_Inventory (LS/LX), Matilda Discovery Assessment (all visible tabs), GEHA_SQLServers_DBDetails_Inventory, DBA Migration Artifacts, Discovery Report Inventory v1.0 (incl. Data and Databases), BIA_Applications_20251113, BIA_Capability_and_Application, Applications Sessions 1–3 responses, DHCP_DNS_list, Policy_list, Key_Vault_Certs_20251110, Subscription_Management_Groups and vmware_hosts_DRS — no record for this application; requested from GEHA (Appendix B) |

Table 8.4 — Post-Migration Review

# 9. Roles & Responsibilities

Responsibility across the migration lifecycle is assigned here using the RACI model, with exactly one accountable owner for each task. The distinction between responsible and accountable matters most at the two points where migrations stall: the go/no-go decision and the rollback decision. Consulted and informed parties are recorded so that teams learn of changes affecting them before rather than after the event. Where this matrix and the ownership register disagree, the ownership register governs and the discrepancy is corrected here.

| Task | App Owner | Migration Team | SaaS Vendor | Security | End Users | Admin / Support Manager Phil Costanzo |
| --- | --- | --- | --- | --- | --- | --- |
| Tenant configuration | C | A/R | C | C | I | C |
| Data mapping & load | C | A/R | C | I | I | C |
| Identity & SSO configuration | C | R | C | A | I | C |
| Account build & role mapping | A | R | C | C | I | C |
| Integration re-point | I | R | C | C | I | A |
| External partner coordination | A | R | I | I | I | I |
| Dress rehearsal | C | A/R | C | I | I | C |
| Go / no-go decision | A | R | I | C | I | C |
| Cutover execution | A | R | C | I | I | C |
| Reconciliation & acceptance | A | R | I | I | C | C |
| Rollback decision | A | R | I | I | I | C |
| Operational readiness | C | R | C | A | I | C |
| Decommission | A | R | I | C | I | C |

Table 9 — Roles & Responsibilities

# 10. Risks, Assumptions, Dependencies & Open Items

Four distinct records are maintained here, and keeping them distinct is what makes them useful. A risk is an event that may occur; an assumption is a reliance not yet verified; a dependency is a requirement controlled by someone outside this migration; and an open item is a question with an owner and a due date. Collapsing them into a single list, which is the usual habit, obscures the fact that they need entirely different treatment. Each record is maintained live through execution rather than completed once at authoring and left to age.

## 10.1 Risks

The risk register records potential events only. An event that has already occurred is an issue and is managed as one, and a reliance not yet verified is an assumption and belongs in the register that follows; keeping the boundary sharp is what stops the register becoming a list of everything anyone is uneasy about. Each risk carries a likelihood, an impact, a mitigation expressed as an action rather than an intention, and a named owner. Risks are reviewed at each program checkpoint rather than at authoring time alone.

| Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| Binding contract cliff 12/19/26 sits only 2 days after the 12/17/26 cutover — any slip past Saturday 12/19/26 triggers the $126,961/yr renewal (BASELINE v2.1 Wave Sequence: margin 2, binding yes) | — | — | Hold the SQLCOTS night; escalate any slip immediately — there is no recovery slot before the cliff | Eric Ullmann |
| CLOSED 26-Aug-2026 — CLUSTER R1 SPLIT superseded by BASELINE v2.1: Archer and OnBase are Wave 1 (29-Oct-26), UiPath/Venafi/Veracore share the 17-Dec-26 SQLCOTS night, Security Cameras relocates (no Azure migration) | — | — | Tracked on the program wave board | Eric Ullmann |
| CLOSED 26-Aug-2026 — engine flag “achievable 2026-10-06 vs plan 2026-09-05” superseded: plan-of-record cutover is 12/17/26 (BASELINE v2.1) | — | — | Tracked on the program wave board | Eric Ullmann |

Table 10.1 — Risks

## 10.2 Assumptions

Every assumption carries an owner and a date by which it must be confirmed or converted into a risk, because an assumption that is never tested becomes a defect at cutover. What is being taken as true is stated plainly alongside what breaks if it proves false, which is what allows the assumption to be prioritized rather than merely listed. Assumptions confirmed by evidence are marked as such with their source, and those that fail are escalated rather than quietly amended. This register is reviewed at the readiness review and again at the go/no-go gate.

| Assumption | Why It Matters | Confirm By | Owner | Status |
| --- | --- | --- | --- | --- |
| Ruled effort size M = 8 weeks; 4 parallel migration tracks | Drives the cutover date and wave capacity | To be confirmed by GEHA | GEHA PMO | Open |
| Wave window 2026-08-01 onward per the program wave plan | Cutover must fall inside the wave window | Confirmed in the Wave Plan Tracker | CitiusTech | Confirmed |

## 10.4 Open Items

Every unresolved question and unassigned ownership raised anywhere in this playbook is collected here, so that nothing depends on a reader noticing a gap buried in a distant section. Each item carries an owner, a due date and a status, and items are closed with the answer recorded rather than simply removed. This register is the practical agenda for the recurring working session with GEHA. An item still open at the go/no-go gate is a decision for the gate rather than an administrative loose end.

| Item | Raised | Owner | Due | Status |
| --- | --- | --- | --- | --- |
| Appendix B item 01 — Azure Migrate project access / first discovery export | 14-Aug-2026 | GEHA (request not yet sent) | 08/25/26 — ELAPSED as of 26-Aug-2026 | Open |
| Appendix B item 02 — Formal G-1 gate completion date | 14-Aug-2026 | GEHA (request not yet sent) | 08/18/26 — ELAPSED as of 26-Aug-2026 | Open |
| Appendix B item 07 — SharePoint playbook library: listing export or W1 zip | 14-Aug-2026 | GEHA (request not yet sent) | 08/21/26 — ELAPSED as of 26-Aug-2026 | Open |
| Appendix B item 10 — Capacity parameters: tracks, freeze calendar, LZ readiness | 14-Aug-2026 | GEHA (request not yet sent) | 08/31/26 — imminent (26-Aug-2026) | Open |
| Appendix B item 11 — Out-of-plan SQL tenant dispositions (incl. CONTROL-M) | 14-Aug-2026 | GEHA (request not yet sent) | 01/31/27 | Open |
| Appendix B item 12 — Backup policy export + per-app protection groups (Cohesity) | 14-Aug-2026 | GEHA (request not yet sent) | 09/30/26 | Open |
| Appendix B item 14 — Current DNS zone + firewall rule exports (refresh) | 14-Aug-2026 | GEHA (request not yet sent) | 09/30/26 | Open |
| Appendix B item 16 — Table-level write audit: per-DB object permissions + SQL Audit/Query Store capture of writes by login | 14-Aug-2026 | GEHA (request not yet sent) | 09/15/26 | Open |
| Engine flag: CLUSTER R1 SPLIT — Archer W3, OnBase W3, Security Cameras W4, UiPath W2, Veracore W3 (by ruling/manual placement) | 14-Aug-2026 | CitiusTech migration lead | — | Closed 26-Aug-2026 — superseded by BASELINE v2.1 (see §10.1) |
| Engine flag: achievable 2026-10-06 vs plan cutover 2026-09-05 (+31d late) | 14-Aug-2026 | CitiusTech migration lead | — | Closed 26-Aug-2026 — superseded by BASELINE v2.1 (see §10.1) |

Table 10.4 — Open Items

# 12. Sign-Off

Approval to execute is recorded here, and each signatory is a named individual accountable for the sections relevant to their role rather than a representative of a team. Signing confirms that the target design, the cutover plan and the rollback position documented in this playbook are approved for execution as written. Signatures are obtained before the go/no-go gate rather than retrospectively. A playbook signed on this basis is the authority under which the cutover proceeds.

By signing below, stakeholders confirm that the vendor boundary, tenant configuration and cutover plan documented in this playbook are approved for execution.

| Name | Role | Date |
| --- | --- | --- |
| Eric Ullmann (Owners tab row 9, BASELINE v2.1) | Application Owner |  |
| To be provided by GEHA | Migration / Technical Lead |  |
| To be provided by GEHA | Security |  |
| Christy Ammel (DBA / Production Control — program record) | DBA / Production Control |  |
| To be provided by GEHA | Network |  |
| To be provided by GEHA | Procurement / Vendor Management |  |

Table 12 — Sign-Off