## Cover Page
CyberArk PAS Test Cases
Project Name: | GEHA Data Center Migration: CyberArk PAS |  |  | Client Name: | GEHA
Application: | CyberArk PAS, Privilege Cloud connectors |  |  | Application Owner: | Eric Ullmann, GEHA Security
Scope: | Dev first, then production |  |  | Test Cases: | 61 cases
Prepared By: | CT Team |  |  | Peer Reviewer: | George Gallindo
Version / Date: | 1.0 / 05-10-2026 |  |  | Status: | Draft for GEHA review
Document Revision History:
Document Version # | Revision Date | Prepared By | Approved By | Approval Date | Summary of Changes
1 | 2026-10-05 | Saikat/Amitendra | TBD
1.1 | 2026-10-06 | Saikat/Amitendra | TBD |  | Added 47 test cases and extra steps in 10 existing test cases from the Post-Migration Test and Validation Plan v2.1 (platform build, network paths, tenant registration, brokered sessions, parallel run, operations, cutover and disaster recovery).
This document is CitiusTech Internal and contains proprietary information, including trade secrets of CitiusTech or the Client. Neither the document nor any of the information contained in it may be reproduced or disclosed to any unauthorized person under any circumstances without the express written permission of CitiusTech.

## TC-INF-01
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm the internal load balancer health probes show both connectors as healthy | Module/Program Name/Menu Path: | Phase 1: Azure infrastructure and network connectivity Azure portal > Internal load balancer > Backend pools, Monitoring > Metrics, Load balancing rules
Test Case ID: | TC-INF-01 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm both connector servers are members of the internal load balancer backend pool, both are healthy on the RDP and session manager probes, and the RDP rule forwards TCP 3389 to 3389. | Pre-requisites/Test Set-up: | 1. Both connector servers, their network interfaces and the internal load balancer have been deployed through the Bicep pipeline, and the pipeline run finished without errors. 2. The connector software is installed on both servers through Connector Management, both are on the same version, and both have been restarted after installation. 3. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off.
Dependencies (H/W and S/W): | 1. Azure portal access to the CIP-DEV subscription (non-production) or the CIP-PRD subscription (production). 2. Internal load balancer: recorded before testing in non-production; lbi-sec-cyberark-cus-prd-01 in rg-sec-cyberark-prd in production. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (Build engineer) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | In the Azure portal, open the internal load balancer for the environment. | Non-production: load balancer name recorded before testing Production: lbi-sec-cyberark-cus-prd-01 | The internal load balancer for the environment opens in the portal.
2 | Open Backend pools and confirm both connector network interfaces are members. | Non-production: connector 01 (zone 1) and connector 02 (zone 2) Production: vm-sec-cyberark-cus-prd-01 and 02 (AZPASPCCPRD101 and AZPASPCCPRD102) | Both connectors are in the backend pool.
3 | Open Monitoring, Metrics, choose Health Probe Status and split by backend IP address. Record the result for each server on both probes. | RDP probe: TCP 3389 Session manager health check: HTTPS 443 (/psm/api/health) | Both connectors show 100% healthy on both probes.
4 | Open Load balancing rules and record the RDP rule and its idle timeout. | RDP rule: TCP 3389 | The RDP rule forwards TCP 3389 to 3389. The idle timeout is recorded.
5 | Open the load balancer overview and Frontend IP configuration, and record the SKU and front end against the build tables load balancer parameters. | lbi-sec-cyberark-cus-prd-01 Front end: 10.9.250.7 | Standard regional SKU with a zone-redundant static front end at 10.9.250.7.
6 | Open the RDP rule and both health probes and record session persistence, TCP reset, probe interval and unhealthy threshold. | rule-rdp probe-rdp probe-psm-health | rule-rdp forwards TCP 3389 to 3389 with no session persistence, idle timeout 20 minutes and TCP reset enabled. probe-rdp on TCP 3389 and probe-psm-health on HTTPS 443 /psm/api/health, interval 30 seconds, unhealthy threshold 3.

## TC-INF-02
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm the connection name resolves to the load balancer private front-end address | Module/Program Name/Menu Path: | Phase 1: Azure infrastructure and network connectivity GEHA DNS: nslookup from an administrative workstation and from connector 01; session manager health page in a browser
Test Case ID: | TC-INF-02 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the name users connect to resolves to the load balancer private front-end address from both the GEHA network and the connector, no public address is returned, and the health page answers with a trusted certificate. | Pre-requisites/Test Set-up: | 1. The connection name for the environment exists in GEHA DNS and points at the load balancer front-end address. 2. An administrative workstation on the GEHA network is available, and connector 01 can be reached through the approved administrative path. 3. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off.
Dependencies (H/W and S/W): | 1. Administrative workstation on the GEHA network with a web browser. 2. Connector 01. 3. Azure portal access to view the load balancer front-end address. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (Build engineer) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | From an administrative workstation on the GEHA network, run nslookup for the connection name. | Non-production: nslookup cyberark-connector-dev.geha.com Production: nslookup cyberark-prd.geha.com | The name resolves to the load balancer private front-end address . No public address is returned.
2 | Run the same lookup from connector 01. | Non-production: nslookup cyberark-connector-dev.geha.com Production: nslookup cyberark-prd.geha.com | The name resolves to the load balancer private front-end address. No public address is returned.
3 | Compare the address returned with the load balancer front-end address shown in the Azure portal. | Non-production: front-end address recorded before testing Production: 10.9.250.7 | The address returned from both machines matches the load balancer front-end address.
4 | From the workstation, browse to the session manager health page using the connection name. | https://<connection name>/psm/api/health | The health page returns HTTP 200 with a trusted certificate.
5 | Request the health page directly on each connector, substituting the connector name. | https://<connector>/psm/api/health | HTTP 200 from each server.

## TC-INF-03
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm approved firewall paths are allowed and traffic to unmigrated on-premises servers is blocked | Module/Program Name/Menu Path: | Phase 1: Azure infrastructure and network connectivity Hub firewall; PowerShell Test-NetConnection on connector 01 and connector 02
Test Case ID: | TC-INF-03 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the hub firewall lets the connectors reach the approved destinations and blocks an Azure connector from reaching an on-premises server that has not migrated yet. | Pre-requisites/Test Set-up: | 1. The CyberArk rule set is applied to the hub firewall: the approved ports are open, and the rule that blocks connector traffic to unmigrated on-premises servers is in place. 2. One migrated Windows server and one migrated Linux server are in Azure, and one on-premises server that has not migrated is available for the blocked-connection test. 3. GEHA Network is available to pull the hub firewall log lines. 4. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off.
Dependencies (H/W and S/W): | 1. Connector 01 and connector 02, reached through the approved administrative path. 2. Windows PowerShell (Test-NetConnection). 3. Hub firewall logs (GEHA Network). | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (Build engineer, GEHA Network) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Medium
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Sign in to connector 01 through the approved administrative path and open PowerShell. | NA | PowerShell is open on connector 01.
2 | Run Test-NetConnection to a GEHA.com domain controller on ports 389 and 3268. | GEHA.com domain controller Ports 389 and 3268 | TcpTestSucceeded returns True on both ports.
3 | Run Test-NetConnection to the Splunk indexer on port 9998. | Splunk indexer Port 9998 | TcpTestSucceeded returns True.
4 | Run Test-NetConnection to the migrated Windows test server on port 3389 and to the migrated Linux test server on port 22. | Migrated Windows test server, port 3389 Migrated Linux test server, port 22 | TcpTestSucceeded returns True for both servers.
5 | Run Test-NetConnection to the CyberArk portal address on port 443. | CyberArk portal address Port 443 | TcpTestSucceeded returns True.
6 | Run Test-NetConnection on port 3389 to the on-premises test server that has not migrated. | Unmigrated on-premises test server Port 3389 | The connection fails. If this connection succeeds, stop testing and raise it with GEHA Network before going further.
7 | Repeat steps 2 to 6 from connector 02. | Same destinations and ports as steps 2 to 6 | Steps 2 to 5 return TcpTestSucceeded True and step 6 fails, the same as on connector 01.
8 | GEHA Network pulls the hub firewall log lines for every connection attempt. | Firewall log for all attempts from both connectors | The firewall log shows an allow rule for each connection in steps 2 to 5, and shows the step 6 connection denied, on both connectors.

## TC-INF-04
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm both connectors can reach the CyberArk tenant on ports 443 and 1858 | Module/Program Name/Menu Path: | Phase 1: Azure infrastructure and network connectivity PowerShell Test-NetConnection on both connectors; hub firewall log; CyberArk portal > Connector Management
Test Case ID: | TC-INF-04 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm both connectors reach the tenant vault on port 1858 and the portal on port 443, port 1858 passes the vault rule without inspection, and both connectors show current communication with the vault. | Pre-requisites/Test Set-up: | 1. The hub firewall public address is on the tenant IP allowlist. 2. The CyberArk rule set is applied to the hub firewall. 3. The connector software is installed on both servers through Connector Management. 4. The CyberArk administrator is available to give the vault and portal addresses, and GEHA Network is available to check the firewall log. 5. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off.
Dependencies (H/W and S/W): | 1. Connector 01 and connector 02. 2. Windows PowerShell (Test-NetConnection). 3. Hub firewall logs (GEHA Network). 4. CyberArk Privilege Cloud portal (Connector Management). | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (Build engineer, GEHA Network) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Medium
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Ask the CyberArk administrator for the vault address and portal address of the tenant. | NA | The vault and portal addresses are received and recorded.
2 | On connector 01, run Test-NetConnection to the vault address on port 1858. | Test-NetConnection <vault address> -Port 1858 | The connection succeeds.
3 | Run Test-NetConnection to the portal address on port 443. | Test-NetConnection <portal address> -Port 443 | The connection succeeds.
4 | Repeat steps 2 and 3 on connector 02. | Same commands as steps 2 and 3 | Both ports succeed from connector 02.
5 | GEHA Network confirms from the firewall log which rule allowed port 1858, and that the traffic was not sent through TLS or IDS/IPS inspection. | Firewall log for port 1858 from both connectors | Port 1858 matches the vault rule and passes without inspection. No resets or drops are logged against it.
6 | In Connector Management, check the last communication time for both connectors. | NA | Both connectors show current communication with the vault.
7 | Save the evidence in the TC-INF-04 subfolder of the evidence folder for the environment. | Command output; firewall log line; Connector Management screenshot | Evidence is saved in the case subfolder and matches the expected results. A case without evidence is recorded as not run, never as passed.
8 | GEHA Network confirms the rule name and host name matched for the port 1858 connection. | Hub firewall log, port 1858 | The log shows allow-vault-1858 matched on the exact vault host name.

## TC-INF-05
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm administrative access to the connectors is restricted to the approved path | Module/Program Name/Menu Path: | Phase 1: Azure infrastructure and network connectivity Azure portal > connector network interfaces; RDP attempts from outside GEHA, from on-premises and from the administrative ranges
Test Case ID: | TC-INF-05 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm neither connector has a public IP address, and that RDP to the connectors works only from the GEHA administrative ranges and is refused from anywhere else. | Pre-requisites/Test Set-up: | 1. The CyberArk rule set is applied to the hub firewall. 2. The test user is a GEHA privileged user working from the administrative ranges. 3. A connection outside the GEHA network (for example, a home internet connection without VPN) and an on-premises workstation outside the GEHA administrative ranges are available. 4. GEHA Network is available to pull the firewall log lines. 5. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off.
Dependencies (H/W and S/W): | 1. Azure portal access. 2. RDP client on each test machine. 3. Azure Bastion, only if GEHA provides it for this subscription. 4. Hub firewall logs (GEHA Network). | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (Build engineer, Test user, GEHA Network) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Medium
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | In the Azure portal, confirm neither connector network interface has a public IP address. | Connector 01 and connector 02 network interfaces | No public address exists on either connector.
2 | From outside the GEHA network, try to open RDP to each connector. | Home internet connection without VPN | The connection is refused on both connectors.
3 | From an on-premises workstation outside the GEHA administrative ranges, try to open RDP to each connector. | On-premises workstation outside the administrative ranges | The connection is refused on both connectors.
4 | From a workstation in the administrative ranges (or through Azure Bastion, if GEHA provides it for this subscription), open RDP to each connector. | Workstation in the GEHA administrative ranges | RDP succeeds on both connectors.
5 | GEHA Network pulls the firewall log lines for steps 3 and 4. | Firewall log for steps 3 and 4 | The firewall log shows the step 3 attempts blocked.
6 | GEHA Network confirms the rule names recorded for the connections in steps 3 and 4. | Hub firewall log | Connections from the administrative ranges match allow-admin-rdp. Attempts from outside those ranges show no matching rule.

## TC-INF-06
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm every resource in the connector resource group matches the build tables resource list | Module/Program Name/Menu Path: | Phase 1: Azure infrastructure and network connectivity Azure CLI: az resource list for rg-sec-cyberark-prd
Test Case ID: | TC-INF-06 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the Azure estate exists exactly as the build tables describe it, with every net new resource present and no extra resources, before any connector test runs. | Pre-requisites/Test Set-up: | 1. Every net new resource in the build tables exists in rg-sec-cyberark-prd, the subnet was created by the Cloud Platform Team in the platform group, and the register values are confirmed or deployed as written. 2. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. Azure CLI with read access to the CIP-PRD subscription. 2. Current copy of the build tables resource list. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Build engineer) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Medium
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Run az resource list for rg-sec-cyberark-prd and export the output to CSV. | Resource group: rg-sec-cyberark-prd | The resource list is exported to CSV.
2 | Compare each row of the export with the build tables resource list. | Build tables resource list | Every net new resource is present with its name, type, size, zone and location as listed.
3 | Record any resource that is present in the resource group but not in the resource list. | NA | No extra resources are found.

## TC-INF-07
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm both connector network interfaces sit in the connector subnet with the expected addresses | Module/Program Name/Menu Path: | Phase 1: Azure infrastructure and network connectivity Azure CLI: az network nic show, az network vnet subnet show
Test Case ID: | TC-INF-07 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm both connector network interfaces are placed in snet-sec-cyberark-cus-prd-01 with the planned private addresses and accelerated networking, and that the subnet has no network security group. | Pre-requisites/Test Set-up: | 1. Every net new resource in the build tables exists in rg-sec-cyberark-prd, the subnet was created by the Cloud Platform Team in the platform group, and the register values are confirmed or deployed as written. 2. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. Azure CLI with read access to CIP-PRD and to rg-alz-centralus-vnet-cip-cus-prd-01. 2. Cloud Platform Team available to confirm the register values. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Build engineer, Cloud Platform Team) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Run az network nic show for both connector network interfaces and record the subnet reference, private address and accelerated networking setting. | nic-sec-cyberark-cus-prd-01 nic-sec-cyberark-cus-prd-02 | Both network interfaces are in snet-sec-cyberark-cus-prd-01 at 10.9.250.8 and 10.9.250.9 (or the confirmed register values), with accelerated networking enabled.
2 | Run az network vnet subnet show for the connector subnet and record the prefix, the network security group field and the route table. | Subnet: snet-sec-cyberark-cus-prd-01 Resource group: rg-alz-centralus-vnet-cip-cus-prd-01 | Subnet prefix is 10.9.250.0/27, there is no network security group, and the route table is as set by the platform.

## TC-INF-08
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm Azure Policy compliance and that the connectors are kept out of Azure Backup | Module/Program Name/Menu Path: | Phase 1: Azure infrastructure and network connectivity Azure portal > Azure Policy > Compliance; Recovery Services vaults
Test Case ID: | TC-INF-08 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the connector resources are compliant with the Corp and Landing Zones policy assignments, carry the backup exclusion tag, and are not held in any policy-created recovery services vault. | Pre-requisites/Test Set-up: | 1. Every net new resource in the build tables exists in rg-sec-cyberark-prd, the subnet was created by the Cloud Platform Team in the platform group, and the register values are confirmed or deployed as written. 2. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. Azure portal access to Azure Policy for CIP-PRD. 2. Read access to the recovery services vaults in the subscription. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Build engineer) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Open Azure Policy, Compliance, filter to rg-sec-cyberark-prd and export the compliance state. | Resource group: rg-sec-cyberark-prd | No resource is non-compliant against the Corp and Landing Zones assignments.
2 | Check the tags on both connector virtual machines for the backup exclusion tag. | vm-sec-cyberark-cus-prd-01 and 02 (AZPASPCCPRD101 and AZPASPCCPRD102) | The backup exclusion tag set in the build tables is present on both virtual machines.
3 | List the recovery services vaults in the subscription and confirm none was created by the Landing Zones backup assignment for these virtual machines. | Recovery services vault list for CIP-PRD | No policy-created vault holds either connector.

## TC-INF-09
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm diagnostic settings send logs from the load balancer and both connectors to Log Analytics | Module/Program Name/Menu Path: | Phase 1: Azure infrastructure and network connectivity Azure portal > Diagnostic settings (load balancer and both virtual machines)
Test Case ID: | TC-INF-09 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm diagnostic settings exist on the load balancer and both connector virtual machines and point at the central Log Analytics workspace. | Pre-requisites/Test Set-up: | 1. Every net new resource in the build tables exists in rg-sec-cyberark-prd, the subnet was created by the Cloud Platform Team in the platform group, and the register values are confirmed or deployed as written. 2. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. Azure portal access to CIP-PRD. 2. Log Analytics workspace alz-log-analytics in the Management subscription. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Build engineer) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Open Diagnostic settings on the internal load balancer and on both connector virtual machines. | lbi-sec-cyberark-cus-prd-01 vm-sec-cyberark-cus-prd-01 and 02 (AZPASPCCPRD101 and AZPASPCCPRD102) | Diagnostic settings are present on all three resources.
2 | Record the destination workspace for each setting. | alz-log-analytics (Management subscription) | All three resources send to alz-log-analytics in the Management subscription.

## TC-INF-10
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Check the certificate bound to HTTPS 443 on each connector | Module/Program Name/Menu Path: | Phase 1: Azure infrastructure and network connectivity IIS Manager > Site bindings (443) on each connector; browser from the administrative ranges
Test Case ID: | TC-INF-10 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm each connector presents a trusted certificate issued under the GEHA certificate standard, with the server name and cyberark-prd.geha.com in its subject alternative names, and that the renewal date is recorded for Venafi. | Pre-requisites/Test Set-up: | 1. Each connector holds a certificate issued under the GEHA certificate standard, with the server name and cyberark-prd.geha.com in the subject alternative names, bound to the HTTPS 443 site. 2. Both servers are built from the CIS Level 2 Windows Server 2025 image and configured in the build tables install order, both are on the same session manager version, and each has been restarted after the install. 3. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. IIS Manager on connector 01 and connector 02. 2. Workstation in the GEHA administrative ranges with a web browser. 3. Venafi, for recording the renewal date. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Build engineer) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | In IIS on each connector, open the site binding for port 443 and export the certificate details. | Site binding: HTTPS 443 | The subject alternative names include the server name and cyberark-prd.geha.com, and the certificate is issued under the GEHA certificate standard.
2 | From a client in the administrative ranges, browse to the health page through the load balancer name and inspect the certificate. | https://cyberark-prd.geha.com/psm/api/health | The certificate chain is trusted and the certificate is not expired.
3 | Record the certificate renewal date for Venafi. | NA | The renewal date is recorded.

## TC-INF-11
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm every resource carries the build tables tag set | Module/Program Name/Menu Path: | Phase 1: Azure infrastructure and network connectivity Azure CLI: az resource list with tag output for rg-sec-cyberark-prd
Test Case ID: | TC-INF-11 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm every resource in the connector resource group carries the keys and values of the build tables tag set, including the backup exclusion tag. | Pre-requisites/Test Set-up: | 1. Every net new resource in the build tables exists in rg-sec-cyberark-prd, the subnet was created by the Cloud Platform Team in the platform group, and the register values are confirmed or deployed as written. 2. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. Azure CLI with read access to CIP-PRD. 2. Build tables tag set. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Build engineer) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Run az resource list with tag output for rg-sec-cyberark-prd and export the result. | Resource group: rg-sec-cyberark-prd | Every resource carries the keys and values of the build tables tag set, including the backup exclusion tag.

## TC-INF-12
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm the connectors reach the CyberArk tenant and connector management services on the approved host lists only | Module/Program Name/Menu Path: | Phase 1: Azure infrastructure and network connectivity PowerShell Test-NetConnection on both connectors; hub firewall application rules allow-cyberark-services and allow-connector-management
Test Case ID: | TC-INF-12 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm each connector can reach every host in the CyberArk services and connector management lists on port 443 and the revocation hosts on port 80, and that a public host outside those lists is refused. | Pre-requisites/Test Set-up: | 1. Rule collection group rcg-sec-cyberark is applied to DefaultFirewallPolicy through the firewall pipeline, the net new IP groups are created with their members, and there is no network security group on the subnet. 2. The session manager farm Azure-PSM-PRD exists as a Configured PSM Server entry with Address cyberark-prd.geha.com, the password manager AZ-CPM-PRD-01 is registered, and the hub firewall egress address is on the tenant IP allowlist. 3. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. Connector 01 and connector 02. 2. Windows PowerShell (Test-NetConnection). 3. Hub firewall logs (GEHA Network). | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Build engineer, GEHA Network) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Medium
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | On each connector, run Test-NetConnection on port 443 to one host in each FQDN set of allow-cyberark-services and allow-connector-management. | Port 443 One host per FQDN set in allow-cyberark-services and allow-connector-management | Every listed host succeeds.
2 | Run the same test to a public host that is not in any set. | Port 443 Public host outside the FQDN sets | The connection is refused.
3 | Run Test-NetConnection to the certificate revocation hosts on port 80. | Revocation hosts, port 80 | Every revocation host succeeds.
4 | GEHA Network pulls the firewall log lines for the tests. | Hub firewall log | The log shows the application rule matched for each successful connection.

## TC-INF-13
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm the Rapid7 Insight agent on both connectors is registered and checking in | Module/Program Name/Menu Path: | Phase 1: Azure infrastructure and network connectivity Services on each connector; Rapid7 Insight console
Test Case ID: | TC-INF-13 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the Rapid7 Insight agent is running on both connectors and checking in with the console through the allow-rapid7 rule. | Pre-requisites/Test Set-up: | 1. Rule collection group rcg-sec-cyberark is applied to DefaultFirewallPolicy through the firewall pipeline, the net new IP groups are created with their members, and there is no network security group on the subnet. 2. Both servers are built from the CIS Level 2 Windows Server 2025 image and configured in the build tables install order, both are on the same session manager version, and each has been restarted after the install. 3. The Rapid7 service owner is available with access to the Insight console. 4. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. Rapid7 Insight agent on connector 01 and connector 02. 2. Rapid7 Insight console. 3. Hub firewall logs (GEHA Network). | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Build engineer, Rapid7 service owner) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | On each connector, confirm the Insight agent service is running. | Rapid7 Insight agent service | The service is running on both connectors.
2 | In the Insight console, locate both servers and record the last check in. | AZPASPCCPRD101 and AZPASPCCPRD102 | Both servers are registered with a last check in within 15 minutes.
3 | Check the hub firewall log for the agent traffic. | Hub firewall log | allow-rapid7 is matched in the log.

## TC-INF-14
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm Kerberos, DNS and time services from the GEHA.com domain controllers on both connectors | Module/Program Name/Menu Path: | Phase 1: Azure infrastructure and network connectivity Command prompt on each connector: klist, nslookup, w32tm
Test Case ID: | TC-INF-14 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm each connector gets a Kerberos ticket, DNS answers and a time resync from the GEHA.com domain controllers through the allow-directory rule. | Pre-requisites/Test Set-up: | 1. Both connectors are joined to GEHA.com inside the connector organizational unit, the CyberArk Privilege Cloud Connector Unified Hardening GPO is linked to that unit with no other hardening policy, and the PSMConnect and PSMAdminConnect pair exists for each connector. 2. Rule collection group rcg-sec-cyberark is applied to DefaultFirewallPolicy through the firewall pipeline, the net new IP groups are created with their members, and there is no network security group on the subnet. 3. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. Connector 01 and connector 02. 2. GEHA.com domain controllers. 3. Hub firewall logs (GEHA Network). | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Build engineer) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | On each connector, run klist purge, then klist get krbtgt. | klist purge klist get krbtgt | A ticket granting ticket is issued.
2 | Run nslookup geha.com and nslookup of the vault host. | nslookup geha.com nslookup <vault host> | DNS answers come from a GEHA.com domain controller.
3 | Run w32tm /resync. | w32tm /resync | The time resync succeeds.
4 | Check the hub firewall log for the directory traffic. | Hub firewall log | allow-directory is matched.

## TC-INF-15
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Install the MECM client on both connectors and confirm policy retrieval and client notification | Module/Program Name/Menu Path: | Phase 1: Azure infrastructure and network connectivity MECM console (MECMSITEPRD101); Control Panel > Configuration Manager on each connector
Test Case ID: | TC-INF-15 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the MECM client installs on both connectors, the device records are active with a management point, policy retrieval and client notification work, and both devices sit in the connector maintenance window collection. | Pre-requisites/Test Set-up: | 1. Rule collection group rcg-sec-cyberark is applied to DefaultFirewallPolicy through the firewall pipeline, the net new IP groups are created with their members, and there is no network security group on the subnet. 2. The two connectors are in their own MECM maintenance window collection, the Cohesity protection policy for the Azure connectors is assigned, and the automatic upgrade windows for the Management Agent and the Identity Connector are set or opted out. 3. The MECM service owner is available with console access. 4. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. MECM site server MECMSITEPRD101 and console. 2. Connector 01 and connector 02. 3. Hub firewall rules allow-sccm-mid-inbound and allow-sccm-client. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (MECM service owner) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Medium
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Push the MECM client from MECMSITEPRD101 to both connectors. | MECMSITEPRD101 | The client installs on both connectors over allow-sccm-mid-inbound.
2 | In the MECM console, open the device record for each connector. | AZPASPCCPRD101 and AZPASPCCPRD102 | Each device record is active with a management point assignment.
3 | On each connector, open Configuration Manager in Control Panel and run Machine Policy Retrieval. | Machine Policy Retrieval and Evaluation Cycle | Policy retrieval succeeds over allow-sccm-client.
4 | Confirm client notification on TCP 10123 in the client log. | TCP 10123 | Client notification succeeds over allow-sccm-client.
5 | Check the collection membership of both devices. | Connector maintenance window collection | Both devices are in the connector maintenance window collection.

## TC-INF-16
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Run ServiceNow discovery against the connector subnet and confirm the connector CI records | Module/Program Name/Menu Path: | Phase 1: Azure infrastructure and network connectivity ServiceNow > Discovery schedules (SNMIDPRD301); CMDB CI records
Test Case ID: | TC-INF-16 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm ServiceNow discovery finds both connectors and creates a CI for each with the correct name, addresses and operating system. | Pre-requisites/Test Set-up: | 1. Rule collection group rcg-sec-cyberark is applied to DefaultFirewallPolicy through the firewall pipeline, the net new IP groups are created with their members, and there is no network security group on the subnet. 2. The ServiceNow service owner is available to run a discovery schedule. 3. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. ServiceNow MID server SNMIDPRD301. 2. ServiceNow Discovery and CMDB. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (ServiceNow service owner) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Medium
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Run a discovery schedule from SNMIDPRD301 that includes the connector subnet. | MID server: SNMIDPRD301 Subnet: 10.9.250.0/27 | The discovery completes for the connector subnet.
2 | Open the CI records created for the connectors. | AZPASPCCPRD101 and AZPASPCCPRD102 | A CI exists for each connector with the correct name, addresses and operating system.

## TC-INF-17
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm Remote Desktop licensing on both connectors | Module/Program Name/Menu Path: | Phase 1: Azure infrastructure and network connectivity PowerShell Get-RDLicenseConfiguration; Event Viewer > TerminalServices-Licensing
Test Case ID: | TC-INF-17 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm both connectors point at the GEHA Remote Desktop license server and that a client access license is issued on the first brokered session. | Pre-requisites/Test Set-up: | 1. Both servers are built from the CIS Level 2 Windows Server 2025 image and configured in the build tables install order, both are on the same session manager version, and each has been restarted after the install. 2. Rule collection group rcg-sec-cyberark is applied to DefaultFirewallPolicy through the firewall pipeline, the net new IP groups are created with their members, and there is no network security group on the subnet. 3. The RDS licensing service owner is available. 4. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. Connector 01 and connector 02. 2. RDS license server RDSLICPRD301. 3. A brokered session from TC-FUN-01. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Build engineer, RDS licensing service owner) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | On each connector, run Get-RDLicenseConfiguration. | Get-RDLicenseConfiguration | RDSLICPRD301 is listed as the license server.
2 | After the first brokered session in TC-FUN-01, open Event Viewer, TerminalServices-Licensing. | Event Viewer > TerminalServices-Licensing | A client access license is issued on the first session over allow-rds-licensing.

## TC-INF-18
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Open RDP to the connection name from each client group and confirm the firewall path | Module/Program Name/Menu Path: | Phase 1: Azure infrastructure and network connectivity RDP to cyberark-prd.geha.com from on-premises, Azure Virtual Desktop and Zscaler private access clients
Test Case ID: | TC-INF-18 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm users in every client group (on-premises workstations, Azure Virtual Desktop session hosts and Zscaler private access clients) reach the load balancer front end through the allow-session-from-clients rule. | Pre-requisites/Test Set-up: | 1. Rule collection group rcg-sec-cyberark is applied to DefaultFirewallPolicy through the firewall pipeline, the net new IP groups are created with their members, and there is no network security group on the subnet. 2. An on-premises workstation, an Azure Virtual Desktop session host and a Zscaler private access client are available to the test user. 3. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. RDP client on each test machine. 2. Hub firewall logs (GEHA Network). | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Test user, GEHA Network) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Medium
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | RDP to cyberark-prd.geha.com from an on-premises workstation. | cyberark-prd.geha.com | The connection reaches the load balancer front end.
2 | RDP to cyberark-prd.geha.com from an Azure Virtual Desktop session host. | cyberark-prd.geha.com | The connection reaches the load balancer front end.
3 | RDP to cyberark-prd.geha.com from a Zscaler private access client. | cyberark-prd.geha.com | The connection reaches the load balancer front end.
4 | GEHA Network pulls the firewall log line for each connection. | Hub firewall log | Each log line shows allow-session-from-clients matched with the expected source group.

## TC-INF-19
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm RDP to the connectors is refused from other landing zone networks | Module/Program Name/Menu Path: | Phase 1: Azure infrastructure and network connectivity PowerShell Test-NetConnection from servers in other landing zone networks and in vnet-cip-cus-prd-01
Test Case ID: | TC-INF-19 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm a server in a different landing zone network cannot reach the connectors on RDP, and to record the result from inside vnet-cip-cus-prd-01, where traffic between subnets is not filtered. | Pre-requisites/Test Set-up: | 1. Rule collection group rcg-sec-cyberark is applied to DefaultFirewallPolicy through the firewall pipeline, the net new IP groups are created with their members, and there is no network security group on the subnet. 2. A server in a landing zone network other than vnet-cip-cus-prd-01, and a server in another subnet of vnet-cip-cus-prd-01, are available. 3. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. Windows PowerShell (Test-NetConnection). 2. Hub firewall logs (GEHA Network). | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Build engineer, GEHA Network) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | From a server in a landing zone network other than vnet-cip-cus-prd-01, run Test-NetConnection to each connector on port 3389. | Test-NetConnection <connector> -Port 3389 | The connection is refused, with no matching rule in the firewall log.
2 | From a server in another subnet of vnet-cip-cus-prd-01, repeat the test and record the result. | Test-NetConnection <connector> -Port 3389 | The result is recorded as it is. Traffic inside the network is not filtered.

## TC-INF-20
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm the connectors reach the Microsoft platform endpoints they depend on | Module/Program Name/Menu Path: | Phase 1: Azure infrastructure and network connectivity PowerShell Test-NetConnection on both connectors
Test Case ID: | TC-INF-20 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm each connector can reach Windows Update, Defender for Endpoint and Azure Monitor hosts on port 443 through the platform rules. | Pre-requisites/Test Set-up: | 1. Rule collection group rcg-sec-cyberark is applied to DefaultFirewallPolicy through the firewall pipeline, the net new IP groups are created with their members, and there is no network security group on the subnet. 2. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. Connector 01 and connector 02. 2. Windows PowerShell (Test-NetConnection). 3. Hub firewall logs (GEHA Network). | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Build engineer, GEHA Network) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | On each connector, run Test-NetConnection on port 443 to a Windows Update host, a Defender for Endpoint host and an Azure Monitor host as published by Microsoft. | Port 443 Windows Update, Defender for Endpoint and Azure Monitor hosts | All connections succeed, through app-cyberark-platform or the existing policy rules named by GEHA Network.

## TC-CON-01
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm both Azure connectors and all their components are active in the CyberArk portal | Module/Program Name/Menu Path: | Phase 2: Connector health and service hardening CyberArk Privilege Cloud portal > Connector Management > Connectors; Configured PSM Servers settings
Test Case ID: | TC-CON-01 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm both Azure connectors are registered and healthy, every component is active and on the same version, the Azure session manager entry uses the load balancer name, and the on-premises connectors are unchanged. | Pre-requisites/Test Set-up: | 1. The connector software is installed on both servers through Connector Management, both are on the same version, and both have been restarted after installation. 2. The Azure session manager entry exists in the tenant with the load balancer name as its address. 3. The CyberArk administrator can sign in to the Privilege Cloud portal. 4. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off.
Dependencies (H/W and S/W): | 1. CyberArk Privilege Cloud portal. 2. CyberArk administrator account. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (CyberArk administrator) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Sign in to the CyberArk Privilege Cloud portal as the CyberArk administrator. | CyberArk administrator account | The portal opens with administrator access.
2 | Go to Connector Management, Connectors. | NA | Both Azure connectors are listed.
3 | Open each Azure connector and record the status and version of every component on it. | Connector 01 and connector 02 Production password manager: AZ-CPM-PRD-01 | Every component on both Azure connectors shows Active with no failed component, and both are on the same version. The session manager runs on both connectors. The password manager runs on connector 01 and is installed but stopped on connector 02.
4 | Open the Configured PSM Servers settings and record the Azure session manager entry and its address. | Load balancer name for the environment | The Azure session manager address is the load balancer name.
5 | Confirm the on-premises connectors are still listed and active. | NA | The on-premises connectors are unchanged.
6 | On each connector, confirm the CyberArk Privileged Session Manager service is running. | CyberArk Privileged Session Manager service | The service is running on both connectors.
7 | In Configured PSM Servers, record the full Azure entry and the on-premises entry. | Azure-PSM-PRD | The Azure entry shows ID Azure-PSM-PRD, Address cyberark-prd.geha.com and the PSM credential object. The on-premises entry is unchanged.
8 | In the portal, confirm the password manager AZ-CPM-PRD-01 is listed. | AZ-CPM-PRD-01 | AZ-CPM-PRD-01 is listed and running on connector 01, and installed but not started on connector 02 (the passive instance). If GEHA Security rules otherwise, the recorded state is the ruled one.

## TC-CON-02
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Verify the CyberArk hardening Group Policy is applied on both connectors | Module/Program Name/Menu Path: | Phase 2: Connector health and service hardening Connector servers: PowerShell (gpupdate, gpresult), Event Viewer, Local Security Policy; Azure portal > load balancer health probes
Test Case ID: | TC-CON-02 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the CyberArk hardening GPO is applied on both connectors with no other hardening policy, the user rights and AppLocker rules match the CyberArk baseline, and the load balancer health probes stay healthy after the refresh. | Pre-requisites/Test Set-up: | 1. Both servers are joined to GEHA.com in the connector organizational unit. The CyberArk hardening GPO is linked to that unit, and no other hardening policy applies to it. 2. Administrator access to each connector through the approved administrative path. 3. GEHA Identity is available to confirm the organizational unit and GPO. 4. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off.
Dependencies (H/W and S/W): | 1. Connector 01 and connector 02 (Windows PowerShell, Event Viewer, Local Security Policy). 2. Active Directory connector organizational unit and the CyberArk hardening GPO. 3. Azure portal access to the load balancer. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (Build engineer, GEHA Identity) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Medium (about 20 minutes)
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | On each connector, open PowerShell as Administrator and run gpupdate /force. | gpupdate /force | The policy refresh completes without errors.
2 | Run gpresult /r /scope computer and record the organizational unit and the applied policies. | gpresult /r /scope computer | The server is in the connector organizational unit. The CyberArk hardening GPO is applied and no other hardening policy is.
3 | Open Event Viewer, System log, and check for Group Policy errors since the update. | Event Viewer > System log | No Group Policy errors are logged since the update.
4 | Open Local Security Policy and record the user rights assignments and the AppLocker rules set by the policy. | Local Security Policy > User Rights Assignment, AppLocker | User rights and AppLocker rules match the CyberArk baseline.
5 | In the Azure portal, check the load balancer health probes are still healthy after the refresh. | Azure probe address: 168.63.129.16 | Both probes stay healthy. If a probe fails, add a Windows firewall exception for the Azure probe address 168.63.129.16 and record it as a policy customization.
6 | On each connector, run nltest /dsgetdc:geha.com and w32tm /query /status. | nltest /dsgetdc:geha.com w32tm /query /status | Secure channel to a GEHA.com domain controller. The time source is a domain controller and the offset is under five minutes.
7 | If a probe reads unhealthy after the refresh, inspect the Windows firewall rules the CyberArk GPO applied for inbound 3389 and 443 from 168.63.129.16. | Azure probe address: 168.63.129.16 Ports 3389 and 443 | Both servers are Healthy on both probes. If a GPO rule blocks the probe source, the inbound exception for 168.63.129.16 is added and recorded as a GPO customization to re-apply after upgrades.

## TC-CON-03
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm endpoint protection is running on both connectors with the CyberArk exclusions in place | Module/Program Name/Menu Path: | Phase 2: Connector health and service hardening Endpoint protection agent on each connector and the agent console
Test Case ID: | TC-CON-03 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm endpoint protection is installed, enabled and reporting on both connectors, the CyberArk folder and process exclusions are in place, and no CyberArk file has been blocked or quarantined. | Pre-requisites/Test Set-up: | 1. The endpoint protection agent is installed on both servers with the CyberArk exclusions applied. 2. The endpoint protection service owner is available with access to the agent console. 3. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off.
Dependencies (H/W and S/W): | 1. Endpoint protection agent and console. 2. Connector 01 and connector 02. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (Build engineer, Endpoint protection service owner) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | On each connector, confirm the endpoint protection agent is running and up to date. | NA | The agent is installed, enabled and up to date on both connectors.
2 | In the agent console, confirm both connectors are checking in. | NA | Both connectors are reporting to the console.
3 | Review the exclusion list and confirm it covers the CyberArk folders and the CyberArk processes. | C:\Program Files (x86)\CyberArk\PSM C:\Program Files (x86)\CyberArk\Password Manager CyberArk processes | The CyberArk folder and process exclusions are in place.
4 | Check the agent event history on each connector for any CyberArk file that was blocked or quarantined. | NA | No CyberArk file has been blocked or quarantined.
5 | Confirm the agent was re-enabled after the connector install, and that it is the agent GEHA Security named for the connectors. | NA | The agent named by GEHA Security is installed and enabled on both connectors with the CyberArk exclusions, and both servers are present in its console.

## TC-CON-04
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Check the session manager service account, Network Level Authentication and Remote Desktop Users on each connector | Module/Program Name/Menu Path: | Phase 2: Connector health and service hardening Services; System Properties > Remote; Local Users and Groups > Remote Desktop Users
Test Case ID: | TC-CON-04 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the session manager service runs under each connector's own PSMConnect account, the password manager service state is correct, Network Level Authentication is set as agreed, and Remote Desktop Users holds only the connector's PSM account pair. | Pre-requisites/Test Set-up: | 1. Both connectors are joined to GEHA.com inside the connector organizational unit, the CyberArk Privilege Cloud Connector Unified Hardening GPO is linked to that unit with no other hardening policy, and the PSMConnect and PSMAdminConnect pair exists for each connector. 2. Both servers are built from the CIS Level 2 Windows Server 2025 image and configured in the build tables install order, both are on the same session manager version, and each has been restarted after the install. 3. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. Administrator access to connector 01 and connector 02. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Build engineer) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Open Services on each connector and record the logon account of the CyberArk Privileged Session Manager service and the state of the CyberArk Password Manager service. | CyberArk Privileged Session Manager service CyberArk Password Manager service | The session manager service runs as that connector's own PSMConnect domain account. The password manager service is running on connector 01 and stopped on connector 02.
2 | Open System Properties, Remote, and record the Network Level Authentication setting. | System Properties > Remote | Network Level Authentication is disabled on both connectors, unless GEHA Security has decided to enable it.
3 | Record the members of the Remote Desktop Users group. | Local group: Remote Desktop Users | Remote Desktop Users holds only the connector's PSMConnect and PSMAdminConnect pair.

## TC-CON-05
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm both connectors are built from the CIS Level 2 image with the expected hardening | Module/Program Name/Menu Path: | Phase 2: Connector health and service hardening Azure CLI: az vm show; winver; registry; PowerShell on each connector
Test Case ID: | TC-CON-05 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm both virtual machines are built from the GEHA CIS Level 2 Windows Server 2025 image, the RDS security settings are applied by the GPO, and SMB1 is disabled. | Pre-requisites/Test Set-up: | 1. Both servers are built from the CIS Level 2 Windows Server 2025 image and configured in the build tables install order, both are on the same session manager version, and each has been restarted after the install. 2. Both connectors are joined to GEHA.com inside the connector organizational unit, the CyberArk Privilege Cloud Connector Unified Hardening GPO is linked to that unit with no other hardening policy, and the PSMConnect and PSMAdminConnect pair exists for each connector. 3. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. Azure CLI with read access to CIP-PRD. 2. Administrator access to connector 01 and connector 02. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Build engineer) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Run az vm show for each virtual machine and record storageProfile.imageReference. | vm-sec-cyberark-cus-prd-01 and 02 (AZPASPCCPRD101 and AZPASPCCPRD102) | Both virtual machines are built from the GEHA CIS Level 2 Windows Server 2025 image.
2 | On each connector, run winver and confirm the operating system. | winver | The operating system is Windows Server 2025.
3 | Read the RDS SecurityLayer and MinEncryptionLevel registry values. | SecurityLayer MinEncryptionLevel | SecurityLayer and MinEncryptionLevel are set by the GPO.
4 | Confirm SMB1 is disabled. | NA | SMB1 is disabled on both connectors.

## TC-CON-06
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm both Azure connectors are healthy on the system health dashboard | Module/Program Name/Menu Path: | Phase 2: Connector health and service hardening CyberArk Privilege Cloud portal > System health
Test Case ID: | TC-CON-06 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm both Azure connectors appear and show as healthy on the tenant system health dashboard. | Pre-requisites/Test Set-up: | 1. Both servers are built from the CIS Level 2 Windows Server 2025 image and configured in the build tables install order, both are on the same session manager version, and each has been restarted after the install. 2. The CyberArk administrator can sign in to the Privilege Cloud portal. 3. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. CyberArk Privilege Cloud portal. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (CyberArk administrator) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Open the system health dashboard in the portal. | NA | The system health dashboard opens.
2 | Record the entries for both Azure connectors. | AZPASPCCPRD101 and AZPASPCCPRD102 | Both Azure connectors are present and healthy.

## TC-CON-07
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Check the Identity Connector status and auto-update setting on each connector | Module/Program Name/Menu Path: | Phase 2: Connector health and service hardening Identity Connector Configuration program > Status tab
Test Case ID: | TC-CON-07 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the Identity Connector on each connector has a recent successful connection, both are registered under the same customer ID, and auto-update is set as GEHA decided. | Pre-requisites/Test Set-up: | 1. Both servers are built from the CIS Level 2 Windows Server 2025 image and configured in the build tables install order, both are on the same session manager version, and each has been restarted after the install. 2. The two connectors are in their own MECM maintenance window collection, the Cohesity protection policy for the Azure connectors is assigned, and the automatic upgrade windows for the Management Agent and the Identity Connector are set or opted out. 3. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. Identity Connector Configuration program on connector 01 and connector 02. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (CyberArk administrator) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | On each connector, open the Identity Connector Configuration program and go to the Status tab. | NA | The Status tab opens on both connectors.
2 | Record the last connection time and result. | NA | The last connection is recent and successful on both, and both are registered under the same customer ID.
3 | Record the auto-update setting and window. | NA | Auto-update is set as GEHA decided for the agent upgrade windows.

## TC-CON-08
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm both connectors are online in the dynamic access connector pool | Module/Program Name/Menu Path: | Phase 2: Connector health and service hardening CyberArk Privilege Cloud portal > Dynamic access connector pool
Test Case ID: | TC-CON-08 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm both Azure connectors are registered and online in the designed dynamic access connector pool. | Pre-requisites/Test Set-up: | 1. Both servers are built from the CIS Level 2 Windows Server 2025 image and configured in the build tables install order, both are on the same session manager version, and each has been restarted after the install. 2. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. CyberArk Privilege Cloud portal. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (CyberArk administrator) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | In the portal, open the dynamic access connector pool and record both connectors. | AZPASPCCPRD101 and AZPASPCCPRD102 | Both connectors are registered and online in the designed pool.

## TC-CON-09
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Check the Management Agent automatic upgrade setting and window | Module/Program Name/Menu Path: | Phase 2: Connector health and service hardening CyberArk Privilege Cloud portal > Connector Management > Automatic upgrade
Test Case ID: | TC-CON-09 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the Management Agent automatic upgrade is set to the CAB maintenance window or opted out, as GEHA decided. | Pre-requisites/Test Set-up: | 1. The two connectors are in their own MECM maintenance window collection, the Cohesity protection policy for the Azure connectors is assigned, and the automatic upgrade windows for the Management Agent and the Identity Connector are set or opted out. 2. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. CyberArk Privilege Cloud portal (Connector Management). | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (CyberArk administrator) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | In Connector Management, open the automatic upgrade setting for the Management Agent and record whether it is on, and the window. | Management Agent automatic upgrade setting | Set as GEHA decided: the CAB maintenance window, or opted out.

## TC-FUN-01
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Open a privileged RDP session to a migrated Windows server through the Azure connectors | Module/Program Name/Menu Path: | Phase 3: Privileged sessions and credential management CyberArk Privilege Cloud portal > Windows test account > Connect; Monitoring
Test Case ID: | TC-FUN-01 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm a privileged RDP session opens through one of the Azure connectors without the user being asked for or shown the password, and that work done in the session reaches the target server. | Pre-requisites/Test Set-up: | 1. A Windows test platform sends sessions to the Azure connectors. 2. One migrated Windows server in Azure with a test account in a test safe. 3. A test user with Use Accounts, List Accounts and Initiate CPM account management rights on the test safes, working from an administrative workstation. 4. A reviewer with Monitor and View Audit rights. 5. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off.
Dependencies (H/W and S/W): | 1. Administrative workstation with a web browser. 2. CyberArk Privilege Cloud portal. 3. Migrated Windows test server in Azure. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (Test user, CyberArk administrator) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Medium (about 20 minutes)
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | The test user signs in to the CyberArk portal from an administrative workstation. | Test user account | The test user is signed in to the portal.
2 | Open the Windows test account and click Connect. | Windows test account in the test safe | The session opens without asking the user for a password.
3 | On the target server, create a text file named with the date and the case reference. | File name: <date>-TC-FUN-01.txt | The file exists on the target server.
4 | Confirm the password was never shown on screen at any point. | NA | The password is never shown.
5 | Sign out of the target to end the session. | NA | The session ends.
6 | The reviewer opens the session in Monitoring and records which connector handled it. | Reviewer account with Monitor and View Audit rights | The session is handled by one of the two Azure connectors.
7 | The reviewer records the PSM server name and plays the recording. | Reviewer account with Monitor and View Audit permissions | The session is brokered by AZPASPCCPRD101 or AZPASPCCPRD102 over allow-brokered-and-rotation, and the recording is complete and playable.

## TC-FUN-02
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Play back the recordings of the RDP and SSH test sessions | Module/Program Name/Menu Path: | Phase 3: Privileged sessions and credential management CyberArk Privilege Cloud portal > Monitoring > Recordings
Test Case ID: | TC-FUN-02 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the RDP sessions are recorded against the right account and time, play to the end without error, and show the action taken on the target and the end of the session. | Pre-requisites/Test Set-up: | 1. TC-FUN-01 have been run in this environment. 2. A reviewer with Monitor and View Audit rights. 3. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off.
Dependencies (H/W and S/W): | 1. CyberArk Privilege Cloud portal. 2. Session recordings from TC-FUN-01 and TC-FUN-02. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (CyberArk administrator) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | The reviewer opens Monitoring, Recordings in the portal. | Reviewer account with Monitor and View Audit rights | The recordings list opens.
2 | Find the sessions from TC-FUN-01 by account name and time. | Windows test account names Session times from TC-FUN-01 | Both recordings are listed against the right account and time.
3 | Play each recording from start to finish. | NA | Both recordings play to the end without error.
4 | Check that each recording shows the action taken on the target and the end of the session. | TC-FUN-01: text file created on the Windows server | The action on the target and the session end are both visible.

## TC-FUN-03
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Change the test account passwords immediately through the Azure password manager | Module/Program Name/Menu Path: | Phase 3: Privileged sessions and credential management CyberArk Privilege Cloud portal > Windows test accounts > Change, Verify
Test Case ID: | TC-FUN-03 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the Azure password manager changes and verifies the password on the Windows test accounts with no error, and that sessions open normally with the new password. | Pre-requisites/Test Set-up: | 1. The test safe is managed by the Azure password manager (AZ-CPM-PRD-01 in production). 2. The password manager is running on connector 01 and is installed and stopped on connector 02. 3. Windows test accounts are in a test safe on migrated servers. 4. A test user with Use Accounts, List Accounts and Initiate CPM account management rights on the test safes. 5. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off.
Dependencies (H/W and S/W): | 1. CyberArk Privilege Cloud portal. 2. Azure password manager on connector 01. 3. Migrated Windows and Linux test servers. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (CyberArk administrator, Test user) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Medium (about 30 minutes, plus the password manager cycle)
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | The CyberArk administrator confirms the test safe is managed by the Azure password manager. | Non-production: password manager on connector 01 Production: AZ-CPM-PRD-01 | The test safe is managed by the Azure password manager.
2 | Open the Windows test account and note the Last modified date. | Windows test account | The current Last modified date is recorded.
3 | Click Change and choose to have the password manager change the password immediately. | NA | The change request is submitted.
4 | Wait for the password manager to pick up the request, refresh the account and record the new Last modified date and status. | NA | The password is changed by the Azure password manager with no error, and Last modified is updated.
5 | Click Verify and wait for the result. | NA | Verify succeeds.
6 | Open a session to the account as in TC-FUN-01 to prove the new password works. | Windows test account | The session opens normally with the new password.
7 | Repeat steps 2 to 6 for the Linux test account. | Linux test account | The password is changed with no error, Last modified is updated, Verify succeeds and the session opens normally with the new password.
8 | Reassign the test safe to AZ-CPM-PRD-01 if needed, click Verify on the Windows test account, wait one CPM cycle, then record the compliance status and which password manager performed the verification. | Windows test account > Overview > Last Verified AZ-CPM-PRD-01 | The account is verified by AZ-CPM-PRD-01 from connector 01 over allow-brokered-and-rotation.

## TC-FUN-04
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm CyberArk audit events from both connectors arrive in Splunk | Module/Program Name/Menu Path: | Phase 3: Privileged sessions and credential management Splunk forwarder on each connector; Splunk search; Splunk deployment server console
Test Case ID: | TC-FUN-04 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the Splunk forwarder on each connector is connected to an indexer, and that the sign-in, session and password change events from the earlier tests arrive in Splunk within a few minutes of the activity. | Pre-requisites/Test Set-up: | 1. TC-FUN-01 to TC-FUN-04 have been run in this environment. 2. The Splunk forwarder is in place on both connectors. 3. The Splunk service owner is available with search access and access to the deployment server console. 4. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off. 5. Evidence folder for this test cycle is in place, with a subfolder for this case.
Dependencies (H/W and S/W): | 1. Splunk forwarder on connector 01 and connector 02. 2. Splunk indexer (port 9998). 3. Splunk deployment server (port 8089). | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (Build engineer, Splunk service owner) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Medium (about 20 minutes)
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | On each connector, run splunk list forward-server from the Splunk forwarder bin folder. | splunk list forward-server | The forwarder on each connector is connected to an indexer on port 9998.
2 | Note the times of the activity in TC-FUN-01 to TC-FUN-04. | Activity times from TC-FUN-01 to TC-FUN-04 | The activity times are recorded.
3 | In Splunk, run the search for each connector and confirm events from both connectors. | index=* host=<connector name> earliest=-60m | Events from both connectors are present.
4 | Search for the CyberArk audit events for that activity. | Portal sign-in, session start and end, and the password change | The sign-in, session and password change events arrive within a few minutes of the activity.
5 | In the Splunk deployment server console, confirm both connectors are listed. | Deployment server, port 8089 | Both connectors are listed on the deployment server.
6 | Save the evidence in the TC-FUN-05 subfolder of the evidence folder for the environment. | Command output; Splunk search results; deployment server screenshot | Evidence is saved in the case subfolder and matches the expected results. A case without evidence is recorded as not run, never as passed.
7 | In the deployment server console, confirm the server both connectors are listed under. | spldepprd101, port 8089 | Both connectors are listed under spldepprd101 on port 8089.

## TC-FUN-05
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Open a privileged SSH session to a migrated Linux server through the Azure farm | Module/Program Name/Menu Path: | Phase 3: Privileged sessions and credential management CyberArk Privilege Cloud portal > Linux test account > Connect; Monitoring
Test Case ID: | TC-FUN-05 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm a privileged SSH session to the migrated Linux server is brokered by one of the Azure connectors on TCP 22, and that the recording is complete and playable. | Pre-requisites/Test Set-up: | 1. The session manager farm Azure-PSM-PRD exists as a Configured PSM Server entry with Address cyberark-prd.geha.com, the password manager AZ-CPM-PRD-01 is registered, and the hub firewall egress address is on the tenant IP allowlist. 2. A test platform cloned from the production Windows platform, and one from the Linux platform, carry the Azure farm ID under UI and Workflows, Privileged Session Management. 3. One migrated Windows server and one migrated Linux server in the Corp landing zone, each with an account onboarded to a test safe on the matching test platform. 4. A test user with Use Accounts and List Accounts permissions on the test safes and Initiate CPM account management operations, and a reviewer with Monitor and View Audit permissions. 5. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. Workstation in the GEHA administrative ranges with a web browser. 2. CyberArk Privilege Cloud portal. 3. Migrated Linux test server in the Corp landing zone. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Test user, CyberArk administrator) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | The test user signs in to the portal from the administrative ranges. | Test user account | The test user is signed in to the portal.
2 | Open the Linux test account (test platform carrying the Azure farm ID) and click Connect. | Linux test account | The SSH session opens on TCP 22.
3 | Run one command on the target that leaves a trace, for example create a file. | touch /tmp/<date>-TC-FUN-05.txt | The trace exists on the target.
4 | End the session. | exit | The session ends.
5 | The reviewer opens the session in Monitoring and records the PSM server name. | Reviewer account with Monitor and View Audit permissions | The session is brokered by AZPASPCCPRD101 or AZPASPCCPRD102 over allow-brokered-and-rotation, and the recording is complete and playable.

## TC-FUN-06
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Open ten sessions in a row and confirm they are spread across both connectors | Module/Program Name/Menu Path: | Phase 3: Privileged sessions and credential management CyberArk Privilege Cloud portal > Windows test account; Monitoring > session list
Test Case ID: | TC-FUN-06 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm sessions through the Azure farm land on both connectors rather than being pinned to one server, and to record the distribution for the load balancing decision. | Pre-requisites/Test Set-up: | 1. The session manager farm Azure-PSM-PRD exists as a Configured PSM Server entry with Address cyberark-prd.geha.com, the password manager AZ-CPM-PRD-01 is registered, and the hub firewall egress address is on the tenant IP allowlist. 2. A test platform cloned from the production Windows platform, and one from the Linux platform, carry the Azure farm ID under UI and Workflows, Privileged Session Management. 3. One migrated Windows server and one migrated Linux server in the Corp landing zone, each with an account onboarded to a test safe on the matching test platform. 4. A test user with Use Accounts and List Accounts permissions on the test safes and Initiate CPM account management operations, and a reviewer with Monitor and View Audit permissions. 5. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. CyberArk Privilege Cloud portal. 2. Migrated Windows test server. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Test user, CyberArk administrator) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Medium
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Open ten sessions in succession to the Windows test target, closing each one before opening the next. | Windows test account 10 sessions | All ten sessions open.
2 | Record the PSM server for each session and export the session list. | Monitoring > session list | Sessions land on both connectors, with no run of sessions pinned to one server. The distribution is by hash, and the result is recorded for the load balancing method decision.

## TC-FUN-07
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Monitor a live session from the portal and confirm it connects to the right connector | Module/Program Name/Menu Path: | Phase 3: Privileged sessions and credential management CyberArk Privilege Cloud portal > Monitoring > Live sessions
Test Case ID: | TC-FUN-07 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm live session monitoring connects to the connector that holds the session, and to record the result for the decision on a direct monitoring route. | Pre-requisites/Test Set-up: | 1. The session manager farm Azure-PSM-PRD exists as a Configured PSM Server entry with Address cyberark-prd.geha.com, the password manager AZ-CPM-PRD-01 is registered, and the hub firewall egress address is on the tenant IP allowlist. 2. A test platform cloned from the production Windows platform, and one from the Linux platform, carry the Azure farm ID under UI and Workflows, Privileged Session Management. 3. One migrated Windows server and one migrated Linux server in the Corp landing zone, each with an account onboarded to a test safe on the matching test platform. 4. A test user with Use Accounts and List Accounts permissions on the test safes and Initiate CPM account management operations, and a reviewer with Monitor and View Audit permissions. 5. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. CyberArk Privilege Cloud portal. 2. Migrated Windows test server. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Test user, CyberArk administrator) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Medium
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | The test user opens a session as in TC-FUN-01 and keeps it open. | Windows test account | The session is open and running.
2 | The reviewer opens live monitoring of that session from the portal. | Reviewer account with Monitor permission | Live monitoring opens.
3 | Record whether monitoring connects and to which server. | NA | Monitoring connects to the connector running the session. If it fails, record it for the load balancing method decision: CyberArk routes live monitoring to the server that holds the session, which the hash-distributed load balancer cannot guarantee.

## TC-FUN-08
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Run five sessions in parallel and record connector CPU and memory | Module/Program Name/Menu Path: | Phase 3: Privileged sessions and credential management CyberArk Privilege Cloud portal; Azure Monitor metrics for both connectors
Test Case ID: | TC-FUN-08 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the connectors broker five parallel sessions and stay within CPU and memory headroom for the Standard_D8ls_v5 size. | Pre-requisites/Test Set-up: | 1. The session manager farm Azure-PSM-PRD exists as a Configured PSM Server entry with Address cyberark-prd.geha.com, the password manager AZ-CPM-PRD-01 is registered, and the hub firewall egress address is on the tenant IP allowlist. 2. A test platform cloned from the production Windows platform, and one from the Linux platform, carry the Azure farm ID under UI and Workflows, Privileged Session Management. 3. One migrated Windows server and one migrated Linux server in the Corp landing zone, each with an account onboarded to a test safe on the matching test platform. 4. Five test users, or one test user with five accounts, on the test safes. 5. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. CyberArk Privilege Cloud portal. 2. Azure Monitor metrics for vm-sec-cyberark-cus-prd-01 and 02 (AZPASPCCPRD101 and AZPASPCCPRD102). | Tear-down: | Close all test sessions.
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Test user, Build engineer) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Medium
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Five test users, or one user with five accounts, open sessions in parallel to the test targets and hold them for ten minutes. | 5 parallel sessions, held 10 minutes | All sessions are brokered.
2 | Record CPU and memory on both connectors from Azure Monitor while the sessions run. | Azure Monitor: CPU and memory | CPU and memory stay within headroom for Standard_D8ls_v5. The figures are recorded for the sizing decision.

## TC-FUN-09
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Run account discovery against the migrated test target | Module/Program Name/Menu Path: | Phase 3: Privileged sessions and credential management CyberArk Privilege Cloud portal > Account discovery
Test Case ID: | TC-FUN-09 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm account discovery still finds a migrated server through the tenant scanner, with no dependency on the Azure connectors. | Pre-requisites/Test Set-up: | 1. One migrated Windows server and one migrated Linux server in the Corp landing zone, each with an account onboarded to a test safe on the matching test platform. 2. The CyberArk administrator can run discovery in the tenant. 3. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. CyberArk Privilege Cloud portal (account discovery). | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (CyberArk administrator) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Run a discovery that includes the migrated test target. | Migrated Windows test server | The discovery runs to completion.
2 | Confirm the target is found. | NA | The target is discovered through the tenant scanner, with no dependency on the Azure connectors.

## TC-HA-01
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Stop the session manager on connector 01 and confirm sessions continue on connector 02 | Module/Program Name/Menu Path: | Phase 4: High availability, failover and recovery Connector 01 Windows services; Azure portal > load balancer health; CyberArk Privilege Cloud portal > Monitoring
Test Case ID: | TC-HA-01 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm that when the session manager on connector 01 goes down, the load balancer marks it unhealthy, new sessions go to connector 02 without any error for the user, sessions on connector 02 carry on, and connector 01 takes sessions again once it is back. | Pre-requisites/Test Set-up: | 1. Phases 1 to 3 have been run in this environment. 2. Both connectors are healthy on the load balancer probes. 3. In production, this case runs in an agreed test window with the CyberArk administrator present. 4. A test user with access to the test accounts, and a reviewer with Monitor rights. 5. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off.
Dependencies (H/W and S/W): | 1. Connector 01 and connector 02. 2. Azure portal access to the load balancer health. 3. CyberArk Privilege Cloud portal (Monitoring). 4. Test accounts and migrated test servers. | Tear-down: | Start the CyberArk Privileged Session Manager service on connector 01 and confirm it returns to healthy and takes sessions again (steps 6 and 7).
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (Build engineer, Test user, CyberArk administrator) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Medium
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | The test user opens a session and the reviewer records which connector is handling it. Repeat until a session is running on connector 02, and keep that session open. | Test account | A session is running on connector 02 and is kept open.
2 | On connector 01, stop the CyberArk Privileged Session Manager service and note the time. | Service: CyberArk Privileged Session Manager | The service stops and the time is recorded. Sessions running on connector 01 when it stops will disconnect; this is expected.
3 | Watch the load balancer health until connector 01 shows unhealthy on the session manager probe, and note the time. | Session manager probe: HTTPS 443 (/psm/api/health) | Connector 01 is marked unhealthy within about 90 seconds.
4 | While connector 01 is down, open three new sessions. | Test account | All three new sessions go to connector 02 without any error for the user.
5 | Check the session opened in step 1 is still working. | NA | The session on connector 02 carries on without interruption.
6 | Start the service on connector 01 and watch its health return to healthy. | Service: CyberArk Privileged Session Manager | Connector 01 returns to healthy.
7 | Open one more session and confirm connector 01 can take sessions again. | Test account | Connector 01 takes sessions again.

## TC-HA-02
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Move the password manager to connector 02 and confirm password changes continue | Module/Program Name/Menu Path: | Phase 4: High availability, failover and recovery Password manager services on connector 01 and connector 02; CyberArk Privilege Cloud portal > Connector Management, Windows test account
Test Case ID: | TC-HA-02 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm that if connector 01 is lost, the password manager on connector 02 can be started manually, takes over under the same name, and completes a password change and verification. | Pre-requisites/Test Set-up: | 1. Phases 1 to 3 have been run in this environment. 2. The password manager is running on connector 01 and installed and stopped on connector 02 (AZ-CPM-PRD-01 in production). 3. In production, this case runs in an agreed test window with the CyberArk administrator present. 4. The Windows test account is in a test safe managed by the Azure password manager. 5. Run in non-production (CIP-DEV) first. Run in production (CIP-PRD) only after every non-production case has passed and the non-production results are signed off.
Dependencies (H/W and S/W): | 1. Connector 01 and connector 02 (Windows services). 2. CyberArk Privilege Cloud portal (Connector Management, Accounts). 3. Windows test account and migrated Windows test server. | Tear-down: | Stop the password manager services on connector 02, start them again on connector 01, and confirm connector 01 is active again (step 7).
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-05
Test Case executed by: | TBD (CyberArk administrator) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | High
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Confirm the password manager service is running on connector 01 and stopped on connector 02. | NA | The password manager is running on connector 01 and stopped on connector 02.
2 | Stop the password manager services on connector 01 to simulate the loss of that connector, and note the time. | Password manager services on connector 01 | The password manager services are stopped on connector 01.
3 | On connector 02, start the password manager services. Only one password manager may run at any time. | Password manager services on connector 02 | The password manager services start on connector 02. The switch is manual.
4 | In Connector Management, confirm the password manager is now active from connector 02. | NA | The password manager on connector 02 takes over under the same name. Record the time it took from step 2 to step 4.
5 | Trigger an immediate password change on the Windows test account, then Verify it. | Windows test account | The password manager on connector 02 completes the change and verification.
6 | Open a session with the account to prove the new password works. | Windows test account | The session opens with the new password.
7 | Stop the services on connector 02, start them again on connector 01, and confirm connector 01 is active again. | Password manager services on both connectors | Connector 01 is active and connector 02 is stopped.

## TC-HA-03
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Take availability zone 1 away and confirm sessions continue on connector 02 | Module/Program Name/Menu Path: | Phase 4: High availability, failover and recovery Azure portal > vm-sec-cyberark-cus-prd-01 (zone 1); CyberArk Privilege Cloud portal
Test Case ID: | TC-HA-03 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm that if the whole of zone 1 is lost, sessions carry on through connector 02, recordings stay retrievable, and connector 01 rejoins with all components active when it is started again. | Pre-requisites/Test Set-up: | 1. TC-HA-01 has been run in this environment. 2. The session manager farm Azure-PSM-PRD exists as a Configured PSM Server entry with Address cyberark-prd.geha.com, the password manager AZ-CPM-PRD-01 is registered, and the hub firewall egress address is on the tenant IP allowlist. 3. A test platform cloned from the production Windows platform, and one from the Linux platform, carry the Azure farm ID under UI and Workflows, Privileged Session Management. 4. One migrated Windows server and one migrated Linux server in the Corp landing zone, each with an account onboarded to a test safe on the matching test platform. 5. A test user with Use Accounts and List Accounts permissions on the test safes and Initiate CPM account management operations, and a reviewer with Monitor and View Audit permissions. 6. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. Azure portal access to deallocate and start vm-sec-cyberark-cus-prd-01. 2. CyberArk Privilege Cloud portal. | Tear-down: | Start vm-sec-cyberark-cus-prd-01 and confirm connector 01 rejoins with all components active (step 3).
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Build engineer, Test user, CyberArk administrator) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | High
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Deallocate vm-sec-cyberark-cus-prd-01 in zone 1. | vm-sec-cyberark-cus-prd-01 (zone 1) | Connector 01 is deallocated.
2 | Repeat TC-FUN-01 and TC-FUN-02. | Windows test account | Sessions continue on connector 02, and the recordings are retrievable.
3 | Start the virtual machine and confirm the connector status in Connector Management returns, as in TC-CON-01. | vm-sec-cyberark-cus-prd-01 | Connector 01 rejoins with all components active.

## TC-PAR-01
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Open a session to an unmigrated server and confirm it still goes through the on-premises connectors | Module/Program Name/Menu Path: | Phase 5: Parallel run and separation CyberArk Privilege Cloud portal > unmigrated test account > Connect; Monitoring
Test Case ID: | TC-PAR-01 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the on-premises estate is unchanged: a session to an unmigrated server is still brokered by the on-premises connectors and its recording is playable. | Pre-requisites/Test Set-up: | 1. One unmigrated on-premises server with an account on a production platform that carries the on-premises farm ID. 2. A test user with Use Accounts and List Accounts permissions on the test safes and Initiate CPM account management operations, and a reviewer with Monitor and View Audit permissions. 3. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. CyberArk Privilege Cloud portal. 2. Unmigrated on-premises test server. 3. On-premises connectors PASPCCPRD101 and PASPCCPRD102. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Test user, CyberArk administrator) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | The test user opens a session to the unmigrated test target, whose account is on a production platform carrying the on-premises farm ID. | Unmigrated test account | The session opens.
2 | The reviewer records the PSM server and plays the recording. | Reviewer account with Monitor and View Audit permissions | The session is brokered by PASPCCPRD101 or PASPCCPRD102, and the recording is playable.

## TC-PAR-02
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Point an unmigrated server at the Azure farm and confirm the session is blocked at the hub firewall | Module/Program Name/Menu Path: | Phase 5: Parallel run and separation CyberArk Privilege Cloud portal > Platforms and Accounts; hub firewall log
Test Case ID: | TC-PAR-02 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To prove no session can cross from the Azure farm to a server that has not migrated: the attempt must be refused at the hub firewall against the deny rule, and the on-premises path must work again after the account is moved back. | Pre-requisites/Test Set-up: | 1. One unmigrated on-premises server with an account on a production platform that carries the on-premises farm ID. 2. A test platform cloned from the production Windows platform, and one from the Linux platform, carry the Azure farm ID under UI and Workflows, Privileged Session Management. 3. A test user with Use Accounts and List Accounts permissions on the test safes and Initiate CPM account management operations, and a reviewer with Monitor and View Audit permissions. 4. Rule collection group rcg-sec-cyberark is applied to DefaultFirewallPolicy through the firewall pipeline, the net new IP groups are created with their members, and there is no network security group on the subnet. 5. TC-PAR-01 has passed. 6. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. CyberArk Privilege Cloud portal. 2. Hub firewall logs (GEHA Network). | Tear-down: | Move the unmigrated test account back to its production platform, wait one configuration refresh and confirm TC-PAR-01 passes again (steps 4 and 5).
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (CyberArk administrator, Test user, GEHA Network) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | High
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | The CyberArk administrator moves the unmigrated target account to the test platform carrying the Azure farm ID. | Unmigrated test account Test platform with the Azure farm ID | The account is on the Azure test platform.
2 | Wait one configuration refresh. | ConfigurationRefreshInterval, default 600 seconds | The refresh interval has passed.
3 | The test user attempts a session to the unmigrated target. | Unmigrated test account | The attempt fails to reach the target, and the hub firewall log shows deny-brokered-to-onprem matched. If the session reaches the target, stop testing: no cutover request goes forward until the rule is fixed and this case reruns clean.
4 | The administrator moves the account back to its production platform and waits one refresh. | Production platform with the on-premises farm ID | The account is back on its production platform.
5 | Repeat TC-PAR-01. | Unmigrated test account | TC-PAR-01 succeeds again after the move back.

## TC-PAR-03
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Rehearse moving a migrated account between the on-premises and Azure platforms | Module/Program Name/Menu Path: | Phase 5: Parallel run and separation CyberArk Privilege Cloud portal > Platforms and Accounts; Monitoring
Test Case ID: | TC-PAR-03 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm sessions follow the platform on the next connection when an account is moved between the Azure and on-premises platforms, and that no account property is lost. | Pre-requisites/Test Set-up: | 1. One migrated Windows server and one migrated Linux server in the Corp landing zone, each with an account onboarded to a test safe on the matching test platform. 2. A test platform cloned from the production Windows platform, and one from the Linux platform, carry the Azure farm ID under UI and Workflows, Privileged Session Management. 3. A test user with Use Accounts and List Accounts permissions on the test safes and Initiate CPM account management operations, and a reviewer with Monitor and View Audit permissions. 4. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. CyberArk Privilege Cloud portal. | Tear-down: | Move the migrated Windows test account back to the test platform with the Azure farm ID (step 3).
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (CyberArk administrator, Test user) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | High
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Export the account properties of the migrated Windows test account, then move it from the test platform (Azure ID) to a platform carrying the on-premises ID. | Migrated Windows test account | The account properties are exported and the account is on the on-premises platform.
2 | Wait one refresh, open a session and record the PSM server. | ConfigurationRefreshInterval, default 600 seconds | The session follows the platform and is brokered by the on-premises farm.
3 | Move the account back, wait one refresh, open a session and record the PSM server. Export the account properties again. | Test platform with the Azure farm ID | The session follows the platform back to the Azure farm, and no account property is lost.

## TC-PAR-04
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm the Secure Tunnel service and the tenant audit feed are not affected | Module/Program Name/Menu Path: | Phase 5: Parallel run and separation Services on PASPCCPRD101; SIEM search
Test Case ID: | TC-PAR-04 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the Secure Tunnel service on the on-premises connector keeps running and tenant audit events keep arriving in the SIEM during the parallel run. | Pre-requisites/Test Set-up: | 1. The SIEM service owner is available with search access. 2. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. On-premises connector PASPCCPRD101. 2. SIEM. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (CyberArk administrator, SIEM service owner) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | On PASPCCPRD101, confirm the Secure Tunnel service is running. | Secure Tunnel service | The service is running.
2 | In the SIEM, confirm audit events from the tenant are still arriving. | SIEM search for tenant audit events | Events are arriving. The re-point of this feed is a separate GEHA decision and is not part of this test.

## TC-PAR-05
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm no migrated server is calling the on-premises credential provider tier | Module/Program Name/Menu Path: | Phase 5: Parallel run and separation IIS logs on the four PASCCP hosts
Test Case ID: | TC-PAR-05 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the credential provider tier stays on premises with its consumers, and that no migrated test target sends requests to it. | Pre-requisites/Test Set-up: | 1. Access to the IIS logs on the four PASCCP hosts for the test window. 2. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. The four PASCCP credential provider hosts. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (CyberArk administrator) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Pull the IIS logs from the four PASCCP hosts for the test window. | PASCCP hosts, IIS logs | The logs for the test window are collected.
2 | Filter the logs for source addresses in the migrated test target set. | Addresses of the migrated test targets | No requests come from any migrated test target. Any request found is recorded for the credential provider decision, since that tier stays on premises with its consumers.

## TC-OPS-01
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm Cohesity backup protection and restore for both connectors | Module/Program Name/Menu Path: | Phase 6: Operations Cohesity console > Protection; restore job
Test Case ID: | TC-OPS-01 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm both connectors are protected by the agreed Cohesity policy, a snapshot exists after build, a restore works or is scheduled, and neither connector is enrolled in Azure Backup. | Pre-requisites/Test Set-up: | 1. The two connectors are in their own MECM maintenance window collection, the Cohesity protection policy for the Azure connectors is assigned, and the automatic upgrade windows for the Management Agent and the Identity Connector are set or opted out. 2. The Cohesity service owner is available with console access. 3. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. Cohesity console. 2. An isolated resource group for the restore test. | Tear-down: | Remove the restored disk from the isolated resource group once the restore is confirmed.
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Cohesity service owner) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Medium
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | In the Cohesity console, open the protection status of both virtual machines and the policy assigned. | vm-sec-cyberark-cus-prd-01 and 02 (AZPASPCCPRD101 and AZPASPCCPRD102) | Both are protected by the confirmed policy (the 8-week policy of the on-premises connector).
2 | Confirm a snapshot completed after build. | NA | A snapshot is present for both virtual machines.
3 | Restore one operating system disk to an isolated resource group, or schedule the restore and record the date. | Isolated resource group | The restore succeeds or is scheduled. Neither connector is enrolled in Azure Backup.

## TC-OPS-02
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Stop the session manager briefly and confirm the Splunk alert fires | Module/Program Name/Menu Path: | Phase 6: Operations Services on one connector; Splunk alerting
Test Case ID: | TC-OPS-02 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the Splunk alert configured for the connectors fires and reaches the named route when the session manager service stops. | Pre-requisites/Test Set-up: | 1. The Splunk owner has configured the alert for the connectors and named its route. 2. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. One Azure connector. 2. Splunk. | Tear-down: | Start the CyberArk Privileged Session Manager service again after two minutes.
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Build engineer, Splunk service owner) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Stop the PSM service on one connector for two minutes, then start it again. | CyberArk Privileged Session Manager service | The service stops and is started again after two minutes.
2 | Record the alert received in Splunk and its route. | Splunk alert | The Splunk alert fires and reaches the named route.

## TC-OPS-03
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Patch both connectors one at a time through MECM with no session interruption | Module/Program Name/Menu Path: | Phase 6: Operations MECM console > connector maintenance window collection; CyberArk Privilege Cloud portal
Test Case ID: | TC-OPS-03 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm an approved update installs on both connectors one at a time through MECM, and that sessions carry on through the other connector during each reboot. | Pre-requisites/Test Set-up: | 1. The two connectors are in their own MECM maintenance window collection, the Cohesity protection policy for the Azure connectors is assigned, and the automatic upgrade windows for the Management Agent and the Identity Connector are set or opted out. 2. TC-INF-15 has passed. 3. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. MECM console. 2. CyberArk Privilege Cloud portal. 3. One approved update. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (MECM service owner, Test user) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | High
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Deploy one approved update to connector 02 through MECM in the connector maintenance window collection. | Connector 02 first | The update installs on connector 02.
2 | Confirm installation and reboot of connector 02, and that sessions continued on connector 01 during the reboot. | NA | The reboot completes and there is no session interruption on connector 01.
3 | The following night, deploy the same update to connector 01. | Connector 01 the following night | The update installs on connector 01.
4 | Confirm installation and reboot of connector 01, and that sessions continued on connector 02 during the reboot. | NA | The reboot completes and there is no session interruption on connector 02.
5 | Check the connector status in Connector Management as in TC-CON-01. | NA | All components are active on both connectors afterwards.

## TC-OPS-04
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm the agent upgrade windows line up with the CAB maintenance window | Module/Program Name/Menu Path: | Phase 6: Operations CyberArk Privilege Cloud portal > Connector Management; Identity Connector Configuration program
Test Case ID: | TC-OPS-04 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm neither the Management Agent nor the Identity Connector can upgrade outside the agreed CAB maintenance window, unless GEHA has opted out. | Pre-requisites/Test Set-up: | 1. TC-CON-07 and TC-CON-09 have been run. 2. The two connectors are in their own MECM maintenance window collection, the Cohesity protection policy for the Azure connectors is assigned, and the automatic upgrade windows for the Management Agent and the Identity Connector are set or opted out. 3. Runs against the production connector pair in CIP-PRD, in parallel with the on-premises connectors PASPCCPRD101 and PASPCCPRD102.
Dependencies (H/W and S/W): | 1. CyberArk Privilege Cloud portal. 2. Identity Connector Configuration program. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (CyberArk administrator) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Record the Management Agent automatic upgrade setting and window from TC-CON-09 and the Identity Connector auto-update window from TC-CON-07, against the CAB maintenance window. | CAB maintenance window | Both are set as GEHA decided, and neither can start outside the agreed window unless opted out.

## TC-CUT-01
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Re-point the first production platform to the Azure farm and validate on cutover day | Module/Program Name/Menu Path: | Phase 7: Cutover day validation and rollback CyberArk Privilege Cloud portal > Platforms, Safes, Monitoring
Test Case ID: | TC-CUT-01 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To move the first production platform, or the first set of production accounts, to the Azure farm and prove on the day that sessions work through both the Azure and the on-premises farms. | Pre-requisites/Test Set-up: | 1. Cutover is approved by GEHA Security, Enterprise Architecture and CAB together. 2. Scheduled in a CAB maintenance window, Thursday evening or a weekend, outside the Open Season, Thanksgiving and year-end freezes. 3. Phases 1 to 6 have passed and the evidence has been accepted by GEHA Security and Enterprise Architecture. 4. The rollback decision rests with Phil Costanzo, application admin and support manager, on the recommendation of the CyberArk administrator.
Dependencies (H/W and S/W): | 1. CyberArk Privilege Cloud portal. 2. One production target per platform being re-pointed. 3. One unmigrated production target. 4. CyberArk PAS Rollback Plan. | Tear-down: | If any of steps 3 to 5 fail, run TC-CUT-02 (rollback).
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Build engineer, CyberArk administrator, Test user) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | High
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | On the morning of cutover, repeat TC-CON-02 step 5, TC-INF-02, TC-CON-01 and TC-CON-06. Once the disaster recovery edition is in service, also confirm both replicated items are Protected as in TC-DR-01. | NA | Probes are healthy, the name and health page answer, all components are active and both connectors are healthy.
2 | Apply the Azure farm ID to the first production platform, or move the first production accounts to the Azure platform, and reassign their safes to AZ-CPM-PRD-01. Wait one configuration refresh. | Azure farm ID: Azure-PSM-PRD Password manager: AZ-CPM-PRD-01 | The platform or accounts point at the Azure farm and the safes are managed by AZ-CPM-PRD-01.
3 | Repeat TC-FUN-01 and TC-FUN-05 against one production target per platform re-pointed. | One production target per platform | RDP and SSH sessions are brokered by the Azure connectors.
4 | Repeat TC-PAR-01 for one unmigrated production target. | One unmigrated production target | The session is brokered by the on-premises connectors.
5 | Confirm the tenant session list shows sessions on both the Azure and the on-premises farms. | Monitoring > session list | Both farms are active. Hypercare begins.

## TC-CUT-02
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Roll back the production platform to the on-premises farm | Module/Program Name/Menu Path: | Phase 7: Cutover day validation and rollback CyberArk Privilege Cloud portal > Platforms, Safes, Monitoring
Test Case ID: | TC-CUT-02 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To return the re-pointed platform or accounts to the on-premises farm and confirm sessions work again, if rollback is invoked on cutover day. | Pre-requisites/Test Set-up: | 1. Run only if rollback is invoked after TC-CUT-01. 2. The rollback call has been made by Phil Costanzo on the recommendation of the CyberArk administrator. 3. CyberArk PAS Rollback Plan available.
Dependencies (H/W and S/W): | 1. CyberArk Privilege Cloud portal. 2. On-premises password manager and session manager farm. | Tear-down: | Return to the acceptance step for the next CAB.
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (CyberArk administrator) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Medium
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Restore the on-premises farm ID on the platform, or move the accounts back to their on-premises platform. | On-premises farm ID | The platform or accounts point at the on-premises farm.
2 | Reassign the safes to the on-premises password manager. | On-premises password manager | The safes are managed by the on-premises password manager.
3 | Wait one configuration refresh. | ConfigurationRefreshInterval, default 600 seconds | The refresh interval has passed.
4 | Repeat step 3 of TC-CUT-01 against the on-premises farm. | One production target per platform | Sessions are brokered by the on-premises connectors. Rollback completes in under 30 minutes with no infrastructure change and no system taken out of service.

## TC-DR-01
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm both connectors are replicating to East US 2 | Module/Program Name/Menu Path: | Phase 8: Disaster recovery Azure portal > Recovery Services vault rsv-sec-cyberark-eus2-dr-01 > Replicated items
Test Case ID: | TC-DR-01 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm both connectors are Protected in the DR vault with recovery points within the replication policy, and to record how long replication took to reach Protected. | Pre-requisites/Test Set-up: | 1. Replication was enabled on both connectors at least one day before the test and both replicated items are Protected. The East US 2 landing zone, DR subnet, DR load balancer and recovery plan are in place, and the Cloud Platform Team has provided an isolated test-failover virtual network in East US 2. 2. Runs against the disaster recovery edition of the build tables once it is issued, using the names of the disaster recovery ruling.
Dependencies (H/W and S/W): | 1. Azure portal access to rg-sec-cyberark-dr. 2. Recovery Services vault rsv-sec-cyberark-eus2-dr-01. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Build engineer, Cloud Platform Team) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | In the portal, open the Recovery Services vault, Replicated items, and record both connectors with status, RPO and last recovery point. | rsv-sec-cyberark-eus2-dr-01 in rg-sec-cyberark-dr | Both items are Protected, RPO is within the replication policy, and recovery points are present for both.
2 | Record the time from enabling replication to Protected. | NA | The time is recorded.

## TC-DR-02
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm the replication network paths from both connectors | Module/Program Name/Menu Path: | Phase 8: Disaster recovery PowerShell Test-NetConnection on both connectors
Test Case ID: | TC-DR-02 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm each connector can reach the cache storage account, Microsoft sign-in and the Site Recovery service on port 443 through the Site Recovery firewall rules. | Pre-requisites/Test Set-up: | 1. Replication was enabled on both connectors at least one day before the test and both replicated items are Protected. The East US 2 landing zone, DR subnet, DR load balancer and recovery plan are in place, and the Cloud Platform Team has provided an isolated test-failover virtual network in East US 2. 2. Runs against the disaster recovery edition of the build tables once it is issued, using the names of the disaster recovery ruling.
Dependencies (H/W and S/W): | 1. Connector 01 and connector 02. 2. Windows PowerShell (Test-NetConnection). 3. Hub firewall logs (GEHA Network). | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Build engineer, GEHA Network) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | On each connector, run Test-NetConnection on port 443 to the cache storage account blob endpoint, to login.microsoftonline.com and to the Site Recovery service host for the vault region. | Port 443 Cache storage blob endpoint login.microsoftonline.com Site Recovery service host | All connections succeed on both connectors through the Site Recovery rules.

## TC-DR-03
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Run a test failover of both connectors into the isolated East US 2 network | Module/Program Name/Menu Path: | Phase 8: Disaster recovery Azure portal > Recovery plan > Test failover
Test Case ID: | TC-DR-03 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the recovery plan brings both connectors up in East US 2, in zone 1 and zone 2 at the planned size, without error. | Pre-requisites/Test Set-up: | 1. Replication was enabled on both connectors at least one day before the test and both replicated items are Protected. The East US 2 landing zone, DR subnet, DR load balancer and recovery plan are in place, and the Cloud Platform Team has provided an isolated test-failover virtual network in East US 2. 2. Runs against the disaster recovery edition of the build tables once it is issued, using the names of the disaster recovery ruling. 3. The CyberArk administrator is available to watch the tenant during the test.
Dependencies (H/W and S/W): | 1. Azure portal access to the recovery plan. 2. Isolated test-failover virtual network in East US 2. | Tear-down: | Clean up the test failover in TC-DR-08.
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Build engineer, CyberArk administrator) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | High
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Open the recovery plan and run Test failover with the latest processed recovery point into the isolated test-failover virtual network. | Latest processed recovery point Isolated test-failover virtual network | The plan completes without error.
2 | Record the start and completion times. | NA | The times are recorded.
3 | Record both test virtual machines with zone, size and tags. | NA | Both replicas are running in East US 2, in zone 1 and zone 2, at Standard_D8ls_v5. Tags are recorded, including the backup exclusion tag.

## TC-DR-04
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Check how the replica connectors start and what the tenant shows for them | Module/Program Name/Menu Path: | Phase 8: Disaster recovery Jump host in the isolated network; CyberArk Privilege Cloud portal > Connector Management
Test Case ID: | TC-DR-04 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To record how the replicas start in the isolated network and how the tenant treats a second instance of a registered connector. | Pre-requisites/Test Set-up: | 1. TC-DR-03 is running. 2. Runs against the disaster recovery edition of the build tables once it is issued, using the names of the disaster recovery ruling.
Dependencies (H/W and S/W): | 1. Jump host in the isolated East US 2 network. 2. CyberArk Privilege Cloud portal (Connector Management). | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (CyberArk administrator, Build engineer) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Medium
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | From a jump host in the isolated network, record on each test virtual machine the computer name, domain membership and the state of the CyberArk Privileged Session Manager service. | Test virtual machines in East US 2 | Computer names are AZPASPCCPRD101 and AZPASPCCPRD102, and the PSM service is running.
2 | In Connector Management, record what the tenant shows for the replica while it runs. | NA | The tenant behaviour is recorded, whatever it is. A conflict or duplicate entry becomes a recovery-plan action owned by GEHA Security.

## TC-DR-05
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Check the DR load balancer with the test virtual machines in its backend pool | Module/Program Name/Menu Path: | Phase 8: Disaster recovery Azure portal > DR load balancer
Test Case ID: | TC-DR-05 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the DR load balancer matches the build tables load balancer parameters for the DR names and sees both test virtual machines as healthy. | Pre-requisites/Test Set-up: | 1. TC-DR-03 is running. 2. Runs against the disaster recovery edition of the build tables once it is issued, using the names of the disaster recovery ruling.
Dependencies (H/W and S/W): | 1. Azure portal access to the DR load balancer. | Tear-down: | Remove the two test virtual machine NICs from the backend pool after TC-DR-08 (step 3).
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Build engineer) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Medium
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Open the DR load balancer and record the front end, probes and rule. | DR load balancer | The parameters match the build tables load balancer parameters for the DR names.
2 | Add the two test virtual machine NICs to the backend pool and record health. | Test virtual machine NICs | Both test virtual machines are Healthy on both probes.
3 | Remove the NICs from the backend pool after TC-DR-08. | NA | The backend pool no longer holds the test NICs.

## TC-DR-06
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Rehearse the DNS re-point to the DR load balancer | Module/Program Name/Menu Path: | Phase 8: Disaster recovery GEHA DNS; nslookup and browser from the isolated network
Test Case ID: | TC-DR-06 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm a DNS record pointing at the DR front end resolves and serves the health page through the DR load balancer, and to record how long the change takes. | Pre-requisites/Test Set-up: | 1. TC-DR-05 step 2 is complete. 2. Runs against the disaster recovery edition of the build tables once it is issued, using the names of the disaster recovery ruling. 3. The GEHA DNS service owner is available.
Dependencies (H/W and S/W): | 1. GEHA DNS. 2. Client in the isolated East US 2 network. | Tear-down: | Remove the cyberark-drtest.geha.com record after TC-DR-08 (step 4).
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Cloud Platform Team, DNS service owner) | Test Case executed date: | TBD
Test Case Priority: | Medium | Test Case Complexity: | Medium
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | GEHA DNS creates cyberark-drtest.geha.com pointing at the DR front end address. | cyberark-drtest.geha.com | The record is created.
2 | From the isolated network, run nslookup and request the health page. | nslookup cyberark-drtest.geha.com https://cyberark-drtest.geha.com/psm/api/health | The record resolves and the health page returns HTTP 200 through the DR load balancer.
3 | Record the time taken to change and propagate the record. | NA | The change time is recorded.
4 | Remove the record after TC-DR-08. | NA | The record is removed.

## TC-DR-07
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm the East US 2 hub egress address is on the tenant allowlist | Module/Program Name/Menu Path: | Phase 8: Disaster recovery CyberArk Privilege Cloud portal > IP allowlist
Test Case ID: | TC-DR-07 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To confirm the tenant will accept connections from the DR region before any real failover is needed. | Pre-requisites/Test Set-up: | 1. Runs against the disaster recovery edition of the build tables once it is issued, using the names of the disaster recovery ruling.
Dependencies (H/W and S/W): | 1. CyberArk Privilege Cloud portal. 2. GEHA Network record of the East US 2 hub egress address. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (CyberArk administrator, GEHA Network) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Low
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | GEHA Network provides the East US 2 hub egress public address. | East US 2 hub egress address | The address is provided.
2 | The CyberArk administrator confirms the address is on the tenant allowlist. | Tenant IP allowlist | The address is present on the allowlist before any real failover.

## TC-DR-08
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Clean up the test failover and confirm replication stays Protected | Module/Program Name/Menu Path: | Phase 8: Disaster recovery Azure portal > Recovery plan > Cleanup test failover
Test Case ID: | TC-DR-08 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To remove the test virtual machines after the test failover and confirm both connectors are still Protected. | Pre-requisites/Test Set-up: | 1. TC-DR-03 to TC-DR-07 are complete. 2. Runs against the disaster recovery edition of the build tables once it is issued, using the names of the disaster recovery ruling.
Dependencies (H/W and S/W): | 1. Azure portal access to the recovery plan. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Build engineer) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Medium
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | Run Cleanup test failover on the recovery plan, with notes. | Recovery plan | The cleanup job completes.
2 | Confirm the test virtual machines are removed and replication remains Protected. | NA | The test virtual machines are removed and both items are Protected. If not, remove the test resources by hand, record it and rerun TC-DR-01.

## TC-DR-09
Test Case
Project Name: | GEHA Data Center Migration: CyberArk PAS, Privilege Cloud connectors (Azure connector estate)
Test Case Name: | Confirm production sessions are not affected during and after the test failover | Module/Program Name/Menu Path: | Phase 8: Disaster recovery CyberArk Privilege Cloud portal > Monitoring; Connector Management
Test Case ID: | TC-DR-09 | Requirement ID: | NA
QA Task Number(for Agile projects): | NA | User Story Number (for Agile projects): | NA
Test Case objective: | To prove the production connector pair keeps working while the test failover runs and after it is cleaned up. | Pre-requisites/Test Set-up: | 1. The session manager farm Azure-PSM-PRD exists as a Configured PSM Server entry with Address cyberark-prd.geha.com, the password manager AZ-CPM-PRD-01 is registered, and the hub firewall egress address is on the tenant IP allowlist. 2. A test platform cloned from the production Windows platform, and one from the Linux platform, carry the Azure farm ID under UI and Workflows, Privileged Session Management. 3. One migrated Windows server and one migrated Linux server in the Corp landing zone, each with an account onboarded to a test safe on the matching test platform. 4. A test user with Use Accounts and List Accounts permissions on the test safes and Initiate CPM account management operations, and a reviewer with Monitor and View Audit permissions. 5. Runs against the disaster recovery edition of the build tables once it is issued, using the names of the disaster recovery ruling.
Dependencies (H/W and S/W): | 1. CyberArk Privilege Cloud portal. 2. Migrated Windows test server. | Tear-down: | NA
Test Case designed by: | Saikat/Amitendra | Test Case designed date: | 2026-10-06
Test Case executed by: | TBD (Test user, CyberArk administrator) | Test Case executed date: | TBD
Test Case Priority: | High | Test Case Complexity: | Medium
Step Number | Step Description | Test Data Used in Step | Expected Result
1 | While TC-DR-03 is running, repeat TC-FUN-01 against production. | Windows test account | The session is brokered by AZPASPCCPRD101 or AZPASPCCPRD102.
2 | The reviewer records the PSM server and the Connector Management status of the production pair. | NA | The production pair is active.
3 | After TC-DR-08, repeat TC-FUN-01 and record the PSM server and Connector Management status again. | Windows test account | The session is brokered by AZPASPCCPRD101 or AZPASPCCPRD102, and the production pair stays active throughout.