EXECUTION WORKFLOW

IBM Turbonomic
On-Premises Appliance to Existing Azure AKS Cluster
Version 1.3 | Implementation Runbook | Helm-based non-production deployment

Prepared for architecture, platform, application, security, network, CAB and operations review

# Document Control

| Document Attribute | Value |
| --- | --- |
| Document reference | Execution Workflow - IBM Turbonomic AKS Migration (v1.3) |
| Source | On-premises VMware-hosted Turbonomic appliance (Lenexa; VM "turbonomic", DNS node1; CentOS 7, 8 vCPU, 128 GB RAM) |
| Target | Existing production AKS cluster; isolated non-production Turbonomic instance in dedicated namespace turbonomic-nonprod |
| Deployment pattern | Helm 3 releases that package IBM's published Turbonomic Operator manifests and the Turbonomic (Xl) Custom Resource. The IBM Operator performs the platform deployment. Azure-side prerequisites (node pool, registry access, DNS, Key Vault) are provided by the Azure and AKS platform teams before deployment. |
| Product version | IBM Turbonomic 8.21.2 with Operator 42.116 proposed (operator image in IBM's release tag 8.21.2). Final version pair confirmed in Step 1. |
| Reference documentation | IBM Documentation 8.21.0: "Installing Turbonomic on an AKS cluster" (last updated 2026-09-04) and "Azure AKS requirements for Turbonomic" (last updated 2026-05-27). Full list in Section 15. |
| Data approach | Fresh deployment; no historical database migration; operator-provisioned containerised database (IBM-supported for non-production use) |
| Related document | SOP - Deploying the Non-Production IBM Turbonomic Instance on AKS with Helm (v1.0) |
| Status | DRAFT - values marked TBD require approval before execution |
| Prepared by | Amitendra / Saikat |
| Date | 2026-10-14 |

## Revision History

| Version | Date | Author | Change |
| --- | --- | --- | --- |
| 1.0 | 2026-10-14 | Cloud Architecture Team | Initial enterprise execution workflow for shared AKS deployment |
| 1.1 | 2026-10-14 | Cloud Architecture Team | Version label carried by the received document. No change entry for 1.1 was recorded in the previous revision table. |
| 1.2 | 2026-10-14 | Amitendra / Saikat | Deployment re-based on Helm releases that wrap IBM's 8.21 Operator and Xl Custom Resource. Added the image, version and registry procedure (Section 4). Expanded isolation controls for the shared production cluster (Section 6). Incorporated IBM 8.21 AKS guidance and listed the points where it conflicts with this design. Re-sequenced the runbook into 19 steps. Corrected section numbering: Sections 7 and 11 were missing, and the cutover step referred to the rollback protocol as Section 10. |
| 1.3 | 2026-10-14 | Amitendra / Saikat | Bicep removed: the deployment is purely Helm, and Azure-side items are prerequisites confirmed in Step 5. All YAML manifests removed; settings are now shown as tables and numbered actions. Operator version updated to 42.116 for 8.21.2 from IBM's release tag. Companion SOP issued. |

## Approvals

| Role | Name | Approval/Date |
| --- | --- | --- |
| Application Owner | TBD |  |
| AKS Platform Owner | TBD |  |
| Cloud Architect | TBD |  |
| Security Architect | TBD |  |
| Network/DNS Owner | TBD |  |
| Change Manager | TBD |  |

# 1. Executive Summary

This workflow describes how IBM Turbonomic moves from its on-premises VMware appliance to the existing production Azure Kubernetes Service (AKS) cluster. The new instance is a non-production workload. It is installed with Helm into its own namespace and node pool. Isolation controls stop it from consuming, reaching or changing anything that belongs to the production workloads already running in the cluster. The instance can therefore be installed, configured and fully tested without affecting production. Historical data is not migrated; targets and integrations are re-created.

Turbonomic is a set of containerised microservices. IBM installs it on AKS with the Turbonomic Operator (t8c-operator). The operator watches a Custom Resource of kind Xl and deploys every platform component from it. IBM does not publish a standalone Helm chart for the Turbonomic platform. The operator is Helm-based internally: the Xl resource belongs to the API group charts.helm.k8s.io, and its settings mirror a chart embedded in the operator image. That embedded chart is not supplied for direct use.

Helm is therefore used as GEHA's packaging and release tool around IBM's unchanged deliverables. There are three Helm releases: one for the platform guardrails, one for the IBM Operator and one for the Xl Custom Resource. Every deployment is versioned, repeatable, reviewable and reversible. The IBM Operator is still the component that builds and manages Turbonomic, so the installation stays within IBM's supported method.

## Key design decisions

| Decision | Approved direction | Control required |
| --- | --- | --- |
| Cluster model | Use existing production AKS cluster | Explicit approval to host a non-production workload in a production cluster (Section 5.2) |
| Isolation | Dedicated namespace turbonomic-nonprod, dedicated node pool, quotas, default-deny network policies, namespace-scoped RBAC, internal-only load balancer | Platform-owned guardrails deployed before the application; isolation tests T02, T11 and T18-T24 |
| Deployment mechanism | Helm 3 releases turbo-np-platform, turbo-np-operator and turbo-np-instance | Charts held in Git and ACR; IBM manifests kept unchanged apart from documented parameters |
| Deployment engine | IBM Turbonomic Operator + Xl Custom Resource | Operator restricted to its own namespace (WATCH_NAMESPACE) |
| Version | Turbonomic 8.21.x with the IBM-paired Operator version | Exact tags pinned; no "latest"; IBM written confirmation |
| Images | Mirrored from icr.io/cpopen into GEHA ACR (recommended) or pulled directly | Digest recorded and image scanned before deployment |
| Data | Clean start; containerised database provisioned by the operator | No historical DB restore; external database only if the instance is later classified as production |
| Kubeturbo | Disabled | Prevents a non-production instance from discovering or acting on production workloads in the same cluster |

## Points that need a decision or IBM confirmation

These items came up while aligning this workflow with IBM's 8.21 AKS documentation and the Turbonomic Migration Playbook (v0.4). Each one is listed with its proposed handling.

| # | Observation | Impact | Proposed handling |
| --- | --- | --- | --- |
| 1 | IBM publishes no Helm chart for the Turbonomic platform. The documented 8.21 AKS method is kubectl + Operator + Xl CR. | A Helm design that bypasses the operator would be unsupported. | Helm wraps IBM's manifests unchanged; IBM to confirm support in writing (Step 1). |
| 2 | IBM's AKS requirements say "Select None for network policy" when creating the cluster. | Conflicts with GEHA's default-deny guardrail. The shared cluster setting cannot change for one workload. | Allow all traffic inside the namespace; restrict only traffic crossing it (Section 6.4). IBM to confirm. |
| 3 | IBM's operator ClusterRole grants all verbs on clusterroles, clusterrolebindings, mutatingwebhookconfigurations, secrets and pods/exec. | Cluster-wide privilege inside a production cluster. | Security review in Step 2; minimum rights requested from IBM; ClusterRole renamed (Section 6.3). |
| 4 | By default the Xl configuration creates an nginx Service of type LoadBalancer and attempts to get a public external IP. | Public exposure from a production cluster. | Internal load balancer annotations are mandatory in values (Step 11); test T22. |
| 5 | IBM's install topic pins operator manifests to the 8.21.0 tag but takes the CRD and AKS sample CR from the main branch. The main-branch sample already references 8.21.2. | Unpinned inputs can change between test and production runs. | Download once, review, store in Git with checksums (Step 1). |
| 6 | Playbook v0.4 records the disposition as RePurchase, with the target undecided between Turbonomic SaaS and Azure-native tooling. | This workflow assumes self-hosted Turbonomic on AKS. | Update the playbook disposition and target-state sections before CAB. |
| 7 | The instance is classified non-production, yet Steps 17-19 move operational use to it and retire the appliance. | Production support expectations on a non-production workload. IBM recommends an external database for production. | Decide at Step 2 whether the AKS instance becomes the operational service. If so, record the classification change and plan the external database. |
| 8 | Playbook integrations include Splunk (monitors the appliance) and LDAP/AD (UI login). Version 1.1 of this workflow did not cover Splunk. | Monitoring gap after cutover. | Splunk decision added to Step 15; LDAP/AD covered in Step 13. |

# 2. Scope, Assumptions and Guardrails

## 2.1 In Scope

Shared-cluster readiness validation and capacity review

Dedicated namespace, node pool and namespace-scoped controls

Helm chart creation, packaging and release management for the platform guardrails, IBM Operator and Turbonomic instance

Turbonomic image sourcing, version pinning, mirroring and scanning

Persistent storage, main encryption-key secret, certificates, internal load balancer and DNS

Recreation of Azure, vCenter, ServiceNow, SMTP and LDAP/AD integrations

Functional, security, isolation, resilience, performance and user-acceptance testing

Cutover, rollback, hypercare and operational handover

## 2.2 Out of Scope

Creation of a new dedicated AKS cluster

Creation of Azure resources. The node pool, registry access, DNS record and Key Vault are prerequisites provided by the platform teams (Step 5).

Changes to cluster-wide settings of the production AKS cluster (network plugin, network policy engine, Kubernetes version)

Historical database migration

Unapproved upgrade of the source appliance

Kubeturbo deployment, or adding the production AKS cluster as a Turbonomic target

Decommissioning of vCenter before all dependent workloads are retired

## 2.3 Assumptions

The AKS cluster is healthy and runs a Kubernetes version that IBM and Microsoft both support for Turbonomic 8.21.

The cluster uses Microsoft Entra ID integration. If the API server is private, the deployment agent has private network access (self-hosted Azure DevOps agent in a peered VNet).

A network policy engine (Azure NPM, Calico or Cilium) is enabled on the cluster. If it is not, NetworkPolicies are accepted but not enforced; Step 4 checks this.

An Azure Container Registry is attached to the cluster, or nodes can reach icr.io through the egress firewall.

The Azure-side prerequisites in Step 5 are in place before Step 6 starts.

The Turbonomic licence is workload-based and transferable to cloud, as recorded in the migration playbook. IBM confirms it covers this instance.

## 2.4 Mandatory Guardrails

No deployment until IBM confirms the product version, Operator version, AKS/Kubernetes version and the Helm-wrapped installation method.

No default-namespace deployment.

No cluster-admin access for routine Turbonomic operations. Cluster-scoped objects are installed only by the AKS Platform team.

No secrets in Git, Helm values, Helm release history, screenshots or command history.

No "latest" or floating image tags. Every image tag and digest is recorded.

No public IP address for any Turbonomic service.

Kubeturbo stays disabled, and no AKS cluster target is added without separate approval.

No manual kubectl edits to resources owned by a Helm release or by the IBM Operator. All changes go through Git and the pipeline.

No application cutover until rollback remains viable and success criteria are signed off.

Non-production data, users and targets must remain isolated from unrelated production workloads.

# 3. Future-State Specification

| Configuration parameter | Specification / decision |
| --- | --- |
| AKS cluster | Existing production AKS cluster: <AKS_CLUSTER> |
| Resource group | <AKS_RESOURCE_GROUP> |
| Subscription | <SUBSCRIPTION_ID_OR_NAME> |
| Kubernetes namespace | turbonomic-nonprod (final name subject to standards) |
| Workload classification | Non-production application workload (see point 7 in Section 1) |
| Deployment tooling | Helm 3 (version pinned on the pipeline agent); releases turbo-np-platform, turbo-np-operator, turbo-np-instance |
| Turbonomic version | <TURBO_VERSION>: 8.21.2 proposed (latest 8.21 patch on IBM's t8c-operator repository); 8.21.0 is the version IBM's AKS topic documents |
| Operator version | <OPERATOR_VERSION>: 42.116 for 8.21.2 (IBM release tag); 42.114 for 8.21.0 (IBM 8.21.0 documentation) |
| Image registry | <ACR_NAME>.azurecr.io/turbonomic (mirror of icr.io/cpopen/turbonomic and icr.io/cpopen/t8c-operator) |
| Node placement | Dedicated user node pool turbonp; label workload=turbonomic-nonprod; taint workload=turbonomic-nonprod:NoSchedule (subject to Step 1 confirmation; see Step 11) |
| Availability | Operator-managed components as delivered by IBM. If the node pool spans availability zones, at least two nodes per zone (IBM requirement, because block storage is zonal). |
| Storage | StorageClass turbo-np-managed-csi-retain: disk.csi.azure.com, Premium_LRS, reclaimPolicy Retain, WaitForFirstConsumer, volume expansion enabled. At least 150 GB for all PVs (IBM minimum). |
| Database | Containerised database provisioned by the operator (externalDbIP not set) |
| Ingress | Turbonomic nginx Service of type LoadBalancer on an internal Azure load balancer with reserved private IP <ILB_PRIVATE_IP> in <ILB_SUBNET_NAME>; corporate/VPN access only |
| DNS | <TURBONOMIC_NP_FQDN> |
| TLS | Enterprise-issued certificate loaded into Turbonomic nginx using IBM's documented certificate procedure |
| Encryption key | Kubernetes secret master-key-secret (32-byte key) in the namespace; source copy held in Key Vault <KEY_VAULT_NAME> |
| Identity | Entra-integrated AKS access; namespace-scoped deployment identity; LDAP/AD (or approved SSO) for Turbonomic UI login |
| Observability | Azure Monitor / Container Insights plus Turbonomic health checks; Splunk forwarding if retained |
| Historical data | Not migrated; clean start |
| Legacy appliance | Retained through rollback and agreed observation period |

# 4. Turbonomic Images, Versions and Helm Packaging

## 4.1 How IBM Delivers Turbonomic for Kubernetes

Before deciding how Helm fits, it is worth listing the IBM pieces that actually exist. All of them are published in the IBM t8c-operator GitHub repository and in the IBM Container Registry.

| IBM deliverable | What it is | Where it comes from |
| --- | --- | --- |
| Custom Resource Definition | Defines the Xl kind (API group charts.helm.k8s.io). Cluster-scoped. | deploy/crds/charts_v1_xl_crd.yaml |
| Operator RBAC | ServiceAccount, Role, RoleBinding, ClusterRole, ClusterRoleBinding, all named t8c-operator | deploy/service_account.yaml, role.yaml, role_binding.yaml, cluster_role.yaml, cluster_role_binding.yaml |
| Operator | Deployment t8c-operator running icr.io/cpopen/t8c-operator:<OPERATOR_VERSION>, plus NetworkPolicy t8c-operator-egress | deploy/operator.yaml |
| Xl Custom Resource | The instance definition: image repository, tag, storage class, ingress, database, encryption and enabled probes | deploy/samples/aks/charts_v1_xl_cr.yaml |
| Platform images | One image per component (for example api, auth, clustermgr, action-orchestrator, nginx, database and each probe) | icr.io/cpopen/turbonomic/<component>:<TURBO_VERSION> |

The operator reads the Xl resource and renders its embedded chart. This is why the "tag" in the Xl resource decides the Turbonomic version every component runs. It is also why the operator image must be a version that IBM pairs with that Turbonomic version.

## 4.2 Version Matrix

| Item | Value to use | Where it is set |
| --- | --- | --- |
| Turbonomic platform | <TURBO_VERSION> in x.x.x format, e.g. 8.21.2 | env/nonprod/instance-values.yaml: xl.global.tag (renders spec.global.tag) |
| Operator image | t8c-operator:<OPERATOR_VERSION>, e.g. 42.116 for 8.21.2 | env/nonprod/operator-values.yaml: image.tag |
| IBM manifests | Repository tag that matches the release, e.g. 8.21.0 or 8.21.2 | vendor/ibm/t8c-operator/<IBM_TAG>/ in Git, with SHA256SUMS |
| Component image repository | icr.io/cpopen/turbonomic, or <ACR_NAME>.azurecr.io/turbonomic | instance-values.yaml: xl.global.repository |
| Operator image repository | icr.io/cpopen/t8c-operator, or <ACR_NAME>.azurecr.io/turbonomic/t8c-operator | operator-values.yaml: image.repository |
| Helm client | Approved Helm 3 release (3.14 or later recommended) | Pipeline agent image |
| GEHA wrapper charts | Semantic version, e.g. 1.0.0; appVersion set to <TURBO_VERSION> | Chart.yaml of each chart |

Rule: the image tag in the Xl resource must always equal the Turbonomic instance version (IBM requirement). Operator 42.114 can manage earlier Turbonomic versions, but a later Turbonomic patch may need a later operator. Check the IBM release notes every time the version changes.

## 4.3 Image Source Options

| Option | How it works | When to use |
| --- | --- | --- |
| A. Direct from IBM | Nodes pull from icr.io/cpopen through the egress firewall. IBM's standard operator.yaml and the sample CR already point there. | Only if production-cluster egress policy allows icr.io and images can be scanned on arrival. |
| B. Mirror into GEHA ACR (recommended) | Images are copied into <ACR_NAME> with az acr import. The operator image and xl.global.repository point to ACR, and the cluster kubelet identity pulls with AcrPull. IBM documents this as the private-repository option. | Production cluster with controlled egress. Needed for digest pinning, Defender for Containers scanning and repeatable rebuilds. |

Step 7 contains the exact commands for Option B.

## 4.4 Helm Wrapper Charts

Three small charts are kept in the deployment repository. They are split by ownership. The AKS Platform team owns everything that protects the rest of the cluster. The application team owns the Turbonomic release itself.

| Chart / release | Owner | Contents | Scope |
| --- | --- | --- | --- |
| turbonomic-platform / turbo-np-platform | AKS Platform Team | ResourceQuota, LimitRange, NetworkPolicies, team RoleBindings, StorageClass, and IBM's operator ClusterRole and ClusterRoleBinding (renamed) | Namespace plus listed cluster-scoped objects |
| turbonomic-operator / turbo-np-operator | Application Engineering | IBM ServiceAccount, Role, RoleBinding, operator Deployment and operator egress NetworkPolicy. Parameterised only for image, namespace and placement. | Namespace |
| turbonomic-instance / turbo-np-instance | Application Engineering | One Xl resource rendered from values, with annotation helm.sh/resource-policy: keep | Namespace |

The CRD is not placed in any chart. Helm installs the files in a chart's crds/ folder once and never upgrades them. A CRD managed as a template would delete every Xl resource in the cluster if its release were uninstalled. The AKS Platform team therefore applies the CRD with kubectl (Step 9).

### Repository layout

turbonomic-aks/

vendor/ibm/t8c-operator/<IBM_TAG>/          # IBM files exactly as downloaded + SHA256SUMS

charts/

turbonomic-platform/                       # guardrails, StorageClass, operator cluster RBAC

turbonomic-operator/                       # IBM operator ServiceAccount, Role, RoleBinding, Deployment

turbonomic-instance/                       # the Turbonomic (Xl) resource

env/nonprod/

platform-values.yaml

operator-values.yaml

instance-values.yaml

scripts/

images-<TURBO_VERSION>.txt                 # component image list for the release

validate.sh

pipelines/azure-pipelines.yml

Each chart carries its own version number (starting at 1.0.0) and an appVersion equal to <TURBO_VERSION>. Charts are packaged and pushed to ACR, so every deployment uses an immutable chart version.

### Settings in the instance values file (env/nonprod/instance-values.yaml)

| Setting | Value | Why |
| --- | --- | --- |
| Instance name | xl-release | Name of the Turbonomic (Xl) resource the operator manages |
| Image repository | <ACR_NAME>.azurecr.io/turbonomic (Option A: icr.io/cpopen/turbonomic) | Approved registry for all component images |
| Image tag | <TURBO_VERSION>, e.g. 8.21.2 | Must equal the Turbonomic instance version (IBM requirement) |
| Storage class | turbo-np-managed-csi-retain | Meets IBM AKS storage rules |
| Hosting provider / platform | azure / aks | As in IBM's AKS sample |
| External secrets | Enabled | Uses master-key-secret, created in Step 8 before the instance |
| Internal load balancer | Annotation azure-load-balancer-internal = "true" | No public IP for the Turbonomic UI |
| Load balancer subnet | Annotation azure-load-balancer-internal-subnet = <ILB_SUBNET_NAME> | Places the private IP in the approved subnet |
| Load balancer IP | Annotation azure-load-balancer-ipv4 = <ILB_PRIVATE_IP> | Reserved IP, so DNS can be created before deployment |
| Database | No external database address set | Operator provisions a containerised database (IBM: suitable for non-production) |
| Components enabled | azure, vcenter, servicenow | Targets required by GEHA |
| Components disabled | kubeturbo, and every other component in IBM's AKS sample | Kubeturbo must stay off in the shared production cluster |

The instance chart has one template that turns these settings into the Xl resource. It marks the resource with the Helm annotation helm.sh/resource-policy: keep, so "helm uninstall" can never delete the Turbonomic platform by accident.

### Settings in the operator values file (env/nonprod/operator-values.yaml)

| Setting | Value | Why |
| --- | --- | --- |
| Operator image repository | <ACR_NAME>.azurecr.io/turbonomic/t8c-operator (IBM default: icr.io/cpopen/t8c-operator) | IBM-documented private-repository option |
| Operator image tag | <OPERATOR_VERSION>, e.g. 42.116 | Must be the operator version IBM pairs with <TURBO_VERSION> |
| Operator image digest | sha256 value recorded in Step 7 | Guarantees the exact scanned image is used |
| Node selector | workload = turbonomic-nonprod | Keeps the operator on the dedicated pool |
| Toleration | workload = turbonomic-nonprod, effect NoSchedule | Allows the operator onto the tainted pool |

### Settings in the platform values file (env/nonprod/platform-values.yaml)

| Setting | Value | Why |
| --- | --- | --- |
| Quota: CPU and memory | Requests and limits from IBM resource recommendations | Caps what Turbonomic can take from the shared cluster |
| Quota: storage | Not below 150 GB (IBM minimum) | Caps persistent disk consumption |
| Quota: PVCs and pods | From IBM sizing plus headroom | Prevents uncontrolled growth |
| Quota: LoadBalancer services | 1 | Only the internal nginx service is allowed |
| Container defaults | Request 100m CPU / 256Mi; limit 1 CPU / 2Gi; no maximum | Defaults only, so IBM's own requests are never blocked |
| Network policy CIDRs | Corporate/VPN, vCenter, ServiceNow, SMTP and LDAP ranges | Explicit allows on top of default deny (Section 6.4) |
| StorageClass | turbo-np-managed-csi-retain: disk.csi.azure.com, Premium_LRS, Retain, WaitForFirstConsumer, expansion on | IBM AKS storage requirements |
| Operator cluster RBAC | ClusterRole and ClusterRoleBinding t8c-operator-turbonomic-nonprod; subject namespace turbonomic-nonprod | IBM permissions, renamed to avoid clashes; IBM hard-codes namespace "turbonomic" |
| Team access | Entra group object IDs for namespace admin and read-only | Least-privilege access for support teams |

## 4.5 How a Version Is Installed or Changed

The same sequence is used for the first install and for every later patch:

Choose the Turbonomic version from IBM release notes and write down the matching operator version.

Import the new images into ACR (Option B) and record their digests.

In a pull request, change operator-values.yaml (only if the operator version changes) and the tag in instance-values.yaml.

The pipeline renders the charts, runs a server-side dry-run and shows the difference. The approver reviews it.

The pipeline runs helm upgrade for turbo-np-operator first, waits for the rollout, and then upgrades turbo-np-instance.

The operator reconciles and replaces the component pods. The validation commands confirm every pod runs the new tag.

Section 8 gives the full upgrade procedure.

## 4.6 What Must Not Be Done

Do not extract the xl chart from the operator image and install it with Helm. That bypasses the operator and is not an IBM-supported method.

Do not edit Deployments or StatefulSets created by the operator. The operator puts them back and the change is lost.

Do not use helm uninstall on turbo-np-instance as a restart. It is a destructive action, protected by the keep annotation, and is used only under Section 10.

Do not put master-key-secret, database passwords or target credentials into Helm values. Helm stores rendered manifests and values in a release Secret inside the namespace.

# 5. Prerequisites and Governance

## 5.1 Access Requirements

| Access scope | Purpose | Granting authority |
| --- | --- | --- |
| Namespace admin for the deployment identity (Azure RBAC "Azure Kubernetes Service RBAC Admin" at namespace scope, or a Kubernetes RoleBinding) | Deploy the operator and instance Helm releases, secrets and PVC-backed workloads | AKS Platform Team |
| Cluster-admin for a named platform engineer, time-bound through PIM | Apply the CRD, StorageClass, operator ClusterRole/ClusterRoleBinding and the turbo-np-platform release | AKS Platform Owner / CAB |
| Azure DevOps repository, pipeline, environment approvals and a self-hosted agent with private access to the API server | Store charts and values; execute controlled deployment | DevOps Platform Team |
| ACR: AcrPush for the pipeline identity; AcrPull for the AKS kubelet identity | Import images and push Helm charts as OCI artifacts; pull images | Azure Platform Team |
| Azure resource read access | Validate AKS, subnets, identities, monitoring and DNS integration | Azure Platform Team |
| Key Vault: Secrets Officer (break-glass) and Secrets User (pipeline) | Store and read the Turbonomic main key, certificate and integration credentials | Security/Key Vault Owner |
| IBM licence and support access | Licence file; IBM case for version and support confirmation | Turbonomic/IBM Owner |
| Turbonomic administrator | Create targets, policies, users and integration settings | Application Owner |

## 5.2 Shared Production Cluster Exception

Before implementation, record approval for the non-production workload to run on a production cluster. The approval must address support ownership, backup, maintenance windows, incident priority, data classification and whether the production cluster SLA applies to the non-production application. It must also list the cluster-scoped objects in Section 6.3 and name who is allowed to change them.

## 5.3 Required Inputs Checklist

☐ Exact Turbonomic target version and matching Operator version

☐ Existing AKS Kubernetes version, network plugin and network policy engine

☐ IBM written confirmation: version pair, Helm-wrapped installation, network policies, cluster-role scope, node placement

☐ Image source decision (direct icr.io or ACR mirror) and ACR name

☐ Component image list for the chosen version

☐ CPU/memory sizing and namespace quota values

☐ Node pool VM size, node count and availability zones

☐ StorageClass name and capacities

☐ Namespace name, labels and Pod Security level

☐ Internal load balancer subnet and reserved private IP

☐ FQDN and TLS certificate

☐ Outbound FQDNs/ports and proxy requirements

☐ vCenter, Azure, ServiceNow, SMTP and LDAP/AD target details

☐ Splunk forwarding decision

☐ Rollback observation period

☐ Named owners and escalation contacts

# 6. Network, Security and Isolation Design

## 6.1 Connectivity Matrix

| Source | Destination | Port | Purpose | Status |
| --- | --- | --- | --- | --- |
| Corporate/VPN users | Internal load balancer IP (Turbonomic nginx) | TCP 443 | Turbonomic UI/API | TBD |
| Pipeline agent | AKS API server (private endpoint) | TCP 443 | Helm and kubectl deployment | TBD |
| Turbonomic namespace | <ACR_NAME>.azurecr.io and its data endpoint | TCP 443 | Pull images (Option B) | TBD |
| Turbonomic namespace | IBM Container Registry (icr.io) | TCP 443 | Pull images (Option A only) | TBD |
| Turbonomic namespace | Azure Resource Manager and Entra ID login endpoints | TCP 443 | Azure target discovery | TBD |
| Turbonomic namespace | vCenter FQDN(s) | TCP 443 | VMware discovery/actions as approved | TBD |
| Turbonomic namespace | ServiceNow endpoint | TCP 443 | Workflow integration if retained | TBD |
| Turbonomic namespace | SMTP relay | TCP 25/587 as approved | Notifications | TBD |
| Turbonomic namespace | LDAP/AD domain controllers | TCP 636 (LDAPS) or 389 | UI login authentication | TBD |
| Turbonomic namespace | kube-dns in kube-system | UDP/TCP 53 | Name resolution | TBD |
| Turbonomic namespace | NTP path | UDP 123 or platform-managed | Time synchronization | TBD |
| Log collector | Splunk indexer/HEC | As approved (e.g. TCP 8088/9997) | Log forwarding if retained | TBD |

## 6.2 Isolation Controls

| Layer | Control | How it is implemented | Owner |
| --- | --- | --- | --- |
| Namespace | Dedicated namespace with labels | Namespace created in Step 6 with environment, owner, cost-centre and Pod Security labels | AKS Platform |
| Compute | Dedicated user node pool | Pool turbonp with label and NoSchedule taint. Other workloads cannot land on it, and Turbonomic cannot land on production pools. | AKS Platform |
| Compute | ResourceQuota and LimitRange | Quota caps CPU, memory, storage, PVC count, pods and LoadBalancer services. LimitRange sets defaults only, with no maximum below IBM's requests. | AKS Platform |
| Network | Default deny plus explicit allows | NetworkPolicies in turbo-np-platform (Section 6.4) | AKS Platform / Network |
| Network | Internal load balancer only | Internal LB annotations in the Xl values; Azure Policy that denies public IPs where in place | Network |
| Identity | Namespace-scoped deployment identity | Azure RBAC role at namespace scope or a RoleBinding; the pipeline never holds cluster-admin | AKS Platform |
| Identity | Operator confined to its namespace | WATCH_NAMESPACE taken from the operator pod's own namespace (IBM default) | Application Engineering |
| Workload | Pod Security Admission | enforce=baseline; warn and audit=restricted. Raise to restricted only if IBM pods pass. | AKS Platform / Security |
| Supply chain | Pinned images from ACR | Tags and digests recorded; Defender for Containers scan before deployment | Security |
| Secrets | Main key and credentials outside Helm | Key Vault is the source; the pipeline creates the Kubernetes secret; never in values | Security |
| Safety | Kubeturbo disabled | kubeturbo: false in Xl values; no AKS cluster target added | Application Owner |
| Change control | Helm-only changes | No manual kubectl edits; drift check during hypercare | Application Engineering |

## 6.3 Cluster-Scoped Objects

Only the objects below are created outside the namespace. They are the only parts of this deployment that can touch the rest of the production cluster, so each one has a named owner and a removal rule.

| Object | Name | Created by | Why it is needed | Risk and mitigation |
| --- | --- | --- | --- | --- |
| CustomResourceDefinition | xls.charts.helm.k8s.io | AKS Platform with kubectl (Step 9) | Defines the Xl kind | Shared by any future Turbonomic instance in the cluster. Never deleted while any Xl exists. |
| ClusterRole | t8c-operator-turbonomic-nonprod (IBM name t8c-operator) | turbo-np-platform | IBM operator cluster permissions | Wildcard rights on RBAC objects and mutating webhooks. Security review; minimum scope requested from IBM. |
| ClusterRoleBinding | t8c-operator-turbonomic-nonprod | turbo-np-platform | Binds the ClusterRole to the t8c-operator ServiceAccount | The subject namespace must be changed from IBM's default to turbonomic-nonprod. |
| StorageClass | turbo-np-managed-csi-retain | turbo-np-platform | IBM storage rules (Retain, WaitForFirstConsumer, expansion) | Retained disks remain after deletion and are removed only by approved change. |
| Node pool | turbonp | AKS Platform (Step 5 prerequisite) | Compute isolation | Cost; removed by a separate change after decommission. |
| Internal LB frontend | Managed by AKS | AKS cloud provider, from the nginx Service | Private UI access | Uses one private IP in the ILB subnet. |

## 6.4 Network Policy Position

IBM's AKS requirements topic tells customers to select None for network policy when creating the cluster, so that all pod traffic flows freely. That guidance is written for a cluster dedicated to Turbonomic. Here the cluster already exists and runs production workloads. Its network policy setting is not changed, and GEHA's default-deny rule applies.

To stay as close as possible to IBM's assumption, the namespace allows all traffic between its own pods. The Turbonomic microservices therefore behave as they would with no policy. Only traffic that crosses the namespace boundary is restricted:

| Policy | Direction | Rule |
| --- | --- | --- |
| default-deny-all | Ingress and egress | Selects every pod in the namespace and denies anything not explicitly allowed |
| allow-intra-namespace | Ingress and egress | Any pod in turbonomic-nonprod may reach any other pod in turbonomic-nonprod |
| allow-dns | Egress | UDP/TCP 53 to kube-dns pods in kube-system |
| allow-ui-from-corporate | Ingress | Corporate/VPN CIDRs to the nginx pods on the nginx container ports. externalTrafficPolicy Local keeps the client IP visible. |
| allow-target-egress | Egress | vCenter, ServiceNow, SMTP and LDAP CIDRs on their ports; TCP 443 to non-private ranges for Azure APIs and ACR, with FQDN filtering at Azure Firewall |
| t8c-operator-egress (IBM) | Egress | Shipped in IBM's operator.yaml. Allows all egress for the operator pod only (it must reach the API server). Kept as delivered and recorded as an accepted exception. |

Network policies only take effect if the cluster runs a network policy engine. Step 4 checks networkProfile.networkPolicy. If it reports none, the isolation in this section is not enforced, and the shared-cluster exception must be revisited.

# 7. Implementation Roadmap

| Phase | Steps | Outcome |
| --- | --- | --- |
| Preparation and approval | 1-3 | Version pair and IBM confirmations, shared-cluster approval, repository, Helm charts and pipeline ready |
| Platform readiness | 4-9 | Capacity and Azure prerequisites confirmed; namespace guardrails, images, storage, main key and CRD in place |
| Application deployment | 10-11 | IBM Operator and Turbonomic instance deployed by Helm and healthy |
| Configuration and validation | 12-16 | Private access, licence, identity, targets, monitoring and end-to-end tests complete |
| Cutover and handover | 17-19 | Controlled go-live, hypercare and decommission decision |

## Step 1: Confirm IBM-Supported Version, Images and Installation Method

| Field | Details |
| --- | --- |
| Owner | Application Owner / IBM Support / Cloud Architect |
| Dependencies | Discovery complete |
| Objective | Freeze the exact Turbonomic version, operator version, image source and the Helm-wrapped installation method before any cluster change. |

### Execution activities

Record the AKS Kubernetes version, network plugin, network policy engine, private-cluster setting and whether local accounts are disabled.

Check the Kubernetes version against IBM's Kubernetes general requirements for 8.21 and Microsoft's AKS supported-versions calendar.

Agree the target release. 8.21.2 with operator 42.116 is proposed: it is the latest pair IBM has published as a release tag on its t8c-operator repository. IBM documents 8.21.0 with 42.114 and 8.21.1 with 42.115. IBM documentation for 8.21.3 exists, but no 8.21.3 release tag was published at the time of writing.

Confirm with IBM whether to stay on 8.21.2 or wait for a published 8.21.3 pair.

Open an IBM case and ask four questions in writing: (1) Is a Helm release that applies IBM's unchanged operator manifests and Xl CR supported? (2) Is Turbonomic supported with NetworkPolicies enforced, given the AKS requirement for network policy None? (3) What is the minimum cluster-scoped permission set when the operator watches only its own namespace? (4) Does the 8.21 Xl CR pass nodeSelector and tolerations to component pods?

Download IBM's manifests at the pinned tag into vendor/ibm/t8c-operator/<IBM_TAG>/, unchanged, and record SHA-256 checksums. IBM's install topic takes the CRD and AKS sample CR from the main branch. Take them once, record the commit ID, and treat that copy as the controlled version.

Decide the image source: direct pull from icr.io, or mirror into ACR (Section 4.3).

### Command-level validation

kubectl version

az aks show -g <AKS_RESOURCE_GROUP> -n <AKS_CLUSTER> --query '{k8s:kubernetesVersion, privateCluster:apiServerAccessProfile.enablePrivateCluster, networkPlugin:networkProfile.networkPlugin, networkPolicy:networkProfile.networkPolicy, azureRbac:aadProfile.enableAzureRbac, localAccountsDisabled:disableLocalAccounts}' -o jsonc

kubectl get crd | grep -i -E 'xl|turbo|t8c' || true

# Download and pin the IBM deliverables

IBM_TAG=<IBM_TAG>            # e.g. 8.21.0 or 8.21.2

BASE=https://raw.githubusercontent.com/IBM/t8c-operator

mkdir -p vendor/ibm/t8c-operator/$IBM_TAG/crds vendor/ibm/t8c-operator/$IBM_TAG/samples/aks

for f in service_account.yaml role.yaml role_binding.yaml cluster_role.yaml cluster_role_binding.yaml operator.yaml; do

curl -fsSL -o vendor/ibm/t8c-operator/$IBM_TAG/$f $BASE/$IBM_TAG/deploy/$f

done

curl -fsSL -o vendor/ibm/t8c-operator/$IBM_TAG/crds/charts_v1_xl_crd.yaml $BASE/main/deploy/crds/charts_v1_xl_crd.yaml

curl -fsSL -o vendor/ibm/t8c-operator/$IBM_TAG/samples/aks/charts_v1_xl_cr.yaml $BASE/main/deploy/samples/aks/charts_v1_xl_cr.yaml

(cd vendor/ibm/t8c-operator/$IBM_TAG && find . -type f -name '*.yaml' -exec sha256sum {} + > SHA256SUMS)

grep -E 'image:' vendor/ibm/t8c-operator/$IBM_TAG/operator.yaml

### Acceptance criteria

Written IBM confirmation of the version pair and the four questions is attached to the change record.

Product, Operator and Kubernetes versions are recorded and mutually supported.

IBM files are in Git with checksums; no placeholder or "latest" image tags remain.

### Evidence to retain

Version matrix

IBM case reference and answers

SHA256SUMS of the vendor files and main-branch commit ID

## Step 2: Approve Shared-Cluster Hosting and Change Governance

| Field | Details |
| --- | --- |
| Owner | Cloud Architect / AKS Platform Owner / Security Architect / CAB |
| Dependencies | Step 1 |
| Objective | Approve the risk and operating model for non-production Turbonomic in a production cluster. |

### Execution activities

Complete architecture, security and operational reviews of this workflow.

Review the cluster-scoped objects in Section 6.3, with particular attention to IBM's operator ClusterRole, and record the decision.

Document namespace ownership, support hours, incident severity, maintenance windows, cost allocation and decommission responsibility.

Decide whether the AKS instance becomes the operational Turbonomic service after cutover (point 7 in Section 1). If yes, record the classification change and whether an external database is required.

Confirm that Kubeturbo stays disabled and that no AKS cluster target is added.

Confirm that production vCenter and Azure data may be discovered by a non-production instance (data classification).

Raise change records for platform preparation, application deployment and cutover.

### Acceptance criteria

All approvers sign the document.

CAB/change IDs are recorded.

Named rollback decision authority is assigned.

The cluster-scoped object list is approved by Security.

### Evidence to retain

Architecture decision record

Security approval including ClusterRole review

CAB/change references

## Step 3: Build the Deployment Repository, Helm Charts and Pipeline

| Field | Details |
| --- | --- |
| Owner | DevOps / Cloud Engineering / Application Engineering |
| Dependencies | Steps 1-2 |
| Objective | Create an auditable and repeatable delivery path for the three Helm releases. |

### Execution activities

Create the repository layout in Section 4.4 and commit the IBM files from Step 1 unchanged under vendor/.

Build the turbonomic-operator chart. Copy IBM's service_account, role, role_binding and operator.yaml into templates/ and change only the namespace, operator image, nodeSelector and tolerations. Every other line stays as IBM delivered it.

Build the turbonomic-platform chart: ResourceQuota, LimitRange, NetworkPolicies, team RoleBindings, StorageClass, and IBM's cluster_role and cluster_role_binding. Rename both to t8c-operator-turbonomic-nonprod and change the binding subject namespace to turbonomic-nonprod.

Build the turbonomic-instance chart with the single xl.yaml template shown in Section 4.4.

Create the non-production values files under env/nonprod/. None of them may contain a secret.

Add pipeline stages in this order: helm lint; helm template; server-side dry-run; manual approval; helm upgrade per release; validation script.

Package the charts and push them to ACR as OCI artifacts, so that each deployment uses an immutable chart version.

Protect the main branch and require review from both Platform and Application Engineering.

### Command-level validation

helm lint charts/turbonomic-platform -f env/nonprod/platform-values.yaml

helm lint charts/turbonomic-operator -f env/nonprod/operator-values.yaml

helm lint charts/turbonomic-instance -f env/nonprod/instance-values.yaml

mkdir -p rendered

helm template turbo-np-operator charts/turbonomic-operator -n turbonomic-nonprod -f env/nonprod/operator-values.yaml > rendered/operator.yaml

git diff --no-index vendor/ibm/t8c-operator/<IBM_TAG>/operator.yaml rendered/operator.yaml   # only approved parameters may differ

# Package and publish charts to ACR (OCI)

helm package charts/turbonomic-platform charts/turbonomic-operator charts/turbonomic-instance --destination dist/

TOKEN=$(az acr login --name <ACR_NAME> --expose-token --output tsv --query accessToken)

echo "$TOKEN" | helm registry login <ACR_NAME>.azurecr.io --username 00000000-0000-0000-0000-000000000000 --password-stdin

for c in dist/*.tgz; do helm push "$c" oci://<ACR_NAME>.azurecr.io/helm; done

### Acceptance criteria

helm lint passes for all three charts.

Rendered operator manifests differ from IBM's files only in approved parameters.

Charts are versioned in ACR; artifacts are peer reviewed.

Secrets are absent from repository history and values files.

### Evidence to retain

Pipeline run

Pull request approval

Rendered-manifest diff

## Step 4: Validate Shared AKS Capacity and Health

| Field | Details |
| --- | --- |
| Owner | AKS Platform Team |
| Dependencies | Steps 1-2 |
| Objective | Ensure the production cluster can safely host Turbonomic and enforce the isolation design. |

### Execution activities

Review allocatable CPU/memory, current requests/limits, node count, maxPods, storage quotas and IP availability.

Compare Turbonomic requirements (IBM resource recommendations for Kubernetes deployments, and at least 150 GB of persistent storage) with spare capacity plus agreed headroom. As a planning reference, the current appliance runs on 8 vCPU and 128 GB RAM.

Confirm the network policy engine is enabled. Without one, Section 6.4 is not enforced.

Confirm the cluster autoscaler behaviour and the decision to use the dedicated turbonp pool.

Verify there are no existing critical alerts or unhealthy nodes.

### Command-level validation

kubectl get nodes -o wide

kubectl describe nodes | egrep 'Name:|Allocatable:|cpu:|memory:|pods:'

kubectl top nodes

kubectl get pods -A -o wide

kubectl get events -A --sort-by=.lastTimestamp | tail -100

az aks nodepool list -g <AKS_RESOURCE_GROUP> --cluster-name <AKS_CLUSTER> -o table

az aks show -g <AKS_RESOURCE_GROUP> -n <AKS_CLUSTER> --query networkProfile.networkPolicy -o tsv   # must return azure, calico or cilium

kubectl get storageclass

### Acceptance criteria

All nodes Ready.

No unresolved cluster health issue.

Capacity report confirms the Turbonomic footprint and headroom.

Required pod/IP capacity is available.

A network policy engine is enabled.

### Evidence to retain

Capacity worksheet

Node health output

Platform owner approval

## Step 5: Confirm Azure-Side Prerequisites

| Field | Details |
| --- | --- |
| Owner | Azure Platform Team / AKS Platform Team |
| Dependencies | Step 4 |
| Objective | Confirm that the Azure items the Helm deployment depends on are in place. These are provided by the platform teams under their own standard change; this workflow does not create Azure resources. |

### Execution activities

Dedicated user node pool turbonp exists, with label workload=turbonomic-nonprod and taint workload=turbonomic-nonprod:NoSchedule. If it does not, the AKS Platform team adds it with the Azure CLI command shown below.

The ACR is attached to the cluster (AcrPull for the kubelet identity), and the pipeline identity has AcrPush.

The AKS cluster identity has Network Contributor on the internal load balancer subnet. AKS needs this to create the internal load balancer in a custom subnet.

The private IP <ILB_PRIVATE_IP> is reserved, and the DNS A record for <TURBONOMIC_NP_FQDN> points to it. It will not answer until Step 11.

Key Vault <KEY_VAULT_NAME> holds the secret names for the main key, TLS certificate and integration credentials, and the pipeline identity can read them.

The pipeline identity has Kubernetes admin rights on the turbonomic-nonprod namespace only.

The self-hosted pipeline agent can reach the AKS API server.

### Command-level validation

# Node pool (AKS Platform team, only if it does not already exist)

az aks nodepool add -g <AKS_RESOURCE_GROUP> --cluster-name <AKS_CLUSTER> -n turbonp --mode User --node-vm-size <NODE_VM_SIZE> --node-count <NODE_COUNT> --vnet-subnet-id <NODE_SUBNET_ID> --labels workload=turbonomic-nonprod --node-taints workload=turbonomic-nonprod:NoSchedule

az aks nodepool show -g <AKS_RESOURCE_GROUP> --cluster-name <AKS_CLUSTER> -n turbonp --query "{mode:mode, count:count, vmSize:vmSize, labels:nodeLabels, taints:nodeTaints}" -o jsonc

kubectl get nodes -l workload=turbonomic-nonprod -o wide

# Registry access

az aks check-acr -g <AKS_RESOURCE_GROUP> -n <AKS_CLUSTER> --acr <ACR_NAME>.azurecr.io

# Load balancer subnet permission for the cluster identity

AKS_PRINCIPAL=$(az aks show -g <AKS_RESOURCE_GROUP> -n <AKS_CLUSTER> --query identity.principalId -o tsv)

az role assignment list --assignee $AKS_PRINCIPAL --scope <ILB_SUBNET_ID> -o table

# DNS record and Key Vault secret names

az network private-dns record-set a show -g <DNS_RESOURCE_GROUP> -z <PRIVATE_DNS_ZONE> -n <RECORD_NAME> -o table

az keyvault secret list --vault-name <KEY_VAULT_NAME> --query "[].name" -o tsv

# Namespace-scoped Kubernetes permission for the pipeline identity (clusters using Azure RBAC for Kubernetes)

AKS_ID=$(az aks show -g <AKS_RESOURCE_GROUP> -n <AKS_CLUSTER> --query id -o tsv)

az role assignment create --assignee <PIPELINE_IDENTITY_OBJECT_ID> --role "Azure Kubernetes Service RBAC Admin" --scope $AKS_ID/namespaces/turbonomic-nonprod

### Acceptance criteria

Nodes in turbonp are Ready and carry the taint.

check-acr succeeds.

Subnet permission, DNS record and Key Vault secret names confirmed.

Pipeline identity has namespace-scoped rights only.

### Evidence to retain

Prerequisite checklist with change references

Command output

## Step 6: Create the Namespace and Apply Platform Guardrails

| Field | Details |
| --- | --- |
| Owner | AKS Platform Team |
| Dependencies | Steps 2, 4, 5 |
| Objective | Create an isolated landing area before any Turbonomic component exists. |

### Execution activities

Create the namespace turbonomic-nonprod.

Add the ownership and environment labels listed below.

Run a server-side dry-run of the Pod Security label to see any warnings, then apply the Pod Security labels.

Install the turbo-np-platform release with the platform identity. This release contains cluster-scoped objects (StorageClass, operator ClusterRole and ClusterRoleBinding), so it cannot run under the namespace-scoped pipeline identity.

Confirm the quota, limit range, network policies, team role bindings, StorageClass, and the renamed operator ClusterRole and ClusterRoleBinding.

Confirm the deployment identity has the necessary namespace rights and no rights in other namespaces.

### Namespace labels

| Label | Value | Purpose |
| --- | --- | --- |
| app.kubernetes.io/part-of | turbonomic | Identifies the application |
| environment | nonprod | Workload classification |
| owner | <OWNER_TEAM> | Support ownership |
| cost-centre | <COST_CENTRE> | Cost allocation |
| pod-security.kubernetes.io/enforce | baseline | Blocks privileged pods |
| pod-security.kubernetes.io/warn and /audit | restricted | Reports anything that would fail the stricter level |

### Command-level validation

kubectl create namespace turbonomic-nonprod

kubectl label namespace turbonomic-nonprod app.kubernetes.io/part-of=turbonomic environment=nonprod owner=<OWNER_TEAM> cost-centre=<COST_CENTRE>

kubectl label --dry-run=server --overwrite namespace turbonomic-nonprod pod-security.kubernetes.io/enforce=baseline

kubectl label --overwrite namespace turbonomic-nonprod pod-security.kubernetes.io/enforce=baseline pod-security.kubernetes.io/warn=restricted pod-security.kubernetes.io/audit=restricted

helm upgrade --install turbo-np-platform oci://<ACR_NAME>.azurecr.io/helm/turbonomic-platform --version 1.0.0 -n turbonomic-nonprod -f env/nonprod/platform-values.yaml --atomic --wait --timeout 5m

helm status turbo-np-platform -n turbonomic-nonprod

kubectl get ns turbonomic-nonprod --show-labels

kubectl get resourcequota,limitrange,networkpolicy,rolebinding -n turbonomic-nonprod -o wide

kubectl get storageclass turbo-np-managed-csi-retain

kubectl get clusterrole,clusterrolebinding t8c-operator-turbonomic-nonprod

kubectl auth can-i --list -n turbonomic-nonprod --as=<DEPLOYMENT_IDENTITY>

kubectl auth can-i create pods -n <ANY_PRODUCTION_NAMESPACE> --as=<DEPLOYMENT_IDENTITY>   # expected: no

### Acceptance criteria

Namespace exists with approved labels.

Default-deny policies exist before any application pod.

Quotas and limits are active.

The deployment identity has namespace rights only.

ClusterRoleBinding subject is t8c-operator in turbonomic-nonprod.

### Evidence to retain

Namespace and Helm status output

RBAC review

Quota and policy output

### Step-level rollback / recovery

Before Step 10 only: helm uninstall turbo-np-platform -n <namespace>, then delete the namespace. After Step 10 use Section 10.

## Step 7: Prepare and Pin the Turbonomic Container Images

| Field | Details |
| --- | --- |
| Owner | Platform / Security / Application Engineering |
| Dependencies | Steps 1, 5, 6 |
| Objective | Make every image the deployment needs available from an approved registry at a recorded tag and digest. |

### Execution activities

Take the component image list for <TURBO_VERSION> from IBM (container image repository topic for the release) and save it as scripts/images-<TURBO_VERSION>.txt, one component name per line.

Option B (recommended): import the operator image and every component image into ACR. Do not use --force, so an existing tag is never overwritten.

Record the digest of every imported image. Put the operator digest in operator-values.yaml.

Let Defender for Containers scan the images and review findings with Security before Step 10.

Confirm the cluster can pull from ACR with az aks check-acr.

Option A only: confirm the firewall allows icr.io from the node subnet, and run a short-lived pull test in the namespace.

Set repository values: operator image to <ACR_NAME>.azurecr.io/turbonomic/t8c-operator and xl.global.repository to <ACR_NAME>.azurecr.io/turbonomic. IBM documents this pattern for private repositories.

### Command-level validation

TAG=<TURBO_VERSION>          # e.g. 8.21.2

OP_TAG=<OPERATOR_VERSION>    # e.g. 42.116

ACR=<ACR_NAME>

az acr import --name $ACR --source icr.io/cpopen/t8c-operator:$OP_TAG --image turbonomic/t8c-operator:$OP_TAG

while read -r img; do

[ -z "$img" ] && continue

az acr import --name $ACR --source icr.io/cpopen/turbonomic/$img:$TAG --image turbonomic/$img:$TAG

done < scripts/images-$TAG.txt

az acr repository show --name $ACR --image turbonomic/t8c-operator:$OP_TAG --query digest -o tsv

az acr repository list --name $ACR -o tsv | grep '^turbonomic/'

az aks check-acr -g <AKS_RESOURCE_GROUP> -n <AKS_CLUSTER> --acr $ACR.azurecr.io

### Acceptance criteria

Every image in the list exists in ACR at the pinned tag.

Operator digest recorded in values.

No unaccepted critical vulnerability.

The cluster can resolve and pull the images.

### Evidence to retain

Image list and digests

Scan report

check-acr output

## Step 8: Prepare Storage, Main Encryption Key, TLS and Load Balancer Inputs

| Field | Details |
| --- | --- |
| Owner | Platform / Security / Network Teams |
| Dependencies | Steps 5-7 |
| Objective | Prepare installation dependencies without exposing credentials. |

### Execution activities

Confirm the StorageClass from Step 6 meets IBM's AKS rules: WaitForFirstConsumer, Retain, volume expansion true, Premium_LRS (recommended for database volumes).

Create the Turbonomic main key before the Xl resource exists. IBM warns that without it the auth pod fails with encryption key errors and the deployment stays in CrashLoopBackOff.

Generate the 32-byte key once, on a controlled admin host or pipeline agent, and store its base64 form in Key Vault. This replaces IBM's example of a local backup file. Without the key, Turbonomic cannot be restored.

Create master-key-secret in the namespace from the Key Vault copy, then delete the local file.

Never regenerate the key after the instance has started.

Issue the TLS certificate with SAN <TURBONOMIC_NP_FQDN> and store it in Key Vault.

Confirm the reserved private IP <ILB_PRIVATE_IP> is free in <ILB_SUBNET_NAME>, and that Azure Policy allows an internal load balancer there.

### Command-level validation

kubectl get storageclass turbo-np-managed-csi-retain -o jsonpath='{.reclaimPolicy} {.volumeBindingMode} {.allowVolumeExpansion}{"\n"}'

# One-time key generation (IBM procedure, with Key Vault as the backup)

openssl rand 32 > /tmp/primary_key_256.out

wc -c < /tmp/primary_key_256.out                       # must print 32

az keyvault secret set --vault-name <KEY_VAULT_NAME> -n turbo-np-master-key-b64 --value "$(base64 -w0 /tmp/primary_key_256.out)" -o none

shred -u /tmp/primary_key_256.out

# Create the Kubernetes secret from Key Vault (pipeline step)

az keyvault secret show --vault-name <KEY_VAULT_NAME> -n turbo-np-master-key-b64 --query value -o tsv | base64 -d > /tmp/primary_key_256.out

kubectl create secret generic master-key-secret -n turbonomic-nonprod --from-file=primary_key_256.out=/tmp/primary_key_256.out

shred -u /tmp/primary_key_256.out

kubectl get secret master-key-secret -n turbonomic-nonprod           # TYPE Opaque, DATA 1

az network vnet subnet show --ids <ILB_SUBNET_ID> --query addressPrefix -o tsv

### Acceptance criteria

StorageClass matches IBM requirements.

master-key-secret exists in the namespace, and its source is in Key Vault.

No key file remains on any host.

Certificate issued; private IP and FQDN reserved.

### Evidence to retain

Storage approval

Secret inventory without values

Certificate details

IP/DNS reservation

## Step 9: Install the Turbonomic Custom Resource Definition

| Field | Details |
| --- | --- |
| Owner | AKS Platform Team (cluster-admin through PIM) |
| Dependencies | Steps 1, 2, 6 |
| Objective | Register the Xl kind in the cluster once, from the reviewed IBM file. |

### Execution activities

Confirm no Xl CRD or Xl resource already exists in the cluster.

Apply the CRD from the pinned copy in Git. IBM's documented command uses the GitHub main-branch URL; the pinned copy keeps the input under change control.

Wait until the CRD reports Established.

Remove the temporary cluster-admin elevation.

### Command-level validation

kubectl get crd | grep -i -E 'xl|charts.helm.k8s.io' || true

kubectl get xl -A 2>/dev/null || true

kubectl create -f vendor/ibm/t8c-operator/<IBM_TAG>/crds/charts_v1_xl_crd.yaml

kubectl wait --for=condition=Established crd/xls.charts.helm.k8s.io --timeout=120s

kubectl get crd xls.charts.helm.k8s.io -o jsonpath='{.spec.versions[*].name}{"\n"}'

### Acceptance criteria

CRD is Established.

No other cluster object was created or changed.

Elevated access removed.

### Evidence to retain

CRD apply output and checksum

PIM activation record

### Step-level rollback / recovery

Delete the CRD only if no Xl resource exists anywhere in the cluster, and only with approval. Deleting the CRD deletes every Xl resource.

## Step 10: Deploy the IBM Turbonomic Operator with Helm

| Field | Details |
| --- | --- |
| Owner | Application Engineering / AKS Platform |
| Dependencies | Steps 6-9 |
| Objective | Run the exact IBM-supported operator version, confined to the Turbonomic namespace. |

### Execution activities

Confirm that the ClusterRoleBinding from Step 6 points to ServiceAccount t8c-operator in turbonomic-nonprod.

Run the pipeline stage for turbo-np-operator. It installs the IBM ServiceAccount, Role, RoleBinding, operator Deployment and the IBM operator egress NetworkPolicy.

Wait for the operator pod to show STATUS Running and READY 1/1 (IBM success condition).

Read the operator log and confirm there are no errors.

Confirm WATCH_NAMESPACE resolves to the operator's own namespace, so it cannot act on Xl resources elsewhere.

Confirm the operator pod runs on a turbonp node and uses the pinned image digest.

### Command-level validation

helm upgrade --install turbo-np-operator oci://<ACR_NAME>.azurecr.io/helm/turbonomic-operator --version 1.0.0 -n turbonomic-nonprod -f env/nonprod/operator-values.yaml --atomic --wait --timeout 10m

helm status turbo-np-operator -n turbonomic-nonprod

kubectl rollout status deployment/t8c-operator -n turbonomic-nonprod --timeout=10m

kubectl get pods -n turbonomic-nonprod -l name=t8c-operator -o wide

kubectl logs deployment/t8c-operator -n turbonomic-nonprod --tail=200

kubectl get deployment t8c-operator -n turbonomic-nonprod -o jsonpath='{.spec.template.spec.containers[0].image}{"\n"}{.spec.template.spec.containers[0].env}{"\n"}'

kubectl auth can-i --list -n turbonomic-nonprod --as=system:serviceaccount:turbonomic-nonprod:t8c-operator | head -40

### Acceptance criteria

Helm release status is deployed.

Operator Deployment Available; pod Ready with no restart loop.

WATCH_NAMESPACE is the operator's own namespace.

Image matches the pinned registry, tag and digest.

### Evidence to retain

Helm status and manifest

Operator rollout output

Operator logs

### Step-level rollback / recovery

helm rollback turbo-np-operator <REVISION> -n <namespace>, or helm uninstall turbo-np-operator if Step 11 has not started.

## Step 11: Deploy the Turbonomic Instance (Xl Custom Resource) with Helm

| Field | Details |
| --- | --- |
| Owner | Application Engineering |
| Dependencies | Step 10 |
| Objective | Ask the IBM Operator to deploy the Turbonomic microservices at the pinned version, privately, on the approved storage. |

### Execution activities

Confirm master-key-secret exists (Step 8). IBM requires it before the CR when enableExternalSecrets is true.

Review instance-values.yaml once more. The tag must equal <TURBO_VERSION>. The repository must be the approved registry and the storage class turbo-np-managed-csi-retain. The internal load balancer annotations must be present. externalDbIP must be absent. kubeturbo must be false.

Run the pipeline stage for turbo-np-instance. Helm creates only the Xl resource; it is not told to wait, because the operator builds the platform afterwards.

Watch the pods. IBM states the deployment takes 5 to 20 minutes. Every pod must reach Running with all containers Ready (1/1, 2/2 and so on).

Confirm all PVCs are Bound on the turbo-np StorageClass.

Confirm the nginx Service has the reserved private IP and no public IP.

Confirm every pod uses the approved registry and the pinned tag.

Do not create or modify individual application Pods.

Node placement note. If IBM confirms that the 8.21 Xl CR does not pass nodeSelector and tolerations to component pods, the taint on turbonp leaves those pods Pending. Two options are then available, and the choice is made in Step 1. The first is to remove the taint and rely on the node label, quota and anti-affinity of other workloads. The second is to use the admission mutation the cluster already runs (Azure Policy/Gatekeeper or Kyverno) to add the toleration and node selector for this namespace only.

### Command-level validation

kubectl get secret master-key-secret -n turbonomic-nonprod

helm upgrade --install turbo-np-instance oci://<ACR_NAME>.azurecr.io/helm/turbonomic-instance --version 1.0.0 -n turbonomic-nonprod -f env/nonprod/instance-values.yaml --timeout 5m

kubectl get xl xl-release -n turbonomic-nonprod

kubectl get pods -n turbonomic-nonprod -w

kubectl get deploy,statefulset,service,pvc,pods -n turbonomic-nonprod -o wide

kubectl get pvc -n turbonomic-nonprod -o custom-columns=NAME:.metadata.name,STATUS:.status.phase,CLASS:.spec.storageClassName,SIZE:.status.capacity.storage

kubectl get services -n turbonomic-nonprod | grep -E "nginx|NAME"

kubectl get pods -n turbonomic-nonprod -o jsonpath='{range .items[*]}{range .spec.containers[*]}{.image}{"\n"}{end}{end}' | sort -u

kubectl get pods -n turbonomic-nonprod -o custom-columns=POD:.metadata.name,NODE:.spec.nodeName

kubectl get events -n turbonomic-nonprod --sort-by=.lastTimestamp | tail -50

kubectl logs deployment/t8c-operator -n turbonomic-nonprod --tail=300

### Acceptance criteria

Operator reconciliation completes without persistent errors.

All required PVCs are Bound.

All expected workloads reach Ready/Available, including api, auth, clustermgr and action-orchestrator.

No Pod is Pending because of quota, placement, capacity or unbound storage.

The nginx Service EXTERNAL-IP is <ILB_PRIVATE_IP>, a private address.

All images come from the approved registry at <TURBO_VERSION>.

### Evidence to retain

Rendered Xl resource (no secrets)

Resource and image inventory

Events and operator logs

### Step-level rollback / recovery

If reconciliation fails before any configuration is entered, follow the removal sequence in Section 10.3 and redeploy.

## Step 12: Configure Private Access: Load Balancer, DNS and TLS

| Field | Details |
| --- | --- |
| Owner | Network / Platform / Application Teams |
| Dependencies | Step 11 |
| Objective | Provide private, encrypted access to the Turbonomic UI/API. |

### Execution activities

Confirm Azure created an internal load balancer frontend (kubernetes-internal) in the node resource group with the reserved IP.

Confirm the DNS record from Step 5 resolves to that IP from corporate and VPN networks.

Load the enterprise certificate into Turbonomic nginx using IBM's documented certificate procedure for 8.21. Take the certificate from Key Vault in the pipeline; do not copy it by hand.

Test HTTPS from an approved client and check the certificate chain, SAN and validity.

Confirm the address is not reachable from the internet.

### Command-level validation

kubectl get svc nginx -n turbonomic-nonprod -o jsonpath='{.status.loadBalancer.ingress[0].ip}{"\n"}'

az network lb list -g <NODE_RESOURCE_GROUP> --query "[].{name:name, frontends:frontendIPConfigurations[].privateIPAddress}" -o jsonc

nslookup <TURBONOMIC_NP_FQDN>

curl -kIv https://<TURBONOMIC_NP_FQDN>/

openssl s_client -connect <TURBONOMIC_NP_FQDN>:443 -servername <TURBONOMIC_NP_FQDN> </dev/null 2>/dev/null | openssl x509 -noout -subject -issuer -dates -ext subjectAltName

### Acceptance criteria

Internal users/VPN can establish an HTTPS connection.

Certificate chain, SAN and validity are correct.

No public exposure exists.

Load balancer health probe reports healthy.

### Evidence to retain

Load balancer and DNS output

TLS output

UI screenshot

### Step-level rollback / recovery

Remove the DNS record; keep the application internal for investigation.

## Step 13: Activate Licence and Configure Authentication and Authorization

| Field | Details |
| --- | --- |
| Owner | Security / Application Owner |
| Dependencies | Step 12 |
| Objective | Establish licensed, least-privilege access to the new instance. |

### Execution activities

Log in immediately after Step 12 as "administrator" and set the password. IBM requires upper and lower case letters, a number and a symbol. Store it in Key Vault as break-glass.

Import the Turbonomic licence through License management, and confirm with IBM/Procurement that the entitlement covers this instance.

Configure LDAP/AD authentication, which the playbook records as the current UI login method. The playbook's identity note is truncated ("Octa is no lo..."). Confirm with Security whether SAML/Entra SSO is now required instead.

Map administrator, operator and read-only roles to approved AD groups.

Create a named administrator account. IBM allows the default administrator to be removed, provided at least one administrator account always exists.

Remove temporary installation access; the pipeline identity keeps namespace scope only.

IBM License Service is optional. It is a cluster-level component, so install it only with separate platform approval.

### Command-level validation

kubectl auth can-i --list -n turbonomic-nonprod --as=<AKS_OPERATOR_IDENTITY>

kubectl get role,rolebinding,serviceaccount -n turbonomic-nonprod -o wide

kubectl get secret -n turbonomic-nonprod -o custom-columns=NAME:.metadata.name,TYPE:.type,AGE:.metadata.creationTimestamp

### Acceptance criteria

Licence is active.

Approved user groups sign in with correct Turbonomic roles.

Unauthorized users are denied.

Temporary elevated rights are removed.

No secret values appear in logs, Helm history or the repository.

### Evidence to retain

Licence screenshot

Role test results

Access review

## Step 14: Recreate Targets and Integrations

| Field | Details |
| --- | --- |
| Owner | Turbonomic Application Team |
| Dependencies | Step 13 |
| Objective | Rebuild the required configuration in the clean instance. |

### Execution activities

Create the Azure targets (management group or subscription) with the approved app registration and IBM-documented permissions.

Create the vCenter target(s) while vCenter remains operational. The playbook rates this integration High.

Configure ServiceNow and SMTP only after the matching egress rules in Section 6.4 are active.

Recreate policies, groups, schedules and dashboards from the approved configuration inventory.

Keep both the legacy appliance and the new instance in recommend-only mode. The playbook records that nothing is automated today, and two instances must never execute actions on the same targets.

Do not add the production AKS cluster as a target, and do not enable Kubeturbo.

### Command-level validation

kubectl run net-test -n turbonomic-nonprod --rm -it --restart=Never --image=<ACR_NAME>.azurecr.io/tools/netshoot:<TAG> -- sh

#   inside the test pod:

#   nslookup <VCENTER_FQDN>

#   curl -vk --connect-timeout 10 https://<VCENTER_FQDN>/sdk

#   curl -vk --connect-timeout 10 https://<SERVICENOW_FQDN>/

#   nc -vz <LDAP_SERVER> 636

kubectl get networkpolicy -n turbonomic-nonprod

### Acceptance criteria

Every target validates successfully.

Expected entity counts are within agreed variance from the source.

No automated action is enabled on either instance.

Integration credentials work and are stored securely.

### Evidence to retain

Target validation screenshots

Entity-count reconciliation

Integration test results

## Step 15: Configure Monitoring, Alerts, Backup and Operational Controls

| Field | Details |
| --- | --- |
| Owner | AKS Platform / Operations |
| Dependencies | Steps 11-14 |
| Objective | Make the workload supportable before cutover. |

### Execution activities

Confirm Container Insights or the approved logging captures namespace events and container logs.

Create alerts for unavailable workloads, crash loops, high CPU/memory, quota usage above 80 percent, PVC capacity, load balancer health, certificate expiry and discovery failure.

Decide whether Splunk keeps monitoring Turbonomic (it monitors the appliance today, per the playbook). If yes, set up forwarding of namespace logs through the platform's approved collector.

Define backup and restore scope: Helm values and charts in Git; master key in Key Vault; persistent volumes through Azure Backup for AKS or disk snapshots. Run one restore test. The playbook notes the live appliance has no backup policy today, so this is a new control.

Document restart, scale, log collection, certificate renewal and upgrade procedures (Section 8).

Agree IBM support case ownership.

### Command-level validation

kubectl get pods -n turbonomic-nonprod -o custom-columns=NAME:.metadata.name,READY:.status.containerStatuses[*].ready,RESTARTS:.status.containerStatuses[*].restartCount,STATUS:.status.phase

kubectl top pods -n turbonomic-nonprod --containers

kubectl describe resourcequota turbonomic-quota -n turbonomic-nonprod

kubectl get pvc -n turbonomic-nonprod -o wide

kubectl get events -n turbonomic-nonprod --sort-by=.lastTimestamp | tail -100

### Acceptance criteria

Dashboards and alerts show current data.

Operations can retrieve logs without cluster-admin.

Backup and restore tested; responsibilities documented.

Runbook and escalation contacts are approved.

### Evidence to retain

Alert test evidence

Restore test record

Operations runbook

## Step 16: Execute End-to-End Validation and UAT

| Field | Details |
| --- | --- |
| Owner | Application Owner / Test Team / AKS Platform |
| Dependencies | Step 15 |
| Objective | Prove functionality, security, isolation and resilience before cutover. |

### Execution activities

Execute the test matrix in Section 9, including the isolation tests T18 to T24.

Reconcile source and target entity counts.

Observe resource usage during discovery cycles and compare it with quota and node capacity.

Test one Pod restart and, with platform approval, one controlled drain of a turbonp node.

Rehearse a Helm rollback of the operator release (T23).

Record defects and retest evidence; obtain formal UAT and readiness sign-off.

### Command-level validation

kubectl get pods -n turbonomic-nonprod -o wide

kubectl top pods -n turbonomic-nonprod --containers

kubectl delete pod <NON_CRITICAL_TEST_POD> -n turbonomic-nonprod

kubectl wait --for=condition=Ready pod --all -n turbonomic-nonprod --timeout=15m

helm list -n turbonomic-nonprod

kubectl get events -n turbonomic-nonprod --sort-by=.lastTimestamp

### Acceptance criteria

All critical tests pass.

No open Sev-1 or Sev-2 defect.

User and application owner sign-off recorded.

Observed resource usage remains within quota and headroom.

No measurable impact on other namespaces.

### Evidence to retain

Completed test matrix

Resource baseline

UAT sign-off

## Step 17: Execute Cutover to the AKS Instance

| Field | Details |
| --- | --- |
| Owner | Change Manager / Application Owner |
| Dependencies | Step 16 and the Step 2 decision on operational use |
| Objective | Move operational use from the appliance to the AKS instance without losing rollback. |

### Execution activities

Open the approved change bridge and confirm all owners.

Freeze configuration changes on the legacy appliance.

Capture final configuration, target inventory and screenshots from the appliance.

Confirm the AKS node pool, operator, workloads, storage, load balancer, DNS and integrations are healthy, and that all three Helm releases show deployed.

Activate the approved user-facing URL or communication change.

Confirm discovery is running on the new instance, and make sure no duplicate automated actions can run.

Execute smoke tests and obtain the go/no-go decision.

Keep the legacy appliance powered and unchanged for rollback.

### Command-level validation

kubectl get nodes -l workload=turbonomic-nonprod

helm list -n turbonomic-nonprod

kubectl get deploy,statefulset,pods,svc,pvc -n turbonomic-nonprod -o wide

kubectl get events -n turbonomic-nonprod --sort-by=.lastTimestamp | tail -50

nslookup <TURBONOMIC_NP_FQDN>

curl -kIs https://<TURBONOMIC_NP_FQDN>/ | head

### Acceptance criteria

UI and login work from approved networks.

All required targets validate and discovery starts.

Entity counts and recommendations are visible.

ServiceNow/SMTP tests pass if in scope.

Application owner approves go-live.

### Evidence to retain

Timestamped cutover log

Smoke-test results

Go-live approval

### Step-level rollback / recovery

Invoke Section 10 when a rollback trigger occurs.

## Step 18: Hypercare and Stabilization

| Field | Details |
| --- | --- |
| Owner | Application / Platform Operations |
| Dependencies | Step 17 |
| Objective | Stabilize the workload and confirm operational ownership. |

### Execution activities

Monitor workload health, restarts, resource saturation, quota use, PVC use, load balancer health, target validation and discovery.

Check daily for drift between the Helm releases and the live cluster.

Review alerts and events at the agreed daily cadence.

Track defects with owner, priority and workaround.

Review actual usage against quotas and shared-cluster headroom, and adjust quota through Git if needed.

Do not enable automation or perform version upgrades during hypercare unless separately approved.

### Command-level validation

kubectl get pods -n turbonomic-nonprod -o wide

kubectl top pods -n turbonomic-nonprod --containers

kubectl get pvc -n turbonomic-nonprod

helm get manifest turbo-np-operator -n turbonomic-nonprod | kubectl diff -n turbonomic-nonprod -f -    # no output = no drift

helm get manifest turbo-np-platform -n turbonomic-nonprod | kubectl diff -n turbonomic-nonprod -f -

kubectl get events -n turbonomic-nonprod --sort-by=.lastTimestamp | tail -100

kubectl logs deployment/t8c-operator -n turbonomic-nonprod --since=24h | tail -300

### Acceptance criteria

No recurring crash loops or unplanned downtime.

Discovery completes consistently.

No drift from the Helm releases.

No adverse impact on other production-cluster workloads.

Operations accepts service ownership.

### Evidence to retain

Daily health report

Issue log

Resource trend

Handover acceptance

## Step 19: Legacy Appliance Retirement Decision

| Field | Details |
| --- | --- |
| Owner | Application Owner / Infrastructure Owner |
| Dependencies | Step 18 |
| Objective | Retire the source only after rollback and retention requirements expire. |

### Execution activities

Confirm the agreed observation/rollback period has completed.

Confirm no historical data or configuration is required from the appliance.

Export the final audit/configuration evidence required by policy.

Remove obsolete DNS, firewall, monitoring, AD groups, certificates and service accounts through separate approved changes. The playbook keeps these closure tasks in scope.

Record the ruling on the powered-off Lee's Summit VM of the same name, which is an open item in the playbook.

Power off first; delete only after final approval and the retention period.

### Acceptance criteria

Formal decommission approval is recorded.

No dependency points to the legacy appliance.

Asset, CMDB and licence records are updated.

### Evidence to retain

Decommission approval

CMDB update

Firewall/DNS cleanup evidence

# 8. Upgrade, Patch and Version Change Procedure

Use this procedure for every Turbonomic patch or upgrade after go-live. Run it in the order shown.

| Seq | Action |
| --- | --- |
| 1 | Read the IBM release notes for the new version. Record the operator version it needs and any CR changes. |
| 2 | Raise a change record. Upgrades are not performed during hypercare unless approved. |
| 3 | Back up: snapshot the persistent volumes and confirm the main key is in Key Vault. |
| 4 | Import the new images into ACR (Step 7) and record digests. Wait for the scan result. |
| 5 | If the operator version changes: update operator-values.yaml, run the pipeline for turbo-np-operator, and wait for the rollout. |
| 6 | Update xl.global.tag in instance-values.yaml and run the pipeline for turbo-np-instance. |
| 7 | Watch the operator replace the component pods; confirm every pod runs the new tag and is Ready. |
| 8 | Validate UI login, targets, discovery and integrations. Record the version shown in the UI. |
| 9 | Do not move back to an older tag with helm rollback once the new version has started; the database may already have been migrated. Restore from the step 3 backup instead, and confirm the approach with IBM before the change. |

helm upgrade turbo-np-operator oci://<ACR_NAME>.azurecr.io/helm/turbonomic-operator --version <CHART_VERSION> -n turbonomic-nonprod -f env/nonprod/operator-values.yaml --atomic --wait --timeout 10m

kubectl rollout status deployment/t8c-operator -n turbonomic-nonprod --timeout=10m

helm upgrade turbo-np-instance oci://<ACR_NAME>.azurecr.io/helm/turbonomic-instance --version <CHART_VERSION> -n turbonomic-nonprod -f env/nonprod/instance-values.yaml

kubectl get pods -n turbonomic-nonprod -o jsonpath='{range .items[*]}{range .spec.containers[*]}{.image}{"\n"}{end}{end}' | sort -u

# 9. End-to-End Test Matrix

| ID | Category | Execution | Acceptance criteria |
| --- | --- | --- | --- |
| T01 | Cluster health | Validate nodes, system pods and events. | Nodes Ready; no unresolved platform failure. |
| T02 | Namespace isolation | Attempt access from approved and unapproved identities/namespaces. | Only approved identities and flows succeed. |
| T03 | Operator health | Review deployment readiness and logs. | Operator Available; no continuous reconciliation error. |
| T04 | Application health | Inspect deployments/statefulsets/Pods/PVCs. | All required workloads Ready; PVCs Bound. |
| T05 | UI/TLS/DNS | Resolve FQDN and browse from corporate/VPN endpoint. | Correct private endpoint and trusted TLS chain. |
| T06 | Authentication/RBAC | Login as admin, operator, reader and unauthorized user. | Each receives only assigned access. |
| T07 | Azure targets | Validate subscriptions/management groups and resource discovery. | Approved scope discovered; counts reconciled. |
| T08 | vCenter target | Validate vCenter connectivity and entity discovery. | Expected clusters/hosts/VMs/datastores appear. |
| T09 | ServiceNow | Run approved test workflow. | Test item/ticket is created or updated. |
| T10 | SMTP | Send test notification. | Message received by approved recipient. |
| T11 | Network policy | Test denied and approved flows in both directions. | Default deny works; explicit allows succeed. |
| T12 | Pod recovery | Delete approved non-critical Pod. | Controller recreates Pod and service recovers. |
| T13 | Node maintenance | Cordon/drain one turbonp node with platform approval. | Workload reschedules within agreed objective. |
| T14 | Resource usage | Observe discovery cycle CPU/memory/storage. | Usage remains within limits and cluster headroom. |
| T15 | Monitoring/alert | Generate an approved test condition. | Alert reaches support channel with runbook link. |
| T16 | Rollback rehearsal | Reverse test DNS/access without deleting target. | Legacy access restoration steps are proven. |
| T17 | Helm release integrity | helm list, helm status and kubectl diff against each release. | All releases deployed; no drift. |
| T18 | Quota enforcement | Create a test pod that exceeds remaining quota. | Request is rejected by ResourceQuota. |
| T19 | Cross-namespace traffic | From a pod in another namespace, connect to a Turbonomic pod IP; from Turbonomic, connect to a pod in another namespace. | Both connections are blocked. |
| T20 | Production workload safety | Check that no Kubeturbo pod exists and no AKS cluster target is configured. | Turbonomic cannot see or act on cluster workloads. |
| T21 | Image provenance | List all images in the namespace. | Every image comes from the approved registry at the pinned tag. |
| T22 | No public exposure | Inspect the nginx Service and Azure load balancers; test from outside. | Private IP only; no public frontend. |
| T23 | Helm rollback | Roll back turbo-np-operator by one revision in a test window, then roll forward. | Operator recovers; platform unaffected. |
| T24 | Secret hygiene | helm get values for each release; search repo history. | No secret values in Helm history or Git. |

# 10. Rollback Protocol

## 10.1 Rollback Triggers

Turbonomic UI or login unavailable beyond the agreed tolerance.

Critical targets cannot validate or discovery does not start.

AKS resource saturation or impact on other production workloads.

Persistent Operator/application crash loops.

Security control failure, unintended exposure or unauthorized access.

Data/configuration defect that blocks agreed operational use.

## 10.2 Rollback Steps

| Seq | Action |
| --- | --- |
| 1 | Declare rollback and record decision/time; stop further change. |
| 2 | Disable new user access by reversing the DNS/URL change as approved. |
| 3 | Disable or pause target/action processing on the AKS instance to prevent duplicates. |
| 4 | Restore the legacy appliance URL/DNS/access path. |
| 5 | Validate legacy login, targets, dashboards and integrations. |
| 6 | Notify stakeholders and update the change record. |
| 7 | Keep the AKS namespace and Helm releases intact for investigation unless Security requires isolation. |
| 8 | Collect Operator/application logs, Kubernetes events and Helm history. |
| 9 | Open an IBM support case if product deployment behaviour is involved. |
| 10 | Schedule a corrective change; do not destroy rollback evidence. |

### Rollback validation commands

helm history turbo-np-operator -n turbonomic-nonprod

helm history turbo-np-instance -n turbonomic-nonprod

helm rollback turbo-np-operator <REVISION> -n turbonomic-nonprod --wait     # operator or guardrail defects only

kubectl get all,pvc -n turbonomic-nonprod

nslookup <LEGACY_TURBONOMIC_FQDN>

curl -kIs https://<LEGACY_TURBONOMIC_FQDN>/ | head

kubectl logs deployment/t8c-operator -n turbonomic-nonprod --since=2h > operator-rollback.log

## 10.3 Complete Removal of the Non-Production Instance

Use this sequence only with an approved change, for example if the instance must be rebuilt or the shared-cluster exception is withdrawn. Run it in this order so that nothing outside the namespace is affected.

| Seq | Action | Command |
| --- | --- | --- |
| 1 | Remove the Turbonomic platform by deleting the Xl resource. The operator removes its components. | kubectl delete xl xl-release -n turbonomic-nonprod |
| 2 | Remove the instance release record. The Xl resource has the keep annotation, so step 1 is needed first. | helm uninstall turbo-np-instance -n turbonomic-nonprod |
| 3 | Remove the operator. | helm uninstall turbo-np-operator -n turbonomic-nonprod |
| 4 | Delete PVCs, then delete the retained PVs and Azure disks after approval. | kubectl delete pvc --all -n turbonomic-nonprod |
| 5 | Remove guardrails, StorageClass and the renamed ClusterRole/Binding. | helm uninstall turbo-np-platform -n turbonomic-nonprod |
| 6 | Delete the namespace. | kubectl delete namespace turbonomic-nonprod |
| 7 | Delete the CRD only if no Xl exists anywhere in the cluster. | kubectl get xl -A ; kubectl delete crd xls.charts.helm.k8s.io |
| 8 | Remove the turbonp node pool and Key Vault secrets by separate change. | az aks nodepool delete -g <AKS_RESOURCE_GROUP> --cluster-name <AKS_CLUSTER> -n turbonp |

# 11. RACI Matrix

| Activity | App Owner | AKS Platform | Cloud/DevOps | Security/Network | IBM Support | Change Manager |
| --- | --- | --- | --- | --- | --- | --- |
| Version compatibility | A/R | C | C | I | C | I |
| Shared-cluster approval | C | A/R | C | C | I | I |
| Azure prerequisites (node pool, ACR, DNS, Key Vault) | I | A/R | R | C | I | I |
| Helm chart development | A | C | R | C | C | I |
| Image mirroring and scanning | I | C | R | A | C | I |
| Namespace guardrails (turbo-np-platform) | I | A/R | R | C | I | I |
| CRD and cluster-scoped objects | I | A/R | C | C | C | I |
| Operator/instance deploy (Helm) | A/R | C | R | I | C | I |
| Targets/integrations | A/R | I | C | C | C | I |
| Testing/UAT | A/R | R | C | C | C | I |
| Cutover | A/R | R | R | R | C | A |
| Rollback | A/R | R | R | R | C | A |
| Upgrades and patches | A | C | R | C | C | I |
| Operations handover | A | R | C | C | C | I |

Legend: R = Responsible | A = Accountable | C = Consulted | I = Informed

# 12. Readiness and Sign-Off Checklist

☐ IBM version compatibility and Helm-wrapped installation confirmed

☐ Shared production-cluster exception approved, including cluster-scoped objects

☐ AKS capacity, IP/pod capacity and network policy engine confirmed

☐ Azure prerequisites confirmed: node pool, ACR access, load balancer subnet, DNS, Key Vault

☐ Namespace guardrails (quota, limits, network policies, RBAC) validated

☐ Images mirrored, pinned and scanned

☐ Main encryption key created and backed up in Key Vault

☐ CRD, Operator and Turbonomic instance healthy

☐ Storage, internal load balancer, DNS and TLS validated

☐ Licence, authentication and roles validated

☐ Targets and integrations validated

☐ Security, isolation and UAT tests passed

☐ Rollback rehearsed/validated

☐ CAB go-live approval recorded

☐ Operations handover accepted

| Approval | Name | Decision | Date/Signature |
| --- | --- | --- | --- |
| Application Owner |  |  |  |
| AKS Platform Owner |  |  |  |
| Security/Network |  |  |  |
| Cloud Architect |  |  |  |
| Change Manager |  |  |  |
| Operations Owner |  |  |  |

# 13. Indicative Execution Schedule

The schedule assumes the AKS cluster is healthy, IBM confirmations and artifacts are available, required approvals are obtained, and no history/database migration is required. Track approval lead time separately from hands-on execution.

Programme dates from the Turbonomic Migration Playbook v0.4: change record by 12/18/26, CAB on 01/06/27, cutover on 01/07/27, and the appliance renewal due on 02/28/27. The SOW bars production cutovers in November 2026.

| Workstream | Indicative duration | Scope |
| --- | --- | --- |
| Readiness and approvals | 2 working days | IBM confirmations, shared-cluster exception, capacity, network, access and change approvals |
| Repository and Helm charts | 2 working days | Vendor files, three Helm charts and pipeline; Azure prerequisites confirmed |
| Namespace, images and cluster controls | 1 working day | Guardrail release, image mirroring and scanning, storage class, main key, CRD |
| Operator and Turbonomic deployment | 1 working day | Operator release, instance release, reconciliation and initial health validation |
| Integrations and configuration | 1-2 working days | Licence, LDAP/AD, Azure, vCenter, ServiceNow, SMTP, policies and dashboards |
| Testing and UAT | 2-3 working days | Functional, security, isolation, resilience, capacity, monitoring and business validation |
| Cutover | One approved change window | Runbook in Step 17 and Section 10; target 2-4 hours including observation |
| Hypercare | 5 working days | Daily application and shared-cluster health review |

# 14. Environment Values to Complete Before Execution

AKS subscription, resource group, cluster name and node resource group

AKS Kubernetes version, network policy engine and private-cluster setting

Namespace name, labels and Pod Security level

<TURBO_VERSION>, <OPERATOR_VERSION> and <IBM_TAG>

Image source, <ACR_NAME>, component image list and digests

Node pool VM size, node count, zones and subnet

CPU/memory/storage quota values

StorageClass name and capacities

<ILB_SUBNET_NAME>, <ILB_PRIVATE_IP>, <TURBONOMIC_NP_FQDN> and TLS certificate reference

<KEY_VAULT_NAME> and secret names

Pipeline identity and Azure target identity/scope

vCenter FQDN(s), account and role

ServiceNow, SMTP, LDAP/AD and Splunk endpoints

Firewall/proxy rules and outbound NAT identity

Monitoring workspace and alert recipients

Change/CAB number, cutover date and rollback authority

Application, platform, security, network and IBM escalation contacts

# 15. References

| Reference | Location |
| --- | --- |
| IBM: Installing Turbonomic on an AKS cluster (8.21.0) | https://www.ibm.com/docs/en/tarm/8.21.0?topic=turbonomic-installing-aks-cluster |
| IBM: Azure AKS requirements for Turbonomic (8.21.0) | https://www.ibm.com/docs/en/tarm/8.21.0?topic=cluster-azure-aks-requirements-turbonomic |
| IBM t8c-operator repository (operator manifests, CRD, AKS sample CR) | https://github.com/IBM/t8c-operator |
| Microsoft: Access a private AKS cluster with command invoke | https://learn.microsoft.com/azure/aks/access-private-cluster |
| Turbonomic Migration Playbook v0.4 (GEHA-DCM-TURBONOMIC-v0.4) and summary | Programme document library |
| SOP - Deploying the Non-Production IBM Turbonomic Instance on AKS with Helm (v1.0) | Companion document |