Execution Workflow

CyberArk PAS

Datacentre to Azure Migration v0.1 — DRAFT, FOR INTERNAL REVIEW

How the CyberArk connectors get built in Azure and put into service, from the first request to the last on-premises server being switched off

| Prepared for | G.E.H.A. Eric Ullmann (Application Owner); Phil Costanzo (Admin / Support Manager) |
| --- | --- |
| Prepared by | Citius Healthcare Consulting. Saikat Majumdar, Amitendra Kushwaha |
| Design authority | George Galindo, Cloud Architect — target design and landing zone placement |
| Companion document | CyberArk PAS Application Migration Playbook v0.1. |
| Peer Reviewer | Not yet assigned |
| Document Status | ☒ DRAFT ☐ RELEASE CANDIDATE ☐ PUBLISHED |
| Date | 11-Sep-2026 |

Table 0.0 — Document Control

# 1.  About This Document

The playbook says what we are building and why. It stops short of saying who does what, in what order, and what has to be in place before each part can start. This document fills that gap. It is written to be worked through from top to bottom by the people doing the build.

Two things are worth settling before the steps begin, because they get asked in every conversation.

## 1.1  Nothing is being moved

This is a build, not a move. There is no server being copied, no disk being replicated and no data being transferred. Four brand new Windows servers are created in Azure, and CyberArk is told about them. The existing on-premises connectors keep running the whole time.

Applications then move across one at a time. As each one migrates to Azure, we change which connector looks after it. When the last application has moved, the on-premises connectors are switched off. That is the whole shape of the work.

## What comes first - Bicep or CyberArk?

Bicep comes first. Not because it matters more, but because the CyberArk side cannot start without it.

When you go into the CyberArk portal and add a connector, what it hands back is a short script. That script must be run on a Windows server. If the server does not exist yet, there is nowhere to run it. So, the server is built first, and CyberArk is brought in afterwards.

That said, some CyberArk work can start on day one and should. Getting access to the CyberArk portal, getting the installer account set up, downloading the software - none of that needs a server, and all of it takes longer than people expect. Start it in week one and it will be ready when you need it.

| First | The requests. Subnets, policy exemptions, firewall rules, access. None of these produce anything visible, and all of them take days. |
| --- | --- |
| Second | Bicep. The repository, the template, then the servers themselves. |
| Third | CyberArk. Registration and component installation onto the servers that now exist. |
| Runs alongside everything | Network and DNS. Start on day one and it will never be the thing holding you up. |

Table 1.1 — Order of work

## 1.1 The Target

| Servers | Four. Two for production, two for non-production. Windows Server 2022, built from the GEHA approved image. |
| --- | --- |
| Size | Standard_D8ls_v5, 8 processors and 16 GB memory, with a single 128 GB disk. |
| Where they sit | CIP-PRD and CIP-DEV subscriptions, Central US, one server in zone 1 and one in zone 2. |
| Subnets | snet-cyberark-cus-prd-01 and snet-cyberark-cus-dev-01, a /27 each. |
| In front of them | An internal load balancer per environment, with a DNS name pointing at it. |
| How admins get in | Azure Bastion only. No server has a public address. |
| What runs on them | The CyberArk connector software, installed from the CyberArk portal after the server is built. |

Table 1.3 — The end result

# 2.  Prerequisites

Everything in this section has to be in place before the build can finish. Most of it is not ours to provide, which is why it is listed first. The single most common reason this kind of work stalls is waiting on something nobody asked for early enough.

Work through all five parts of this section in week one, in parallel. Do not wait for one to finish before starting the next.

## 2.1 Access

Ask for all of these at the same time. They come from different people and they arrive at different speeds.

| What | Why we need it | Who gives it to us |
| --- | --- | --- |
| Contributor on rg-sec-cyberark-npd | To build anything in non-production. Ask for this one first, it is easier to get. | Azure platform team |
| Contributor on rg-sec-cyberark-prd | Same, for production. Production also needs change board approval before each run. | Azure platform team |
| Sandbox subscription | In-order to execute the trial with end to end without raising a change. The platform team has already offered this. | Azure platform team |
| Azure DevOps project access | To hold our repository and run the pipeline. | Azure platform team |
| Read access to the shared module library | We reference their modules rather than writing our own. We need to read them first. Need Read Access | Azure platform team |
| CyberArk portal access | Nothing in Steps 6 and 7 can start without it. This is the slowest one. To make required changes in CyberArk Portal | GEHA CyberArk administration |
| Bastion access to the built servers | The only way to sign in to a connector. | Azure platform team |

Table 2.1 — Access required

Note: we will not be given Owner on the subscriptions, and we do not need it. Subnets and private endpoints stay with the platform team. Role assignments stay with Security. Plan around that rather than asking for more.

## 2.2 Platform Team Provisioning Requirements

These are requests, not tasks. We raise them and wait. Raise them in week one.

| Requirement | Detail |
| --- | --- |
| A /27 subnet in production | snet-cyberark-cus-prd-01 inside vnet-cip-cus-prd-01. Ask for the actual address range back in writing. |
| A /27 subnet in non-production | snet-cyberark-cus-dev-01 inside vnet-cip-cus-dev-01. |
| Policy exemption — Remote Desktop role | The connector needs this role turned on. It breaks the standard security baseline, so it needs a written exemption. |
| Policy exemption — network level authentication | The CyberArk listener needs this turned off. Same baseline, same kind of exemption. |
| The approved server image reference | We need the exact gallery path to put in the template. George confirmed the image exists but did not have the path. |
| Quota check | Four D8ls_v5 machines is 32 processors in Central US. Confirm both subscriptions have room. |

Table 2.2 — Platform requests

Important: the two policy exemptions have to be approved before the first deployment, not after. Without them the deployment gets refused by policy, and it looks exactly like a broken template. People lose a day hunting in the wrong place.

## 2.3 Network Connectivity and Firewall

Seven firewall rules govern this workload at the Central US hub. Raise them as one change, early. A rule that exists in the policy is not the same as a rule that works, so test each one by hand afterwards.

| Rule | Ports | Purpose |
| --- | --- | --- |
| Admin session in | 3389 and 443 | Administrators reaching the load balancer to start a session. |
| Connector to target | 3389, 22, 443 | The actual brokered session to a migrated server. |
| Connector to CyberArk | 1858 and 443 outbound | The connector talking to the CyberArk tenant. Nothing works without this one. |
| Connector to directory | 389 and 3268 | Reaching the six domain controllers over ExpressRoute. |
| Connector to log platform | 9998, and 8089 for management | Sending logs to the four indexers. |
| Connector to endpoint security | 443 outbound | Carried by the approved image. |
| Deny to on-prem targets | All | Stops the Azure connectors picking up work that still belongs to the on-premises ones. |

Table 2.3 — Firewall rules required

One special instruction for the network team: intrusion detection has to be set to skip inspection on port 1858. The CyberArk vault protocol does not survive being inspected. Put this in the change request in writing.

## 2.4 CyberArk Pre-requisites and dependencies from GEHA

| Required Item | Purpose |
| --- | --- |
| Access to the CyberArk portal | Either credentials for us, or a GEHA person on a shared screen. Either works. Neither is arranged yet. |
| The installer service account password | A GEHA CyberArk administrator has to set this. |
| The right role for whoever installs | System Administrator, or the narrower Connector Management Admin role. |
| Whether the tenant uses an IP allow list | If it does, our outbound Azure address has to be registered before a connector will be accepted. |
| The software packages | Two separate downloads from the CyberArk marketplace. The prerequisites script is not in the main package. |

Table 2.4 — CyberArk prerequisites

## 2.5  Paperwork

Two things are needed for the reviews, and they are easy to forget until someone asks.

- Save the vendor installation pages we actually follow, with their version numbers. George needs these uploaded to the GEHA enterprise architecture portal. It is a process requirement for the review, not a technical one.

- Book the security review and the architecture review now. They can run at the same time and there is no fixed meeting slot, so someone has to set it up.

# 3.  Implementation Roadmap

Eleven steps, in order. Steps 1 to 3 produce nothing visible and take the longest. Steps 4 to 8 are the build. Steps 9 to 11 are proving it and putting it into service. The Implementation consist of seven sequential steps.

| Step | What happens | Depends on |
| --- | --- | --- |
| Step 1 | Initiate Access and Pre-requisite Requests | NA |
| Step 2 | Subnets and policy exemptions come back | Step 1 |
| Step 3 | Configure the Bicep Infrastructure Repository | Step 1 |
| Step 4 | Provision and Configure Server Infrastructure | Steps 2 and 3 |
| Step 5 | Firewall rules and DNS in place | Step 2 |
| Step 6 | Register connector with CyberArk | Steps 4 and 5 |
| Step 7 | Install connector components | Step 6 |
| Step 8 | Implement Security Hardening and Complete Configuration | Step 7 |
| Step 9 | Validate the End-to-End Solution | Step 8 |
| Step 10 | Migrate Application in a Phased Approach | Step 9 |
| Step 11 | Hand over and decommission | Step 10 |

Table 3.0 — Step sequence

# Step 1 - Initiate Access and Pre-requisite Requests

Nothing gets built in this step. All it does is start the clocks on things other people control. Do it all on day one.

1.1   Ask for Contributor rights on the non-production resource group first. It is the easier approval and it is where we will do all our learning.    (We will have the least privileged Reader Access only )

1.2   Ask for the same on production at the same time, even though we will not use it for weeks. Getting it later becomes a bottleneck. (We will have the least privileged Reader Access only )

1.1   Request for the sandbox subscription. The platform team already offered one. Use this environment to develop and Validate the Bicep templates before deploying resources into the target environment.

1.4   Ask which Azure DevOps project our repository should live in. The answer is either their main project or the security team's project. It is a one-line answer and it decides where everything is kept.  (We will use the TIO project)

1.2   Request access to the CyberArk portal.

1.3   Coordinate with the CyberArk administrator to configure the installer service-account password and confirm the role and permissions assigned to the Implementation team

1.4   Confirm whether the CyberArk tenant enforces an IP allow list. If enabled, need to co-ordinate with the Network and Security teams to register the required Azure outbound IP address and ensure firewall dependencies are addressed.

Do not move past this step quietly. If any of these is still outstanding after a week, escalate it. Every one of them blocks something later, and they all take longer than the technical work.

# Step 2 - Subnets and policy exemptions

This is the step people skip because it feels like admin. It is the one that, done late, pushes everything else out by two weeks.

2.1   Submit the subnet provisioning request with Cloud and Platform Service Team. They own the IP address space and the landing zone network configuration. Subnets must be provisioned through the established platform and governance process

2.2   Request a dedicated /27 subnet for each environment and get the actual address ranges. We need them for three things: the load balancer address, the two server addresses, and the firewall rule.

2.3   Retain the /27 subnet size to support failure scalability. We only use three addresses today. These capacity will accommodate additional CyberArk connectors without requiring a new subnet.

2.4   Raise the two policy exemptions. Explain what each one is for:

- The Remote Desktop Services role must be enabled. The CyberArk session manager runs on top of it.

- Network level authentication must be off on the CyberArk listener. The product requires it. Document the compensating controls: the listener is accessible only through the internal load balancer and the load balancer is restricted to the approved administrative network, preventing direct exposure

2.5   Review the inherited policies before writing any template, so nothing comes as a surprise later. Four of them shape what we can build.

| Existing Policy Control | Implementation Impact |
| --- | --- |
| Public IP on a network card is denied | Fine. Our design has none anyway. |
| Gateway resources are denied | Do not plan an Application Gateway here. |
| Creating private DNS zones is denied | The DNS record goes in the on-premises zone instead, placed by the platform team. |
| Management ports from the internet are blocked | This is why Bastion is the only way in. |

Table 2.5 — Policies we inherit

2.6   Confirm the quota. Four machines of the chosen size is 32 processors in Central US. Check both subscriptions have the headroom before the build is scheduled. An increase is a support ticket measured in days.

# Step 3 – Configure the Bicep Infrastructure Repository
This implementation will leverage GEHA’s existing library of standardized, reusable Bicep modules. The repository will be configured to reference the appropriate modules, versions and deployment parameters.

## Bicep Module Library Example

The platform team keeps all the shared Bicep in one repository. When a change is merged there, a pipeline publishes the modules into a container registry with a version number on each one. Application teams never copy that code. We point at a module by its registry path and version, and it gets pulled down when the build runs.

module sa 'br:gehabicep.azurecr.io/bicep/modules/storageaccounts:v1.0' = {

name: 'storageDeploy'

params: { ... }

}

Every module call we write looks like that. The path and the version change. The pattern does not.

## Repository Configuration Activities

3.1   Review the shared module repository. There is already a virtual machine module, and a fuller one is being built in a separate repository. Ask which one to target.

3.2   Review the landing zone repository too. Virtual networks, subnets, and peering are all defined there centrally. Our template uses them. It does not create them.

3.3   Note what we will not be building. Three things are worth confirming rather than assuming:

- The platform does not use network security groups. Azure Firewall manages the separation between networks.

- Backups are managed by the enterprise backup platform, so we probably do not deploy a backup vault.

- Private endpoints are built into most modules already, though not the virtual machine one.

3.4   Create the repository with the naming they use. Dot notation, so cyberark.bicep, not hyphens or underscores.

3.5   Maintain the structure simple. One main template, one parameter file for each environment, one pipeline definition. Both environments use the same template and differ only in subscription, network, names, and alert severity.

3.6   Do not copy the shared modules into our repository. Reference them. If a shared module is missing something we need, work on a branch, and raise a pull request against theirs. The platform team has explicitly invited that and asked to be tagged in the request.

Worth knowing: the platform team has said that most of the GEHA estate is platform services rather than virtual machines, and their standards for this kind of build are still being written. Expect some answers to be worked out with us rather than handed to us.

# Step 4 - Provision and Configure Server Infrastructure

Now something visible gets produced. This is an ordinary Windows server build. What makes it is the image, the sizing, and the load balancer settings.

4.1   Develop the infrastructure template to provision two virtual machines from the approved GEHA image. That image already carries the operating system build, the hardening, the agents, the endpoint protection, and the patch management configuration; therefore, these components only need to be referenced in the template

4.2   Size of the virtual machines:  Standard_D8ls_v5. One machine in zone one, one in zone two.

4.3   Allocate a single 128 GB operating system disk to each virtual machine. There is no second disk because session recordings go straight up to the CyberArk tenant rather than being kept on the server.

4.4   Assign private static IP addresses to all components. The load balancer takes the fourth usable address in the subnet, the first server the fifth, the second server the sixth. No public addresses anywhere.

4.5   Deploy and configure the internal load balancer using the key configuration settings specified in following table:

| Setting | Value | Reason |
| --- | --- | --- |
| Persistence | Client address | The session handshake reconnects halfway through. If that second connection lands on the other server, the session fails. |
| Health probe | TCP 3389, every 5 seconds, 2 failures | Checks the actual service, not just whether the machine is powered on. |
| Idle timeout | 30 minutes | A privileged session can sit idle while someone reads something. |
| TCP reset on idle | Enabled | So, the client is told the connection has gone rather than hanging. |

Table 4.5 — Load balancer settings

4.6   Add the tags the platform expects, applied by the module: environment, owner, application name, business unit, cost centre, criticality, data classification, and disaster recovery tier.

4.7   Add the six alerts, pointed at the existing platform action group: connector unreachable, session manager stopped, rotation engine stopped, tunnel disconnected, both load balancer probes failing, and disk above 85 per cent.

4.8   Trial it in the sandbox first, end to end.

4.9   Run a what-if against the real subscription. Anything policy will block shows up here rather than halfway through a deployment.

4.10   Deploy non-production through the pipeline. Then production, which also needs change board approval. Lower environment first was agreed on the call and there is no reason to change it.

4.11   Check what was built: four machines, right sizes, right zones, addresses in the right order, no public addresses, tags present, load balancer settings as above.

# Step 5 - Firewall rules and DNS

This runs alongside Step 4 rather than after it. The security system rules have to be working before Step 6 can start. The DNS record can follow shortly after.

5.1   Get the seven rules from Table 2.3 raised as a single change. Include the instruction about not inspecting port 1858.

5.2   Ask for the DNS records. Production needs cyberark-prd.geha.com pointing at the production load balancer. Non-production needs cyberark-npd.geha.com. Both records live in the on-premises zone and are placed by the platform team, because we are not allowed to create DNS zones in Azure.

5.3   Azure machines resolve names through the on-premises domain controllers, so once the record exists both the connectors and the administrators can see it.

5.4   Test every path by hand from a built server through Bastion. Try the CyberArk tenant, the domain controllers and the log indexers. Do not report the network as ready until you have.

Still open: George raised whether we get access to the domain controllers to make DNS changes ourselves, or whether a GEHA person makes them with us in the room at cutover. He was taking it to Dale. Until we hear back, assume it needs two people and plan the time in.

# Step 6 - Register Connectors with CyberArk

This is the point where the two halves meet. We have servers and we have network paths. Now CyberArk takes over.

Confirm that each server must be reachable, joined to the domain, and able to reach the CyberArk tenant on port 443 before registration.

## Prepare the Servers

6.1   Sign in through Azure Bastion as a local administrator. There is no other way in, and there should not be.

6.2   Download the Privilege Cloud software package from the CyberArk customer portal

6.3   Download the tools package separately. It holds the prerequisites script, which is not in the main package.

6.4   Copy and extract the hardening policy package to a domain controller and unzip it there. We need it in Step 8.

6.5   Temporarily disable the endpoint protection during installation and re-enable it after step-8

## Validate pre-requisites.

6.6   Copy the prerequisites script onto the server and run it as a local administrator:

.\ConnectorCheckPrerequisites_PrivilegeCloud.ps1

6.7   It prints a pass or fail against each check and usually tells you how to fix a failure.

6.8   It also installs the Remote Desktop role and the connection broker. It is also why the policy exemption from Step 2 has to already be approved.

6.9   Fix everything it flags before going further. This step is cheap. The ones after it are not.

Open question worth closing here: Syed raised checking with CyberArk support about Azure builds where machines are Entra-joined rather than domain-joined. Our design joins the on-premises domain, so it should not apply, but the script behaves differently out of domain. Confirm rather than assume.

## Register the servers.

6.10   In the CyberArk portal go to Connector Management → Connectors → Add a connector.

6.11   Leave the installation location at the default unless Program Files sits on another drive.

6.12   Assign a connector pool. Pools group connectors that serve the same targets so they can cover for each other. Use one pool per environment.

6.13   Leave proxy configuration alone. The traffic goes out through the firewall.

6.14   Click Next. It will provide a PowerShell script, Have a PowerShell window already open on the server before you copy it.

6.15   Paste the script in and run it. It installs a small agent, and the agent calls out to CyberArk.

6.16   Go back to the connector list. The server should now appear. If it does not, the first thing to check is outbound 443.

Five minute clock. The script expires after five minutes. If it does, click Renew and it gives you another five. Trivial, but it catches everyone the first time.

# Step 7 - Install connector components.

The agent on its own does nothing useful. It is just a messenger. Now we tell it what to install.

7.1   Select the connector row, then ⋮ → Add component.

7.2   Look at which components you are offered. If there is no option for the password rotation engine, the tenant uses the newer managed rotation service, and we install the session manager only.

7.3   Set installation mode to Production. There is a proof-of-concept mode that skips the hardening. Do not use it.

7.4   Enter the installer service account and password, and a local administrator account for this server. On a domain-joined build that has to be a domain account.

7.5   The tenant address is usually filled in already. Leave it as it is.

7.6   Click Install, wait for it to finish, then restart the machine.

7.7   Repeat the whole of Steps 6 and 7 for the second server, then for both production servers.

One at a time. Finish a connector completely before starting the next one. Installing two at once is not supported and fails in ways that are hard to unpick.

# Step 8 – Implement Security Hardening and Complete Configuration
Apply the mandatory CyberArk Group Policy to secure the connector servers and ensure compliance with the supported configuration

8.1   On a domain controller, open Group Policy Management.

8.2   Create a new policy object and put the version number in the name, so whoever looks at it in a year knows what is applied.

8.3   Right-click it, choose Import Settings, and point it at the folder unzipped in Step 6.4.

8.4   Check the Settings tab afterwards to confirm the import worked.

8.5   Link it to the organisational unit holding the connector servers, and only that unit. This policy is restrictive on purpose and linking it somewhere broad will lock down servers that were never meant to be touched.

8.6   Restart the server or run gpupdate /force.

8.7   Complete the vendor's post-installation steps for the version we are on.

8.8   Turn endpoint protection back on and add the exclusions CyberArk asks for.

8.9   Check the connector list. We want green against the agent and against every component.

Green is not finished. It means the agent can talk to CyberArk. It says nothing about whether a session works. That is Step 9.

# Step 9 - Validate the End-to-End Solution

The following baseline test plan validates connector availability and core functionality. Execute each test in a non-production environment, retain supporting evidence and update the test plan as requirements evolve,

| No. | Test | What to do | Pass means |
| --- | --- | --- | --- |
| 1 | Connector reachable | Check both connectors show as connected in the portal with all components active. | Green on every row. |
| 2 | Load balancer healthy | Check both servers show healthy on the probe. | Both healthy. |
| 3 | Name resolves | From an admin machine, resolve the DNS name. | It returns the load balancer address. |
| 4 | A real session | A privileged user opens a session through the CyberArk portal to a test server. | Session opens and the password is never shown on screen. |
| 5 | Recording | Find that session in the CyberArk tenant and play it back. | The full recording plays. |
| 6 | Password rotation | Rotate a test account through the Azure engine, then have the application connect. | Rotation works and the application still connects. |
| 7 | Directory | Confirm the connector reaches the domain controllers. | Works from both servers. |
| 8 | Logging | Confirm events arrive at the log platform. | Events visible. |
| 9 | Stop a server | Stop one connector. Watch what happens to sessions and rotation. | Sessions carry on. Rotation moves to the other server. |
| 10 | The deny rule | From an Azure connector, try to reach an on-premises server that has not migrated. | Blocked at the firewall. |
| 11 | Bastion only | Check there is no other way into the operating system. | No public address, no open management port. |
| 12 | Rebuild | Delete a non-production connector and rebuild it from the pipeline, then register it again. | Back in service using only the runbook. |
| 13 | Server Heartbeat | Check Datadog or Splunk for required logs even offline | Splunk/Datadog shows server is offline |

Table 9.0 — Test set

Test 12 is the one that matters most. Our whole recovery position is that we rebuild rather than restore. Until somebody has actually rebuilt one, that is a claim rather than a fact.

# Step 10 – Migrate Application in a Phased Approach
Migrate applications individually by updating their assigned CyberArk connectors. Prepare eligible configurations changes in advance and complete the remaining updates during the scheduled cutover.

Four things change. Two can be set up in advance. Two cannot.

| What changes | Where | Who does it | Can it be done early? |
| --- | --- | --- | --- |
| Session manager for the moving servers | Platform setting in CyberArk | GEHA CyberArk admin | Yes. Copy the setting in advance, switch it on at cutover. |
| Rotation engine for the safe | Safe properties in CyberArk | GEHA CyberArk admin | No. This change is the move. |
| The address administrators use | DNS | Platform team | Yes. Created at build time. |
| Firewall rules | Central US hub | Network team | Yes. Staged before the build, in its own change window. |

Table 10.0 — What changes at each cutover

## Before the window

10.1   Copy the platform setting and point the copy at the Azure connectors. Leave it switched off.

10.2   Confirm the servers for this application are actually in Azure and reachable from the connector subnet.

10.3   Confirm which accounts are involved and who owns them.

## In the window

10.4   Switch on the copied platform setting for the servers that have moved.

10.5   Change the rotation engine on the safe to the Azure one. This is the point of no return for that safe.

10.6   Open a session to one of the moved servers and check it works end to end.

10.7   Rotate one password and confirm the application still connects afterwards.

## If it goes wrong

10.8   Point the safe and the platform setting back at the on-premises connectors. They are still running. That is the entire reason we run both estates in parallel.

10.9   There is no server to fail back, because no server moved. Rollback is a configuration change, which is why it is quick.

Why this is safer than it sounds: one cutover affects one application's safe. If it goes wrong we point that safe back. Nothing else is touched and no other application notices.

# Step 11 - Hand over and decommission

11.1   Check the six alerts are firing into the right place and reaching the service desk.

11.2   Check the servers are excluded from the native Azure backup by tag and picked up by the enterprise backup platform instead.

11.3   Check patching is staggered so a maintenance window never takes both servers in an environment at the same time.

11.4   Hand over four runbooks: build, register, rebuild, and add another connector.

11.5   Agree a standing change for adding connectors in later waves. If every new connector is a fresh project, CyberArk becomes the thing that holds up every later wave.

11.6   Leave the on-premises connectors alone until the final wave. Not until hypercare ends. Until there is no on-premises server left for them to look after.

11.7   GEHA decommissions them under their own process. The cost saving arrives at that point, not at go-live. Both estates are funded for the length of the programme, and that is built into the approach rather than being a planning mistake.

# 4.  Who Does What

| Name | What they own here |
| --- | --- |
| George Galindo | The target design, landing zone placement, the architecture diagram, the security and architecture reviews, and the open question with Dale about DNS access. |
| Saikat Majumdar | This document, the Bicep repository and template, the build in both environments, and running the cutovers. |
| Bhagyashri Sangale | Preparing the servers, installing and hardening the connectors, and collecting the test evidence. |
| Amitendra Kushwaha | Connector registration and component configuration alongside Saikat. |
| Syed Ahmed | The seven firewall rules, the paths to the domain controllers and log platform, and the DNS request. |
| Mulinti Reddy | Database servers and their privileged accounts, rotation testing against databases, and applications that fetch database passwords. |
| GEHA CyberArk admin | Portal access, the installer account, and the platform and safe changes at every cutover. |
| Cloud and Platform Services | Subnets, address space, DNS records, policy exemptions and the module library. |

Table 4.0 — Roles

# 5.  Common Deployment Risks and Preventive Measures

- Policy exemptions raised too late. The deployment gets refused and it looks like a broken template.

- Outbound 443 not open when you run the registration script. It hangs rather than giving an error.

- Load balancer persistence not set to client address. Sessions drop halfway through and nothing in the logs explains why.

- Port 1858 being inspected. The vault protocol does not survive it. The rule has to say skip inspection.

- The registration script expiring. Five minutes. Have the window open before you copy it.

- Installing two connectors at the same time. Not supported. Finish one first.

- Renaming a server after it is built. CyberArk registers the server by name. Get the name right in the parameter file.

- Assuming we own the subnet or the DNS record. We own neither. Both are requests, and DNS may need a GEHA person present.

- Treating a green status light as done. It is not done until somebody has watched a recorded session play back.

# 6.  Still Open

These are tracked here rather than buried in the steps, so they can be picked up in a status call.

| Open item | Why it matters | Owner |
| --- | --- | --- |
| Who makes the DNS change, and do we get domain controller access? | Decides whether every cutover window needs a GEHA person in the room. | George, with Dale |
| CyberArk portal access for the team | Steps 6 and 7 cannot start without it. Longest lead item on the list. | George, with Dale |
| The exact gallery path for the approved image | One value, but the template cannot be finished without it. | Saikat, with platform team |
| Which Azure DevOps project the repository lives in | Decides where everything is kept and who reviews it. | Saikat, with platform team |
| Entra-joined versus domain-joined, and group policy behaviour | Changes how the prerequisites script runs and how hardening is applied. | Syed, with CyberArk support |
| Whether the CyberArk tenant enforces an IP allow list | If it does, the firewall address has to be registered before registration will work. | Amitendra, with CyberArk admin |
| The full test plan | Section 9 is a starting set. It needs reviewing and signing off. | Saikat and Amitendra, reviewed by George |
| Target state architecture diagram | Needed for the design review and for briefing the platform and network teams. | George |

Table 6.0 — Open items

# 7.  References

| What you need | Where to find it |
| --- | --- |
| Connector installation, step by step | CyberArk docs, then your product, then Setup, then Deploy and maintain Privilege Cloud connectors, then Install the Connector using Connector Management. |
| Machine requirements and the sizing table | CyberArk docs, Setup, System requirements, Privilege Cloud Connector. |
| Addresses that need opening | CyberArk docs, Deployment, Outbound traffic network and port requirements. Hand this page to Syed as it is. |
| The software | CyberArk marketplace. The version package under Software, and the tools package under Integrations and Tools. |
| Shared Bicep modules | The platform module repository in Azure DevOps, published to the container registry with a version on each module. |
| Network and subnet configuration | The landing zone repository in Azure DevOps, under config and custom-parameters. |
| Policy assignments and exemptions | The same landing zone repository, in the default policy assignment parameters file. |
| The design itself | CyberArk PAS Application Migration Playbook, section 5. |

Table 7.0 — References

A word of warning about the CyberArk site. It is split by product and by version, and it is easy to end up reading instructions for a different installer. Check the product name in the top left corner before following anything. Save the pages we use, with their versions, for the architecture review.

The three figures in this document are drawings showing where the fields sit on each screen. They are not screen captures, because that needs a signed-in session in our own tenant. Replace them with real screenshots the first time we run through this, and the document becomes far more useful.